## Slide 1: TGbe January 2022 Closing Report
Date: 2022-01-24
Authors:

## Slide 2: TGbe (Extremely High Throughput)
TGbe had scheduled 4 conf. calls during the January electronic interim
  Two Joint calls, and two parallel MAC/PHY calls
    Covered comment resolution documents
    Approved the resolution of several technical/editorial comments and PDT submissions
      ~60% of all CC36 comments are now resolved
  Approved the creation of TGbe D1.4
    TGbe D1.4 is expected to be available by end of this month
Agenda is available in 1971r8, with queue statuses available in 0110r0
  Future Teleconference Plan is provided in the next slide
Motions List is available in 1982r59
Distribution of ~4350 CIDs
9%
67%
24%
Resolution Status

## Slide 3: Teleconference Plan
Feb 14 Monday – MAC/PHY 19:00-21:00 ET
Feb 16 Wednesday – Joint** 10:00-12:00 ET
Feb 17 Thursday – MAC 10:00-12:00 ET
Feb 21 Monday – MAC/PHY 19:00-21:00 ET
Feb 23 Wednesday – Joint** 10:00-12:00 ET
Feb 24 Thursday – MAC 10:00-12:00 ET
Feb 28 Monday – MAC/PHY 19:00-21:00 ET
Mar 02 Wednesday – Joint (Motions) 10:00-12:00 ET
Mar 03 Thursday – MAC 10:00-12:00 ET
Mar 07 Monday – MAC/PHY 19:00-21:00 ET
Mar 09 Wednesday – Joint** 10:00-12:00 ET
Mar 10 Thursday – MAC 10:00-12:00 ET
** Can be modified to MAC/PHY on the fly with pre-announcement.
Jan 26 Wednesday – MAC (No SP) 10:00-12:00 ET
Jan 27 Thursday – MAC 10:00-12:00 ET
Jan 31 Monday – No Conf Call Holiday
Feb 02 Wednesday – No Conf Call Holiday
Feb 03 Thursday – No Conf Call Holiday
Feb 07 Monday – MAC/PHY 19:00-21:00 ET
Feb 09 Wednesday – Joint (Motions) 10:00-12:00 ET
Feb 10 Thursday – MAC 10:00-12:00 ET

## Slide 4: Timeline
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sep 2020
D1.0 WG Comment Collection May 2021
D2.0 WG Comment Collection Mar 2022
D3.0 Letter Ballot Nov 2022
Initial Sponsor Ballot (D4.0) May 2023
Final 802.11 WG approval Mar 2024
802 EC approval Mar 2024
RevCom and SASB approval May 2024