## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-21/2018r0
Venue Date: | Dec 2021
First Author: | Yujin Noh
Subject: | LB259-Comment Collection on D3.0
Full Date: | 2021-12-16
Author(s): | Yujin Noh
| Company: | Senscomm
| email: | yujin.noh@senscomm.com
Abstract: | LB259 - comments on D3.0

## Sheet1
Revision | Date | Description
0 | 2021-12-16 | Initial export from DB.
1 | 2021-12-17 | Initial comment assignment
2 | 2021-12-22 | Comment reassignement completed. All the comments have been assigned as of today.
3 | 2022-01-20 | 87 out of 107 comments are ready for motion
4 | 2022-01-21 | 3002 and 3051 updated from r3
5 | 2022-01-25 | 87 out of 107 comments resolved by motion passed
6 | 2022-02-15 | 20 out of 107 comments are ready for motion.

## All Comments
CID | Commenter | Must Be Satisfied | Clause Number(C) | Page(C) | Line(C) | Category | Clause | Page | Comment | Proposed Change | Ad-hoc | Comment Group | Ad-hoc Notes | Status | Assignee | Submission | Resn Status | Resolution | Ready For Motion | Motion Number | Edit Status | Edited in Draft | Edit Notes | Last Updated | Last Updated By
3000 | Jonathan Segev | Yes | 32.3.13 | 120 | 19 | T | 32.3.13 | 120.19 | "Set PHY_CCA indication() in accordance with TBD" , please clarify what is the TBD value for CCA | Define an acceptable CCA level. |  |  |  | Resolution approved | yujin noh | 22/0019r2 | V | REVISED [01/20/2022, EDITOR] Agreed in principle. Add the reference to fill the TBD. Same resolution is applied to CIDs 3000 and 3059. TGbd Editor: replace TBD with 32.3.11.5. (https://mentor.ieee.org/802.11/dcn/22/11-22-0019-02-00bd-resolutions-to-resolutions-to-ngv-preamble-and-ngv-receive-procedure.docx) under CID 3000. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3001 | Jonathan Segev | Yes | 9.4.2.298 | 40 | 18 | T | 9.4.2.298 | 40.18 | The Format and BW is an ordered list, meaning support for a BW suggests support for lower BWs. The additions 11bd made break this rule. As a result the support during negotiation of the STA is unclear. | Insert text in the element description that clarifies that support for values 6 and 7 does is limited to NGV formats only. i.e. support for 7 suggests support for 6 but not to 5 and below. |  |  |  | Resolution approved | Stephan Sand | 22/0007r3 | V | REVISED [01/18/2022, EDITOR] Agree with comment. TGbd editor: Please add the following sentence after Table 9-322h23fb and add “*” after NGV in the Format column: * Values 6 and 7 may only be supported when dot11NGVActivated is true. (https://mentor.ieee.org/802.11/dcn/22/11-22-0007-03-00bd-lb259-comment-resolution.docx) under CID 3001. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3002 | Jonathan Segev | Yes | 9.3.1.19 | 38 | 9 | T | 9.3.1.19 | 38.09 | In 9.3.1.19 the title now suggest there are 3 kinds of NDPA: VHT HE and NGV Ranging this is not correct because 11az has its own NDPA type of Ranging NDP and it is not NGV Ranging | Adjust the name to separate the NGV Ranging NDPA from the Ranging NDPA |  |  |  | Resolution approved | Stephan Sand | 22/0007r7 | V | REVISED [01/21/2022, EDITOR] Agree with comment. Since subclause 9.3.1.19 has been significantly updated in 11az D4.0 an update to the changes on NGV Ranging NDPA and Ranging NDPA frame is provided. TGbd editor: Please change the subclause heading of 9.3.1.19 to “VHT/HE/Ranging NDP Announcement frame format” and incorporate the changes in https://mentor.ieee.org/802.11/dcn/22/11-22-0007-07-00bd-lb259-comment-resolution.docx and apply editorial modifications to fix unnecessary capitalization under CID 3056 in DCN 11-22/0016r2 (https://mentor.ieee.org/802.11/dcn/22/11-22-0007-05-00bd-lb259-comment-resolution.docx) under CID 3002. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3003 | Brian Hart | No | 32.3.13 | 116 | 55 | E | 32.3.13 | 116.55 | TXVECTOR is typically described as having parameters not elements, so "The TXVECTOR elements ..." is odd | Change to "The TXVECTOR parameters ..." |  |  |  | Resolution approved | Editor | 22/0016r2 | A | ACCEPTED [01/19/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0016-02-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 3003. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3004 | Stephan Sand | No |  | 7 | 17 | E |  | 7.17 | 11bd D3.0 amends REVme D0.4. According to REVme D0.4 subclause 4.3.17 became 4.3.19 (STA transmission of Data frames outside the context of a BSS). Similar 4.3.22, 9.2.4.7, 9.7.3 of 11-2020 became 4.3.24, 9.2.4.8, 9.7.2 in REVme D0.4. | Update subclause number 4.3.17 according to REVme D0.4 to 4.3.19 on P19L7. Also update subclause number 4.3.22 according to REVme D0.4 to 4.3.24 on P20L53, 9.2.47 to 9.2.4.8 on P36L9, and 9.7.3 to 9.7.2 on P41L57. |  |  |  | Resolution approved | Editor | 22/0015r2 | J | REJECTED [01/18/2022, EDITOR] Given the resolution in CID3042, 11bd D3.0 should consider IEEE Std 802.11™-2020, 11ax, 11ay, 11ba, 11az, and 11bc (not REVmeD0.4) because we have REVme publishing after 11bd. No need to update the number based on REVme D0.4. (https://mentor.ieee.org/802.11/dcn/22/11-22-0015-02-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 3004. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3005 | Stephan Sand | No |  | 9 | 17 | E |  | 9.17 | In REVme D0.4 there already exists sublcaus 17.2.2.9. | Update subclause numbers 17.2.2.9 and 17.2.2.10 to 17.2.2.10 and 17.2.2.11 on P55L36 and P55L45. |  |  |  | Resolution approved | Editor | 22/0015r2 | J | REJECTED [01/18/2022, EDITOR] Given the resolution in CID3042, 11bd D3.0 should consider IEEE Std 802.11™-2020, 11ax, 11ay, 11ba, 11az, and 11bc (not REVmeD0.4) because we have REVme publishing after 11bd. No need to update the number based on REVme D0.4. (https://mentor.ieee.org/802.11/dcn/22/11-22-0015-02-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 3005. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3006 | Stephan Sand | No |  | 13 | 11 | E |  | 13.11 | Several of the table numbers have been updated from 11-2020 to REVme D0.4 and need to be udpated in 11bd D3.0: Table 9-25 , 9-45, 9-69, 9-94 to Table 9-34, 9-73, 9-97, 9-128 | Update Table 9-25 to Table 9-34 on P36L17, Table 9-45 to Table 9-73 on P38-L41, Table 9-69 to Table 9-97 on P39L30, Table9-94 to Table 9-128 on P39L57. |  |  |  | Resolution approved | Editor | 22/0015r2 | V | REVISED [01/18/2022, EDITOR] Given the resolution in CID3042, 11bd D3.0 should consider IEEE Std 802.11™-2020, 11ax, 11ay, 11ba, 11az, and 11bc (not REVmeD0.4) because we have REVme publishing after 11bd. No need to update the number based on REVme D0.4. However, it turned out that Table 9-94 should be Table 9-92 based on IEEE Std 802.11™-2020. TGbd Editor: replace Table 9-94 with Table 9-92. (https://mentor.ieee.org/802.11/dcn/22/11-22-0015-02-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 3006. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3007 | Stephan Sand | No |  | 12 | 4 | E |  | 12.04 | Several of the figure numbers have been udpated from 11-2020 to REVme D0.4 and need to be updated in 11bd D3.0: Figure 9-79, 9-848, 9-849a, | Update Figure 9-79 to Figure 9-126 on P39L8, Figure 9-848 to Figure 9-1063 on P41L19, Figure 9-849a to Figure 9-1065 on P41L35 |  |  |  | Resolution approved | Editor | 22/0015r2 | J | REJECTED [01/18/2022, EDITOR] Given the resolution in CID3042, 11bd D3.0 should consider IEEE Std 802.11™-2020, 11ax, 11ay, 11ba, 11az, and 11bc (not REVmeD0.4) because we have REVme publishing after 11bd. No need to update the number based on REVme D0.4. (https://mentor.ieee.org/802.11/dcn/22/11-22-0015-02-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 3007. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3008 | Stephan Sand | No | 5.2.3.2 | 23 | 65 | E | 5.2.3.2 | 23.65 | According to resolution of CID #2248, "transmit power level" is replaced by "transmit power spectral density". | Replace "transmit power level" by "transmit power spectral density". |  |  |  | Resolution approved | Editor | 22/0016r2 | A | ACCEPTED [01/19/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0016-02-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 3008. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3009 | Stephan Sand | No | 5.2.3.2 | 24 | 24 | T | 5.2.3.2 | 24.24 | "data rate/NGV-MCS" is defined in the cases of the PPDU format value beiing 0 or 1, but not for 2. | At the end of the paragraph on L24 add the following sentence: "If the PPDU format has value 2, the data rate/NGV-MCS member is set to value 14 indicating that the actual data-rate/MCS is decided by the MAC layer." Apply the same change at the end of paragraph on P26L23. |  |  |  | Resolution approved | Liwen Chu | 22/0048r1 | A | ACCEPTED [01/20/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0048-01-00bd-d3-0-comment-resolution-5-3-2.docx) under CID 3009. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3010 | Stephan Sand | No | 5.2.3.2 | 24 | 52 | T | 5.2.3.2 | 24.52 | "frequency band member" is only applicable for dot11NGVActived true (NGV STA) or dott11NONNGVRadioEinvironmentSupported true (non-NGV STA with dott11OCBActivated true). Since both NGV and non-NGV STAs transmit in the 5.9 GHz band, the frequency band member should indicate either the channel in the 5.9 GHz band or that the channel in the 5.9 GHz band is selected by the MAC layer. P67L37 suggest the same definition, i.e. the "channel defined by the frequency band member, ...". Further the term "frequency band" is usally not used for individual channels but e.g. for 2.4, 5 or 6 GHz band, e.g. REVme D0.4 Clause 27.1.1 P4275. Hence it would be more clear to rename the "frequency band member" to "channel member" or "channel number member". | Replace the sentence on P24L52-53 with "The channel member indicates the channel where the MSDU is transmitted in the 5.9 GHz band as defined in subclauses E.2.3 (5.9 GHz band in the United States (5.850- 5.925 GHz)) and E.2.4 (5.9 GHz band in Europe (5.855-5.925 GHz)) with the exception for value 0, which means the MAC layer will select the channel." Apply the same changes to paragraph on P26L28-29. |  |  |  | Resolution approved | Liwen Chu | 22/0048r1 | V | REVISED [01/20/2022, EDITOR] TGbd editor: Please replace the sentence on P24L52-53 with "The channel member indicates the channel where the MSDU is transmitted in the 5.9 GHz band as defined in subclauses E.2.3 (5.9 GHz band in the United States (5.850- 5.925 GHz)) and E.2.4 (5.9 GHz band in Europe (5.855-5.925 GHz)) with the exception for value 0, which means the MAC layer will select the channel.". Please apply the same changes to paragraph on P26L28-29. TGbd editor: Please change “ frequency band member” to “channel member” through the document. (https://mentor.ieee.org/802.11/dcn/22/11-22-0048-01-00bd-d3-0-comment-resolution-5-3-2.docx) under CID 3010. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3011 | Stephan Sand | No | 6.3.128.2.2 | 34 | 33 | T | 6.3.128.2.2 | 34.33 | The "RadioEnviornmentMeasurementPeriod" parameter of the MLME-RADIOENVIRONMENT.request primitive is not defined. | Please provide a definition similar to the MIB entry dot11RadioEnvironmentMeasurementPeriod on P135L54-65. |  |  |  | Resolution approved | Joseph Levy | 22/0111r1 | V | REVISED [01/21/2022, EDITOR] The RadioEnvironmentMeasurementPeriod is defined, please see the modification provide in 11-21/0111r2 for CID 3011/3015. Additional correction: The definition of the MIB variables should be aligned with these new definitions in clause 6.3.128.2.2, as provided in 11-22/0111r1 for CID 3111/3015. (https://mentor.ieee.org/802.11/dcn/22/11-22-0111-01-00bd-some-clause-5-6-comment-resolutions-for-lb-259.docx) under CID 3011. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3012 | Stephan Sand | No | 9.4.2.298 | 40 | 22 | T | 9.4.2.298 | 40.22 | The last two columns in the last row of Table 9-322h23fb have not the same entries as in Table 9-322h23fb on P77 in 11az D4.0. | In the last row of Table 9-322h23fb change the FORMAT and Bandwidth value to "Reserved" as in 11az D4.0. |  |  |  | Resolution approved | Stephan Sand | 22/0007r3 | A | ACCEPTED [01/18/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0007-03-00bd-lb259-comment-resolution.docx) under CID 3012. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3013 | Stephan Sand | No | 10.23.2.8 | 44 | 49 | E | 10.23.2.8 | 44.49 | In 11az D4.0 there are no numbers between "HE Ranging" and "NDP" on P110L10-11, but in 11bd D3.0 P44L49-50 there is a "10" and an "11". | Remove "10" and "11" between "HE Ranging" and "NDP" on L49 and L50. |  |  |  | Resolution approved | Editor | 22/0016r2 | A | ACCEPTED [01/19/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0016-02-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 3013. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3014 | Stephan Sand | No | 31.3.1 | 65 | 27 | E | 31.3.1 | 65.27 | "The DMG STA shall set the Discovery Mode field to 1 and the OCB subfield in the Clustering Control field set to 1" is grammatically incorrect. | Replace with "The DMG STA shall set the Discovery Mode field to 1 and set the OCB subfield in the Clustering Control field to 1" |  |  |  | Ready for motion | Hiroyuki Motozuka | 22/0091r3 | V | REVISED [02/08/2022, EDITOR] Proposed Change: Replace "The DMG STA shall set the Discovery Mode field to 1 and the OCB subfield in the Clustering Control field set to 1" with “The DMG STA shall set the Discovery Mode field and OCB subfield in the Clustering Control field to 1.” (https://mentor.ieee.org/802.11/dcn/22/11-22-0091-03-00bd-d3-0-comment-resolution-related-to-dmg-sta-communicating-ocb.docx) under CID 3014. | Yes |  |  |  |  | 2022-02-08 17:57
3015 | Stephan Sand | No | 31.6 | 67 | 64 | T | 31.6 | 67.64 | The MLME-RADIOENVIRONMENT.request primitive only contains the RadioEnvironmentMeasurementPeriod as a a parameter, but not the StationMeasurementPeriod as mentioned on P67L64-P68L1. | Please add the parameter "StationMeasurementPeriod" and provide a defintion similar to the MIB entry dot11StationmeasurementPeriod on P136L12-22 |  |  |  | Resolution approved | Joseph Levy | 22/0111r1 | V | REVISED [01/21/2022, EDITOR] The StationMeasurementPeriod is added and defined, please see modification provide in 11-22/0111r2 for CID 3011/3015. Additional corrections: The awkward text in clause 31.6 should be corrected as shown in 11-22/0111r1 for CID 3011/3015. (https://mentor.ieee.org/802.11/dcn/22/11-22-0111-01-00bd-some-clause-5-6-comment-resolutions-for-lb-259.docx) under CID 3015. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3016 | Stephan Sand | No | 32.2.2 | 75 | 46 | E | 32.2.2 | 75.46 | Singular "s" at the end of "Indicate" is missing | Replace "Indicate" with "Indicates" |  |  |  | Resolution approved | Bo Sun | 21/2034r0 | A | ACCEPTED [01/11/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/21/11-21-2034-00-00bd-lb259-cr-clause-32-2-2-and-annex-b.docx) under CID 3016. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3017 | Stephan Sand | No | 32.3.15 | 122 | 49 | T | 32.3.15 | 122.49 | Table 32-11 defined NNGV-LTF newley in 11bd D3.0 compared to 11bd D2.0. Hence Figure 32-18 needs to be updated. | Remove the factor "(LTF_REP+1)" above the brace of the NGV-LTF symbols |  |  |  | Resolution approved | Stephan Sand | 22/0007r3 | A | ACCEPTED [01/18/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0007-03-00bd-lb259-comment-resolution.docx) under CID 3017. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3018 | Stephan Sand | No | 32.3.15 | 123 | 26 | T | 32.3.15 | 123.26 | Table 32-11 defined NNGV-LTF newley in 11bd D3.0 compared to 11bd D2.0. Hence Figure 32-19 needs to be updated. | 1. Replace "NNGV-LTF" by "NSS" on L26 twice. 2. Remove the factor "(LTF_REP+1)" after "NNGV-LTF" on L28. |  |  |  | Resolution approved | Stephan Sand | 22/0007r3 | V | REVISED [01/18/2022, EDITOR] TGbd editor: Please incorporate the changes in https://mentor.ieee.org/802.11/dcn/22/11-22-0007-03-00bd-lb259-comment-resolution.docx In addition to the proposed changes by the commentor, please change L6 “NUM_SS” to “the TXVECTOR parameter NUM_SS” (https://mentor.ieee.org/802.11/dcn/22/11-22-0007-03-00bd-lb259-comment-resolution.docx) under CID 3018. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3019 | Stephan Sand | No | B.4.38.2 | 132 | 58 | T | B.4.38.2 | 132.58 | In the status column on P132L58 NGV1.1 is not defined | Replace "NGV1.1" with "NGVP1.1" |  |  |  | Resolution approved | Bo Sun | 21/2034r0 | A | ACCEPTED [01/11/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/21/11-21-2034-00-00bd-lb259-cr-clause-32-2-2-and-annex-b.docx) under CID 3019. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3020 | Stephan Sand | No | B.4.38.2 | 133 | 3 | T | B.4.38.2 | 133.03 | In the status column on P133L3 NGV1.2 is not defined | Replace "NGV1.2" with "NGVP1.2" |  |  |  | Resolution approved | Bo Sun | 21/2034r0 | A | ACCEPTED [01/11/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/21/11-21-2034-00-00bd-lb259-cr-clause-32-2-2-and-annex-b.docx) under CID 3020. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3021 | Stephan Sand | No | C3 | 135 | 26 | E | C3 | 135.26 | The "dot11NONNGVRadioEnvionrmentSupported" entry is not formated as the other entries | Format the entry as the other entries |  |  |  | Resolution approved | Editor | 22/0017r1 | V | REVISED [01/19/2022, EDITOR] Agreed in principle TGbd Editor: Incorporate the changes in 11-22-0017-01-00bd-Resolutions to Annex C. (https://mentor.ieee.org/802.11/dcn/22/11-22-0017-01-00bd-resolutions-to-annex-c.docx) under CID 3021. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3022 | Stephan Sand | No | C.3 | 135 | 42 | T | C.3 | 135.42 | In C.3 dot11NGVActivated is defined twice on P135L42-52 and differently on P136L2-10. | Delete second definition on P136L2fl10 |  |  |  | Resolution approved | Editor | 22/0017r1 | V | REVISED [01/19/2022, EDITOR] It turned out that the second “dot11NGVActivated” should be replaced with “dot11VirtualCSonOCBSecondaryImplemented” in DCN 21/0070r5. TGbd Editor: change “dot11NGVActivated” should be replaced to “dot11VirtualCSonOCBSecondaryImplemented” at P136L02 Note: TGbd Editor: the location is at P136L12. (https://mentor.ieee.org/802.11/dcn/22/11-22-0017-01-00bd-resolutions-to-annex-c.docx) under CID 3022. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3023 | Stephan Sand | No | C3. | 136 |  | T | C3. | 0.00 | The description of "dot11StationmeasurementPeriod" should be similar to "dot11RadioEnvironmentMeasurementPeriod". | Please add "It is written by an external management entity or the SME. Changes take effect as soon as practical in the implementations." after the first sentence in the description |  |  |  | Resolution approved | Editor | 22/0017r1 | A | ACCEPTED [01/19/2022, EDITOR] Accepted. Note: TGbd Editor: the location is at P136L12. (https://mentor.ieee.org/802.11/dcn/22/11-22-0017-01-00bd-resolutions-to-annex-c.docx) under CID 3023. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3024 | Lisa Ward | No | 17.3.5.5 | 57 | 54 | E | 17.3.5.5 | 57.54 | there seems to be an extra/unneeded '(' after 'sequence) and before '(with) in line 54 of the following: The first 7 bits of the scrambling sequence shall be set as shown in Table 17-7 (Contents of the first 7 bits of the scrambling sequence) (with field values defined in Table 17-8 (TXVECTOR parameter CH_BANDWIDTH_IN_NON_HT values), Table 17-8a (TXVECTOR parameter CH_BANDWIDTH_ IN_NON_NGV values),and Table 17-10 (DYN_BANDWIDTH_IN_NON_HT values) and Table 17-10a (DYN_BANDWIDTH_IN_NON_NGV values) and shall be also used to initialize the state of the scrambler Consider deleting the '(' | change "...7 bits of the scrambling sequence) (with field values defined in Table 17-8 ..." to "7 bits of the scrambling sequence) with field values defined in Table 17-8" |  |  |  | Resolution approved | Editor | 22/0016r2 | A | ACCEPTED [01/19/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0016-02-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 3024. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3025 | Lisa Ward | No | 17.3.5.5 | 58 | 18 | E | 17.3.5.5 | 58.18 | I wonder if DYN_BANDWIDTH_IN_NOT_HT should be instead DYN_BANDWIDTH_IN_NON_HT in table 17-7 under the condition column | Check if this is correct: "DYN_BANDWIDTH_IN_NOT_HT" If not, replace it with "DYN_BANDWIDTH_IN_NON_HT" for the 3 occurrences in table 17-7 |  |  |  | Resolution approved | Editor | 22/0016r2 | A | ACCEPTED [01/19/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0016-02-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 3025. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3026 | Lisa Ward | No | 5.2.3.2 | 24 | 26 | E | 5.2.3.2 | 24.26 | In the first sentence of the following paragraph, it says 'number of spatial streams member'. In the 2nd sentence it says 'number of spatial streams parameter'. It would be better to be consistent. Suggest changing 'member' in the 1st sentence to 'parameter' "The number of spatial streams member with value 1 or 2 indicates the number of spatial streams being used to transmit the PPDU carrying the MSDU. The number of spatial streams parameter with value 0 means that the number of spatial streams is decided by the MAC layer." | Change 'member' to 'parameter' in the following sentence: "The number of spatial streams member with value 1 or 2 indicates the number of spatial streams being used to transmit the PPDU carrying the MSDU." so that it reads instead: "The number of spatial streams parameter with value 1 or 2 indicates the number of spatial streams being used to transmit the PPDU carrying the MSDU. Also, consider changing 'member' to 'parameter' for the other terms in the subclause such as number of repetitions, permitted aggregation, etc. |  |  |  | Resolution approved | Editor | 22/0016r2 | V | REVISED [01/19/2022, EDITOR] Agreed in principle. However, by definition, the radio environment request vector parameter contains different members such as PPDU format, data rate/NGV-MCS, etc at P23L45. So, parameter should be replaced with member to be consistent. TGbd Editor: Incorporate the changes in 11-22-0016-02-00bd-Resolutions to Editorial Comments Part 2 (https://mentor.ieee.org/802.11/dcn/22/11-22-0016-02-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 3026. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3027 | yujin noh | Yes | 32.2.2 | 71 | 37 | T | 32.2.2 | 71.37 | add the reference for non-NGV duplicate PPDU format similar to the PPDU format for 10 MHZ channel spacing "as defined in Clause 17" | add "as defined in 32.3.9.10 (Non-NGV duplicate transmission)" as a reference to non-NGV duplicate PPDU format |  |  |  | Resolution approved | Bo Sun | 21/2034r0 | A | ACCEPTED [01/11/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/21/11-21-2034-00-00bd-lb259-cr-clause-32-2-2-and-annex-b.docx) under CID 3027. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3028 | yujin noh | Yes | 32.3.1 | 80 | 47 | T | 32.3.1 | 80.47 | add NGV-STF and NGV-LTF after RNGV-SIG fields because two field are part of NGV PHY preamble followed by PSDU. | For example, it could be "During transmission, a single PSDU is processed and appended to the NGV PHY preamble including L-STF, L-LTF, L-SIG, RL-SIG, NGV-SIG, RNGV-SIG, NGV-STF, and NGV-LTF fields to create the NGV PPDU." |  |  |  | Resolution approved | yujin noh | 22/0018r3 | A | ACCEPTED [01/20/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0018-03-00bd-resolutions-to-resolutions-to-ngv-phy-introduction-to-mathematical-description-of-signals.docx) under CID 3028. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3029 | yujin noh | Yes | 32.3.2 | 81 | 33 | T | 32.3.2 | 81.33 | N_NGV_LTF can be determined by SS and LTF_REP(not only SS) as currently described. | For example, sentence could be updated as ".....N_NGV_LTF can be 1, 2, or 4 and is determined by the total number of spatial streams .... and LTF_REP..." If needed, the reference to LTF_REP also could be added. |  |  |  | Resolution approved | yujin noh | 22/0018r3 | V | REVISED [01/20/2022, EDITOR] Agreed in principle. The same resolution to CID3029 and 3091. TGbd Editor: change to "can be 1, 2 or 4 and is determined by the total number of spatial streams being transmitted in the NGV PPDU and whether the NGV-LTF is repeated in NGV ranging NDP" (https://mentor.ieee.org/802.11/dcn/22/11-22-0018-03-00bd-resolutions-to-resolutions-to-ngv-phy-introduction-to-mathematical-description-of-signals.docx) under CID 3029. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3030 | yujin noh | Yes | 32.3.3 | 83 | 1 | T | 32.3.3 | 83.01 | MCS field should be NGV-MCS field. | as in comment |  |  |  | Resolution approved | yujin noh | 22/0018r3 | A | ACCEPTED [01/20/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0018-03-00bd-resolutions-to-resolutions-to-ngv-phy-introduction-to-mathematical-description-of-signals.docx) under CID 3030. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3031 | yujin noh | Yes | 32.3.3 | 83 | 2 | T | 32.3.3 | 83.02 | NGV SIG should be NGV-SIG field | as in comment |  |  |  | Resolution approved | yujin noh | 22/0018r3 | A | ACCEPTED [01/20/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0018-03-00bd-resolutions-to-resolutions-to-ngv-phy-introduction-to-mathematical-description-of-signals.docx) under CID 3031. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3032 | yujin noh | Yes | 32.3.4.4 | 85 | 24 | T | 32.3.4.4 | 85.24 | L-SIG should be L-SIG field | as in comment |  |  |  | Resolution approved | yujin noh | 22/0018r3 | A | ACCEPTED [01/20/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0018-03-00bd-resolutions-to-resolutions-to-ngv-phy-introduction-to-mathematical-description-of-signals.docx) under CID 3032. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3033 | yujin noh | Yes | 32.3.4.5 | 85 | 65 | T | 32.3.4.5 | 85.65 | NGV-SIG should be NGV-SIG field. | as in comment |  |  |  | Resolution approved | yujin noh | 22/0018r3 | A | ACCEPTED [01/20/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0018-03-00bd-resolutions-to-resolutions-to-ngv-phy-introduction-to-mathematical-description-of-signals.docx) under CID 3033. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3034 | yujin noh | Yes | 32.3.6 | 88 | 58 | T | 32.3.6 | 88.58 | add LTF_REP at the end of the Table 32-7 | as in comment |  |  |  | Resolution approved | yujin noh | 22/0018r3 | J | REJECTED [01/20/2022, EDITOR] It is defined in the Table 32-1 (TXVECTOR and RXVECTOR parameters) (https://mentor.ieee.org/802.11/dcn/22/11-22-0018-03-00bd-resolutions-to-resolutions-to-ngv-phy-introduction-to-mathematical-description-of-signals.docx) under CID 3034. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3035 | yujin noh | Yes | 32.3.7.1 | 89 | 8 | T | 32.3.7.1 | 89.08 | delete "and 21.3.7.1 (Notation)". There is no meaning added by refering 21.3.7.1 (Notation) | as in comment |  |  |  | Resolution approved | yujin noh | 22/0018r3 | J | REJECTED [01/20/2022, EDITOR] 21.3.7.1 is the first location to describe the dimension of the Q matrix which is important concept. It is good to have here in Notation part. (https://mentor.ieee.org/802.11/dcn/22/11-22-0018-03-00bd-resolutions-to-resolutions-to-ngv-phy-introduction-to-mathematical-description-of-signals.docx) under CID 3035. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3036 | yujin noh | Yes | 32.3.7.3 | 91 | 44 | T | 32.3.7.3 | 91.44 | MCS 0 or MCS 15 should be NGV-MCS 0 or NGV-MCS 15. | as in comment |  |  |  | Resolution approved | yujin noh | 22/0018r3 | V | REVISED [01/20/2022, EDITOR] TGbd editor: Check the same case through the spec. (https://mentor.ieee.org/802.11/dcn/22/11-22-0018-03-00bd-resolutions-to-resolutions-to-ngv-phy-introduction-to-mathematical-description-of-signals.docx) under CID 3036. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3037 | yujin noh | Yes | 32.3.8.2.2 | 93 | 5 | T | 32.3.8.2.2 | 93.05 | The cyclic shift values defined in 32.3.8.2.1 (Cyclic shift for pre-NGV modulated fields) have nothing to do with the values in Cyclic shift for NGV modulated field. | delete the text "The cyclic shift values defined in 32.3.8.2.1 (Cyclic shift for pre-NGV modulated fields) apply to NGV-SIG and RNGV-SIG fields in the NGV format preamble." |  |  |  | Resolution approved | yujin noh | 22/0019r2 | A | ACCEPTED [01/20/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0019-02-00bd-resolutions-to-resolutions-to-ngv-preamble-and-ngv-receive-procedure.docx) under CID 3037. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3038 | yujin noh | Yes | 32.3.8.3 | 93 | 43 | T | 32.3.8.3 | 93.43 | MCS0 or MCS15 should be NGV-MCS 0 or NGV-MCS 15 | as in comment |  |  |  | Resolution approved | yujin noh | 22/0019r2 | A | ACCEPTED [01/20/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0019-02-00bd-resolutions-to-resolutions-to-ngv-preamble-and-ngv-receive-procedure.docx) under CID 3038. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3039 | yujin noh | Yes | 32.3.8.7 | 97 | 17 | T | 32.3.8.7 | 97.17 | delete perid before B14 | as in comment |  |  |  | Resolution approved | yujin noh | 22/0019r2 | A | ACCEPTED [01/20/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0019-02-00bd-resolutions-to-resolutions-to-ngv-preamble-and-ngv-receive-procedure.docx) under CID 3039. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3040 | yujin noh | Yes | 32.3.8.9 | 98 | 57 | T | 32.3.8.9 | 98.57 | delete period before ,28. -28.,28 should be -28,28 | as in comment |  |  |  | Resolution approved | yujin noh | 22/0019r2 | A | ACCEPTED [01/20/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0019-02-00bd-resolutions-to-resolutions-to-ngv-preamble-and-ngv-receive-procedure.docx) under CID 3040. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3041 | yujin noh | Yes | 32.3.8.10 | 99 | 31 | T | 32.3.8.10 | 99.31 | This is the first place to use NGV-LTF such that delete NGV Long Training field and use NGV-LTF instead. | For examplem, "The NGV Long Training field (NGV-LTF) field provides" should be "The NGV-LTF field provides" |  |  |  | Resolution approved | yujin noh | 22/0019r2 | A | ACCEPTED [01/20/2022, EDITOR] Agreed in principle. The intention in the comment seems that this is not the first place to use NGV-LTF. (https://mentor.ieee.org/802.11/dcn/22/11-22-0019-02-00bd-resolutions-to-resolutions-to-ngv-preamble-and-ngv-receive-procedure.docx) under CID 3041. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3042 | Hiroyuki Motozuka | No | 1 | 1 | 5 | G | 1 | 1.05 | REVme is not an amendment or baseline of 11bd. | Remove "as amended by IEEE P802.11-REVme(TM)/D0.4," |  |  |  | Resolution approved | Editor | 22/0015r2 | A | ACCEPTED [01/18/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0015-02-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 3042. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3043 | Hiroyuki Motozuka | No | 1 | 1 | 32 | G | 1 | 1.32 | There are 5 amendments preceeding 11bd (ax, ay, ba, az, bc) so this amendment should be Amendment 6. As a matter of the fact, 11bc for sale has title of "Amendment 5" | Change "Amendment 5" to "Amendment 6". |  |  |  | Resolution approved | Editor | 22/0015r2 | J | REJECTED [01/18/2022, EDITOR] Based on the discussion in Editor’s meeting on 1/17/2022, 11bd is decided to Amendment 5 in accordance with Projected REVCOM Date. (https://mentor.ieee.org/802.11/dcn/22/11-22-0015-02-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 3043. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3044 | Hiroyuki Motozuka | No | 4.3.17 | 19 | 12 | T | 4.3.17 | 19.12 | Although it is doubtful that such implementation exists, it is not ruled out in 802.11-2020 to implement a DMG STA with dot11OCBActivated set to true. Defining new restrictions to such STAs might be regarded as backward compatibility issue on standardization. | - Define a new MIB attribute "dot11DMGOCBActivated" and add to Dot11DMGSTAConfigEntry. - Replace dot11OCBActivated with dot11DMGOCBActivated, at P20L60, P38L47(in Table 9-45), P41L42, P47L14, P47L21, P47L35, P47L46, P61L15, P65L25, P65L38, P65L52, P65L57. - In subclause 4.3.17 P19L11, replace "A STA with dot11OCBActivated equal to true may operate as a DMG STA with MAC and MLME functions ..." with "A STA with dot11OCBActivated equal to true may operate as a DMG STA. A DMG STA with dot11DMGOCBActivated equal to true provides MAC and MLME functions..." |  |  |  | Ready for motion | Hiroyuki Motozuka | 22/0091r3 | V | REVISED [02/08/2022, EDITOR] Agreed in principle. Proposed change: - Replace dot11OCBActivated with dot11DMGOCBActivated at P20L60, P38L47(in Table 9-45), P41L42, P47L14, P47L21, P47L35, P47L46, P61L15, P65L25, P65L38, P65L52, P65L57. - Replace “if(If) the STA is a DMG STA,” with “if(If) the STA is a DMG STA for which dot11DMGOCBActivated is true,” P50L46, P50L53. - In addition to above, incorporate the change for subclauses 4.3.17 and C.3 in https://mentor.ieee.org/802.11/dcn/22/11-22-0091-03-00bd-d3-0-comment-resolution-related-to-dmg-sta-communicating-ocb.docx under CID3044 (https://mentor.ieee.org/802.11/dcn/22/11-22-0091-03-00bd-d3-0-comment-resolution-related-to-dmg-sta-communicating-ocb.docx) under CID 3044. | Yes |  |  |  |  | 2022-02-08 17:59
3045 | Hiroyuki Motozuka | No | 6.3.126 | 29 | 9 | E | 6.3.126 | 29.09 | 11bc already uses subclauses 6.3.126 and 6.3.127. Additionally, for readers convenience, the subclauses may be re-ordered within this amendment so that 5.9GHz related subclauses are arranged nearby. | Change subclause - 6.3.126(Cancel transmissions...) to 6.3.128, - 6.3.127(DMG...) to 6.3.130, and - 6.3.128(NGV radio environment measurement) to 6.3.129, and reorder the subclauses based on the new subclause number. |  |  |  | Resolution approved | Editor | 22/0015r2 | A | ACCEPTED [01/18/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0015-02-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 3045. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3046 | Hiroyuki Motozuka | No | C.3 | 138 | 36 | T | C.3 | 138.36 | "dot11PhyNGVEntry 5" is used twice. | Please change "dot11PhyNGVEntry 5" to "dot11PhyNGVEntry 6" for dot11NGVDYN20MAllowed that is at P138L36. |  |  |  | Resolution approved | Editor | 22/0017r1 | A | ACCEPTED [01/19/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0017-01-00bd-resolutions-to-annex-c.docx) under CID 3046. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3047 | Hiroyuki Motozuka | No | C.3 | 138 | 51 | T | C.3 | 138.51 | The values for dot11Compliances are maintained in the ANA database, but dot11PhyNGVComplianceGroup is not on the current ANA database(11-11/0270r57), so "dot11Compliances 25" for it (P138L65) is not appropriate. Also, when we follow practice of the other amendments, dot11***Compliance should be in dot11Compliences, and dot11***ComplianceGroup should be in dot11Groups of ANA Database. | - Add definition for dot11NGVCompliance in Annex C of 11bd; - Change allocation of {dot11Compliances 25} from dot11NGVComplianceGroup to dot11NGVCompliance; - Get two allocations {dot11Groups <ANA>} for dot11NGVComplianceGroup(P138L51) and dot11PhyNGVComplianceGroup(P138L65). |  |  |  | Resolution approved | Hiroyuki Motozuka | 22/0033r2 | V | REVISED [01/21/2022, EDITOR] Change the description for dot11NGVComplianceGroup and dot11PhyNGVComplianceGroup so the variables have allocated values in dot11Groups. Add description for “dot11Compliance MODULE-COMPLIANCE” and “dot11NGVCompliance MODULE-COMPLIANCE”. TGbd Editor: Incorporate the change in https://mentor.ieee.org/802.11/dcn/22/11-22-0033-02-00bd-d3-0-comment-resolution-annex-c-mib.docx for CID 3047. Note to the TGbd Editor: Please process <ANA> values in the proposed text. (https://mentor.ieee.org/802.11/dcn/22/11-22-0033-02-00bd-d3-0-comment-resolution-annex-c-mib.docx) under CID 3047. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3048 | Kazuto Yano | No | 4.3.17a | 19 | 39 | E | 4.3.17a | 19.39 | "clause E.1" should be "subclause E.1" or "E.1". | Please correct as in the comment. |  |  |  | Ready for motion | Hiroyuki Motozuka | 22/0091r3 | V | REVISED [02/08/2022, EDITOR] Discussion: “E.1” looks popular in REVme. Proposed change: Delete “clause” from “clause E.1” at P19.39 in Draft D3.0. (https://mentor.ieee.org/802.11/dcn/22/11-22-0091-03-00bd-d3-0-comment-resolution-related-to-dmg-sta-communicating-ocb.docx) under CID 3048. | Yes |  |  |  |  | 2022-02-08 17:55
3049 | Kazuto Yano | No | 9.4.2.308 | 40 | 46 | E | 9.4.2.308 | 40.46 | Periods at the end this sentence are duplicated. | Please remove one period. |  |  |  | Resolution approved | Editor | 22/0016r2 | A | ACCEPTED [01/19/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0016-02-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 3049. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3050 | Kazuto Yano | No | 9.5.3 | 41 | 27 | E | 9.5.3 | 41.27 | In Figure 9.849-a, the Poll Required subfield should use B16, not B9-B23. | Please correct it. |  |  |  | Resolution approved | Editor | 22/0016r2 | A | ACCEPTED [01/19/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0016-02-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 3050. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3051 | Kazuto Yano | No | 31.4 | 66 | 39 | E | 31.4 | 66.39 | It is not clear which paragraph(s) indicates "the following differences". | Please apply any marking (such as indent) to the paragraph(s) that indicates "the following differences". |  |  |  | Resolution approved | Stephan Sand | 22/0007r7 | V | REVISED [01/21/2022, EDITOR] In principle agree with comment. TGbd editor: Please incorporate the changes in https://mentor.ieee.org/802.11/dcn/22/11-22-0007-07-00bd-lb259-comment-resolution.docx and grant editorial license to fix field and subfield namings adhering to 802.11 style guide. (https://mentor.ieee.org/802.11/dcn/22/11-22-0007-05-00bd-lb259-comment-resolution.docx) under CID 3051. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3052 | Kazuto Yano | No | 31.5 | 67 | 8 | E | 31.5 | 67.08 | It is not clear which paragraph(s) indicates "the following rules". | Please apply any marking (such as indent) to the paragraph(s) that indicates "the following rules". |  |  |  | Resolution approved | Stephan Sand | 22/0007r3 | V | REVISED [01/18/2022, EDITOR] In principle agree with comment. TGbd editor: Please incorporate the changes in https://mentor.ieee.org/802.11/dcn/22/11-22-0007-03-00bd-lb259-comment-resolution.docx (https://mentor.ieee.org/802.11/dcn/22/11-22-0007-03-00bd-lb259-comment-resolution.docx) under CID 3052. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3053 | Kazuto Yano | No | 32.3.9.9 | 107 | 45 | T | 32.3.9.9 | 107.45 | N_SYM is not defined in 32.3.9.4. | Please refer the correct subclause. |  |  |  | Ready for motion | Rui Cao | 22/0150r0 | V | REVISED [02/08/2022, EDITOR] TGbd editor: please replace P107L45 with “where N_SYM is the total number of data symbols in the Data field, and is given in Clause 21.3.10.5.4 (LDPC coding) (computed using Equation (19-41) in step d) of Clause 19.3.11.7.5 (LDPC PPDU encoding process)).“ (https://mentor.ieee.org/802.11/dcn/22/11-22-0150-00-00bd-cid-3053-for-midambles.docx) under CID 3053. | Yes |  |  |  |  | 2022-02-08 18:00
3054 | Robert Stacey | No | 3.2 | 17 | 13 | T | 3.2 | 17.13 | "A feature of a VHT STA or a NGV STA..." It is feature of both STA types, not just one or the other. Similarly at 17.23. | Change "or" to "and" and 17.13 and 17.23 |  |  |  | Resolution approved | Joseph Levy | 22/0112r0 | J | REJECTED [01/20/2022, EDITOR] Features that are used by multiple STA types typically use “or” between the types. e.g., bandwidth signaling transmitter address (TA): A TA that is used by a very high throughput (VHT) station (STA) or a high-efficiency (HE) STA to indicate the presence of additional signaling … and individually addressed resource unit (RU): A resource unit in a high-efficiency (HE) multi-user (MU) physical layer (PHY) protocol data unit (PPDU) transmitted by an access point (AP) or a tunneled direct link setup (TDLS) peer station (STA) that is intended for a single associated non-AP STA or a TDLS peer STA, respectively. (https://mentor.ieee.org/802.11/dcn/22/11-22-0112-00-00bd-some-clause-3-comment-resolutions-for-lb-259.docx) under CID 3054. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3055 | Robert Stacey | No | 4.3.17a | 19 | 53 | E | 4.3.17a | 19.53 | The relationship of the dot bullets items to the dash bullet items is not clear and should be explicitly stated. Also, it is not clear if the mandatory support for some items applies to all 10 MHz and 20 MHz PPDUs or just 10 MHz and 20 MHz NGV PPDUs. | Rewrite as follows (dash bullet level): - Mandatory support for the 10 MHz NGV PPDU format and optional support for the 20 MHz NGV PPDU and 20 MHz non-NGV duplicate PPDU formats. - For the 20 MHz and 10 MHz NGV PPDU, mandatory support for LDPC coding, midambles, BPSK-DCM, and 256-QAM. - For the 20 MHz NGV PPDU, mandatory support for transmit spectral mask C2. |  |  |  | Resolution approved | Editor | 22/0016r2 | V | REVISED [01/19/2022, EDITOR] Agreed in principle. TGbd Editor: Incorporate the changes in 11-22-0016-02-00bd-Resolutions to Editorial Comments Part 2 (https://mentor.ieee.org/802.11/dcn/22/11-22-0016-02-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 3055. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3056 | Robert Stacey | No | 4.3.17a | 20 | 40 | E | 4.3.17a | 20.40 | Non-TB Ranging: unnecessary capitalization | Change to "non-TB ranging". TGaz should make a similar change. |  |  |  | Resolution approved | Editor | 22/0016r2 | V | REVISED [01/19/2022, EDITOR] Agreed in principle. There are additional locations to be modified as suggested. TGbd Editor: Incorporate the changes as proposed at P20L41, P38L13, P66L5, P66L21, P66L24, P141L25, and P142L40. TGbd Ediotr: as for reference, 11.21.6.4.4 (Non-TB Ranging measurement exchange) should be replaced with 11.21.6.4.4 (Non-TB ranging measurement exchange) at P20L43, P38L13, P66L5, P66L52, P129L60, and P131L06. TGbd Editor: Incorporate the changes in 11-22-0016-02-00bd-Resolutions to Editorial Comments Part 2 (https://mentor.ieee.org/802.11/dcn/22/11-22-0016-02-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 3056. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3057 | Robert Stacey | No | 5.2.3.2 | 23 | 48 | T | 5.2.3.2 | 23.48 | The slash in "non-NGV/NGV" and "data rate/NGV-MCS" is ambiguous. | Change to "PPDU format (non-NGV or NGV)" and "data rate (if non-NGV PPDU) or "NGV-MCS (if NGV PPDU)" respectively |  |  |  | Resolution approved | Liwen Chu | 22/0048r1 | J | REJECTED [01/20/2022, EDITOR] Discusison: “/” is widely used in 802.11 specification as “or”. (https://mentor.ieee.org/802.11/dcn/22/11-22-0048-01-00bd-d3-0-comment-resolution-5-3-2.docx) under CID 3057. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3058 | Robert Stacey | No | 5.2.3.2 | 24 | 7 | T | 5.2.3.2 | 24.07 | I see a bunch of problems here. 1. Since this is an abstract interface, using specific numeric values is unnecessary. 2) It is not clear what it means for the PPDU format if it is decided by the MAC. Isn't it always decided by the MAC? | Explain what "PPDU format = PPDU format decided by MAC" means. Or remove and just use "non-NGV" and "NGV" as settings for PPDU format. |  |  |  | Resolution approved | Liwen Chu | 22/0048r1 | J | REJECTED [01/20/2022, EDITOR] Discussion: there is a requirement for the up layer to decide the PPDU format in NGV device, e,g, when the up layer has more information than MAC layer. (https://mentor.ieee.org/802.11/dcn/22/11-22-0048-01-00bd-d3-0-comment-resolution-5-3-2.docx) under CID 3058. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3059 | yujin noh | Yes | 32.3.13 | 120 | 21 | T | 32.3.13 | 120.21 | Fill TBD | as in comment |  |  |  | Resolution approved | yujin noh | 22/0019r2 | V | REVISED [01/20/2022, EDITOR] Agreed in principle. Add the reference to fill the TBD. Same resolution is applied to CIDs 3000 and 3059. TGbd Editor: replace TBD with 32.3.11.5 (https://mentor.ieee.org/802.11/dcn/22/11-22-0019-02-00bd-resolutions-to-resolutions-to-ngv-preamble-and-ngv-receive-procedure.docx) under CID 3059. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3060 | Song-Haur An | Yes | 3.2 | 17 | 17 | T | 3.2 | 17.17 | The sentence " ... negotiates a potentially reduced channel width (compared to the channel width indicated by the RTS) for subsequent transmissions within the current transmission opportunity (TXOP)" suggests that the dynamic bandwidth operation can be initiated only when the RTS specifies 20 MHz channel width to begin with for the NGV STA. It seems counter-intuitive because the mandatory channel width for the NGV PPDU is 10 MHz, and 20 MHz is optional. May need a separate paragraph to illustrate the dynamic bandwidth operation for the NGV PPDU. | As in comment. |  |  |  | Resolution approved | Joseph Levy | 22/0112r0 | J | REJECTED [01/20/2022, EDITOR] Dynamic bandwidth operation is only applicable for an NGV STA using a 20 MHz channel. If the STA configured to use a 10 MHz channel there can be no reduction in the bandwidth, as all PPDUs will be transmitted over the 10 MHz channel. Dynamic bandwidth operation only works for a STA operating using a non-NGV duplicate PPDU in a 20 MHz bandwidth, such a STA can dynamically reduce its BW to 10 MHz by sending a single non-NGV PPDU 10 MHz PPDU (a non-duplicate PPDU) on one of the two channels. (https://mentor.ieee.org/802.11/dcn/22/11-22-0112-00-00bd-some-clause-3-comment-resolutions-for-lb-259.docx) under CID 3060. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3061 | Song-Haur An | Yes | 4.3.17a | 19 | 31 | T | 4.3.17a | 19.31 | Change "higher" to "better" or "lower" to reflect the intended objective. | As in comment. |  |  |  | Resolution approved | Stephan Sand | 22/0007r3 | J | REJECTED [01/18/2022, EDITOR] As explained by the commenter of CID 2053 in LB254 of 11bd D2.0, “The number that represents the sensitivity is lower (more negative) but the sensitivty is higher (more sensitive).” Since “higher sensitivity” is technical more accurate than “better sensitivity”, the proposed change is rejected. (https://mentor.ieee.org/802.11/dcn/22/11-22-0007-03-00bd-lb259-comment-resolution.docx) under CID 3061. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3062 | Song-Haur An | Yes | 4.3.17a | 19 | 38 | T | 4.3.17a | 19.38 | Please add or clarify the purpose of this"co-located" sentence. As IS, it's an open statement that conveys no connection between the said NGV STA and the said DMG STA. | Please add the objective of this sentence or delete it. |  |  |  | Ready for motion | Hiroyuki Motozuka | 22/0091r3 | V | REVISED [02/08/2022, EDITOR] Discussion In D3.0, an example procedure to perform DMG discovery OCB using assist of higher layer information exchange is shown in 11.1.4.7. This information exchange is, although not limited, performed over 5.9 GHz band by co-located NGV STAs in most expected scenario. Propose to add this explanation into 4.3.17a. TGbd Editor: Please incorprate the change for 4.3.17a in https://mentor.ieee.org/802.11/dcn/22/11-22-0091-03-00bd-d3-0-comment-resolution-related-to-dmg-sta-communicating-ocb.docx under CID3062. (https://mentor.ieee.org/802.11/dcn/22/11-22-0091-03-00bd-d3-0-comment-resolution-related-to-dmg-sta-communicating-ocb.docx) under CID 3062. | Yes |  |  |  |  | 2022-02-08 17:55
3063 | Song-Haur An | Yes | 4.3.17a | 19 | 65 | T | 4.3.17a | 19.65 | Not clear about what "the same Channel" is meant. Does it mean the allocated DSRC spectrum or something else? Please clarify. | As in comment. |  |  |  | Resolution approved | Stephan Sand | 22/0007r3 | J | REJECTED [01/18/2022, EDITOR] The terms channel and channel spacing are defined in 802.11-2020 in Subclause 3.1. An NGV STA is using either a channel with 10 MHz or 20 MHz channel spacing and corresponding PPDU width. The possible channel allocations in the 5.9 GHz band are defined in Annex E.1 of 802.11-2020. See also CID 3064 (https://mentor.ieee.org/802.11/dcn/22/11-22-0007-03-00bd-lb259-comment-resolution.docx) under CID 3063. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3064 | Song-Haur An | Yes | 4.3.17a | 20 | 14 | T | 4.3.17a | 20.14 | Not clear about what "the same Channel" is meant. Does it mean the allocated DSRC spectrum or something else? Please clarify. | As in comment. |  |  |  | Resolution approved | Stephan Sand | 22/0007r3 | J | REJECTED [01/18/2022, EDITOR] The terms channel and channel spacing are defined in 802.11-2020 in Subclause 3.1. An NGV STA is using either a channel with 10 MHz or 20 MHz channel spacing and corresponding PPDU width. The possible channel allocations in the 5.9 GHz band are defined in Annex E.1 of 802.11-2020. See also CID 3063 (https://mentor.ieee.org/802.11/dcn/22/11-22-0007-03-00bd-lb259-comment-resolution.docx) under CID 3064. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3065 | Song-Haur An | Yes | 5.2.3.2 | 24 | 28 | G | 5.2.3.2 | 24.28 | P24L28 says, "The number of spatial streams parameter with value 0 means that the number of spatial streams is decided by the MAC layer." As a result, there is a need to add a paragraph to illustrate how the MAC layer decides the number of the spatial streams (criteria and the procedure). Pointing to some VHT subclause is OK wherever is applicable. This "... decided by the MAC layer" is applied to other members of the radio environment request vector as well. | As in comment. |  |  |  | Resolution approved | Liwen Chu | 22/0048r1 | J | REJECTED [01/20/2022, EDITOR] Discussion: NGV STA has d ot11OCBActivated being equal to true.The behavior of subclause 10.6 will be followed per the following sentence in 31.1: An NGV STA supports the MAC and MLME functions defined in 31.2 (Operation in the 5.9 GHz band) in addition to the MAC functions defined in Clause 10 (MAC sublayer functional description) and the MLME functions defined in Clause 11 (MLME) for STAs communicating Data frames outside the context of a BSS. (https://mentor.ieee.org/802.11/dcn/22/11-22-0048-01-00bd-d3-0-comment-resolution-5-3-2.docx) under CID 3065. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3066 | John Coffey | Yes | 32.3.11 | 112 | 24 | T | 32.3.11 | 112.24 | "The requirements on receiver minimum input sensitivity in 32.3.11.1 (Receiver minimum input sensitivity), adjacent channel rejection in 32.3.11.2 (Adjacent channel rejection) and nonadjacent channel rejection in 32.3.11.3 (Nonadjacent channel rejection) are derived from the corresponding requirements for VHT PPDUs specified in 21.3.18 (VHT receiver specification)." Apparently, this statement functions as an explanatory note (since there is no normative statement in it). However, the explanation is puzzling. Clause 21.3.18 specifies minimum receiver sensitivities for VHT PPDUs that use BCC, whereas 32.3.11 specifies LDPC. Presumably, this should make a difference, but the numbers are the same for the 20 MHz case. Also, no "derivation" is given in this draft. Rather than giving a derivation, or adapting the wording, it seems simplest to delete the cited sentence. | Delete the cited sentence. |  |  |  | Ready for motion | Rui Cao | 22/0152r1 | V | REVISED [02/15/2022, EDITOR] Agree that the word “derived” is not accurate, and the statement text here is not normative. Move the description to a note and change “derived” to “reference”. TGbd editor: please make the changes as in: https://mentor.ieee.org/802.11/dcn/22/11-22-0152-01-00bd-d3-0-cr-for-receive-specification.docx (https://mentor.ieee.org/802.11/dcn/22/11-22-0152-01-00bd-d3-0-cr-for-receive-specification.docx) under CID 3066. | Yes |  |  |  |  | 2022-02-15 17:35
3067 | John Coffey | Yes | 32.3.11 | 112 | 12 | T | 32.3.11 | 112.12 | "The requirements ... [in the next few subclauses] ... apply to PPDUs that meet all the following conditions:(#2199) -- 1.6 µs GI is used. -- NGV-LTF-2x is used. -- LDPC is used. -- The PPDU is an NGV PPDU." If the PPDU is an NGV PPDU, then isn't LDPC automatically used? It seems so from 32.1.1 (69.34) and 32.3.9.4 (103.13). Therefore, it is superfluous (and confusing) to call out LDPC here. | Delete "-- LDPC is used." |  |  |  | Ready for motion | Rui Cao | 22/0152r1 | V | REVISED [02/15/2022, EDITOR] Agree with the commenter in principle. Also remove “1.6us GI” as it is the only GI format. TGbd editor: please make the changes as in: https://mentor.ieee.org/802.11/dcn/22/11-22-0152-01-00bd-d3-0-cr-for-receive-specification.docx (https://mentor.ieee.org/802.11/dcn/22/11-22-0152-01-00bd-d3-0-cr-for-receive-specification.docx) under CID 3067. | Yes |  |  |  |  | 2022-02-15 17:35
3068 | John Coffey | Yes | 32.3.11 | 112 | 12 | T | 32.3.11 | 112.12 | ""The requirements ... [in the next few subclauses] ... apply to PPDUs that meet all the following conditions: ... -- NGV-LTF-2x is used." However, compare 99.64 (32.3.8.10): "When BPSK-DCM is applied to the NGV Data field of PPDU in 10 MHz, the NGV-LTF symbol uses NGV-LTF-2x-Repeat regardless of the value of the LTF Format subfield in the NGV-SIG field." Isn't this a contradiction? | Change "NGV-LTF-2x is used" to "NGV-LTF-2x-Repeat is used for BPSK-DCM in 10 MHz; NGV-LTF-2x is used otherwise" |  |  |  | Ready for motion | Rui Cao | 22/0152r1 | V | REVISED [02/15/2022, EDITOR] Agree with the commenter in principle. Rephrase the sentence with clarification of NGV-LTF format. TGbd editor: please make the changes as in: https://mentor.ieee.org/802.11/dcn/22/11-22-0152-01-00bd-d3-0-cr-for-receive-specification.docx (https://mentor.ieee.org/802.11/dcn/22/11-22-0152-01-00bd-d3-0-cr-for-receive-specification.docx) under CID 3068. | Yes |  |  |  |  | 2022-02-15 17:35
3069 | John Coffey | Yes | 32.3.11.1 | 112 | 34 | T | 32.3.11.1 | 112.34 | "The PSDU length shall be 2048 octets for BPSKDCM or 4096 octets for all other modulations." There is no need to distinguish BPSK DCM from other modulations in this way. It is true that BPSK-DCM *in 10 MHz* cannot specify 4096 octets, as that would exceed the maxuimum PPDU duration. However, that does not explain why BPSK-DCM in 20 MHz also specifies 2048 octets. One possible solution would be to add "in 10 MHz" after BPSK-DCM here. However, the simpler and better solution, and the one proposed here, is to define the same reference length, 2048 octets, for all modulation types. Plotting error probabilitiy curves versus received signal power at 2048 octets and 4096 octets for any normal device will produce curves that differ by tiny amounts (perhaps a couple of tenths of a dB) and that are separated by a vast gulf (10 dB or more) from the minimum receiver senstivity requirement, and so there is no material change in performance. | Change the cited sentence to "The PSDU length shall be 2048 octets." |  |  |  | Ready for motion | Rui Cao | 22/0152r1 | J | REJECTED [02/15/2022, EDITOR] The current 11bd defines shorter PSDU length of 2048 octets for BPSK-DCM due to the limitation of max LSIG Length (for 10MHz/Nss1). The generalization for BPSK-DCM is trying to spell out the different requirement for the new modulation of BPSK-DCM, so readers can easily pick up the information when reading the spec. This is the same definition practice as 11ax. Generally agree that the sensitivity difference between 2048 octets and 4096 octets is likely not significant, however, if the 11bd spec further generalize 2048 octets for all MCS/NSS/BW, while 4096 octets is used for all other PHY amendments as the baseline PSDU length, it will likely cause confusion and trigger more questions from readers. Prefer to keep the consistency, and indicate the difference only for new MCS. (https://mentor.ieee.org/802.11/dcn/22/11-22-0152-01-00bd-d3-0-cr-for-receive-specification.docx) under CID 3069. | Yes |  |  |  |  | 2022-02-15 17:36
3070 | John Coffey | Yes | 32.3.11.1 | 112 | 46 | T | 32.3.11.1 | 112.46 | The minimum receiver sensitivity requirement for BPSK-DCM in 20 MHz (-82 dBm) is identical to the minimum receiver sensitivity requirement for BPSK in 20 MHz. This is jarring: it would be natural for BPSK-DCM, with half the data rate, to have a requirement 3 dB lower than for BPSK, as in the proposed resolution. Note: a similar comment in the last round was rejected based on reasons dealing with preamble processing (no 3 dB boost, and no NGV-LTF-2x-Repeated, unlike the 10 MHz case). But this is essentially irrelevant for the minimum receiver sensitivity *requirement*, which is much, much looser than typical minimum receiver sensitivity performance (e.g., typical performance of -91 dBm or so for 11a/g 6 Mbps, versus -82 dBm requirement, and the preamble processing not the limiting factor even there). The minimum receiver sensitivity *requirement* simply sets a very loose lower limit on acceptable performance for all modes. If we are to bother specifying these at all, the values should at least be reasonable. A value of -85 dBm should still provide large margins for devices. | In Table 32-15, change the entry for BPSK-DCM for 20 MHz from "-82" to "-85". |  |  |  | Ready for motion | Rui Cao | 22/0152r1 | J | REJECTED [02/15/2022, EDITOR] Agree that most products on the market can do better than -82dBm for BPSK. The number in the table serves as a guideline to reflect the difference among MCS, BW, etc. As the regular preamble is designed to match MCS0 sensitivity, the 3dB better sensitivity of BPSK-DCM needs preamble definition support of power boost and LTF repetition. For 20 MHz transmission, there is no preamble power boost or NGV LTF repetition, the spec should not define 3dB lower sensitivity as a baseline requirement. In addition, this is the same definition practice for 11ax DCM. Better keep the consistency unless there is strong reason to change globally in Maintenence amendment. (https://mentor.ieee.org/802.11/dcn/22/11-22-0152-01-00bd-d3-0-cr-for-receive-specification.docx) under CID 3070. | Yes |  |  |  |  | 2022-02-15 17:36
3071 | Joseph Levy | No | 4.3.17 | 19 | 15 | T | 4.3.17 | 19.15 | A DMG STA operating OCB is not restricted to the case where it operates with the MAC and MLME functions defined in 31.3. Therefore, this type of STA (one that does operate with the MAC and MLME functions 31.3) be in referred to as a DMG STA communicating OCB is confusing because there are other DMG STA that don not operate with the MAC and MLME functions of 31.3 that could be considered a DMG STA communicating OCB. | Replace: "This kind of STA is referred to as a DMG STA communication outside the context of a BSS (OCB). With: "A DMG STA communicating OCB may be this kind of STA." |  |  |  | Ready for motion | Hiroyuki Motozuka | 22/0091r3 | V | REVISED [02/08/2022, EDITOR] Agreed in principle. The term “A DMG STA communicating OCB” should not be used for representing a DMG STA with 11bd features. Proposed change: - Remove "This kind of STA is referred to as a DMG STA communication outside the context of a BSS (OCB).” at P19L15 of D3.0. - Replace “DMG STA communicating OCB” with “DMG STA for which dot11DMGOCBActivated is true” at P19L38 (4.3.17a), P43L41(10.3.6) and P51L62(11.27.1.1). (https://mentor.ieee.org/802.11/dcn/22/11-22-0091-03-00bd-d3-0-comment-resolution-related-to-dmg-sta-communicating-ocb.docx) under CID 3071. | Yes |  |  |  |  | 2022-02-08 17:58
3072 | Joseph Levy | No | 4.3.17 | 19 | 15 | E | 4.3.17 | 19.15 | OCB is defined in the first paragraph in the OCB clause, so there is no need to spell it out in the forth paragraph. Simply used OCB. | Delete "outside the context of a BSS" and remove the parentheses from around OCB. |  |  |  | Resolution approved | Editor | 22/0016r2 | A | ACCEPTED [01/19/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0016-02-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 3072. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3073 | Joseph Levy | No | 4.3.17 | 19 | 7 | E | 4.3.17 | 19.07 | Clause 4.3.17 is not the OCB clause in the current baseline, it is clause 4.3.19 (.11 REVmd D1.0) | Correct the clause reference to 4.3.19 |  |  |  | Resolution approved | Editor | 22/0015r2 | J | REJECTED [01/18/2022, EDITOR] Given the resolution in CID3042, 11bd D3.0 should consider IEEE Std 802.11™-2020, 11ax, 11ay, 11ba, 11az, and 11bc (not REVmeD0.4) because we have REVme publishing after 11bd. No need to update the number based on REVme D0.4. (https://mentor.ieee.org/802.11/dcn/22/11-22-0015-02-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 3073. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3074 | Joseph Levy | No | 4.3.17a | 19 | 22 | E | 4.3.17a | 19.22 | The clause reference 4.3.17a is not correct as the intent is to place this clause following the OCB clause (4.3.19 in .11 REVmd D1.0) | Correct the clause reference to 4.3.19a |  |  |  | Resolution approved | Editor | 22/0015r2 | J | REJECTED [01/18/2022, EDITOR] Given the resolution in CID3042, 11bd D3.0 should consider IEEE Std 802.11™-2020, 11ax, 11ay, 11ba, 11az, and 11bc (not REVmeD0.4) because we have REVme publishing after 11bd. No need to update the number based on REVme D0.4. (https://mentor.ieee.org/802.11/dcn/22/11-22-0015-02-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 3074. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3075 | Joseph Levy | No | 4.3.17a | 19 | 25 | E | 4.3.17a | 19.25 | NGV must be spelled out at first use, in the paragraph, it is not enough to spell it out in the clause title. | Replace the first instance of: "NGV" With: "Next Generation Vehicle-to-everything (NGV)" |  |  |  | Resolution approved | Editor | 22/0016r2 | A | ACCEPTED [01/19/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0016-02-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 3075. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3076 | Joseph Levy | No | 4.3.17.a | 19 | 39 | E | 4.3.17.a | 19.39 | What is clause E.1? | Insert the correct clause reference. |  |  |  | Ready for motion | Hiroyuki Motozuka | 22/0091r3 | V | REVISED [02/08/2022, EDITOR] The issue is addressed in CID 3048 and 3079. Resolution for CID3048 (22/0091) proposes to replace “clause E.1” with “E.1”, and resolution for CID3079 (22/0015r1) proposes to replace “E.1” with “E.1 (Country information and operating classes)” with cross-reference link. TGbd Editor: No further action is required for CID3076. (https://mentor.ieee.org/802.11/dcn/22/11-22-0091-03-00bd-d3-0-comment-resolution-related-to-dmg-sta-communicating-ocb.docx) under CID 3076. | Yes |  |  |  |  | 2022-02-08 17:55
3077 | Joseph Levy | No | 4.3.17.a | 19 | 42 | T | 4.3.17.a | 19.42 | Fairness is not a defined 802.11 term and does not seem to clearly define that an NGV STA will fairly contend with non-NGV STAs for the medium. | Replace "fairness" With: "fairness in contending for the medium" |  |  |  | Resolution approved | Stephan Sand | 22/0007r3 | A | ACCEPTED [01/18/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0007-03-00bd-lb259-comment-resolution.docx) under CID 3077. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3078 | Joseph Levy | No | 4.3.17.a | 19 | 46 | E | 4.3.17.a | 19.46 | Clause 11.18 is not OCB - it is clause 11.9 in .11 REVmd D1.0. | Insert the correct clause reference. |  |  |  | Resolution approved | Editor | 22/0015r2 | V | REVISED [01/18/2022, EDITOR] Given the resolution in CID3042, 11bd D3.0 should consider IEEE Std 802.11™-2020, 11ax, 11ay, 11ba, 11az, and 11bc (not REVmeD0.4) because we have REVme publishing after 11bd. No need to update the number based on REVme D0.4. However, it should tag the cross-reference because 11bd D3.0 contains the corresponding subclause. To TGbd editor: tag the cross-reference for 11.18 (STAs communicating Data frames outside the context of a BSS) at P19L46 (https://mentor.ieee.org/802.11/dcn/22/11-22-0015-02-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 3078. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3079 | Joseph Levy | No |  |  |  | G |  | 0.00 | Review and update all clause references to align with the 802.11bd baseline documents. It seems that many of the clause references are incorrect. | Correct all incorrect clause references |  |  |  | Resolution approved | Editor | 22/0015r2 | V | REVISED [01/18/2022, EDITOR] Agreed in principle. This resolution includes to 1) fix the references and 2) add the cross-references. TGbd Editor: incorporate the changes below P11L48, MIB Detail should be MIB detail. The corresponding subclause should be updated together through the spec. P19L13, add the cross-reference in 31.3 (Operation in the 60 GHz band). P19L39, E.1 replaced with E.1 (Country information and operating classes). P19L45, add cross-reference in 11.18 (STAs communicating Data frames outside the context of a BSS) P20L38, add cross-reference in 11.21.6 (Fine timing measurement (FTM) procedure) and P.3 (Differential Distance Computation using Fine Timing Measurement frames) P20L45, add cross-reference in P.3 (Differential Distance Computation using Fine Timing Measurement frames) P20L53, in 4.3.22 (DMG STA) each subclause is not completed with its title. Add the title after each subclause in 4.3.22 (DMG STA). There are examples such as Clause 10 (MAC sublayer functional description), Clause 11 (MLME), Clause 20 (Directional multi-gigabit (DMG) PHY specification), 10.39 (DMG and CMMG channel access), 10.42 (DMG beamforming) and 20.9 (Beamforming) and GCM encryption as described in 12.5.5 (GCM protocol (GCMP)). P37L29, Table 20-29 (DMG PHY characteristics) replaced with Table 20-30 (DMG PHY characteristics). P39L56, Table 9-94 (Element IDs) replaced with Table 9-92 (Element IDs) P53L4, 12.12 (Pre Association Security Negotiation) should be 12.12 (Preassociation security negotiation) P56L50, delete 17.3.1 (Introduction) and 17.3.2.1 (General) since there is no modification applied to this subclause. P65L65 add cross-reference in 11.21.6 (Fine timing measurement (FTM) procedure) P66L8, add cross-reference in P.3 P66L13, add cross-reference in 11.21.6 (Fine timing measurement (FTM) procedure) P66L61, 12.12 (Pre Association Security Negotiation) should be 12.12 (Preassociation security negotiation) P72L19 17.2.2.5 replaced with 17.2.2.5 (TXVECTOR TXPWR_LEVEL_INDEX) P113L25, add cross-reference in D.2.2 (Transmit power levels)) P114L29, add cross-reference in D.2.2 (Transmit power levels)) (https://mentor.ieee.org/802.11/dcn/22/11-22-0015-02-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 3079. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3080 | Joseph Levy | No | 4.3.22 | 21 | 2 | E | 4.3.22 | 21.02 | OCB is defined in the first paragraph in the OCB clause, so there is no need to spell in a following clause. Simply used OCB. | Replace" "outside the context of a BSS" With: "OCB" |  |  |  | Ready for motion | Hiroyuki Motozuka | 22/0091r3 | A | ACCEPTED [02/08/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0091-03-00bd-d3-0-comment-resolution-related-to-dmg-sta-communicating-ocb.docx) under CID 3080. | Yes |  |  |  |  | 2022-02-08 17:55
3081 | Joseph Levy | No | 4.3.23 | 21 | 16 | E | 4.3.23 | 21.16 | OCB is defined in the first paragraph in the OCB clause, so there is no need to spell in a following clause. Simply used OCB. Replace it in both occurrences. | Replace" "outside the context of a BSS" With: "OCB" at both occurrences in this sentence. |  |  |  | Ready for motion | Hiroyuki Motozuka | 22/0091r3 | A | ACCEPTED [02/08/2022, EDITOR] Discussion The proposed changes are acceptable. “OCB” is applied for similar case in the proposed resolution for CID 3086 in 22/0016r2. Note: This is in subclause 4.3.22. (https://mentor.ieee.org/802.11/dcn/22/11-22-0091-03-00bd-d3-0-comment-resolution-related-to-dmg-sta-communicating-ocb.docx) under CID 3081. | Yes |  |  |  |  | 2022-02-08 17:55
3082 | Joseph Levy | No | 10.3.6 | 43 | 43 | T | 10.3.6 | 43.43 | The statement "with a peer STA" implies there is only one peer STA, I don't think this is the intent. An DMG STA communicating OCB may be communicating with more than on peer. | Replace "a peer STA" With: "peer STAs" |  |  |  | Ready for motion | Hiroyuki Motozuka | 22/0091r3 | A | ACCEPTED [02/08/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0091-03-00bd-d3-0-comment-resolution-related-to-dmg-sta-communicating-ocb.docx) under CID 3082. | Yes |  |  |  |  | 2022-02-08 17:55
3083 | Joseph Levy | No | 10.3.6 | 43 | 44 | E | 10.3.6 | 43.44 | Grammar - transmission is singular and directions is plural, these should align. Also, if the criteria for transmission "in an antenna configuration" is that a beam link is maintained, wouldn't it be simpler to simply state that if no beam link is maintained the STA may omit transmission? | Replace: "the directions where presence of any peer STA is not anticipated" With: "any direction where the presence of a peer STA is not anticipated" or "any antenna configuration where a beam link is not maintained." |  |  |  | Ready for motion | Hiroyuki Motozuka | 22/0091r3 | V | REVISED [02/08/2022, EDITOR] Agreed with the commenter regarding the grammer issue and accept the first option.. Replace: "omit transmission in the directions where presence of any peer STA is not anticipated" With: "omit transmissions that use an antenna configuration over which a beam link is not maintained." (https://mentor.ieee.org/802.11/dcn/22/11-22-0091-03-00bd-d3-0-comment-resolution-related-to-dmg-sta-communicating-ocb.docx) under CID 3083. | Yes |  |  |  |  | 2022-02-08 17:56
3084 | Joseph Levy | No | 10.23.2.9 | 44 | 65 | T | 10.23.2.9 | 44.65 | The dot11OCBActivated is true requirement that TXOP limits are set to 0, applies to more than just non-NGV STA, it applies to any STA transmitting OCB that is not an NGV STA. Therefore the requirement in the base line should not be changed and an exception should be added for NGV STAs. | Delete the proposed change and return to base line text with the following addition: "When dot11OCBActivated is true, TXOP limits shall be 0 for each AC, unless the STA is an NGV STA supporting Clause 31. This change will also require a change to clause 10.2.3.2: change: "... the EDCA parameters are the corresponding default values or are as set by the SME in dot11EDCATable (except for TXOP limits for a non-NGV STA, which shall be set to 0 for each AC as specified in 10.23.2.9 (TXOP limits). to: "... the EDCA parameters are the corresponding default values or are as set by the SME in dot11EDCATable (except when the TXOP limits are set to 0 for each AC as specified in 10.23.2.9 (TXOP limits)." |  |  |  | Ready for motion | Hiroyuki Motozuka | 22/0091r3 | V | REVISED [02/08/2022, EDITOR] Discussion: Agree that the term “non-NGV STA” should not be used for rephrasing of the baseline spec. Propose to use MIB variable to specify the condition rather than “STA supporting clause 31” for 10.23.2.9, and keep “except for TXOP limits” in 10.23.2.9 and add “when the TXOP limits are ...” after that to keep the baseline intent clearly. TGbd Editor: Incorporate the change for subclauses 10.23.2.9 and 10.2.3.2 in https://mentor.ieee.org/802.11/dcn/22/11-22-0091-03-00bd-d3-0-comment-resolution-related-to-dmg-sta-communicating-ocb.docx under CID3084 (https://mentor.ieee.org/802.11/dcn/22/11-22-0091-03-00bd-d3-0-comment-resolution-related-to-dmg-sta-communicating-ocb.docx) under CID 3084. | Yes |  |  |  |  | 2022-02-08 17:56
3085 | Song-Haur An | Yes | 31.1 | 61 | 10 | G | 31.1 | 61.10 | Clause 10 (MAC sublayer functional description) contains much more functions and features that are needed by an NGV STA. "An NGV STA supports ... in addition to the MAC functions defined in Clause 10 (MAC sublayer functional description) ..." is a very broad statement and perhaps beyond the scope for an NGV STA. Note that there is no subclause of STAs communicating Data Frames outside of the context of a BSS in Clause 10. | Suggest creating a subclause to specify all the NGV STA MAC functions required in this amendment. Can use pointers to Clause 10 wherever appropriate. |  |  |  | Resolution approved | Liwen Chu | 22/0047r0 | J | REJECTED [01/20/2022, EDITOR] Discussion: the commenter is right that clause 10 includes much more functions and features that needed by an NGV STA. Subclause 10 defines the rules for the STAs that are outside the context of the BSS ( dot11OCBActivated is true). NGV STA will only implement the functions for a STA whose dot11OCBActivated is true in clause 10 since a NGV STA has dot11OCBActivated equal to true. (https://mentor.ieee.org/802.11/dcn/22/11-22-0047-00-00bd-d3-0-comment-resolution-31-1.docx) under CID 3085. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3086 | Song-Haur An | Yes | 31.1 | 61 | 19 | E | 31.1 | 61.19 | Spell out OCB to be consistent with the style in the paragraph above. | As in comment. |  |  |  | Resolution approved | Editor | 22/0016r2 | V | REVISED [01/19/2022, EDITOR] Agreed in principle to keep the consistent style. However, since OCB is introduced at P17L35 first, outside the conext of a BSS is replaced with OCB. TGbd Editor: replace “outside the conext of a BSS” with “OCB” at P61L13. (https://mentor.ieee.org/802.11/dcn/22/11-22-0016-02-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 3086. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3087 | Song-Haur An | Yes | 32.2.2 | 72 | 52 | T | 32.2.2 | 72.52 | N_TX and NUM_SS are not necessarily the same vales in the TXVECTOR. NUM_SS is included in the radio environment request vector. N_TX is not specified in the same request vector nor in the MAC section. | Please clarify where N_TX is defined at the STA level. Add it to the radio environment request vector if needed. |  |  |  | Resolution approved | Bo Sun | 21/2034r0 | J | REJECTED [01/11/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/21/11-21-2034-00-00bd-lb259-cr-clause-32-2-2-and-annex-b.docx) under CID 3087. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3088 | Song-Haur An | Yes | 32.1.1 | 69 | 62 | E | 32.1.1 | 69.62 | The first "NGV Ranging" can be deleted. It looks redundant. | As in comment. |  |  |  | Ready for motion | John Kenney | 22/0330r0 | J | REJECTED [02/15/2022, EDITOR] The current text is: “NGV Ranging NDP frames for NGV ranging” The proposed revision is: “NDP frames for NGV ranging” However, there are multiple types of null data PPDU (NDP), so in this case it is better to refer specifically to NGV Ranging NDP frames rather than generally to NDP frames. “NGV Ranging NDP” is specified in 32.3.15. (https://mentor.ieee.org/802.11/dcn/22/11-22-0330-00-00bd-lb259-comment-resolution-cid-3088.docx) under CID 3088. | Yes |  |  |  |  | 2022-02-15 17:38
3089 | Rui Cao | Yes | 32.1.1 | 69 | 54 | T | 32.1.1 | 69.54 | Spectrum mask C2 is only for power class C. Suggest to add that information similar as the previous bullet. | Change "Spectrum mask C2 requirement" to "Spectrum mask C2 for power Class C requirement" |  |  |  | Ready for motion | Rui Cao | 22/0151r0 | A | ACCEPTED [02/08/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0151-00-00bd-d3-0-cr-for-phy-introduction.docx) under CID 3089. | Yes |  |  |  |  | 2022-02-08 18:01
3090 | Rui Cao | Yes | 32.1.1 | 69 | 60 | T | 32.1.1 | 69.60 | The wording for spectrum mask is not aligned with the previous paragraph. | Change "Classes A, B, and D of spectrum mask" to "Spectrum mask for Classes A, B, and D" |  |  |  | Ready for motion | Rui Cao | 22/0151r0 | V | REVISED [02/08/2022, EDITOR] Agree with the commenter. Made editorial changes to the proposed changes. TGbd editor: Please make the following changes in P69L60 of D3.0: Change "Classes A, B, and D of spectrum mask" to "Spectrum mask for power Classes A, B, and D" (https://mentor.ieee.org/802.11/dcn/22/11-22-0151-00-00bd-d3-0-cr-for-phy-introduction.docx) under CID 3090. | Yes |  |  |  |  | 2022-02-08 18:02
3091 | Rui Cao | Yes | 32.3.2 | 81 | 33 | T | 32.3.2 | 81.33 | N_NGV_LTF can be 4 for NGV ranging NDP. | Change "can be either 1 or 2 and is determined by the total number of spatial streams being transmitted in the NGV PPDU" to "can be 1, 2 or 4 and is determined by the total number of spatial streams being transmitted in the NGV PPDU and whether the NGV-LTF is repeated in NGV ranging NDP"; |  |  |  | Resolution approved | yujin noh | 22/0018r3 | A | ACCEPTED [01/20/2022, EDITOR] The same resolution to CID3029 and 3091. (https://mentor.ieee.org/802.11/dcn/22/11-22-0018-03-00bd-resolutions-to-resolutions-to-ngv-phy-introduction-to-mathematical-description-of-signals.docx) under CID 3091. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3092 | Rui Cao | Yes | 32.3.3 | 81 | 55 | T | 32.3.3 | 81.55 | There is no "LDPC tone mapper" in NGV PPDU, remove block i) in the list. | As in the comment. |  |  |  | Resolution approved | yujin noh | 22/0018r3 | A | ACCEPTED [01/20/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0018-03-00bd-resolutions-to-resolutions-to-ngv-phy-introduction-to-mathematical-description-of-signals.docx) under CID 3092. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3093 | Rui Cao | Yes | 32.3.3 | 83 | 13 | T | 32.3.3 | 83.13 | "Pilot Insertion" block is missing in Figure 32-7. | Add "Pilot Insertion" block in the figure. |  |  |  | Resolution approved | yujin noh | 22/0018r3 | V | REVISED [01/20/2022, EDITOR] Same resolution to CIDs 3093 and 3094. Combing Figure 32-7 and 32-8, the comment is naturally resolved. TGbd Editor: Incorporate the text changes in 11-22-0018-03-00bd-Resolutions to NGV PHY Introduction to Mathematical description of signals. TGbd Editor: Incorporate the figure changes in 11-22-0020-00-00bd-Fig32-7 transmitter block diagram for the data field of an NGV transmssion with single SS which is visio file. TGbd Editor: add “NOTE - Transmission with two spatial streams is optional.” in the Figure32-7. Editorial change is allowed in accordance with the 11 guide style. (https://mentor.ieee.org/802.11/dcn/22/11-22-0018-03-00bd-resolutions-to-resolutions-to-ngv-phy-introduction-to-mathematical-description-of-signals.docx) under CID 3093. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3094 | Rui Cao | Yes | 32.3.3 | 83 | 13 | T | 32.3.3 | 83.13 | "Sptial Mapping" block is missing in Figure 32-7. As there is only one PPDU format and coding for NGV Data, and the only difference between Figure 32-7 and Figure 32-8 is the number of sreams. Suggest to merge two figures into one, same as 11n/ac. | as in the comment. |  |  |  | Resolution approved | yujin noh | 22/0018r3 | V | REVISED [01/20/2022, EDITOR] Agreed in principle. Two figures are merged into Figure 32-7. Same resolution to CIDs 3093 and 3094. TGbd Editor: Incorporate the text changes in 11-22-0018-03-00bd-Resolutions to NGV PHY Introduction to Mathematical description of signals. TGbd Editor: Incorporate the figure changes in 11-22-0020-00-00bd-Fig32-7 transmitter block diagram for the data field of an NGV transmssion with single SS which is visio file. TGbd Editor: add “NOTE - Transmission with two spatial streams is optional.” in the Figure32-7. Editorial change is allowed in accordance with the 11 guide style. (https://mentor.ieee.org/802.11/dcn/22/11-22-0018-03-00bd-resolutions-to-resolutions-to-ngv-phy-introduction-to-mathematical-description-of-signals.docx) under CID 3094. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3095 | Rui Cao | No | 32.3.8.6 | 96 | 5 | E | 32.3.8.6 | 96.05 | Change "RL-SIG shall be modulated same as L-SIG" to "RL-SIG shall be modulated the same as L-SIG". | As in the comment. |  |  |  | Resolution approved | Editor | 22/0016r2 | V | REVISED [01/19/2022, EDITOR] Agreed in principle. And additional modification is applied. TGbd Editor: Incorporate the changes in 11-22-0016-02-00bd-Resolutions to Editorial Comments Part 2 (https://mentor.ieee.org/802.11/dcn/22/11-22-0016-02-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 3095. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3096 | Rui Cao | Yes | 32.3.8.7 | 96 | 60 | T | 32.3.8.7 | 96.60 | The description in "NOTE" is confusing. It says "Reserved", and also "set to 1 if NGV-LTF-2x-Repeat is used". | Change the NOTE as "NOTE-If NGV-LTF-2x-Repeat is used (see 32.3.8.10 (NGV-LTF definition) with B2 set to 0, B3-B6 set to 15 and B7 set to 0, this field is Reserved and set to 1." |  |  |  | Resolution approved | yujin noh | 22/0019r2 | A | ACCEPTED [01/20/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0019-02-00bd-resolutions-to-resolutions-to-ngv-preamble-and-ngv-receive-procedure.docx) under CID 3096. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3097 | Rui Cao | Yes | 32.3.8.7 | 97 | 11 | T | 32.3.8.7 | 97.11 | The description for value 0 is redundant. Suggest to follow B11, and describe as "Set to 1 for .... Set to 0 otherwise". | As in the comment. |  |  |  | Resolution approved | yujin noh | 22/0019r2 | V | REVISED [01/20/2022, EDITOR] Agreed in principle TGbd Editor: Incorporate the changes in 11-220019-02-00bd-Resolutions to NGV preamble and NGV receive procedure. (https://mentor.ieee.org/802.11/dcn/22/11-22-0019-02-00bd-resolutions-to-resolutions-to-ngv-preamble-and-ngv-receive-procedure.docx) under CID 3097. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3098 | Rui Cao | Yes | 32.3.8.8 | 98 | 25 | T | 32.3.8.8 | 98.25 | Add the definition of p_3 in Eq. (32-13), similar to p_1 definition in Eq. (32-11). | As in the comment. |  |  |  | Resolution approved | yujin noh | 22/0019r2 | V | REVISED [01/20/2022, EDITOR] Agreed in principle. TGbd Editor: Incorporate the changes in 11-22-0019-02-00bd-Resolutions to NGV preamble and NGV receive procedure. (https://mentor.ieee.org/802.11/dcn/22/11-22-0019-02-00bd-resolutions-to-resolutions-to-ngv-preamble-and-ngv-receive-procedure.docx) under CID 3098. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3099 | Rui Cao | Yes | 32.3.8.9 | 99 | 10 | T | 32.3.8.9 | 99.10 | Change "N_STS" to "N_SS" in Eq. (32-16). | As in the comment. |  |  |  | Resolution approved | yujin noh | 22/0019r2 | A | ACCEPTED [01/20/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0019-02-00bd-resolutions-to-resolutions-to-ngv-preamble-and-ngv-receive-procedure.docx) under CID 3099. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3100 | Rui Cao | Yes | 32.3.8.10 | 99 | 63 | T | 32.3.8.10 | 99.63 | "When BPSK-DCM is applied to the NGV Data field of PPDU in 10 MHz, the NGV-LTF symbol uses NGV-LTF-2x-Repeat", need to add the condition of one spatial stream. It is also not clear how transmitter chooses LTF format and how to signal it. Need to add text to describe that. | Change the text to "A transmitter shall use the NGV-LTF-2x-Repeat format if the NGV Data field of a 10 MHz NGV PPDU is modulated with BPSK-DCM and one spatial stream; the transmitter shall use the NGV-LTF-2x for NGV ranging NDP; Otherwise, the transmitter can choose either NGV-LTF-2x or NGV-LTF-1x. The NGV-LTF format of NGV-LTF-1x or NGV-LTF-2x is signaled by B10 in NGV-SIG field. The NGV-LTF-2x-Repeat format is signaled by the combination of B2 equals 0, B3-B6 equals 15 and B7 equals 0 in NGV-SIG, and B10 is Reserved". |  |  |  | Resolution approved | yujin noh | 22/0019r2 | V | REVISED [01/20/2022, EDITOR] Agreed in principle. This description is not enough to cover all the cases for each NGV-LTF format to be used under certain condition. Resolution to CID 3096 is reused for the condition of NGV-LTF-2x Repeat format. TGbd Editor: Incorporate the changes in 11-22-0019-02-00bd-Resolutions to NGV preamble and NGV receive procedure. (https://mentor.ieee.org/802.11/dcn/22/11-22-0019-02-00bd-resolutions-to-resolutions-to-ngv-preamble-and-ngv-receive-procedure.docx) under CID 3100. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3101 | Rui Cao | Yes | 32.3.8.10 | 100 | 1 | T | 32.3.8.10 | 100.01 | The sentence of "NGV-LTF-2x-Repeat is constructed by repeating the time domain symbol of NGV-LTF-2x ... " is a standalone one. Suggest to move it to P102L1 for complete description of NGV-LTF-2x-Repeat construction. | As in the comment. |  |  |  | Resolution approved | yujin noh | 22/0019r2 | V | REVISED [01/20/2022, EDITOR] Agreed in principle. TGbd Editor: Incorporate the changes in 11-22-0019-02-00bd-Resolutions to NGV preamble and NGV receive procedure. (https://mentor.ieee.org/802.11/dcn/22/11-22-0019-02-00bd-resolutions-to-resolutions-to-ngv-preamble-and-ngv-receive-procedure.docx) under CID 3101. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3102 | Rui Cao | Yes | 32.3.8.10 | 102 | 38 | T | 32.3.8.10 | 102.38 | The N_NGV-LTF mapping has been changed in Table 32-11 to accommodate LTF_REP. The size of A/R/P matrix is not correct now, which should be NssxN_NGV-LTF. Correspondingly, the definition of P in Eq. (32-26) also needs to be updated to [P2x2 P2x2] to accomodate repeated LTF in NGV ranging NDP. | As in the comment. |  |  |  | Resolution approved | yujin noh | 22/0019r2 | V | REVISED [01/20/2022, EDITOR] Agreed in principle TGbd Editor: Incorporate the changes in 11-22-0019-02-00bd-Resolutions to NGV preamble and NGV receive procedure. (https://mentor.ieee.org/802.11/dcn/22/11-22-0019-02-00bd-resolutions-to-resolutions-to-ngv-preamble-and-ngv-receive-procedure.docx) under CID 3102. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3103 | Rui Cao | Yes | 32.3.15 | 123 | 1 | T | 32.3.15 | 123.01 | As NGV ranging NDP can only use "NGV-LTF-2x", so MCS 15 cannot be signaled in NGV-SIG for ranging NDP. We can either set some rules for NGV-SIG when transmitting ranging NDP or make NGV-MCS field reserved and set to a default value, like 0. | As in the comment. |  |  |  | Resolution approved | Stephan Sand | 22/0007r3 | V | REVISED [01/18/2022, EDITOR] In principle agree with comment. TGbd editor: Please add the following bullet to the end of the bullet list on P122L60: - The TXVECTOR parameter NGV-MCS shall be set to 0. (https://mentor.ieee.org/802.11/dcn/22/11-22-0007-03-00bd-lb259-comment-resolution.docx) under CID 3103. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3104 | Rui Cao | No | Annex D | 139 | 18 | E | Annex D | 139.18 | As there is no change to Annex D.2.1 and D.2.2, suggest to remove these two subclauses in the 11bd draft. | As in the comment. |  |  |  | Resolution approved | Editor | 22/0016r2 | A | ACCEPTED [01/19/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0016-02-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 3104. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3105 | Mark Hamilton | Yes | 5.2.3.2 | 23 | 31 | T | 5.2.3.2 | 23.31 | The response to CID 2211 did not address the question raised. The question is how the new parameter this being added to MA-UNITDATA will map to the _use_ of MA-UNITDATA per 802.1AC (which defines how the MAC SAP primitives are invoked and how they map to the defined SAP interface to the LLC sub-layer (the M_UNITDATA primitives). The response to CID 2211 explained why the parameter is useful, or is used by an application/higher-layer. What is still missing is how the parameter will map to/be mapped by the convergence function. (We can add parameters to these primitives, we just need to explain how they work/get up the stack.) | Add explanation for the new parameters, and how 802.1AC operation should treat them. (This probably also includes a liaison with 802.1 to update the 802.11 mapping clauses/annexes.) |  |  |  | Resolution approved | Joseph Levy | 22/0111r1 | V | REVISED [01/21/2022, EDITOR] Discussion: These parameters are not intended to support 802.1AC LLC operation. These parameters are intended to be used by other higher layer entities, e.g., entities based on IEEE Std 1609 and other ITS standards that use IEEE Std 802.11bd to provide wireless communication for V2X. These parameters have been liaised to IEEE P1609. Insert the following: “5.2.2a NGV MAC data service specification An NGV STA coordinates with higher layer ITS entities (e.g., IEEE 1609 family of standards) to provide wireless communications services via the LLC sublayer. The MA-UNITDATA primitives contain the radio environment request vector to facilitate the coordination.” (https://mentor.ieee.org/802.11/dcn/22/11-22-0111-01-00bd-some-clause-5-6-comment-resolutions-for-lb-259.docx) under CID 3105. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40
3106 | Mark Hamilton | Yes | 6.3.126.2 | 29 | 9 | T | 6.3.126.2 | 29.09 | The response to CID 2216 did not address the concern raised. The point is that for a primitive in clause 6, there needs to be _some_ text in a normative behavior clause that explains what this primitive is doing, how/when it would be used, etc. Even if minimal, we really need to say _something_ about what these primitives do, and the behavior does not go in clause 6. | Add text in a normative behavior clause (probably clause 31) to explain the use of these primitives. |  |  |  | Resolution approved | Joseph Levy | 22/0111r1 | V | REVISED [01/21/2022, EDITOR] Discussion: These additions to the MLME SAP introduced in 802.11bd are intended to be used by other higher layer entities, e.g., entities based on IEEE 1609 family and other ITS standards that use IEEE Std 802.11bd to provide wireless communication for V2X. These primitives allow for the management/control of the NGV STA. These parameters have been liaised to IEEE P1609. Agree with the commentor that this management/control capability should also be described in the MAC section. However, clause 31 does not discuss how NGV queues are managed or even mention that there are queues. Therefore, an addition is made to the clause in 10.3 where the queues are discussed. Modify 6.3.126.1 to be: “This primitive allows higher layer entities (e.g., entities based on the IEEE 1609 [B20] family of standards) to cancel transmission of MSDUs that were previously sent to the STA and are still in the MAC entity’s transmit queue.” Add to clause 10.2.3.2 following current addition “… as specified in 10.23.2.9.” the following sentence: “For a STA operating OCB the STA’s transmit queue for an AC may be cleared by the invocation of the MLME-CANCELTX.request primitive (see 6.3.126).” Editor, please see 11-21.0111r2 CID 3106 discussion for inline edits. Also note there is an inconsistent word use in the draft: communicating OCB and operating OCB. Based on the 802.11 base line draft (802.11-2020) the preferred phrase is operating OCB. Please align the draft with this preferred wording. (https://mentor.ieee.org/802.11/dcn/22/11-22-0111-01-00bd-some-clause-5-6-comment-resolutions-for-lb-259.docx) under CID 3106. |  | Tue Jan 21 2022 |  |  |  | 2022-01-25 21:40