## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: 11-22-0009-r13
First Author: | Claudio da Silva (Meta Platforms, Inc.)
Subject: | TGbf D0.1 Writing Status
Full Date: | 2022-02-22
Author(s): | Name(s) | Claudio da Silva
| Company | Meta Platforms, Inc.
Address
Phone:
Fax:
| email: | claudiodasilva@fb.com
Abstract:
This document was generated and is maintained by the TGbf Technical Editor for the purpose of tracking D0.1 draft text writing of the various topics identified in the TGbf SFD, as well as the POC and volunteers of each topic.

## Revision History
Revision | Date | Description
0 | 1/3/2022 | Initial version of the document based on r5 of the TGbf SFD (11-21/0504r5).
1 | 1/5/2022 | Updated list of POCs and TTT members. Baseline SFD: 0504r5.
2 | 1/6/2022 | Updated list of POCs and TTT members. Baseline SFD: 0504r5.
3 | 1/7/2022 | Updated list of POCs and TTT members. Baseline SFD: 0504r5.
4 | 1/12/2022 | Updated list of POCs and TTT members. Baseline SFD: 0504r6.
5 | 1/13/2022 | Updated list of POCs and TTT members. Baseline SFD: 0504r6.
6 | 1/14/2022 | Updated list of POCs and TTT members. Baseline SFD: 0504r6.
7 | 1/24/2022 | Updated list of POCs and TTT members. Updated baseline documents. Baseline SFD: 0504r7.
8 | 01/28/2022 | Updated list of POCs, TTT members, and baseline documents. Baseline SFD: 0504r7.
9 | 1/31/2022 | Updated list of TTT members and baseline documents. Baseline SFD: 0504r7.
10 | 2/04/2022 | Updated list of TTT members and baseline documents. Baseline SFD: 0504r7.
11 | 2/11/2022 | Updated status and documents. Baseline SFD: 0504r7.
12 | 2/18/2022 | Updated status and documents. Baseline SFD: 0504r7.
13 | 02/22/2022 | Add correct DCN for the baseline document of the trigger frame PDT. Baseline SFD: 0504r8
Status
Baseline pending
Baseline uploaded
Presented to TGbf
Under discussion in TGbf
Pending motion
Complete

## Sheet1
Topic ID | Topic Title | Status | POC | TTT/Volunteers | Documents | Motions
1 | Sensing NDPA frame | Baseline uploaded | Editor | Dongguk (potential POC), Junghoon (potential POC), Mengshi, Lei, Jinsoo, Osama, Cheng, Mahmoud, Rojan, Rajat, Ali, Dong, Satya, Dash | 22/0194r0
2 | Trigger frame | Baseline uploaded | Dongguk | Xiandong, Lei, Osama, Dibakar, Mahmoud, Ali, Mengshi | 22/0325r0
3 | Sensing Measurement Report frame (excl. format) | Presented | Claudio | Chaoming, Osama, Chris, Oscar, Rojan, Rajat, Ali, Mahmoud | 22/0235r4
4 | SBP frames | Presented | Chaoming | Claudio, Dongguk, Xiandong, Jinsoo, Cheng, Oscar, Ali, Mahmoud | 22/0223r1
5 | SENS procedure: Overview | Presented | Claudio | Chaoming, Osama, Cheng, Chris, Oscar, Rajat | 22/0079r2
6 | Sensing session setup | Presented | Chaoming | Insun, Osama, Dibakar, Sang, Oscar, Anirud, Rojan, Ali, Mike, Naren | 22/0181r0
7 | Sensing measurement setup | Baseline uploaded | Insun | Xiandong, Chaoming, Osama, Dibakar, Sang, Oscar, Anirud, Rojan, Rajat, Ali, Satya | 22/0229r1
8 | Sensing measurement instance: General | Presented | Cheng | Pei, Chris, Oscar, Rajat, Dong, Edward, Mahmoud | 22/0172r3
9 | TB sensing measurement instance | Presented | Cheng | Xiandong, Pei, Chris, Oscar, Naren, Ali, Dash, Mahmoud | 22/0173r3
10 | TB sensing measurement instance: Reporting | Presented | Rajat | Chaoming, Cheng, Chris, Oscar, Rojan, Ali, Dash, Mahmoud | 22/0170r3
11 | Non-TB sensing measurement instance | Presented | Cheng | Dongguk, Xiandong, Pei, Chris, Oscar, Rojan, Rajat, Ali, Dash, Mahmoud | 22/0174r2
12 | Sensing measurement setup termination | Baseline uploaded | Pei | Insun, Dibakar, Sang | 22/0126r0
13 | Sensing session termination | Presented | Chaoming | Insun, Dibakar, Sang | 22/0182r0
14 | Threshold-based procedure | Presented | Mengshi | Dongguk, Chaoming, Rui Y., Oscar, Naren, Rajat, Leif, Ali | 22/0134r2
15 | SBP | Baseline uploaded | Claudio | Dongguk, Xiandong, Rui D., Chaoming, Jinsoo, Cheng, Chris, Oscar, Leif, Mahmoud | 22/0234r2
16 | DMG sensing: Monostatic configurations | Baseline uploaded | Rui D. | Lei, Ning, Assaf, Naren, Alecs, Edward, Solomon | 22/0132r0
17 | CSI_ESTIMATE format | Baseline uploaded | Editor | Steve (potential POC), Junghoon (potential POC), Claudio, Dongguk, Lei, Ning, Jinsoo, Chris, Oscar, Rojan, Leif, Dong, Edward, Qinghua, Hao, Zinan | 22/0147r0
18 | NDP format (including secure LTF) | Presented | Yan | Claudio, Dongguk, Xiandong, Rui D., Lei, Rui Y., Ning, Steve, Chris, Mahmoud, Naren, Rajat, Dong, Satya, Cheng, Dash | 22/0236r0
19 | Sensing Measurement Setup frames | Presented | Insun | Oscar, Rajat, Xiandong | 22/0229r1
20 | BRP frames | Baseline pending | Assaf | Yan, Lei, Xiandong, Ning, Rui D.
21 | DMG sensing capability | Baseline uploaded | Assaf | Yan, Lei, Xiandong, Solomon, Ning, Rui D., Alecs | 22/0240r1
22 | DMG Sensing Measurement Setup frames | Baseline pending | Assaf | Yan, Lei, Solomon, Ning, Rui D., Alecs
23 | DMG sensing measurement information element | Presented | Alecs | Yan, Lei, Solomon, Ning, Rui D. | 22/0251r1
24 | DMG sensing: Bistatic configuration | Baseline pending | Assaf | Yan, Lei, Xiandong, Solomon, Ning, Rui D., Alecs
25 | MLME | Presented | Claudio | Edward, Oscar, Solomon, Rajat | 22/0233r3
26 | DMG passive sensing | Baseline uploaded | Assaf | Claudio, Rui D., Alecs | 22/0241r2
27 | Bi/multistatic sounding | Baseline pending | Assaf | Claudio, Rui D., Alecs
28 | DMG sensing procedure (incl. frames) | Baseline uploaded | Solomon | Claudio, Rui D., Alecs | 22/0243r2