## Slide 1: REVme Closing Report – January 2022
Date: 2022-01-24
Authors:

## Slide 2: Work Completed
Approved remaining CC35 comment resolutions
Initiated comment resolution for comments received in initial LB
  Approved 108 comment resolutions
Timeline change (next slide)

## Slide 3: Updated Timeline
Feb 2021 – PAR Approval
March 2021– Initial meeting, issue comment collection on IEEE Std 802.11-2020
March 2021 – Draft 0.00 available
May 2021 – Process CC input, 11ax, 11ay, 11ba integration begins
Nov 2021 – Initial D1.0 WG Letter ballot
Jul 2022 – D2.0 Recirculation LB
Mar 2023 – D3.0 Recirculation LB (11az + other amendments <11bc, 11bd, 11bb> )
Sep 2023 – D4.0 Recirculation (<other amendments – if Jul>)
Nov 2023 – D5.0 Initial SA Ballot
Mar 2024 – D6.0 Recirculation SA Ballot
May 2024 – D7.0 Recirculation SA Ballot
Jun 2024 – D7.0 Recirculation SA Ballot (clean recirculation)
Sep 2024 – RevCom/SASB Approval

## Slide 4: Plans for March
Teleconferences:
  Next call: Monday 31 January 2022 at 10am ET, 2hrs
  7, 14, 25, 28 Feb – 10am ET, 2hrs
  21 Mar – 10am ET, 2hrs
Request 5 sessions for the March Plenary
Continue comment resolution on initial LB