## Slide 1: TGbe March 2022 Closing Report
Date: 2022-03-14
Authors:

## Slide 2: TGbe (Extremely High Throughput)
TGbe had scheduled 6 conf. calls during the March electronic plenary
  Two Joint calls, and four parallel MAC/PHY calls
    Covered comment resolution documents
    Approved the resolution of several technical/editorial comments and PDT submissions
      ~75% of all CC36 comments are now resolved
  Instructed the editor to generate IEEE802.11 TGbe D1.5
    TGbe D1.5 is expected to be available by end of this month
  Amended TGbe timeline and approved 11-21/0706r5 as the TGbe CAD
    TGbe did not reach consensus on generating D2.0 and go to WG letter ballot
Agenda is available in 11-22/271r13, with queues available in 11-22/428r2
  Future Teleconference Plan is provided in the next slide
Motions List is available in 1982r66
Distribution of ~4350 CIDs
9%
67%
24%
Resolution Status

## Slide 3: Teleconference Plan
Apr 06 Wednesday – Joint** 10:00-12:00 ET
Apr 07 Thursday – MAC 10:00-12:00 ET
Apr 11 Monday – MAC/PHY 19:00-21:00 ET
Apr 13 Wednesday – Joint (Motions) 10:00-12:00 ET
Apr 14 Thursday – MAC 10:00-12:00 ET
Apr 18 Monday – MAC/PHY 19:00-21:00 ET
Apr 20 Wednesday –Joint TGbe/TSN 10:00-12:00 ET
Apr 21 Thursday – MAC 10:00-12:00 ET
Apr 25 Monday – MAC/PHY 19:00-21:00 ET
Apr 27 Wednesday – Joint (Motions) 10:00-12:00 ET
Apr 28 Thursday – MAC 10:00-12:00 ET
May 02 Monday – No Conf Call Holiday
May 04 Wednesday – No Conf Call Holiday
May 05 Thursday – No Conf Call Holiday
** Can be modified to MAC on the fly with pre-announcement.
Mar 16 Wednesday – MAC 10:00-12:00 ET
Mar 17 Thursday – MAC 10:00-12:00 ET
Mar 21 Monday – MAC/PHY 19:00-21:00 ET
Mar 23 Wednesday – Joint (Motions) 10:00-12:00 ET
Mar 24 Thursday – MAC 10:00-12:00 ET
Mar 28 Monday – MAC/PHY 19:00-21:00 ET
Mar 30 Wednesday – Joint** 10:00-12:00 ET
Mar 31 Thursday – MAC 10:00-12:00 ET
Apr 04 Monday – No Conf Call Holiday

## Slide 4: Amended TGbe Timeline And Status
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sep 2020
D1.0 WG Comment Collection May 2021
D2.0 WG Comment CollectionLetter Ballot Mar 2022*
D3.0 Letter Ballot Nov 2022
Initial SAponsor Ballot (D4.0) May 2023
Final 802.11 WG approval Mar 2024
802 EC approval Mar 2024
RevCom and SASB approval May 2024
*Mar 2022 milestone needs to be updated