## Slide 1: Guidelines: Update
Date: 2022-03-01
Authors:
Alfred Asterjadhi, et. al.

## Slide 2: Introduction
The presentation focuses on the following two aspects:
  Proposed plan for post TGbe D2.0
  Proposal to go to WG letter ballot on TGbe D2.0
    Amending timeline milestone terminology

## Slide 3: Current TGbe Timeline
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sept 2020
D1.0 WG Comment Collection May 2021
D2.0 WG Comment Collection Mar 2022
D3.0 LB Nov 2022
Initial Sponsor Ballot (D4.0) May 2023
Final 802.11 WG approval Mar 2024
802 EC approval Mar 2024
RevCom and SASB approval May 2024
We are here

## Slide 4: Current Status
Undergoing a WG comment collection on TGbe D1.0
  With more than 80% of comments in Joint and PHY ad-hoc already resolved
    Currently on track to resolve their CIDs by March’22 deadline
  A little more than 55% of MAC ad-hoc comments are already resolved
    Resolution pace (in terms of #CIDs) has slowed a bit recently
      MAC group’s mainly focusing on fixing major/contentious issues
      Realistically not all MAC comments will be resolved by March’22 deadline

## Slide 5: Planning Observations
Majority of conf call times is dedicated to CRs for existing functionalities
  CR discussions and progress is following established guidelines (984r12)
  Inline with general expectations at this stage for the standard development
And we have some items currently deprioritized or on hold
  Technical presentations pending in the technical queues
    Generally, presentations focusing on MAC functionalities [for which there is no CIDs]
  Some new features/enhancements are yet to be discussed for adding to TGbe draft
    Expectation is that these functionalities be developed and added gradually to TGbe D3.0 as part of the comment resolution process
Once our current target is reached (release of D2.0 out of March 2022)
  Plan is to have the same priority for all the above items
    Following slide provides an overview of this

## Slide 6: Planning
Conclude CC36 comment resolution process (as in item 10:984r12)
  More specifically to conclude by end of Electronic March plenary
  Target resolving as many CIDs as possible on all groups (MAC/PHY/Joint)
  Remaining CIDs that are unresolved can be brought next round
    This is a WG comment collection for which we need not resolve all comments
Generate TGbe D2.0 and start a new round of review on the draft
  During which members can submit comments targeting D2.0
    Members have the option to submit comments that were left unresolved during CC36
      Appreciated that members check that the issue at hand is not resolved indirectly by another CID
    Members can submit comments for functionalities that are not yet in the draft
  Continue processing the existing CC36 CR queues during this period (after which queue reset)
    These are CR documents that resolve CIDs from CC36, however, to be identified by a new CID
      Author to submit a comment during the new review round for tracking purposes (references w.r.t., D2.0)
    CR docs may be SPed but motions are expected to be ran on new comment identifiers (to be published)
      If author is POC then the author is encouraged to include other CIDs that might have been resolved in the same doc
  This is generally aligned with existing guidelines used for CC34 to CC36 transition

## Slide 7: Proposal to initiate a WG Letter Ballot for D2.0
Benefits:
  The group will have a wider pool of experts commenting on the draft
    WG members are required to vote on a WG LB while no such requirement exists for WG CC
  The group will have a quantitative sense of the progress being made with the spec text
    Will be able to identify which comments must be satisfied (for getting the support of a No voter)
      Including on comments that are related to new functionalities
    This is not possible with a WG CC
  D2.0 is available for purchase if WG LB passed (>=75% support); not available otherwise
    Will not be available no matter what in the case of a WG CC
  Members can submit comments for functionalities that are not yet in the draft
  Provides the opportunity for members not wishing to participate in comment resolutions to move on to next gen mainstream MAC/PHY amendment
    Expected to be exclusively handled via comment submission/resolution (i.e., expected to not have technical submissions without CIDs)
We need the following to have a WG letter ballot on TGbe D2.0:
  Get approval by the TG to have a change in the timeline milestone terminology (see next slide)
  Get approval by the WG for a 30-day WG technical LB on TGbe D2.0 out of March plenary

## Slide 8: Proposed amendment to TGbe Timeline
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sept 2020
D1.0 WG Comment Collection May 2021
D2.0 WG Comment Collection Letter Ballot Mar 2022
D3.0 LB Nov 2022
Initial Sponsor SA Ballot (D4.0) May 2023
Final 802.11 WG approval Mar 2024
802 EC approval Mar 2024
RevCom and SASB approval May 2024

## Slide 9: WG LB Motion
Instruct the editor to prepare TGbe Draft D2.0
Approve a 30 day Working Group Technical Letter Ballot asking the question “Should TGbe Draft 2.0 be forwarded to Sponsor Ballot?”
[Moved by <name> on behalf of <group>
<group> vote:
Moved:, Seconded:, Result: