## Slide 1
Task Group BF March 2022 Closing Report
Date: 2022-03-14
Authors:
Name | Affiliation | Address | Phone | Email
Tony Xiao Han | Huawei Technologies Co., Ltd. | F3, Huawei Base, Shenzhen, China |  | Tony.hanxiao@huawei.com

## Slide 2: Abstract
This document is the closing report for Task Group BF for the March 2022 session.

## Slide 3: TGbf (WLAN Sensing)– March 2022
Progress during March 2022 meeting
  4 teleconference calls for TGbf (March 8, 9, 11, 14)
  Presentation of technical submissions (e.g., Feedback type, general protocol and procedure, DMG/EDMG, PDT……)
  Worked towards the creation of TGbf D0.1 (Updated plan in the next slide)
Goals for the next two months
  Presentation of technical submissions (e.g., PDT for D0.1, Feedback type, general protocol and procedure ……)
  Speed up the technical discussion and developing the SFD and D0.1 (Requested 3 calls per week)
  Editor releases D0.1, and plan to request to the WG chair to start the comment collection (based on the supportive of TGbf)

## Slide 4: TGbf Timeline (Updated)
  PAR approved Sep 2020
  First TG meeting Oct 2020
  Comment Collection (D0.1) Jan 2022Mar 2022
   April 2022
  Initial Letter Ballot (D1.0) Jul 2022 Sep 2022
  Recirculation LB (D2.0) Jan 2023
  Recirculation LB (D3.0) May 2023
  Recirculation LB (D4.0) July 2023
  Initial SA Ballot (D4.0) Sep 2023
  Final 802.11 WG approval July 2024
  802 EC approval July 2024
  RevCom and SASB approval Sep 2024
Timeline for D0.1 (Updated)
Week of January 3
  Editor provides initial list of topics (and updated SFD revision) (Tuesday)
  Chair issues call for volunteers (Tuesday)
  POCs and volunteers are identified for topics in the initial list (Friday)
January 2128, 2022
  Deadline for baseline document for each topic (in the initial list) to be uploaded
After March Plenary
  Editor releases D0.01 (only for reference, not for comment collection)
April 1
  Deadline for sending the Motion request.
April 12 or 14 (10+ days after Motion request)
  Deadline for contributions to pass motion and be included in D0.1
  Seek TGbf approval to go to comment collection (“Move to Approve a 30-day comment collection on TGbf D0.1.”)
April 22 (Around)
  Editor releases D0.1
  If the Motion is favorable, the TG chair sends a request to the WG chair (Dorothy) to start the comment collection
  30-day comment collection window opens

## Slide 5: Teleconference Times
  Confirmed:
    March 2022 IEEE Plenary (March 7-15) (Deadline for contributions to pass motion and be included in D0.1)
    March 8 (Tuesday), 9am - 11:00am ET
    March 9 (Wednesday), 10pm - 11:59pm ET (Not sure if this slot is ok for Plenary and Interim? It’s ok!!)
    March 11 (Friday), 9am - 11:00am ET
    March 14 (Monday), 9am - 11:00am ET
    March 17 (Thursday), 23 ：00 - 01:00am ET
    March 21 (Monday), 10am - 12:00pm ET March 22 (Tuesday), 10am - 12:00pm ET
    March 24 (Thursday), 23：00 - 01:00am ET
    March 28 (Monday), 10am - 12:00pm ET March 29 (Tuesday), 10am - 12:00pm ET
    March 31 (Thursday), 23：00 - 01:00am ET
    April 7 (Thursday), 10am - 12:00pm ET
    April 11 (Monday), 10am - 12:00pm ET April 12 (Tuesday), 10am - 12:00pm ET
    April 14 (Thursday), 23：00 - 01:00am ET
    April 18 (Monday), 10am - 12:00pm ET April 19 (Tuesday), 10am - 12:00pm ET
    April 21 (Thursday), 23：00 - 01:00am ET
    April 25 (Monday), 10am - 12:00pm ET April 26 (Tuesday), 10am - 12:00pm ET
    April 28 (Thursday), 23：00 - 01:00am ET
    May 5 (Thursday), 10am - 12:00pm ET
  ** Note:
  1. when conflict with CAC, the call will be changed from 10am -12:00pm to 11am -12:00pm (March - May 2022 CAC calls (TBD): )
  2. Thursday 23:00 - 01:00am ET (Thursday 20：00 – 22:00 PT, Friday 11am-13:00 in China, Friday 5am-7am in Israel, Friday 4am – 6am in Central Europe), and Sang Kim will help to take the minutes for these slots.
 | Time Central Europe Warsaw | Eastern Time | Pacific time | Beijing Time
AM1 | 08:00-10:00 | 02:00-04:00 | 23:00-01:00 | 14:00-16:00
AM2 | 10:30-12:30 | 04:30-06:30 | 01:30-03:30 | 16:30-18:30
PM1 | 13:30-15:30 | 07:30-09:30 | 04:30-06:30 | 19:30-21:30
PM2 | 16:00-18:00 | 10:00-12:00 | 07:00-09:00 | 22:00-00:00
Evening 1 | 19:30-21:30 | 13:30-15:30 | 10:30-12:30 | 01:30-03:30
Evening 2 | 22:00-00:00 | 16:00-18:00 | 13:00-15:00 | 04:00-06:00