## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-22/0730r0
Venue Date: | May 2022
First Author: | Yujin Noh
Subject: | Initial SA ballot - Comment Collection on D4.0
Full Date: | 2022-05-10
Author(s): | Yujin Noh
| Company: | Senscomm
| email: | yujin.noh@senscomm.com
Abstract: | Initial SA ballot - comments on D4.0

## Revision History
Revision | Date | Description
0 | 2022-05-10 | Initial export from DB.
1 | 2022-05-10 | Initial comment assignment
2 | 2022-05-10 | CID fixed to be matched to comment database
3 | 2022-05-13 | 34 editorial comments and 8 technical comments are resolution-approved
4 | 2022-06-14 | all the comments are resolved and motion approved

## All Comments
CID | Commenter | Must Be Satisfied | Clause Number(C) | Page(C) | Line(C) | Category | Clause | Page | Comment | Proposed Change | Ad-hoc | Comment Group | Ad-hoc Notes | Status | Assignee | Submission | Resn Status | Resolution | Ready For Motion | Motion Number | Edit Status | Edited in Draft | Edit Notes | Last Updated | Last Updated By
5000 | Patil, Abhishek | Yes | 4.3.17a | 19 | 25 | T | 4.3.17a | 19.25 | Per this clause, a TGbd STA will share the same bands / channels of operation as a regular (i.e., 11n, 11ac, 11ax etc) Wi-Fi device. However it is not clear how it would inter-op with a regular Wi_Fi device that is operating on the same channel if the preamble is not a true 20 MHz LTF. TGbd needs to conform to the same preambles as regular Wi-Fi. In other words, it should perform the same preamble detection (20 MHz based) as regular Wi-Fi systems. Not conforming will lead to serious interop/coexistence issues affecting millions of Wi-Fi devices that are already deployed in the field. | As in comment |  |  |  | Resolution approved | John Kenney | 22/0827r5 | J | REJECTED [06/14/2022, EDITOR] The P802.11bd PAR scope states "This amendment shall provide interoperability, coexistence, backward compatibility, and fairness with deployed OCB (Outside the Context of a BSS) devices". The PPDU modes requested in the comment would not provide coexistence with those devices and are thus outside the scope of the amendment. Also, the task group has consistently declined to have the amendment support the modes requested in this comment. See for example the straw poll from document 11-20-1012r1 (https://mentor.ieee.org/802.11/dcn/20/11-20-1012-01-00bd-on-802-11bd-mandatory-features-input-from-the-car-2-car-communications-consortium.pptx), as recorded in document 11-19-0276r11 (https://mentor.ieee.org/802.11/dcn/20/11-20-0276-11-00bd-tgbd-feb-2020-teleconference-minutes.docx) Also, the TGbd Coexistence Assessment Document 11-20-1564/r5 (https://mentor.ieee.org/802.11/dcn/20/11-20-1564-05-00bd-tgbd-coexistence-assessment-document.docx) includes the following: “802.11bd can coexist with other 802.11 devices with operating bandwidth wider than 10 MHz working on 5.9 GHz frequency band using -65dBm CCA sensitivity per 10 MHz channel.” (https://mentor.ieee.org/802.11/dcn/22/11-22-0827-05-00bd-resolutions-to-clause-4-3-17-and-4-3-17a-cids.docx) under CID 5000. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:17
5001 | Segev, Jonathan | Yes | 9.3.1.19 | 38 | 14 | T | 9.3.1.19 | 38.14 | "An NGV STA may use the Ranging NDP Announcement frame format for non-TB ranging measurement exchange" it may be interpreted that the NDPA is a may for NTB while its mandatory part of the sequence. Furthermore clause 9 is about frame formats not normative behavior so a "May" statement here is not in accordance with the style guide. | Delete the sentence it does not provide additional information. |  |  |  | Resolution approved | Stephan Sand | 22/0747r1 | V | REVISED [05/13/2022, EDITOR] Agree with comment TGbd editor: Please delete sentence on P38L14-16, remove editing instructions and subclause headings 9.3.1 and 9.3.1.19 (https://mentor.ieee.org/802.11/dcn/22/11-22-0747-01-00bd-sa-ballot-cr-11bd-d4-0-ngv-ranging.docx) under CID 5001. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:35
5002 | Smely, Di Dieter | No |  |  |  | E |  | 0.00 | Check for typos: "inset" used instead "insert", "subcaluse" used instead "subclause", "a NGV..." used instead of "an NGV..." | see comment |  |  |  | Resolution approved | Editor | 22/0743r1 | V | REVISED [05/13/2022, EDITOR] Agreed in principle. TGbd Editor: Change “inset” to “insert” at P47L40. Change " subcaluse” to "subclause" at P53L9 and P53L21 Change “a NGV” to “an NGV” at P45L23, P67L28, P84L24, P125L42. (https://mentor.ieee.org/802.11/dcn/22/11-22-0743-01-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 5002. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5003 | Smely, Di Dieter | No | 10.12.4 | 44 | 6 | E | 10.12.4 | 44.06 | Here it is unclear what is meant, since the new version of following sentence could be interpreted differently than the previous version:"A STA that is not an AP, a mesh STA, or an NGV STA shall not transmit an A-MPDU containing an MPDU with an RA that is a group address." I guess what is meant is: When NOT(a OR b OR c) do NOT transmit... But it could also be read: When NOT(a) OR b OR c do NOT transmit... This interpretation would not be in line with the previous version of IEEE 802.11 | When my guess is right, than following applies: NOT(a OR b OR c) = NOT(a) AND NOT(b) AND NOT(c) And the sentence could either be written as follows: "A STA that is not an AP, not a mesh STA, and not an NGV STA shall not transmit an A-MPDU containing an MPDU with an RA that is a group address." Or even simpler, when taking out all the negations: "Only STAs that are an AP, a mesh STA, or an NGV STA shall transmit an A-MPDU containing an MPDU with an RA that is a group address." In case my guess is wrong, rewrite the requirement in an unambiguous way, please. |  |  |  | Resolution approved | Liwen Chu | 22/0828r1 | V | REVISED [05/31/2022, EDITOR] TGbd editor:Please change “ A STA that is not an AP, a mesh STA, or an NGV STA shall not transmit an A-MPDU containing an MPDU with an RA that is a group address” to “ A STA that is not one of an AP, a mesh STA, or and an NGV STA shall not transmit an A-MPDU containing an MPDU with an RA that is a group address” Note to editor: please check whether “:” is needed here. (https://mentor.ieee.org/802.11/dcn/22/11-22-0828-01-00bd-11bd-d4-0-comment-resolution.docx) under CID 5003. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5004 | Smely, Di Dieter | No | 12.12.1 | 53 | 13 | E | 12.12.1 | 53.13 | unclear use of the word "by" in following sentence: "It may also be used by two STAs each co-located by an NGV STA (see 31.4 (NGV ranging))." | I guess following was meant: "It may also be used by two STAs each co-located with an NGV STA (see 31.4 (NGV ranging))." |  |  |  | Resolution approved | Stephan Sand | 22/0747r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0747-01-00bd-sa-ballot-cr-11bd-d4-0-ngv-ranging.docx) under CID 5004. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:48
5005 | Lansford, James | Yes | 4.3.17a | 19 | 32 | T | 4.3.17a | 19.32 | This clause states that 802.11bd operates in 5.850-5.925GHz in the United States. Current FCC rules have allocated a portion of that band (5.850-5.895GHz) for unlicensed use as U-NII-4, which would allow other technologies including "regular" 802.11 (Wi-Fi) to operate in that band. While not required by the PAR, there is no preamble defined that is interoperable with any of the 802.11 PHY standards since 802.11a; there has been discussion in IEEE 802 and SAE about operating NGV in unlicensed bands on a shared basis with other 802.11 devices, but without a 20MHz 802.11n/ac/ax/be 20MHz preamble to enable preamble detection, only Energy Detection is possible. This limits the ability of NGV to operate in unlicensed band with minimal interference from other 802.11 devices. A request was also made by Car to Car Communication Consortium to comment on unlicensed band usage. Furthermore, the FCC has proposed eliminating DSRC (based on 802.11p) from the upper part of the band (5.895-5.925GHz), so there would be no spectrum available for 11bd operation in the US except the unlicensed U-NII-4 band. The current 802.11bd preambles (10 and 10+10MHz in BW) would cause interference to Wi-Fi systems based on 802.11a/n/ac/ax/be in U-NII-4. | Add a mode in 802.11bd that has a true 20MHz Legacy Training Field (LTF) to allow preamble detection by "conventional" Wi-Fi devices operating in U-NII-4 (5.850-5.895GHz) |  |  |  | Resolution approved | John Kenney | 22/0827r5 | J | REJECTED [06/14/2022, EDITOR] The P802.11bd PAR scope states "This amendment shall provide interoperability, coexistence, backward compatibility, and fairness with deployed OCB (Outside the Context of a BSS) devices". The PPDU modes requested in the comment would not provide coexistence with those devices and are thus outside the scope of the amendment. Also, the task group has consistently declined to have the amendment support the modes requested in this comment. See for example the straw poll from document 11-20-1012r1 (https://mentor.ieee.org/802.11/dcn/20/11-20-1012-01-00bd-on-802-11bd-mandatory-features-input-from-the-car-2-car-communications-consortium.pptx), as recorded in document 11-19-0276r11 (https://mentor.ieee.org/802.11/dcn/20/11-20-0276-11-00bd-tgbd-feb-2020-teleconference-minutes.docx) Also, the TGbd Coexistence Assessment Document 11-20-1564/r5 (https://mentor.ieee.org/802.11/dcn/20/11-20-1564-05-00bd-tgbd-coexistence-assessment-document.docx) includes the following: “802.11bd can coexist with other 802.11 devices with operating bandwidth wider than 10 MHz working on 5.9 GHz frequency band using -65dBm CCA sensitivity per 10 MHz channel.” (https://mentor.ieee.org/802.11/dcn/22/11-22-0827-05-00bd-resolutions-to-clause-4-3-17-and-4-3-17a-cids.docx) under CID 5005. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:17
5006 | Sand, Stephan | Yes | 32.3.15 | 123 | 5 | T | 32.3.15 | 123.05 | "The number of NGV-LTF symbols in an NGV ranging NDP is the product of the number of spatial streams the TXVECTOR parameter NUM_SS and the number of LTF repetitions..." is incorrect because for zero LTF repetitions there would be zero NGV-LTF symbols. | Modify to "The number of NGV-LTF symbols in an NGV ranging NDP is the product of thethe TXVECTOR parameter NUM_SS and (LTF_REP+1), see Table 32-11 (Number of NGV-LTFs required for different numbers of spatial streams)." |  |  |  | Resolution approved | Stephan Sand | 22/0747r1 | V | REVISED [05/13/2022, EDITOR] Agree with comment, resolution revised as proposed change contains typo. See also CID 5047 TGbd editor: Please replace the sentence starting on P123L4 with “The number of NGV-LTF symbols in an NGV ranging NDP is the product of the TXVECTOR parameter NUM_SS and (LTF_REP+1), see Table 32-11 (Number of NGV-LTFs required for different numbers of spatial streams)." (https://mentor.ieee.org/802.11/dcn/22/11-22-0747-01-00bd-sa-ballot-cr-11bd-d4-0-ngv-ranging.docx) under CID 5006. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:48
5007 | Sand, Stephan | Yes | 32.2.2 | 75 | 47 | T | 32.2.2 | 75.47 | Change "PSDU_LENGTH" to "APEP_LENGTH" because PDSU_LENGTH (shown on P74L33) is not a TXVECTOR parameter but APEP_LENGTH. | As in comment |  |  |  | Resolution approved | Bo Sun | 22/0817r1 | A | ACCEPTED [05/24/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0817-01-00bd-crc-cr-clause-32-2.docx) under CID 5007. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5008 | Sand, Stephan | Yes | 11.21.6.4.6 | 51 | 62 | T | 11.21.6.4.6 | 51.62 | Remove sentence "The PSDU_LENGTH parameter is set to 0." as PDSU_LENGTH is not a TXVECTOR parameter. The same sentence on P52L14 can be removed for the above reason. | As in comment |  |  |  | Resolution approved | Stephan Sand | 22/0747r1 | A | ACCEPTED [05/13/2022, EDITOR] See also CID 5080 (https://mentor.ieee.org/802.11/dcn/22/11-22-0747-01-00bd-sa-ballot-cr-11bd-d4-0-ngv-ranging.docx) under CID 5008. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:47
5009 | Sand, Stephan | Yes | 31.4 | 67 | 14 | E | 31.4 | 67.14 | The sentence starting with "For ranging on IEEE Std. 802.11 bands ..." should not be part of the last bullet but a new paragraph as in D3.0. | As in comment |  |  |  | Resolution approved | Editor | 22/0744r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0744-01-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 5009 |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5010 | Sand, Stephan | No | 11.27.1.1 | 52 | 30 | E | 11.27.1.1 | 52.30 | "a A DMG STA" should be "a DMG STA" | As in comment |  |  |  | Resolution approved | Editor | 22/0743r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0743-01-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 5010. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5011 | Sand, Stephan | No | 4.3.22 | 20 | 62 | E | 4.3.22 | 20.62 | Before it read "for which dot11OCBActivated is true". Now it is changed to "with dot11OCBActivated is true", which is grammtically incorrect. Please rephrase, e.g. "with dot11OCBActivated equal to true" | As in comment |  |  |  | Resolution approved | Editor | 22/0743r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0743-01-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 5011. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5012 | Sand, Stephan | No | 4.3.17a | 19 | 27 | E | 4.3.17a | 19.27 | "An Next " should read "A Next" since the pronounciation is a consonant | Replace "An" with "A" since the pronounciation following is a consonant |  |  |  | Resolution approved | Editor | 22/0743r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0743-01-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 5012. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5013 | YANG, RUI | Yes | 32.3.5 | 86 | 64 | E | 32.3.5 | 86.64 | Change DCM to BPSK-DCM, which is one of the modulation type. | Delete the first sentence and change the second sentence to "The use of BPSK-DCM on the Data field of an NGV PPDU is indicated…" |  |  |  | Resolution approved | Editor | 22/0745r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0745-01-00bd-resolutions-to-editorial-comments-part-3.docx) under CID 5013. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5014 | YANG, RUI | Yes | 32.3.3 | 82 | 44 | E | 32.3.3 | 82.44 | BPSK-DCM is one of the modulation type, but not DCM. | Change DCM to BPSK-DCM. Other places in the document should be changed as well. |  |  |  | Resolution approved | Editor | 22/0745r1 | V | REVISED [05/13/2022, EDITOR] To TGbd editor: Change DCM to BPSK-DCM at P82L44. Change “dualcarrier modulation (DCM)” to “BPSK- dualcarrier modulation (DCM)” at P69L22 (https://mentor.ieee.org/802.11/dcn/22/11-22-0745-01-00bd-resolutions-to-editorial-comments-part-3.docx) under CID 5014. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5015 | YANG, RUI | Yes | 31.4 | 66 | 1 | E | 31.4 | 66.01 | The sentence is confusing. | Change to "Fine timing measurement procedures, including negotiation and termination, for non-TB ranging …" |  |  |  | Resolution approved | Editor | 22/0744r1 | V | REVISED [05/13/2022, EDITOR] Agreed in principle. 11.21.6.3 (Fine timing measurement procedure negotiation) is only the FTM procedure negotiation. The FTM session termination is in 11.21.6.6 (Fine Timing Measurement session termination). To TGbd editor: Change the sentence at P66L01 to “Fine timing measurement procedures, including FTM procedure negotiation and FTM session termination for non-TB ranging as defined in 11.21.6.3 (Fine timing measurement procedure negotiation) and in 11.21.6.6 (Fine Timing Measurement session termination), with the modifications specified in this subclause.” (https://mentor.ieee.org/802.11/dcn/22/11-22-0744-01-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 5015 |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5016 | YANG, RUI | Yes | 31.2.1 | 61 | 44 | E | 31.2.1 | 61.44 | Change "transmit either of a non-NGV PPDU or an NGV PPDU" to "transmit either a non-NGV PPDU or an NGV PPDU" | as in comment |  |  |  | Resolution approved | Editor | 22/0744r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0744-01-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 5016 |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5017 | YANG, RUI | Yes | 32.3.2 | 80 | 62 | E | 32.3.2 | 80.62 | "per NGV-LTF symbols" should be "per NGV-LTF symbol". | As in comment |  |  |  | Resolution approved | Editor | 22/0745r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0745-01-00bd-resolutions-to-editorial-comments-part-3.docx) under CID 5017. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5018 | YANG, RUI | Yes | 32.2.2 | 75 | 19 | E | 32.2.2 | 75.19 | Remove space between "CBW" and "20". | As in comment |  |  |  | Resolution approved | Editor | 22/0744r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0744-01-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 5018 |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5019 | YANG, RUI | Yes | 11.21.6.4.6 | 51 | 58 | T | 11.21.6.4.6 | 51.58 | In 11az D4.1, "R2I N_STS" is used, instead of "R2I NUM_STS". | Change "R2I NUM_STS" to "R2I N_STS". The same change should be made in other parts of the spec related to his parameter. Similarly, Change "I2R NUM_STS" to "I2R N_STS". |  |  |  | Resolution approved | Stephan Sand | 22/0747r1 | V | REVISED [05/13/2022, EDITOR] Agree with comment, additionally found a wrong occurrence of NUM_STS which should be NUM_SS, an extra occurrence of FEC_CODING, and N_SS which should be NSS TGbd editor: Please replace NUM_STS on P51L58 and P52L9 with N_STS. Further replace NUM_STS on P116L65 with NUM_SS, remove FEC_CODING on P116L64, and replace N_SS on P123L28 with NSS. (https://mentor.ieee.org/802.11/dcn/22/11-22-0747-01-00bd-sa-ballot-cr-11bd-d4-0-ngv-ranging.docx) under CID 5019. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:47
5020 | YANG, RUI | Yes | 32.2.2 | 73 | 47 | T | 32.2.2 | 73.47 | Just say "The allowed value are 1 or 2" is confusing. | Change to "The allowed value: Set to 0 to indicate the number of spatial streams is one; Set to 1 to indicate the number of spatial streams is two. " |  |  |  | Resolution approved | Bo Sun | 22/0817r1 | A | ACCEPTED [05/24/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0817-01-00bd-crc-cr-clause-32-2.docx) under CID 5020. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5021 | YANG, RUI | Yes | 32.1.1 | 69 | 59 | E | 32.1.1 | 69.59 | "An NGV PHY may support the following features" should be "An NGV STA may support the following PHY features" | As in comment |  |  |  | Resolution approved | Editor | 22/0744r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0744-01-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 5021 |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5022 | YANG, RUI | Yes | 32.1.1 | 69 | 41 | E | 32.1.1 | 69.41 | "An NGV PHY shall support the following features" should be "An NGV STA shall support the following PHY features" | As in comment |  |  |  | Resolution approved | Editor | 22/0744r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0744-01-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 5022 |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5023 | YANG, RUI | Yes | 32.1.1 | 69 | 56 | E | 32.1.1 | 69.56 | All CID tags should be removed. | As in comment |  |  |  | Resolution approved | Editor | 22/0744r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0744-01-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 5023 |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5024 | YANG, RUI | Yes | 32.1.3.2 | 70 | 28 | E | 32.1.3.2 | 70.28 | The title of this subclause should be "PHY layer management entity (PLME)". | As in comment |  |  |  | Resolution approved | Editor | 22/0744r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0744-01-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 5024 |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5025 | Hunter, David | Yes | D.2.3 | 145 | 36 | T | D.2.3 | 145.36 | The subject of "complying" is ambiguous -- is the STA or the channel spacing the thing that must comply? Replacing "complying" with "that complies" would make it clear that it is the channel spacing that shall comply with the power class specification. | Replace "complying" with "that complies". Same change is necessary on line 41. |  |  |  | Resolution approved | Rui Cao | 22/0870r1 | V | REVISED [06/14/2022, EDITOR] Agree with the commenter that the word “complying with” is not accurate. The issue has been resolved in the resolution to CID 5038, where the phrase “complying with” is deleted as in https://mentor.ieee.org/802.11/dcn/22/11-22-0827-05-00bd-resolutions-to-clause-4-3-17-and-4-3-17a-cids.docx No further changes are needed. (https://mentor.ieee.org/802.11/dcn/22/11-22-0870-01-00bd-resolutions-for-misellaneous-phy-comments-for-11bd-initial-sa-ballot.docx) under CID 5025. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:27
5026 | Cao, Rui | No | 32.3.15 | 122 | 41 | E | 32.3.15 | 122.41 | To follow other amendment, suggest to move 32.3.15 (NGV ranging NDP) forward and before "Transmit specification". | as in the comment. |  |  |  | Resolution approved | Editor | 22/0745r1 | J | REJECTED [05/13/2022, EDITOR] There is no technical reason to reorganize the subclause. (https://mentor.ieee.org/802.11/dcn/22/11-22-0745-01-00bd-resolutions-to-editorial-comments-part-3.docx) under CID 5026. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5027 | Cao, Rui | No | 32.3.9.7 | 105 | 15 | T | 32.3.9.7 | 105.15 | NGV-LTF-2x-Repeat format is not included, suggest to either remove "for NGV-LTF-1x and NGV-LTF-2x" or add "NGV-LTF-2x-Repeat" to the list. | as in the comment. |  |  |  | Resolution approved | yujin noh | 22/0813r1 | V | REVISED [05/24/2022, EDITOR] Agreed in principle. TGbd Editor: add "NGV-LTF-2x-Repeat" to the list. Change “NGV-LTF-1x and NGV-LTF-2x” to “NGV-LTF-1x, NGV-LTF-2x, and NGV-LTF-2x-Repeat” (https://mentor.ieee.org/802.11/dcn/22/11-22-0813-01-00bd-resolutions-to-ngv-preamble-and-data-field.docx) under CID 5027. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5028 | Cao, Rui | No | 32.3.9.5 | 104 | 21 | T | 32.3.9.5 | 104.21 | "FEC encoders" shall be changed to "FEC encoder" as there is only one encoder for LDPC. | as in the comment. |  |  |  | Resolution approved | yujin noh | 22/0813r1 | A | ACCEPTED [05/24/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0813-01-00bd-resolutions-to-ngv-preamble-and-data-field.docx) under CID 5028. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5029 | Cao, Rui | No | 32.3.9.4 | 104 | 14 | T | 32.3.9.4 | 104.14 | The sentence does not read well and can be improved. In addition, the last part "and the LDPC Extra Symbol filed setting in NGV-SIG" seems irrelavent. | Suggest to change to "The Data field of an NGV PPDU shall use LDPC coding. The LDPC code and encoding process shall follow the same definition as described in 21.3.10.5.4 (LDPC coding) for a VHT SU PPDU with parameter m_STBC set to 1". |  |  |  | Resolution approved | yujin noh | 22/0813r1 | V | REVISED [05/24/2022, EDITOR] Agreed in principle. One long sentence is better to be split. However, NGV-SIG is required because the value of LDPC Extra Symbol field in NGV-SIG (not VHT-SIG-A) needs to be used. TGbd Editor: change to “The Data field of an NGV PPDU shall be encoded using LDPC coding. The LDPC code and encoding process shall follow as described in 21.3.10.5.4 (LDPC coding) for a VHT SU PPDU with parameter m_STBC set to 1 and the LDPC Extra Symbol field setting in NGV-SIG. (https://mentor.ieee.org/802.11/dcn/22/11-22-0813-01-00bd-resolutions-to-ngv-preamble-and-data-field.docx) under CID 5029. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5030 | Cao, Rui | No | 32.3.8.10 | 99 | 37 | T | 32.3.8.10 | 99.37 | As NGV-LTF-2x-Repeat is only defined for 10MHz Nss1 MCS15 transmission, suggest to change the condition from "… if the NGV Data field …" to "if and only if the NGV Data field ...". | as in the comment. |  |  |  | Resolution approved | Rui Cao | 22/0870r1 | A | ACCEPTED [06/14/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0870-01-00bd-resolutions-for-misellaneous-phy-comments-for-11bd-initial-sa-ballot.docx) under CID 5030. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:26
5031 | Cao, Rui | No | 32.3.8.2.2 | 92 | 55 | T | 32.3.8.2.2 | 92.55 | "The row for NSTS, …, is replaced with Nss, …", the word "replace" is not clear. Need to rephrase. | Suggest to change to ", where the values in the row for NSTS = m is used". |  |  |  | Resolution approved | Rui Cao | 22/0870r2 | A | ACCEPTED [06/14/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0870-02-00bd-resolutions-for-misellaneous-phy-comments-for-11bd-initial-sa-ballot.docx) under CID 5031. | Yes | Tue Jun 14 2022 |  |  | Classify CID5031 into editorial comment | 2022-06-14 16:32
5032 | Cao, Rui | No | 32.3.7.2 | 88 | 42 | T | 32.3.7.2 | 88.42 | The first paragraph should be describing non-NGV PPDU format, instead of NGV PPDU | Change the paragraph to "For a 10 MHz non-NGV PPDU, the signal is transmitted on subcarriers –26 to –1 and 1 to 26, with 0 being the center (DC) subcarrier. See 17.3.2.6 (Discrete time implementation considerations)." |  |  |  | Resolution approved | Rui Cao | 22/0870r1 | A | ACCEPTED [06/14/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0870-01-00bd-resolutions-for-misellaneous-phy-comments-for-11bd-initial-sa-ballot.docx) under CID 5032. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:26
5033 | Cao, Rui | No | 32.3.4.5 | 85 | 05 | T | 32.3.4.5 | 85.05 | In step d), the total number of interleaved bits should be 48 instead of 24. | Change the sentence to "Constellation Mapper: BPSK modulate the 48 interleaved bits as described in Clause 17.3.5.8 (Subcarrier modulation mapping) to form the NGV-SIG symbol." |  |  |  | Resolution approved | Rui Cao | 22/0870r1 | A | ACCEPTED [06/14/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0870-01-00bd-resolutions-for-misellaneous-phy-comments-for-11bd-initial-sa-ballot.docx) under CID 5033. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:26
5034 | Cao, Rui | No | 32.3.4.5 | 84 | 62 | E | 32.3.4.5 | 84.62 | In step a), a space is missing between "LTF_REP" and "Add". | as in the comment. |  |  |  | Resolution approved | Editor | 22/0745r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0745-01-00bd-resolutions-to-editorial-comments-part-3.docx) under CID 5034. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5035 | Cao, Rui | No | 32.2.2 | 73 | 26 | T | 32.2.2 | 73.26 | The description of "NGV_LTF_TYPE" value definition does not match the definition in NGV-SIG. Suggest to unify the definition. | Change the definition to "Set to 0 to indicate NGV-LTF-2x is used in the transmitted PPDU. Set to 1 to indicate NGV-LTF-1x is used in the transmitted PPDU." |  |  |  | Resolution approved | Bo Sun | 22/0817r1 | A | ACCEPTED [05/24/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0817-01-00bd-crc-cr-clause-32-2.docx) under CID 5035. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5036 | Cao, Rui | No | 31.6 | 68 | 23 | E | 31.6 | 68.23 | "(The SME is notified of the status …)" should be linked to a reference, rather than the text. | as in the comment. |  |  |  | Resolution approved | Editor | 22/0744r1 | V | REVISED [05/13/2022, EDITOR] Its reference should be “6.3.129 (NGV radio environment measurement)” TGbd Editor: Change "(The SME is notified of the status …)" to “6.3.129 (NGV radio environment measurement)” |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5037 | Cao, Rui | No | 31.6 | 68 | 17 | E | 31.6 | 68.17 | "(The SME is notified of the status …)" should be linked to a reference, rather than the text. | as in the comment. |  |  |  | Resolution approved | Editor | 22/0744r1 | V | REVISED [05/13/2022, EDITOR] Its reference should be “6.3.129 (NGV radio environment measurement)” TGbd Editor: Change "(The SME is notified of the status …)" to “6.3.129 (NGV radio environment measurement)” (https://mentor.ieee.org/802.11/dcn/22/11-22-0744-01-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 5037 |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5038 | Cao, Rui | No | 4.3.17a | 20 | 3 | T | 4.3.17a | 20.03 | "class C transmit spectrum mask for 10MHz NGV PPDU", the term used here is not consistent with Clause 32. | Change the sentence to "transmit spectrum mask of power Class C for 10MHz NGV PPDU" |  |  |  | Resolution approved | John Kenney | 22/0827r5 | V | REVISED [06/14/2022, EDITOR] Agree in principle with the commenter. See document 11-22/0827r1 (https://mentor.ieee.org/802.11/dcn/22/11-22-0827-05-00bd-resolutions-to-clause-4-3-17-and-4-3-17a-cids.docx) for redline edits, including edits to Clause 32.1.1, 32.3.10.1, and Annex D for consistent use of power class terminology (https://mentor.ieee.org/802.11/dcn/22/11-22-0827-05-00bd-resolutions-to-clause-4-3-17-and-4-3-17a-cids.docx) under CID 5038. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:18
5039 | Hunter, David | Yes | 4.3.17a | 20 | 39 | T | 4.3.17a | 20.39 | Phony requirement in General Descriptions section. | Replace "may" with "might". Same change is necessary on line 50. |  |  |  | Resolution approved | John Kenney | 22/0827r5 | A | ACCEPTED [06/14/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0827-05-00bd-resolutions-to-clause-4-3-17-and-4-3-17a-cids.docx) under CID 5039. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:18
5040 | Hunter, David | Yes | 4.3.17a | 19 | 39 | T | 4.3.17a | 19.39 | Phony requirement in General Description section. | Replace "may" with "might". Same change is necessary on line 42. |  |  |  | Resolution approved | John Kenney | 22/0827r5 | A | ACCEPTED [06/14/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0827-05-00bd-resolutions-to-clause-4-3-17-and-4-3-17a-cids.docx) under CID 5040. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:18
5041 | Hunter, David | Yes | 4.3.17 | 19 | 12 | T | 4.3.17 | 19.12 | Phony requirement in General Description. | Replace "may" with "might". |  |  |  | Resolution approved | John Kenney | 22/0827r5 | A | ACCEPTED [06/14/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0827-05-00bd-resolutions-to-clause-4-3-17-and-4-3-17a-cids.docx) under CID 5041. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:18
5042 | Hunter, David | Yes | 4.3.17a | 20 | 31 | E | 4.3.17a | 20.31 | Plural needed | In "primary and ... secondary channel" replace "channel" with "channels". |  |  |  | Resolution approved | Editor | 22/0743r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0743-01-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 5042. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5043 | Hunter, David | Yes | 4.3.17a | 20 | 30 | T | 4.3.17a | 20.30 | Phony requirement in General Description. | Replace "shall support" with "supports". |  |  |  | Resolution approved | John Kenney | 22/0827r5 | A | ACCEPTED [06/14/2022, EDITOR] Note to editor: The resolution of CID 5089 refers to this resolution (https://mentor.ieee.org/802.11/dcn/22/11-22-0827-05-00bd-resolutions-to-clause-4-3-17-and-4-3-17a-cids.docx) under CID 5043. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:18
5044 | Hunter, David | Yes | 4.3.17a | 19 | 35 | T | 4.3.17a | 19.35 | Phony requirement located in General Description section. | Replace "shall set" with "sets". Same change is necessary on line 36. |  |  |  | Resolution approved | John Kenney | 22/0827r5 | V | REVISED [06/14/2022, EDITOR] Agree that “shall set” is not appropriate for this clause (two places: P19.L35 and P19.L36). See document 11-22/0827r1 (https://mentor.ieee.org/802.11/dcn/22/11-22-0827-05-00bd-resolutions-to-clause-4-3-17-and-4-3-17a-cids.docx) for redline edits to the two sentences. Note to editor: CID 5090 addresses the same content. (https://mentor.ieee.org/802.11/dcn/22/11-22-0827-05-00bd-resolutions-to-clause-4-3-17-and-4-3-17a-cids.docx) under CID 5044. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:18
5045 | An, Song-Haur | Yes |  |  |  | G |  | 0.00 | Even though NUM_SS > 1 is optional, it may be preferred to compete the rival technology like C-V2X. It is not clear if it must be initiated by the higher layer via the number of spatial streams in the radio environment request vector. Another optional feature NGV ranging, it has an informative subclause to show how to start it. | Suggest adding a subclause to show how SU_MIMO may be initiated even though it is an optional feature. |  |  |  | Resolution approved | Rui Cao | 22/0870r1 | J | REJECTED [06/14/2022, EDITOR] The text for “radio environment request” in paragraph starting P24L26 clearly indicates that how number of spatial stream is set depending on different settings of member values of “PPDU format” and “number of spatial stream”. “The number of spatial streams member with value 1 or 2 indicates the number of spatial streams being used to transmit the PPDU carrying the MSDU. The number of spatial streams member with value 0 means that the number of spatial streams is decided by the MAC layer. If the PPDU format has value 2, the data rate/NGV-MCS member is set to value 14 indicating that the actual data-rate/MCS is decided by the MAC layer.” (https://mentor.ieee.org/802.11/dcn/22/11-22-0870-01-00bd-resolutions-for-misellaneous-phy-comments-for-11bd-initial-sa-ballot.docx) under CID 5045. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:25
5046 | An, Song-Haur | Yes |  |  |  | G |  | 0.00 | The terms "higher layer" and "upper layer" appear 22 and 7 instances, respectively, in this amendment. It's not clear if this is intentional. They seem to convey the same point. | Please clarify the rationale of using these two terms in the context, and perhaps add a note to the first occurrence each. If there is nothing specific that supports using the different terms, suggest unifying them to one term throughout the amendment. |  |  |  | Resolution approved | Stephan Sand | 22/0747r2 | V | REVISED [05/24/2022, EDITOR] Agree with comment 802.11-2020 base line uses 28 times upper layer(s) and 232 times higher layer(s) Term higher layer preferred over upper layer TGbd editor: Please replace all 7 occurences of “the upper layer” with “a higher layer” on P30L56, P64L38, P68L6, P68L15, P68L16, P68L21, and P68L23. Further please add “a” before “higher layer” on P49L8, replace “the” with “a” on P53L45, remove “the” in front of “higher layers” on P66L17, P67L16, and replace “the higher layer” with “higher layers” on P67L17. (https://mentor.ieee.org/802.11/dcn/22/11-22-0747-02-00bd-sa-ballot-cr-11bd-d4-0-ngv-ranging.docx) under CID 5046. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5047 | An, Song-Haur | Yes | 32.3.15 | 123 | 5 | T | 32.3.15 | 123.05 | " … the product of the number of spatial streams the TXVECTOR parameter NUM_SS and the number of LTF repetitions…" is incorrect because the number of LTF repetitions as indicated by LTF_REP could be zero. | Modify to " ...the product of the number of spatial streams the TXVECTOR parameter NUM_SS and (LTF_REP+1). LTF_REP indicates if LTF repetition is used or not. When LTF repetition is used, LTF_REP=1. Otherwise, LTF_REP is 0." |  |  |  | Resolution approved | Stephan Sand | 22/0747r1 | V | REVISED [05/13/2022, EDITOR] Agree with comment that LTF_REP could be zero and thus number of NGV-LTFs could be zero. See also CID 5006. Second part of proposed change not improving current spec text and hence is not applied. TGbd editor: Please replace the sentence starting on P123L4 with “The number of NGV-LTF symbols in an NGV ranging NDP is the product of the TXVECTOR parameter NUM_SS and (LTF_REP+1), see Table 32-11 (Number of NGV-LTFs required for different numbers of spatial streams)." Further, please replace “denotes” with “indicates” on P122L63 (https://mentor.ieee.org/802.11/dcn/22/11-22-0747-01-00bd-sa-ballot-cr-11bd-d4-0-ngv-ranging.docx) under CID 5047. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:48
5048 | An, Song-Haur | Yes | 32.3.13 | 120 | 37 | T | 32.3.13 | 120.37 | Change "CRC fail" to "Invalid CRC or Reserved NGV-SIG indication" to be consistent with the paragraph description. | As in comment |  |  |  | Resolution approved | yujin noh | 22/0815r4 | V | REVISED [06/14/2022, EDITOR] Agreed in principle. However, one modification should be the box for “Evaluate NGV-SIG” not “RX NGV-SIG” since Reserved NGV-SIG indication should be evaludated after CRC ok. Further consideration is required as below. Replace” CRC Fail” to Invalid CRC” add "Reserved NGV-SIG Indication: Set PHY RXEND.indication(FormatViolation)" below the arrow from "Evaluate NGV-SIG" to "End of Wait" TGbd Editor: Incorporate the changes in 11-22-0815-02-00bd- Resolutions to Transmit specification to NGV receive procedure. The corresponding visio file is in in 22/0826. (https://mentor.ieee.org/802.11/dcn/22/11-22-0815-04-00bd-resolutions-to-transmit-specification-to-ngv-receive-procedure.docx) under CID 5048. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:11
5049 | An, Song-Haur | Yes | 32.3.13 | 120 | 26 | T | 32.3.13 | 120.26 | The outgoing arrow "Parity or RATE check failed" is a fatal event and should not go back to Detect SIG for non-NGV. Instead, it should go to End of Wait with an error condition as stated in P121L15. | According to P121L15, the outgoing arrow should show PHY-RXEND.indication(FormatViolation) primitive and point to End of Wait to be consistent with other primitives in the figure. As such, need to add this error condition to the End of Wait box. |  |  |  | Resolution approved | yujin noh | 22/0815r4 | V | REVISED [06/14/2022, EDITOR] Agreed in principle. However, if Parity or RATE check is failed, next step is to continue to detect the received signal using non-NGV receive procedure. This procedure is known common understanding on how to operate auto-dection when RL-SIG has been introduced back in 11ax. If RL-SIG detection is failed, or specific conditions in L-SIG(RL-SIG) are not correct then next step is recommended to check whether it is legacy PPDU. Since the same modification in CID5050 has been applied, no further modification is required. (https://mentor.ieee.org/802.11/dcn/22/11-22-0815-04-00bd-resolutions-to-transmit-specification-to-ngv-receive-procedure.docx) under CID 5049. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:10
5050 | An, Song-Haur | Yes | 32.3.13 | 120 | 16 | T | 32.3.13 | 120.16 | In NGV receive, "Detect SIG for non-NGV" is determined by not detecting RL_SIG. | The incoming arrow of the box "Detect SIG for non-NGV" from CS/CCA should be replaced by the arrow from the "Detect RL-SIG" box labeling "Repetition failed." The label is suggested changed to "RL_SIG detection failed" for clarity because the word "repetition" is used for other context as well like N_PPDU_REP and LTF_REP. |  |  |  | Resolution approved | yujin noh | 22/0815r4 | V | REVISED [06/14/2022, EDITOR] Agreed in principle. For 11bd, there is no other types other than NGV and non-NGV(11p), there is no need to further determine preamble types if 11bd check fails (fails detecting RL-SIG). 1) delete the "Detect SIG for non-NGV" and point two arrows to the block “NON_NGV_10 repetition” 2) "Repetition failed" to "RL-SIG detection failed" 3) "Repetition detected" to "RL-SIG detected" TGbd Editor: Incorporate the changes in 11-22-0815-04-00bd- Resolutions to Transmit specification to NGV receive procedure. The corresponding visio file is in DCN 22/0826. (https://mentor.ieee.org/802.11/dcn/22/11-22-0815-04-00bd-resolutions-to-transmit-specification-to-ngv-receive-procedure.docx) under CID 5050. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:10
5051 | An, Song-Haur | Yes | 32.3.12 | 118 | 37 | E | 32.3.12 | 118.37 | Change "space-time stream" to "spatial streams." | As in comment |  |  |  | Resolution approved | Editor | 22/0745r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0745-01-00bd-resolutions-to-editorial-comments-part-3.docx) under CID 5051. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5052 | An, Song-Haur | Yes | 32.3.12 | 117 | 6 | E | 32.3.12 | 117.06 | Midamble is required in an NGV PPDU. | Change " … if present" to "… except for the last OFDM symbol if mod(N_SYM,M)=0 ." |  |  |  | Resolution approved | yujin noh | 22/0815r4 | J | REJECTED [06/14/2022, EDITOR] The midamble feature shall be supported but it does not mean midamble is inserted in every NGV PPDU. For example, the number of OFDM symbol is small enough, there is a case that midamble is not existed in NGV PPDU. So “If present” is necessary under the condition with Equation (32-35) which covers the midamble not inserted after the last OFDM. “If present” deliver its intention clearly. (https://mentor.ieee.org/802.11/dcn/22/11-22-0815-04-00bd-resolutions-to-transmit-specification-to-ngv-receive-procedure.docx) under CID 5052. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:10
5053 | An, Song-Haur | Yes | 32.3.12 | 117 | 5 | T | 32.3.12 | 117.05 | According to the description in P103L40 of subclause 32.3.9.1, PHY padding to ensure integral number of octets in an OFDM data symbol. | change " … integer multiple of the number of coded bits per OFDM symbol" to "… integer multiple of the number of coded octets per OFDM data symbol." |  |  |  | Resolution approved | yujin noh | 22/0815r4 | V | REVISED [06/14/2022, EDITOR] In original text, coded PSDU might mislead the intentsion that data field consists of an integer multiple of the OFDM symbols (N_SYM,init x N_DBPS). To TGbd: change to “PHY padding bits are appended to the PSDU to make the number of bits in the coded SERVICE field and PSDU an integer multiple of the number of coded bits per OFDM symbol.” (https://mentor.ieee.org/802.11/dcn/22/11-22-0815-04-00bd-resolutions-to-transmit-specification-to-ngv-receive-procedure.docx) under CID 5053. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:11
5054 | An, Song-Haur | Yes | 32.3.12 | 117 | 1 | E | 32.3.12 | 117.01 | In general, scrambling the input data prior to FEC encoding is performed to endure sufficient randomness for better decoding performance. | Suggest adding "scrambled and" to result in "The SERVICE field and PSDU are scrambled and encoded…" |  |  |  | Resolution approved | yujin noh | 22/0815r4 | A | ACCEPTED [06/14/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0815-04-00bd-resolutions-to-transmit-specification-to-ngv-receive-procedure.docx) under CID 5054. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:10
5055 | An, Song-Haur | Yes | 32.3.10.4.4 | 111 | 12 | E | 32.3.10.4.4 | 111.12 | Midamble is required in an NGV PPDU. | Remove "If midambles are present in the Data field of the PPDU" and fix the sentence. The change is applied to L21 on the same page. |  |  |  | Resolution approved | yujin noh | 22/0815r4 | J | REJECTED [06/14/2022, EDITOR] The midamble feature shall be supported but it does not mean midamble is inserted in every NGV PPDU. For example, the number of OFDM symbol is small enough, there is a case that midamble is not existed in NGV PPDU. So “If present” is necessary under the condition with Equation (32-35) (https://mentor.ieee.org/802.11/dcn/22/11-22-0815-04-00bd-resolutions-to-transmit-specification-to-ngv-receive-procedure.docx) under CID 5055. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:10
5056 | An, Song-Haur | Yes | 32.3.10.4.3 | 110 | 7 | T | 32.3.10.4.3 | 110.07 | Since this is addressing NGV-PPDUs, Table 21-24 should be changed to Table 32-14. | As in comment |  |  |  | Resolution approved | yujin noh | 22/0815r4 | A | ACCEPTED [06/14/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0815-04-00bd-resolutions-to-transmit-specification-to-ngv-receive-procedure.docx) under CID 5056. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:09
5057 | An, Song-Haur | Yes | 32.3.9.9 | 107 | 63 | T | 32.3.9.9 | 107.63 | The NON_NGV_10 duplicate PPDU may be received by a non NGV STA. For the backward compatibility, the modulation dependent power scaling factor in the L-STF and L-LTF fields is not applied. | Add "the modulation dependent power scaling factor in the L-STF and L-LTF fields is set to 1 and that" immediately following except that. |  |  |  | Resolution approved | yujin noh | 22/0813r1 | V | REVISED [05/24/2022, EDITOR] Agreed in principle. However, power scaling factor squre root (2) is applied under the specified condition which are found at 91.13 and 93.16. This value is not applicable to NON_NGV_10 duplicate PPDU for 20MHz transmission. Adding Note could make the text clear. TGbd Editor: Incorporate the changes in 11-22-0813-01-00bd-Resolutions to NGV preamble and NGV receive procedure. (https://mentor.ieee.org/802.11/dcn/22/11-22-0813-01-00bd-resolutions-to-ngv-preamble-and-data-field.docx) under CID 5057. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5058 | An, Song-Haur | Yes | 32.3.9.9 | 107 | 35 | T | 32.3.9.9 | 107.35 | The use of midamble is required in the NGV PPDU. | Remove "If present" and fix the sentence. |  |  |  | Resolution approved | yujin noh | 22/0813r1 | J | REJECTED [05/24/2022, EDITOR] The midamble feature shall be supported but it does not mean midamble is inserted in every PPDU. For example, the number of OFDM symbol is small enough, there is a case that midamble is not existed in PPDU. So “If present” is necessary under the condition with Equation (32-35) (https://mentor.ieee.org/802.11/dcn/22/11-22-0813-01-00bd-resolutions-to-ngv-preamble-and-data-field.docx) under CID 5058. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5059 | An, Song-Haur | Yes | 32.3.9.9 | 107 | 12 | E | 32.3.9.9 | 107.12 | Suggest unifying the style of nth (L12 & L13) and M-th (L50) on this page. | As in comment |  |  |  | Resolution approved | Editor | 22/0745r1 | V | REVISED [05/13/2022, EDITOR] Agreed in principle. TGbd Editor: Change n^th to n-th at P107L12 and P107L13 (https://mentor.ieee.org/802.11/dcn/22/11-22-0745-01-00bd-resolutions-to-editorial-comments-part-3.docx) under CID 5059. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5060 | An, Song-Haur | Yes | 32.3.9.6 | 104 | 41 | E | 32.3.9.6 | 104.41 | The symbol d'k appears once and not used elsewhere. | Please clarify and complete its usage or delete it if not needed. |  |  |  | Resolution approved | yujin noh | 22/0813r1 | V | REVISED [05/24/2022, EDITOR] Agreed in principle. TGbd Editor: Incorporate the changes in 11-22-0813-01-00bd-Resolutions to Resolutions to NGV preamble and Data field (https://mentor.ieee.org/802.11/dcn/22/11-22-0813-01-00bd-resolutions-to-ngv-preamble-and-data-field.docx) under CID 5060. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5061 | An, Song-Haur | Yes | 32.3.9.6 | 104 | 34 | E | 32.3.9.6 | 104.34 | It would be more clear for dk,m,n in equation (32-29) by adding "out of constellation mapping" immediately following "The streams of complex numbers." | As in comment |  |  |  | Resolution approved | Editor | 22/0745r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0745-01-00bd-resolutions-to-editorial-comments-part-3.docx) under CID 5061. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5062 | An, Song-Haur | Yes | 32.3.8.10 | 101 | 38 | E | 32.3.8.10 | 101.38 | The caption of Figure 32-10 shows NGV-LTF. N_SS is either 1 or 2 in an NGV PPDU. | Remove one extra box of "CSD per SS" and the dotted vertical lines associated with it. This proposed change is applied to Figure 32-11 as well. |  |  |  | Resolution approved | yujin noh | 22/0813r1 | A | ACCEPTED [05/24/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0813-01-00bd-resolutions-to-ngv-preamble-and-data-field.docx) under CID 5062. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5063 | An, Song-Haur | Yes | 32.3.8.7 | 96 | 60 | E | 32.3.8.7 | 96.60 | Make a space immediately following the 2nd period on this line. | As in comment |  |  |  | Resolution approved | Editor | 22/0745r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0745-01-00bd-resolutions-to-editorial-comments-part-3.docx) under CID 5063. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5064 | An, Song-Haur | Yes | 32.3.8.5 | 95 | 28 | E | 32.3.8.5 | 95.28 | Remove "pilot" from the sentence. It is the first value of the pn sequence not a pilot value. Similarly, please also remove "pilot" from L64 on the same page and on P98L5. | As in comment |  |  |  | Resolution approved | yujin noh | 22/0813r1 | J | REJECTED [05/24/2022, EDITOR] Since this description has been used in common and its meansing is well understood for IEEE 2020 specification, better to keep it as it is to be consistent with IEEE 2020 specification. (https://mentor.ieee.org/802.11/dcn/22/11-22-0813-01-00bd-resolutions-to-ngv-preamble-and-data-field.docx) under CID 5064. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5065 | An, Song-Haur | Yes | 32.3.7.2 | 88 | 42 | T | 32.3.7.2 | 88.42 | Firstly, change "a 10 MHz NGV PPDU" to "a NON_NGV_10 PPDU." Then, for an NGV PPDU 10 MHz or 20 MHz in the subsequent paragraphs, need to separate pre-NGV modulated fields and NGV modulated fields to discuss the subcarrier usage. | As in comment |  |  |  | Resolution approved | Rui Cao | 22/0870r1 | V | REVISED [06/14/2022, EDITOR] The first part of the comment is the same as CID5032. No further change is needed. For the second part of the comment on 10MHz and 20MHz NGV PPDU, there is no need to separate pre-NGV modulated fields and NGV modulated fields. This subclause only specifies the lower and upper bound of the modulated tones in the entire PPDU. Different fields will have different loaded tones described in each corresponding subclauses. It is not practical to list all details in this subclause. Similar text style is also used in other PHY subclauses. (https://mentor.ieee.org/802.11/dcn/22/11-22-0870-01-00bd-resolutions-for-misellaneous-phy-comments-for-11bd-initial-sa-ballot.docx) under CID . |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:26
5066 | An, Song-Haur | Yes | 32.3.4.5 | 85 | 5 | T | 32.3.4.5 | 85.05 | "… 24 interleaved bits…" should be "48 interleaved encoded bits…" | As in comment |  |  |  | Resolution approved | Rui Cao | 22/0870r1 | A | ACCEPTED [06/14/2022, EDITOR] The same comment as CID5033. No change is needed. (https://mentor.ieee.org/802.11/dcn/22/11-22-0870-01-00bd-resolutions-for-misellaneous-phy-comments-for-11bd-initial-sa-ballot.docx) under CID 5066. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:26
5067 | An, Song-Haur | Yes | 32.3.3 | 83 | 12 | E | 32.3.3 | 83.12 | Please remove the dotted vertical line on the left. NUM_SS is either 1 or 2 only for an NGV STA. The dotted vertical line on the right can be kept. | As in comment |  |  |  | Resolution approved | yujin noh | 22/0814r1 | A | ACCEPTED [05/24/2022, EDITOR] To TGbd editor: location of the title of Figure 32-7 should be centered. (https://mentor.ieee.org/802.11/dcn/22/11-22-0814-01-00bd-resolutions-to-ngv-ppdu-format-and-transmiiter-block-diagram.docx) under CID 5067. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5068 | An, Song-Haur | Yes | 32.3.3 | 83 | 2 | E | 32.3.3 | 83.02 | Please add "CSD per chain is included in the Spatial Mapping block" to the end of the paragraph to account for item l) on P81L61. | As in comment |  |  |  | Resolution approved | yujin noh | 22/0814r1 | J | REJECTED [05/24/2022, EDITOR] First of all, there is no paragraph corresponding to the l) CSD per chain insertion in the current specification since it is about the transmitter block diagram for the Data field. For some cases, Q (Spatial mapping) could be CSD per chain when it is not beamformed but Q is implementation depent, no reason to fix that CSD per chain is included in the Sptail Mapping block in 11bd (https://mentor.ieee.org/802.11/dcn/22/11-22-0814-01-00bd-resolutions-to-ngv-ppdu-format-and-transmiiter-block-diagram.docx) under CID 5068. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5069 | An, Song-Haur | Yes | 32.2.5.2 | 78 | 41 | T | 32.2.5.2 | 78.41 | The phrase "...but with the CHANNEL WIDTH parameter discarded from PHYCONFIG_VECTOR…" appears confusion. The parameter CHANNEL_WIDTH is not included in NGV PHYCONFIG_VECTOR defined in 32.2.3. | Add CHANNEL_WIDTH back to PHYCONFIG_VECTOR in 32.2.3. Please note that VHT PHYCONFIG_VECTOR includes CHANNEL_WIDTH. |  |  |  | Resolution approved | Bo Sun | 22/0817r1 | V | REVISED [05/24/2022, EDITOR] Discussion: Agree with the comment that the NGV PHYCONFIG_VECTOR doesn’t contain CHANNEL_WIDTH. In fact, the NGV PHYCONFIG_VECTOR contains “OPERATING_CHANNEL” and “SECONDARY_CHANNEL_OFFSET”. But it’s not proper to add CHANNEL_WIDTH parameter back. A proposed change is to replace “CHANNEL_WIDTH” with “SECONDARY_CHANNEL_OFFSET” Instruction to TGbd Editor: Please replace “…but with the CHANNEL WIDTH parameter discarded…” with “…but with the SECONDARY_CHANNEL_OFFSET parameter discarded…” at pg78/ln41. (https://mentor.ieee.org/802.11/dcn/22/11-22-0817-01-00bd-crc-cr-clause-32-2.docx) under CID 5069. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5070 | An, Song-Haur | Yes | 32.2.5.1 | 77 | 12 | E | 32.2.5.1 | 77.12 | The phrase "Clause 32 Transmit Procedure" appears to be the label of the outer dotted box. Should move it to the bottom edge of the box to avoid confusing with the vertical arrow line. The inner dotted box "Clause 17 Transmit Procedure" should not include "32.3.9.10 and 32.3.9 Non-NGV duplicate PPDU." Suggest making them two separate boxes. Also, "and 32.3.9" should be removed. | As in comment |  |  |  | Resolution approved | Bo Sun | 22/0817r1 | V | REVISED [05/24/2022, EDITOR] Discussion: Agree on the comment that the location of the phrase “Clause 32 Transmit Procedure” could be moved to a better place to avoid confusing with the arrow. But the assignee believes it’s “32.3.9.10” to be removed instead of “32.3.9” because the box addressed is to cover the non-NGV duplicate PPDU which is explained over the whole sub-clause 32.3.9. The assignee doesn’t agree to separate the box marked “32.3.9” from the box marked “Clause 17 Transmitting Procedure” because the bigger box is to indicate the transmitting procedure is based on clause 17 but with non-NGV duplicate PPDU format defined in clause 32.3.9. Instruction to TGbd Editor: Please move the label “Clause 32 Transmit procedure” to the bottom of the dot-lined box to avoid any confusing with any arrow. And please remove “32.3.9.10” from the solid-lined box inside the dot-lined box labeled with “Clause 17 Transmit procedure”. (https://mentor.ieee.org/802.11/dcn/22/11-22-0817-01-00bd-crc-cr-clause-32-2.docx) under CID 5070. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5071 | An, Song-Haur | Yes | 32.2.2 | 75 | 47 | E | 32.2.2 | 75.47 | Change "PSDU_LENGTH" to "APEP_LENGTH" because PDSU_LENGTH (shown on P74L33) is not a TXVECTOR parameter. | As in comment |  |  |  | Resolution approved | yujin noh | 22/0814r1 | A | ACCEPTED [05/24/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0814-01-00bd-resolutions-to-ngv-ppdu-format-and-transmiiter-block-diagram.docx) under CID 5071. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5072 | An, Song-Haur | Yes | 32.2.2 | 75 | 29 | T | 32.2.2 | 75.29 | Clause 17 is the core of 11p (WAVE). Although the parameter TIME_OF_DEPARTURE_REQUESTED appears in several clauses, Table 17-1 should be a better pointer in the context of V2X. | Change Table 19-1 to Table 17-1. |  |  |  | Resolution approved | Bo Sun | 22/0817r1 | V | REVISED [05/24/2022, EDITOR] Discussion: Agree on the comment that Table 19-1 is not a good reference for NGV TXVECTOR parameters. Table 17-1 is a better reference when same parameters are defined for NGV as for Non-NGV format. A minor change to the original proposed change is that the title of Table 17-1 is “TXVECTOR parameters” and it should be optional for TXVECTOR and N for RXVECTOR. Instruction to TGbd Editor: Please incorporate the proposed modification as part of resolution to CID 5072 in document 11-22/0817r1. (https://mentor.ieee.org/802.11/dcn/22/11-22-0817-01-00bd-crc-cr-clause-32-2.docx) under CID 5072. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5073 | An, Song-Haur | Yes | 32.2.2 | 75 | 19 | E | 32.2.2 | 75.19 | Remove the space between CHW and 20 for consistency with CHW10. | As in comment |  |  |  | Resolution approved | Editor | 22/0744r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0744-01-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 5073 |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5074 | An, Song-Haur | Yes | 32.2.2 | 74 | 36 | T | 32.2.2 | 74.36 | The sentence "The value of 0 indicates an NGV ranging NDP." can be removed because PSDU_LENGTH is not a TXVECTOR parameter. | As in comment |  |  |  | Resolution approved | Bo Sun | 22/0817r1 | J | REJECTED [05/24/2022, EDITOR] Reason: The parameter PSDU_LENGTH is used to indicate to the RX MAC an NDP is received when PSDU_LENGTH is equal to 0. A similar statement to APEP_LENGTH has been added as resolution to CID 5075. (https://mentor.ieee.org/802.11/dcn/22/11-22-0817-01-00bd-crc-cr-clause-32-2.docx) under CID 5074. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5075 | An, Song-Haur | Yes | 32.2.2 | 74 | 28 | E | 32.2.2 | 74.28 | in subclause 11.21.6.4.6 (Transmission of a ranging NDP), the APEP_LENGTH parameter is set to 0 to indicate a ranging NDP. Need to keep consistency here. | Add "The value of 0 indicates an NGV ranging NDP." at the end of the description. Also, need to change the starting value to 0 from 1. |  |  |  | Resolution approved | Editor | 22/0744r1 | V | REVISED [05/13/2022, EDITOR] Agreed in principle. TGbd Editor: Replace the description as below. If 0, indicates an NGV ranging NDP. Otherwise, indicates the number of octets in the range 1 to …. that is carried in the PSDU” (https://mentor.ieee.org/802.11/dcn/22/11-22-0744-01-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 5075 |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5076 | An, Song-Haur | Yes | 32.2.2 | 73 | 26 | T | 32.2.2 | 73.26 | In TXVECTOR (Table 32-1), the parameter NGV_LTF_TYPE is defined as Set to 0 to indicate NGV-LTF-1x is used in the transmitted PPDU. Set to 1 to indicate NGV-LTF-2x is used in the transmitted PPDU. But, in NGV_SIG field (Table 32-10), B10 (on P96L31) says Set to 0 for NGV-LTF-2x Set to 1 for NGV-LTF-1x Such reversed assignment may introduce confusion unless there is a rationale not currently shown in the two tables. | Please clarify the reversed assignment. If it's a typo, please correct it. If it is intentional with a reason, please add a note to B10 in Table 32-10. |  |  |  | Resolution approved | Bo Sun | 22/0817r1 | V | REVISED [05/24/2022, EDITOR] Discussion: Agree on the comment that the inconsistent description may cause confusion to potential readers. Similar issue is addressed in CID 5035 as well. The addressed issue could be resolved with implementation of resolution to CID 5035. Instruction to TGbd Editor: No further modification is needed. (https://mentor.ieee.org/802.11/dcn/22/11-22-0817-01-00bd-crc-cr-clause-32-2.docx) under CID 5076. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5077 | An, Song-Haur | Yes | 32.2.2 | 73 | 24 | E | 32.2.2 | 73.24 | Suggest changing "the type of NGV-LTF" to "the NGV-LTF format." LTF "format" seems used more frequently than LTF "type" in this amendment. | As in comment |  |  |  | Resolution approved | Editor | 22/0744r1 | J | REJECTED [05/13/2022, EDITOR] In the different amendments, same descriptions have been used without any technical issues. It is good to have consistent descriptions through different amendments for better understandings. (https://mentor.ieee.org/802.11/dcn/22/11-22-0744-01-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 5077 |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5078 | An, Song-Haur | Yes | 32.2.2 | 72 | 44 | E | 32.2.2 | 72.44 | Suggest adding "Note: Set to 0 for NGV ranging NDP" as required in 32.3.15 (NGV ranging NDP) at the bottom of the Value description. | As in comment |  |  |  | Resolution approved | Editor | 22/0744r1 | V | REVISED [05/13/2022, EDITOR] Agreed in principle. TGbd Editor: Add “Note: Set to 0 for NGV ranging NDP. See 32.3.15 (NGV ranging NDP)” below the value description. (https://mentor.ieee.org/802.11/dcn/22/11-22-0744-01-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 5078 |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5079 | An, Song-Haur | Yes | 32.1.1 | 69 | 51 | T | 32.1.1 | 69.51 | The NON_NGV_10 PPDU is required for backward compatibility as indicated on P20L10. | Add NON_NGV_10 PPDU to the "shall support" list. |  |  |  | Resolution approved | Rui Cao | 22/0870r1 | V | REVISED [06/14/2022, EDITOR] Agree with the comment to specify it in the PHY subclause. TGbd editor: please make the changes as in https://mentor.ieee.org/802.11/dcn/22/11-22-0870-00-00bd-resolutions-for-misellaneous-phy-comments-for-11bd-initial-sa-ballot.docx (https://mentor.ieee.org/802.11/dcn/22/11-22-0870-01-00bd-resolutions-for-misellaneous-phy-comments-for-11bd-initial-sa-ballot.docx) under CID 5079. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:26
5080 | An, Song-Haur | Yes | 11.21.6.4.6 | 51 | 62 | T | 11.21.6.4.6 | 51.62 | The statement "The PSDU_LENGTH parameter is set to 0." can be removed because PDSU_LENGTH is not a TXVECTOR parameter. The same on P52L14 can be removed for the same reason. | As in comment |  |  |  | Resolution approved | Stephan Sand | 22/0747r1 | A | ACCEPTED [05/13/2022, EDITOR] See also CID 5008 (https://mentor.ieee.org/802.11/dcn/22/11-22-0747-01-00bd-sa-ballot-cr-11bd-d4-0-ngv-ranging.docx) under CID 5080. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:47
5081 | An, Song-Haur | Yes | 11.21.6.4.6 | 51 | 65 | T | 11.21.6.4.6 | 51.65 | To be consistent with subclause 32.3.15 (NGV ranging NDP), suggest adding "NGV_MCS is set to 0" in both paragraphs RSTA transmitting … to ISTA and ISTA transmitting … to RSTA. | As in comment |  |  |  | Resolution approved | Stephan Sand | 22/0747r1 | J | REJECTED [05/13/2022, EDITOR] As P122L65 in 32.3.15 already defines “NGV_MCS shall be set to 0” there is no need to repeat this in 11.21.6.4.6 (https://mentor.ieee.org/802.11/dcn/22/11-22-0747-01-00bd-sa-ballot-cr-11bd-d4-0-ngv-ranging.docx) under CID 5081. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:48
5082 | An, Song-Haur | Yes | 5.2.4.2 | 26 | 21 | E | 5.2.4.2 | 26.21 | It's odd to include "decided by the MAC layer" upon the received PPDU that carries the MPDU of interest. | Remove the phrases or sentences that address "decide by the MAC layer." |  |  |  | Resolution approved | Liwen Chu | 22/0828r1 | V | REVISED [05/31/2022, EDITOR] Discussion: this sentence is in subclause about reception. “0” for MAC layer decision is not needed. TGbd editor: Please change “The data rate can be either 0 (decided by MAC layer), 3, 4.5, 6, 9, 12, 18, 24, or 27 Mb/s as defined in Table 17-4 (Modulation-dependent parameters).” to “The data rate can be one of 3, 4.5, 6, 9, 12, 18, 24, or 27 Mb/s as defined in Table 17-4 (Modulation-dependent parameters).” (https://mentor.ieee.org/802.11/dcn/22/11-22-0828-01-00bd-11bd-d4-0-comment-resolution.docx) under CID 5082. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5083 | An, Song-Haur | Yes | 5.2.3.2 | 24 | 28 | E | 5.2.3.2 | 24.28 | The sentence "If the PPDU has value 2…." seems in wrong place. | Move it to the previous paragraph on the data rate/NGV-MCS member. |  |  |  | Resolution approved | Liwen Chu | 22/0828r1 | V | REVISED [05/31/2022, EDITOR] TGbd editor: Move the sentence to the end of the previous paragraph (L23P24). (https://mentor.ieee.org/802.11/dcn/22/11-22-0828-01-00bd-11bd-d4-0-comment-resolution.docx) under CID 5083. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5084 | Rolfe, Benjamin | Yes | 31.2.5 | 65 | 8 | E | 31.2.5 | 65.08 | "shall be set to any channel width that the CCA on secondary 10 MHz channel has been idle for a PIFS prior to the start of the RTS frame and that is less than or equal to the channel width indicated in the RTS frame’s RXVECTOR parameter CH-BANDWIDTH_IN_NON_NGV." seems to be missing something - maybe "that the CCA on the secondary 10 MHz channel indicates has been idle" ??? | Clarify. See comment for suggested insertion of missing words. |  |  |  | Resolution approved | Joseph Levy | 22/0769r1 | V | REVISED [05/31/2022, EDITOR] Agree in principle with the commenter, the behavior is not clearly specified. Clarifying text is added. See 11-22/0769r1 for redline edits (https://mentor.ieee.org/802.11/dcn/22/11-22-0769-01-00bd-initial-sa-ballot-proposed-resolution-for-cids-5084-5088-5093.docx) under CID 5084. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5085 | Rolfe, Benjamin | Yes | 31.2.1 | 61 | 33 | T | 31.2.1 | 61.33 | It seems odd that "Rules for determining the PPDU type to be used in transmissions by NGV STAs are outside the scope of this standard" can be true for a standard that defines PHY layer and MAC sub-layer, thus when and which PPDUs are transmitted, but if that's what is meant, it raises a question of how this is controlled by the entity that is out of scope of this standard. At some point the PHY has to know what PPDU type to transmit. So this note must be wrong: the rules for determining the PPDU type to be transmitted MUST be part of this standard! I find some rules here and there for example in 31.5 I find some rules for what PPDU type is transmitted via the MAC data service parameters. What may or may not be meant is that this is controlled via the MAC service or other mechanisms exposed to the higher layer and the setting of those parameters is out of scope? But this is clearly out of scope of this standards (the scope of which is PHY layer and MAC sublayer as defined in the base standard). | Delete the note. |  |  |  | Resolution approved | Bo Sun | 22/0817r1 | V | REVISED [05/24/2022, EDITOR] Discussion: Agree on the comment that the addressed statement is not 100% in consistence with sub-clause 31.5 that “when a member in radio environment request vector represents ‘selection within MAC sublayer’ , the NGV STA shall select the related member value by itself. While there’s no valid discussion why the first sentence of the note should be deleted. So it’s preferred to keep the first sentence of the note. Instruction to TGbd Editor: Please delete “Rules for determining the PPDU type to be used in transmissions by NGV STAs are outside the scope of this standard” from the note at pg61/ln33. . (https://mentor.ieee.org/802.11/dcn/22/11-22-0817-01-00bd-crc-cr-clause-32-2.docx) under CID 5085. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5086 | Rolfe, Benjamin | Yes | 11.18 | 50 | 46 | E | 11.18 | 50.46 | "In addition, " is not needed (and begs the question "in addition to what?") | Delete extraneous text. |  |  |  | Resolution approved | Hiroyuki Motozuka | 22/0764r3 | V | REVISED [05/24/2022, EDITOR] Discussion: The intent of “In addition,” was to clarify all the subtypes a DMG STA shall not send. Clearer expression is proposed below: Proposed change: TGbd Editor: Please remove “In addition,” as suggested by the commenter. Then Insert “in addition to not sending Control frames of subtype PS-Poll and CF-End,” after “If the STA… is true,”. (https://mentor.ieee.org/802.11/dcn/22/11-22-0764-03-00bd-tgbd-d4-0-cr-related-to-dmg-sta-communicating-ocb.docx) under CID 5086. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5087 | Rolfe, Benjamin | Yes | 11.1.4.7 | 48 | 2 | T | 11.1.4.7 | 48.02 | Regarding: "When the STA receives one or more DMG Beacon frames with the OCB subfield equal to 1 from a peer STA, and the address of the peer STA is an address that is newly discovered, the STA shall perform an SLS with the OCB subfield set to 1 in transmitted SSW frames during the A-BFT following the DMG Beacon frames if present, or during the DTI. " it is not clear how the "or" applies. The comma list implies "and" (and implied is not always good) so is the frame "during the DTI" applied if ANY of the and conditions fail or does it mean that "during the DTI" applies if DMG beacon frames are not present (which makes more sense to me). It would be clearer if broken up into two or more sentences. | Clarify the requirement so that a common implementation is more likely. |  |  |  | Resolution approved | Hiroyuki Motozuka | 22/0764r3 | V | REVISED [05/24/2022, EDITOR] Discussion: The intent of the description is that the STA shall perform an SLS during the A-BFT or DTI. Since the STA is allowed to perform an SLS during the DTI even if A-BFT is present, “if present” should be removed. Additionally, there’s a typo in the 5th paragraph of the same subclause (DMGDISCOVER”E”Y) Proposed change: TGbd Editor: Please change “during the A-BFT following the DMG Beacon frames, if present, or during the DTI” to “during the A-BFT following the DMG Beacon frames or the DTI” in the 4th paragraph of 11.1.4.7, and replace “DMGDISCOVEREY” with “DMGDISCOVERY” in the 5th paragraph. (https://mentor.ieee.org/802.11/dcn/22/11-22-0764-03-00bd-tgbd-d4-0-cr-related-to-dmg-sta-communicating-ocb.docx) under CID 5087. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5088 | Rolfe, Benjamin | Yes | 6.3.129.3.2 | 31 | 22 | T | 6.3.129.3.2 | 31.22 | The description contains a requirement for a different parameter. The requirement "When StationCount is equal to 0, the NGVCapabilityPercentage shall be set to 0." belongs in the defintion of NGVCapabilityPercentage, the value of which apparently depends upon the value of station count. | Move to the description of NGVCapabilityPercentage. |  |  |  | Resolution approved | Joseph Levy | 22/0769r1 | A | ACCEPTED [05/31/2022, EDITOR] Note to Editor: Redline markup provided in 11-22/0769r1 (https://mentor.ieee.org/802.11/dcn/22/11-22-0769-01-00bd-initial-sa-ballot-proposed-resolution-for-cids-5084-5088-5093.docx) under CID 5088. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5089 | Rolfe, Benjamin | Yes | 4.3.17a | 20 | 30 | T | 4.3.17a | 20.30 | In IEEE Std 802.11-2020 clause 4 does not contain any statement of requirements ("shalls") as it is described as a general (informative) overview of the operations defined in the standard. These two "shalls" are likely to be overlooked and belong in an appropriate normative clause. While there is no rule that says clause 4 can not contain requirements, the convention of the standard being amended should be followed. | Remove the statement(s) of requirements from Clause 4. |  |  |  | Resolution approved | John Kenney | 22/0827r5 | V | REVISED [06/14/2022, EDITOR] Agree with commenter that “shall support” is not appropriate for this clause. Revised to “supports”. Note to editor: CID 5043 has a resolution of “Replace ‘shall support’ with ‘supports’” (https://mentor.ieee.org/802.11/dcn/22/11-22-0827-05-00bd-resolutions-to-clause-4-3-17-and-4-3-17a-cids.docx) under CID 5089. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:19
5090 | Rolfe, Benjamin | Yes | 4.3.17a | 19 | 35 | T | 4.3.17a | 19.35 | In IEEE Std 802.11-2020 clause 4 does not contain any statement of requirements ("shalls") as it is described as a general (informative) overview of the operations defined in the standard. These two "shalls" are likely to be overlooked and belong in an appropriate normative clause. While there is no rule that says clause 4 can not contain requirements, the convention of the standard being amended should be followed. | Remove these statements of requirements from Clause 4. |  |  |  | Resolution approved | John Kenney | 22/0827r5 | V | REVISED [06/14/2022, EDITOR] Agree with commenter that “shall set” is not appropriate for this clause (two places: P19.L35 and P19.L36) See document 11-22/0827r1 (https://mentor.ieee.org/802.11/dcn/22/11-22-0827-05-00bd-resolutions-to-clause-4-3-17-and-4-3-17a-cids.docx) for redline edits to the two sentences. Note to editor: CID 5044 addresses the same content. (https://mentor.ieee.org/802.11/dcn/22/11-22-0827-05-00bd-resolutions-to-clause-4-3-17-and-4-3-17a-cids.docx) under CID 5090. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:19
5091 | Rolfe, Benjamin | Yes | 3 | 17 | 64 | T | 3 | 17.64 | The second sentence "The OCB secondary channel is adjacent to the OCB primary channel and together with the OCB primary channel form a 20 MHz channel for the transmission of 20 MHz next generation vehicle-to-everything (V2X) (NGV) physical layer (PHY) protocol data units (PPDUs)" is stating a required characteristic of the thing do which the term refers and not appropriate in clause 3 definition of terms. This belongs in an appropriate normative clause. | Delete the requirement statement or explanatory text from the definition in clause 3. |  |  |  | Resolution approved | Joseph Levy | 22/0768r1 | V | REVISED [05/31/2022, EDITOR] Agree with the Commenter that requirements should not be in the definition clause. However, the commented text is descriptive and not a requirement. The requirement that the OCB primary and secondary channels are contiguous is in clause 31.2.2. It is preferred to state in the definition that the contiguous primary and secondary channels form the channel for 20 MHz NGV PPDUs. During the review of these definitions, it was noted that the definition of the OCB secondary channel should be aligned with the OCB primary definition. See 11-22/0768r1 for redline edits. Note to Editor: there are also some editorial changes. (https://mentor.ieee.org/802.11/dcn/22/11-22-0768-01-00bd-initial-sa-ballot-proposed-resolution-for-cids-5091-5092.docx) under CID 5091. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5092 | Rolfe, Benjamin | Yes | 3 | 17 | 56 | T | 3 | 17.56 | "The OCB primary channel and OCB secondary channel are contiguous and together form a 20 MHz channel for transmission of 20 MHz next generation vehicle-to-everything (V2X) (NGV) physical layer (PHY) protocol data units (PPDUs)." Is specifying required characteristics of the thing to which the term refers and does not belong in a clause 3 definition of terms. This should be in an appropriate normative clause. | Remove the second sentence "The OCB primary channel and OCB secondary channel are contiguous and together form a 20 MHz channel for transmission of 20 MHz next generation vehicle- to-everything (V2X) (NGV) physical layer (PHY) protocol data units (PPDUs)." |  |  |  | Resolution approved | Joseph Levy | 22/0768r1 | J | REJECTED [05/31/2022, EDITOR] Agree with the Commenter that requirements should not be in the definition clause. However, the commented text is descriptive and not a requirement. The requirement that the OCB primary and secondary channels are contiguous is in clause 31.2.2. Note to Editor: there is a minor editorial change, see 11-22/0768r1 for redline edits. (https://mentor.ieee.org/802.11/dcn/22/11-22-0768-01-00bd-initial-sa-ballot-proposed-resolution-for-cids-5091-5092.docx) under CID 5092. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5093 | Motozuka, Hiroyuki | No | B.4.38.3 | 133 | 20 | T | B.4.38.3 | 133.20 | 6.3.129 should be added as references for NGVE1.1. | As in the comment |  |  |  | Resolution approved | Joseph Levy | 22/0769r1 | V | REVISED [05/31/2022, EDITOR] Agree in principle with commenter. See 11-22/0769r1 for redline edits. Note to Editor: Additional editorial clean up also provided (https://mentor.ieee.org/802.11/dcn/22/11-22-0769-01-00bd-initial-sa-ballot-proposed-resolution-for-cids-5084-5088-5093.docx) under CID 5093. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5094 | Motozuka, Hiroyuki | No | B.4.38.3 | 133 | 20 | E | B.4.38.3 | 133.20 | Some error in the reference for NGVE1.1 (unnecessary text "(The SME is notified ... MAC entity.)") | Please fix the cross reference. |  |  |  | Resolution approved | Editor | 22/0743r1 | V | REVISED [05/13/2022, EDITOR] To TGbd editor Delete "The SME is notified ... MAC entity.”, and add the proper cross-reference “6.3.129 (NGV radio environment measurement)” (https://mentor.ieee.org/802.11/dcn/22/11-22-0743-01-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 5094. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5095 | Motozuka, Hiroyuki | No | 31.1 | 61 | 15 | E | 31.1 | 61.15 | Please add comma after "If ... is true" | As in the comment |  |  |  | Resolution approved | Editor | 22/0744r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0744-01-00bd-resolutions-to-editorial-comments-part-2.docx) under CID 5095 |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5096 | Motozuka, Hiroyuki | No | 10.3.6 | 43 | 46 | E | 10.3.6 | 43.46 | "a beam link is not maintained" - "a beamformed link" should be consistent to description in 11.27.1.1. | Change to "a beamformed link is not maintained" |  |  |  | Resolution approved | Editor | 22/0743r1 | V | REVISED [05/13/2022, EDITOR] Agreed in principle. Additional editorial fix is required. To TGbd editor Change to "a beamformed link is not maintained" Add space between “maintained” and “If” (https://mentor.ieee.org/802.11/dcn/22/11-22-0743-01-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 5096. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5097 | Motozuka, Hiroyuki | No | 9.4.2 | 39 | 57 | E | 9.4.2 | 39.57 | Instruction for 9.4.2.298 is incorrect. Subclause 9.4.2.298 (Ranging Parameters element) exists in 11az already, while 9.4.2.308 (DMG OCB element) is new. | Remove the instruction "Insert the following after the last subclause of 9.4.2:" for 9.4.2.298, and insert it before 9.4.2.308. |  |  |  | Resolution approved | Editor | 22/0743r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0743-01-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 5097. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5098 | Motozuka, Hiroyuki | No | 11.27.1.1 | 52 | 30 | T | 11.27.1.1 | 52.30 | Condition for issuing MLME-OCB-LINKSTATUS.indication primitive with BeamLinkStatus parameter set to EXPIRED is specified, but not specified for status ESTABLISHED or NOT_ESTABLISHED that are defined in 6.3.130.6.2. | Add description to 11.27.1.1 and/or 6.3.130.6.2. The primitive with ESTABLISHED is issued when a beamformed link is established, as described in 11.27.1.1 of the baseline. NOT_ESTABLISHED indicates other (likely, unexpected) case. |  |  |  | Resolution approved | Hiroyuki Motozuka | 22/0764r3 | V | REVISED [05/24/2022, EDITOR] Discussion: A STA should issue the primitive with status ESTABLISHED to inform the higher layer of availability of the link with a peer STA. This should be specified in 11.27.1.1. (Editorial) In the title of subclause 11.27.1.1, “(11ay)” is in REVme but not in baseline. It should be removed. Proposed change: Add description to 11.27.1.1 that specifies the condition where a STA is required to generate an MLME-OCB-LINKSTATUS.indication primitive with status ESTABLISHED. TGbd Editor: Please incorporate the proposed change in https://mentor.ieee.org/802.11/dcn/22/11-22-0764-03-00bd-tgbd-d4-0-cr-related-to-dmg-sta-communicating-ocb.docx under CID5098. (https://mentor.ieee.org/802.11/dcn/22/11-22-0764-03-00bd-tgbd-d4-0-cr-related-to-dmg-sta-communicating-ocb.docx) under CID 5098. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5099 | Motozuka, Hiroyuki | No | 6.3.130.6.2 | 25 | 17 | E | 6.3.130.6.2 | 25.17 | In description for BeamLinkStatus, "Indicates the status of beamformed link and the beam link maintenance timer as described in 11.27.1.1 (General(11ay))." - "status change of beam link maintenance timer" is unclear. "beamformed link" is sufficient. (CID4004 is related) | Remove "and the beam link maintenance timer" from the description. |  |  |  | Resolution approved | Hiroyuki Motozuka | 22/0764r3 | V | REVISED [05/24/2022, EDITOR] Discussion The intent of this primitive is to notify of the status of the beamformed link. Thus agree with the proposed change. Additionally, propose to change the status enumerate of “EXPIRED” to “TIMER_EXPIRED” since what to be expired is “timer,” not “beamformed link”. Note: Right location in D4.0 for this comment should be P35L17 rather than 25.17. Proposed change: TGbd Editor: Please change “EXPIRED” to “TIMER_EXPIRED” in Valid Range for BeamLinkStatus, and remove "and the beam link maintenance timer" from the description. Note: CID4004 pointed out the same problem but was rejected in [3] due to procedural reason. (https://mentor.ieee.org/802.11/dcn/22/11-22-0764-03-00bd-tgbd-d4-0-cr-related-to-dmg-sta-communicating-ocb.docx) under CID 5099. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5100 | Motozuka, Hiroyuki | No | 6.3.130.6.1 | 34 | 64 | E | 6.3.130.6.1 | 34.64 | "This primitive indicates the status change of beamformed link and beam link maintenance timer with a peer STA" - status change of beam link maintenance timer is unclear. (CID4003 is related) | Change to "This primitive indicates the status change of beamformed link with a peer STA" (i.e. remove "and beam link maintenance timer ") |  |  |  | Resolution approved | Hiroyuki Motozuka | 22/0764r3 | A | ACCEPTED [05/24/2022, EDITOR] Discussion: Agree that “status of beam link maintenance timer” is unclear. “beamformed link” is the term used in 11.27.1.1, and the modified statement “This primitive indicates the status change of beamformed link and beam link maintenance timer with a peer STA.” should be clear. Note: CID4003 pointed out the same problem but was rejected in [3] due to procedural reason. (https://mentor.ieee.org/802.11/dcn/22/11-22-0764-03-00bd-tgbd-d4-0-cr-related-to-dmg-sta-communicating-ocb.docx) under CID 5100. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5101 | Motozuka, Hiroyuki | No | 5.2.4.2 | 26 | 25 | E | 5.2.4.2 | 26.25 | "with an exception that the value 14 means the actual MCS is decided by MAC layer." "If the PPDU format has value 2, the data rate/NGV-MCS member is set to value 14 indicating that the actual data-rate/MCS is decided by the MAC layer. (#3009)" A primitive that includes this member is issued based on reception. Thus "decided by the MAC layer" is not relevant. | Remove the text indicated in the comment. |  |  |  | Resolution approved | Liwen Chu | 22/0828r1 | A | ACCEPTED [05/31/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0828-01-00bd-11bd-d4-0-comment-resolution.docx) under CID 5101. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5102 | Motozuka, Hiroyuki | No | 5.2.3.2 | 24 | 28 | E | 5.2.3.2 | 24.28 | "If the PPDU format has value 2, the data rate/NGV-MCS member is set to value 14 indicating that the actual data-rate/MCS is decided by the MAC layer. (#3009)" - This sentence should be included in the previous paragraph, since the paragraph starting 26 is talking about the number of spatial streams member. | Move the sentence as in the comment. |  |  |  | Resolution approved | Liwen Chu | 22/0828r1 | V | REVISED [05/31/2022, EDITOR] TGbd editor: Move the sentence to the end of the previous paragraph ( L23P24). (https://mentor.ieee.org/802.11/dcn/22/11-22-0828-01-00bd-11bd-d4-0-comment-resolution.docx) under CID 5102. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5103 | Motozuka, Hiroyuki | No | 5.2.3.2 | 25 | 29 | T | 5.2.3.2 | 25.29 | "with values in the range 0 to 60 representing -20 dBm / 10 MHz to 40 dBm / 10 MHz" - value 60 looks inclusive. Reserved values should be from 61 to 126. | Replace "Values from 60" to "Values from 61" |  |  |  | Resolution approved | Liwen Chu | 22/0828r1 | A | ACCEPTED [05/31/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0828-01-00bd-11bd-d4-0-comment-resolution.docx) under CID 5103. |  | Tue Jun 14 2022 |  |  |  | 2022-06-14 15:33
5104 | Motozuka, Hiroyuki | No | 5.2.3.2 | 24 | 22 | E | 5.2.3.2 | 24.22 | Please remove unnecessary space between "NGV-" and "MCS" | As in the comment |  |  |  | Resolution approved | Editor | 22/0743r1 | A | ACCEPTED [05/13/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-0743-01-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 5104. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25
5105 | Motozuka, Hiroyuki | No | 4.3.17 | 19 | 14 | E | 4.3.17 | 19.14 | "Clause" is missing before "10" and "11". Note: same comment as CID4012 (for subclause 31.1), but please apply the same for subclause 4.3.17. | As in the comment |  |  |  | Resolution approved | Editor | 22/0743r1 | V | REVISED [05/13/2022, EDITOR] Agreed in principle. Additional location should be fixed as well. TGbd Editor: Add “Clause” to 10 and 11 at P19L14 Add “Clause” to 10 and 11 at P19L14 and P61L12, P61L17 (https://mentor.ieee.org/802.11/dcn/22/11-22-0743-01-00bd-resolutions-to-editorial-comments-part-1.docx) under CID 5105. |  | Fri May 13 2022 |  |  |  | 2022-05-13 16:25