## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-22/0973r19
Venue Date: | March 2023
First Author: | Mark Hamilton (Ruckus/CommScope)
Subject: | TGbh Comment Collection 41
Full Date: | 2023-03-16
Author(s): | Name(s) | Mark Hamilton
| Company | Ruckus/CommScope
| Address | 350 W Java Dr, Sunnyvale, CA, 94089
| Phone: | +1-303-818-8472
Fax:
| email: | mark.hamilton2152@gmail.com
Abstract:
This document contains the comments received on 802.11bh during working group comment collection (CC41), and resolutions under discussion by 802.11 TGbh.

## Revision History
Revision | Date | Description
0 | 2022-05-07 | Added Initial WG Comment Collection comments (CC41). Added some "Comment Group" suggestions for similar/related comments.
1 | 2022-07-11 | Assigned all comments, reviewed quickly by the TG, a few comments added
2 | 2022-07-13 | Corrected/clarified that "STA-generated identifier" is correctly "non-AP STA generated identifier"
3 | 2022-07-13 | Added submission references received to-date. Marked CIDs 27 and 30 as "Editorial-reclassify" as the Editor has determined that these comments are beyond Editorial scope.
4 | 2022-07-27 | Reassigned some ID verification coments to Kurt Lumbatis
5 | 2022-08-02 | Updates per today's teleconference. CIDs ready for motion:
6 | 2022-08-02 | After off-line review, modified CID 55 to return to review by the TG, to confirm making the change in two locations. Also, modified CID 13 to indicate that we are still awaiting confirmation from the commenter that this is withdrawn.
7 | 2022-08-09 | Confirmed withdrawl of CID 13.
8 | 2022-08-16 | Updated CID 55 to Ready for motion, per Aug 2 discussion.
9 | 2022-09-05 | Updated CIDs 1, 3, 13, 14, 55, 59, 60 as Resolved. Updated CIDs 21, 22, 23, 34, 54 as Ready for motion.
10 | 2022-09-15 | Resolutions agreed for CIDs 50, 51, and 52; ready for motion.
11 | 2022-09-27 | Updated CIDs 21, 22, 23, 34, 54, 51 and 52 as Resolved.
12 | 2022-10-11 | Color-coded the "controversial" topics CIDs. Updated assignments per Oct 11 call.
13 | 2022-11-07 | Added Comment Group for all the "Device ID" term and/or use of "opaque identifier" terminology CIDs.
14 | 2023-02-25 | Added Notes for CIDs covered by 11-23/83r5 and 11-22/1329r15, per straw poll on Feb 21. These are ready for motion.
15 | 2023-03-12 | Prepared motion-ready resolutions for CIDs in 11-23/85r5, 11-22/1329r15 and 11-22/1599r3. Note that CID 63 says it is not a complete resolution - needs to be checked/clarified/completed.
16 | 2023-03-13 | More prepared motion-ready resolutions for CIDs effectively covered by (but not explicitly listed in) 11-23/83, 11-22/1329 and 11-22/1599. All CIDs have NOTEs column to indicate next steps/what's left.
17 | 2023-03-14 | Updated/corrected rev level on documents incorporated in "Ready for motion" CIDs resolutions
18 | 2023-03-15 | Added resolution to CIDs 16, 62.
19 | 2023-03-16 | Added resolution to CIDs 5. Added draft text to resolve the open CIDs.

## Comments
CID | Commenter | Comment | Category | Page Number | Subclause | Line Number | Proposed Change | Assignee | Comment Group | Status | Submission | Resn Type | Resolution Text | Notes | Motion Number
1 | Jay Yang | The ID Blob field contains an opaque identifier from an AP in the ESS. need to consider the single AP case. | Technical | 24 | 9.4.2.296a | 38 | The ID Blob field contains an opaque identifier from the assocaited AP in the BSS or an AP in ESS. | Jay Yang |  | Resolved | 11-22/1082 | Revised | Delete "from an AP in the ESS" |  | 9
2 | Jay Yang | please clarify what's the meaning of "opt-in" | Technical | 26 | 12.2.11 | 9 | as the comments. | Sid Thakur/Kurt Lumbatis | Opt-in | Ready for motion | 11-22/1329r15 | Revised | Resolve by removing opt-in and replacing with text in 12.2.11 describing actions taken by the non-ap STA indicating Device ID activated per submission 11-22-1599r3 TGbh Editor: Incorporate the Text changes in 11-22-1599r3 and 11-22-1329r17 | Agreed 21 Feb, 2023 Straw Poll
3 | Jay Yang | "When using FILS authentication, the non-AP STA sends the identifier", need to clarify the identifier here, like the latest one received from BSS or ESS. | Technical | 19 | 12.2.11 | 19 | as the comments | Jay Yang/Kurt Lumbatis |  | Ready for motion | 11-22/1329r15 | Revised | Text changes provided to the editor with the breakout of FILS and non-FILS sections in the provided text for both non-AP STA and AP. TGbh Editor: Incorporate the text changes in 11-22-1329r17. Note, this incorporates this changes shown in 11-22/1082r4 under "Proposed text", which also break the text into four paragaphs (the new first sentence/paragraph, FILS, FT, and "other cases"). | Double-check that the CID 1, 14 and 60 resolutions are consistent with this new text. | 9
4 | Jay Yang | "AP sends a new identifier", before AP send a new one, AP shall verify the old one, need to add verification sucessful and failure case. | Technical | 26 | 12.2.11 | 21 | as the comments | Kurt Lumbatis | ID verification | Ready for motion | 11-22/83r5, 11-22/1329r15 | Revised | Resolve by edits to the baseline text describing the process utilized by the AP when it has received a Device ID from a non-AP STA. TGbh Editor: Incorporate the text changes in 11-22-1329r17 | Agreed 21 Feb, 2023 Straw Poll
5 | Jay Yang | "the AP sends a new identifier in the EAPOL-Key message 3/4." Need to define MIB to save and obtain the identifier locally on both side | Technical | 26 | 12.7.1 | 28 | as the comments. | Mark Hamilton | MIB |  | 11-23/0461 | Revised | Incorporate the changes indicated in 11-230461r2. | Mark H to simplify: setting/storing Device ID on AP is beyond 802.11 scope/implementaiton-dependent, on non-AP STA, only need to store one (the current) Device ID.
6 | Jay Yang | the device ID verification proceudre is missing, need to add this part | Technical | 26 | 12.2.11 | 6 | as the comments. | Kurt Lumbatis | ID verification | Ready for motion | 11-22/1329r15 | Revised | Text changes provided with the addition of added text which states recognized and non-recognized Identifier use cases. TGbh Editor: Incorporate the text changes in 11-22-1329r17 | Agreed 21 Feb, 2023 Straw Poll
7 | Jay Yang | Device ID only can be used in post association, we need to a solution to cover the probling case. | Technical | 26 | 12.2.11 | 6 | the commenter will provide a solution. | Jay Yang | Pre/un-assoc |  | 11-22/1079 |  |  | Way forward?
8 | Jay Yang | need to define a reason code in the assocation response frame to cover the verification failure case | Technical | 23 | 9.3.3.6 | 23 | as the comments. | Kurt Lumbatis | ID verification | Ready for motion | 11-22/1218 | Revised. | Incorporate the changes in 11-22-0083r7, which define an Identifier Status response.
9 | Jay Yang | an AP may not grant a identifier to some STAs once it's regoconzed via the MAC address. RMA causes such implement broken, need to provide a solution to address it. | Technical | 26 | 12.2.11 | 6 | the commenter will provide a solution on it. | Jay Yang |  |  | 11-22/1079 |  |  | Way forward?
10 | Jay Yang | "if it has one and opts-in to using it" how to prevent the STA using a very old device ID if it has a new one already. | Technical | 26 | 12.2.11 | 19 | as the comments | Kurt Lumbatis/Mark Hamilton | ID verification/MIB | Ready for motion | 11-22/1329r15 | Revised | Resolved with changes to the baseline text defining what Device ID active means, (11-22-1599r3) as well as a may statement for the non-ap STA to provide the Identifier to the AP. TGbh Editor: Incorporate the text changes in 11-22-1329r17 | Agreed 21 Feb, 2023 Straw Poll
11 | Jay Yang | the device ID doesn't need to be updated in each assocation as it's exchanged in protected frame, it's very safe. | Technical | 26 | 12.2.11 | 23 | change to "and the AP may sends a new identifier in the EAPOL-Key message 3/4". also, add some sentece to say"if the identifier is not updated in the association, the STA will use the old one." | Kurt Lumbatis | Quick review | Ready for motion | 11-22/1329r15 | Revised | Additional text added to where the Identifier is passed for the differing use cases and in which frames. There is no stipulation that an AP send a new Identifier per association. An AP sends an Identifier if it has activated Device ID per the following: 1) When using FILS authentication in the Device ID element in the (Re)Association Response frame. 2) When not using FILS authentication, in the Device ID KDE in message 3 of the 4 way handshake. TGbh Editor: Incorporate the text changes in 11-22-1329r17 | Agreed 21 Feb, 2023 Straw Poll
12 | Antonio DeLaOlivaDelgado | Device ID is already defined (something very similar in terms of naming) in IEEE 802.1AR (Secure Device Identity) I suggest changing the name to avoid confusion. I am only showing one instance but of course the change should be across the whole doc. | General | 22 | 6.3.7.5.2 | 20 | Select a different name for the Device ID | Antonio DeLaOlivaDelgado | Device ID term/opaque | Ready for motion |  | Rejected | The commenter has withdrawn the comment.
13 | Antonio DeLaOlivaDelgado | The inclusion of Device ID in the Association Request and Response indicates it is only used for FILS. In clause 12.2.11 it indicates it is also used in FT and in other cases. This is a contradiction. | Technical | 23 | 9.3.3.5 | 17 | It applies to clauses 9.3.3.5 and 9.3.3.6, I think the Device ID element should not be constrained to FILS. |  |  | Resolved |  | Rejected | To be withdrawn by commenter |  | 9
14 | Antonio DeLaOlivaDelgado | Text is saying the ID Blob field is an opaque identifier from an AP in the ESS. In case the Device ID is sent from an STA, it should not say it is from an AP. | Technical | 24 | 9.4.2.296a | 38 | Just remove "from an AP in the ESS" | Jay Yang | non-AP STA-generated | Resolved | 11-22/1082 | Accepted |  |  | 9
15 | Antonio DeLaOlivaDelgado | There should be normative text explaining what to do with the Device ID and most importantly what to do if the Device ID does not match a previous registration | Technical | 31 | 11 | 1 | Add a subclause in clause 11 explaining how to use the DEvice ID and what to do when it does not match a previously assigned one | Kurt Lumbatis | ID verification | Ready for motion | 11-22/1218 | Revised. | Incorporate the changes in 11-23-0083r7 and 11-22-1329r17, which add behavior explanation.
16 | Graham Smith | Device ID is presumably allocated by a higher level app. Hence I think we need to have an MLME-SAP primitive that provides the ID for the AP to send to the non-AP STA, and then receives the ID when the non-AP STA sends it to the AP. | Technical | 18 | 6.3 |  | Add new MLME-DEVICEID primitives. Note, ARC and 11me is working on simplifying this section. I suspect requirement is an MLME-DEVICEIDALLOCATE.request and an MLME-DEVICEID.indication (a type 2a and a type 6) | Graham Smith/Mark Hamilton | MLME/MIB |  |  | Revised | Incorporate the changes in 11-23/0459r1, which adds parameters to existing MLME primitives, resolving the concern. | Jay Yang volunteered to work on this. For FILS case, we need an extension to the existing FILS MLME primitives. For the non-FILS case, this is covered by the MIB updates in 1329 and 83, and per CID 5.
17 | Graham Smith | Also in the MLME SAP area, need an MLME-RCM primitive to tell the STA to support Device ID | Technical | 18 | 6.3 |  | Add new MLME-RCM.request primitive (Type 2a). | Mark Hamilton | MIB | Ready for motion |  | Revised. | Incorporate the changes in 11-23/0083r7 And 11-22/1329r17 which add control over STA support/operation of Device ID
18 | Graham Smith | Have to admit I find "Device ID" boring. Needs an acronym, I rather like NGID (network generated ID) | Editorial |  |  |  | Change the "device ID" to "NGID".
19 | Jonathan Segev | It is not clear how the Device ID mechanism supports unassociated PASN operation. the PASN operation is required to support management procedure that do not require data transfer, examples are FTM and 11ba. | Technical | 26 | 12.2.11 | 19 | Add support for Device ID in PASN. | Okan Mutgan | Pre/un-assoc |  | 11-22/1732 |  |  | Okan/Jonathon to do. 11-22/1732r1, 11-22/1806r0. More work to update some details, and choose a specific mechanism. |  | TGbh discussed options for such a mechanism, during the Atlanta face-to-face meetings, and could not come to consensus on a specific proposal that provided such a solution. Points of debate remain on whether to use, for example, PASN messages 2 and/or 3 and whether to add an encryption mechanism to these PASN messages and/or use Annex Z-style opaque identifier.
20 | Jonathan Segev | The mechanism for device ID should be such that to a single network a device with an on going unassociated session should be identifiable as single device to the network (ESS). an example of such operation is the need to two way report for FTM; The client STA reports measurement conducted to each individual AP while the multiple outstanding FTM sessions are in progress, the NW is able to associate the measurement from multiple sessions to be attributed to a single client and thus can identify client location. This client may not be associated to the network. | Technical | 26 | 12.2.11 | 6 | Add a functionality that allows a device to be identified to the ESS as a single entity. | Okan Mutgan | Pre/un-assoc |  | 11-22/1732 |  |  | Okan/Jonathon to do. 11-22/1732r1, 11-22/1806r0. More work to update some details, and choose a specific mechanism.
21 | Okan Mutgan | What is the meaning of "foil traffic analysis" in the context of the sentence? | General | 33 | Z.2 | 19 |  | Dan Harkins |  | Resolved | 11-22/1069 | Revised | Change “foil” to “mitigate”. |  | 11
22 | Okan Mutgan | "The overhead added to each frame by the scheme is 16 octets of AES-SIV tag plus length of tweak plus one octet of padding indication plus padding. For an 8 octet tweak that would be 25 octets." The overhead octets are not clear. According to text, it should be (for 8 octet tweak): 16 (Tag) + 8 (tweak) + 1 (padding indication) + K (padding) Does blob (ID) have a fixed value or variable value? It would be better to indicate the exact overhead so the vendors would take overhead into consideration when implementing. | Technical | 34 | Z.5 | 14 |  | Dan Harkins |  | Resolved | 11-22/1069 | Revised | Delete “For an 8 octet tweak that would be 25 octets.” |  | 11
23 | Okan Mutgan | "There is a single symmetric secret, k, shared by all APs in an ESS." Should we consider how to derive this key? Should we consider how to share this key with all APs in an ESS? Should we consider updating the key with all APs in an ESS? | Technical | 33 | Z.2 | 16 |  | Dan Harkins |  | Resolved | 11-22/1069 | Rejected | Specification of how this key is managed is unnecessary and out-of-scope. |  | 11
24 | Okan Mutgan | "If AES-SIV returns FAIL, the protocol using the opaque device identifier fails." The overall protocol needs a more clear mechanism when AES-SIV fails such as: - Does AP need to inform STA about the failure? - If failure, STA is recognized. How to overcome this issue? - If failure, AP assigns new ID to STA? | Technical | 33 | Z.3 | 48 |  | Dan Harkins |  | Ready for motion |  | Rejected | The commenter has withdrawn the comment.
25 | Okan Mutgan | "When the non-AP STA sends the opaque identifier, it shall send the most recently received value from an AP in the ESS without modification." This sentences uses "opaque identifier", whereas the rest of the paragraph uses "identifier". To be compatible within the paragraph, I suggest to change it to "identifier". Generally speaking, there are various definitions in the protocol such as "identifier" , "opaque identifier", "blob", "ID". All of them need to be explained clearly in the context. | General | 26 | 12.2.11 | 28 | "When the non-AP STA sends the identifier, it shall send the most recent received value from an AP in the ESS" | Antonio DeLaOlivaDelgado (/Kurt Lumbatis?) | Device ID term/opaque | Ready for motion | 11-22/1329r15 | Revised | A non-AP STA shall return the most recently received Identifier for an ESS when associating with any AP in that ESS when Device ID is active for both the non-AP STA and the AP. Awaiting final definition of what Identifier is and what terms need to be defined. TGbh Editor: Incorporate the text changes in 11-22-1329r17 | Agreed 21 Feb, 2023 Straw Poll
26 | Okan Mutgan | Generally speaking, device ID verification (fail ,success) should be considered in the protocol. | Technical | 26 | 12.2.11 | 19 |  | Kurt Lumbatis | ID verification | Ready for motion | 11-22/83r5, 11-22/1329r15 | Revised | Text changes provided with the addition of added text which states recognized and non-recognized Identifier use cases. TGbh Editor: Incorporate the text changes in 11-22-1329r17 | Agreed 21 Feb, 2023 Straw Poll
27 | Chaoming Luo | What is "opt-in"? | Editorial-reclassify | 17 | 4.5.4.10 | 18 | Give a description for "opt-in" |  | Opt-in | Ready for motion |  | Revised | Resolve by removing opt-in and replacing with text in 12.2.11 describing actions taken by the non-ap STA indicating Device ID activated per submission 11-22-1599r3 TGbh Editor: Incorporate the Text changes in 11-22-1599r3 and 11-22-1329r17
28 | Chaoming Luo | "an opaque identifier from an AP" is may misread as the id is an id of the AP | Editorial | 24 | 9.4.2.296a | 38 | change to "an opaque identifier of the non-AP assigned by an AP"
29 | Chaoming Luo | It should be "Table 9-363--Extended RSN Capabilities field" instead of "Table 9-363--Extended Capabilities field" | Editorial | 24 | 9.4.2.241 | 8 | As commented
30 | Chaoming Luo | Does this mean an AP shall indicate support for this capability? | Editorial-reclassify | 26 | 12.2.11 | 16 | Please clarify | Kurt Lumbatis |  | Ready for motion | 11-22/1329r15 | Revised | Text added defining how the non-AP STA and AP indicates support for Device ID active and in which frames this indication shall reside. TGbh Editor: Incorporate the text changes in 11-22-1329r17 | Agreed 21 Feb, 2023 Straw Poll
31 | Chaoming Luo | It's not clear how the transition (ie., has no ID -> has one ID) happens, because at the very beginning the non-AP STA does have one identifier and the ID staff described in this paragragh does not occur. | Technical | 26 | 12.2.11 | 19 | Please clarify | Sid Thakur/Kurt Lumbatis |  | Ready for motion | 11-22/1329r15 | Revised | When a non-AP STA with Device ID active associates to any AP in an ESS and does not provide an Identifier, the AP shall assign an Identifier to the non-AP STA. TGbh Editor: Incorporate the text changes in 11-22-1329r17 | Agreed 21 Feb, 2023 Straw Poll
32 | Fumihide Goto | Which is correct description for Device ID? In Section6, it says, "Specifies the Device ID for the requesting STA. Optionally present if Device ID is supported, otherwise not present." but, In section 9, it says, "The Device ID element is optionally present when using FILS authentication; otherwise, it is not present" Is it equal "Device ID is supported" and "using FILS authentication"? | Technical | 18,23 | 6.3.7.2.2 9.3.3.5 |  | Align these unmatched description. | Antonio DeLaOlivaDelgado | Device ID term/opaque | Ready for motion |  | Revised | Incorporate the changes in 11-23/0452r1. | Kurt, Goto, Antonio to do
33 | Amelia Andersdotter | At the risk of me word-smithing, maybe the discussions are better reflected by the following wording: "An AP may provide an identifier to a non-AP STA and the non-AP STA may optionally return that identifier to any AP in the same ESS..." | General | 26 | 12.2.11 | 8 | As in comment | Sid Thakur/Kurt Lumbatis | Opt-in | Ready for motion | 11-22/1329r15 | Revised | Text changes in the provided text utilizing the terms may and shall in the appropriate text. TGbh Editor: Incorporate the text changes in 11-22-1329r17 | Agreed 21 Feb, 2023 Straw Poll
34 | Amelia Andersdotter | At the end of this sentence it would make sense to have a reference to Annex Z. | General | 24 | 9.4.2.296a | 38 | Add "(see Annex Z)" before the full stop at the end of the sentence. | Dan Harkins |  | Resolved | 11-22/1069 | Accepted |  |  | 11
35 | Amelia Andersdotter | I guess I'm in general a bit confused as to whether "the identifier" is always an "opaque identifier" as in Annex Z, or whether there are different identifiers defined in subclause 12.2.11. Adding a sentence on identifiers would help, perhaps along the lines of "An opaque identifier can be constructed by the network according to the example procedure in Annex Z, but an identifier can also be differently constructed by a mechanism chosen by the network." I guess the non-AP STA would not technically need to be concerned with how the identifier is constructed. | General | 26 | 12.2.11 | 6 | As in comment. It's very general. | Dan Harkins | Device ID term/opaque |  |  |  |  | Insert a new paragraph at the end of 12.2.11, "An opaque identifier can optionally be constructed by the network using the procedure in Annex Z or can employ a different mechanism provided it affords comparable security and privacy."
36 | Julien Sevin | No privacy enhancement mechanism is specified for covering the pre-association use cases specified by the 11bh group in the document 332r37. | Technical | 16 | 1.3 | 9 | Specify a privacy enhancement mechanism for identifying a STA operating with a Random MAC Address before the association | Jay Yang | Pre/un-assoc |  | 11-22/1079 |  |  | Way forward? |  | TGbh discussed at least 8 unique proposals for such a mechanism, across almost a year of teleconferences and sessions, and could not come to consensus on a proposal that provided such a solution. (See minutes and agenda decks for recent TGbh calls/meetings for details.) Points of debate remain on whether to use a MAC address-based method or an IE-based method, how much security /privacy is required or provided by the proposals, how much computation or storage is required, and exactly which use cases are or are not addressed by each proposal.
37 | Stephen McCann | The Amendment order is 3 not 7. | Editorial | 1 |  | 38 | Change "7" to "3" and also change "X" to "3" on P14L25
38 | Stephen McCann | typo "12-481" | Editorial | 26 | 12.7.2 | 48 | Change "12-481" to "12-48a"
39 | Stephen McCann | typo "is the prepended" | Editorial | 33 | Z.2 | 27 | Change "is the prepended" to "is prepended"
40 | stephane baron | Issue tracking document contains scenario (especially 4.2 : returning device) agreed by the group and that is not addressed by the current draft. | General | 24 | 12 | 9 | Provide a mechanism that supports scenario 4.2 by providing a MAC address based mechanism that allows a returning station to be recognized. | Jay Yang | Pre/un-assoc |  | 11-22/1079 |  |  | Way forward?
41 | Patrice Nezou | The document 332r37 describes some scenarios related to the pre-association procedure. The current draft does not propose any privacy enhancement during this procedure. | Technical | 24 | 12 | 9 | Need additional mechanisms to enhance the privacy during the pre-association procedure. | Jay Yang | Pre/un-assoc |  | 11-22/1079 |  |  | Way forward?
42 | Mikael Lorgeoux | A mechanism for privacy enhancement is missing for the coverage of pre-association use cases specified in the doc 332r37. | Technical | 16 | 1.3 | 9 | Specify a privacy enhancement mechanism for covering pre-association use cases of doc 332r37. | Jay Yang | Pre/un-assoc |  | 11-22/1079 |  |  | Way forward?
43 | Kurt Lumbatis | While discovering network | Editorial | 17 | 4.5.4.10 | 15 | While discovering a network
44 | Kurt Lumbatis | Such a STA. when reconnecting to a network. | Editorial | 17 | 4.5.4.10 | 18 | Such a STA, when reconnecting to a network,
45 | Kurt Lumbatis | Opt-In --- Needs further text to show what this means and that it is outside of the standard to define the mechanism. | General | 17 | 4.5.4.10 | 18 | None at this time. Pending resolution of 802.11-22/0832. | Sid Thakur | Opt-in | Ready for motion |  | Revised. | Incorporate the changes in 11-23-0083r7 and 11-22-1329r17, which add behavior explanation.
46 | Robert Stacey | Invalid editing instruction -- see page 14 for valid options | Editorial | 17 | 4.5.4.10 | 11 | Change to "Change the last paragraph as follows:"
47 | Robert Stacey | "Opt-in" implies optional support. Say so. Also, there is no precedent for "such a STA" (previous references are indefinite -- to "a STA"). We have an established term for "connecting to a network": association. Decide whether it is "device identifier" or "identifier" and use the term consistently. | Technical | 17 | 4.5.4.10 | 18 | Change sentence to "During association, an AP optionally provides a non-AP STA with an identifier. The non-AP STA optionally uses that identifier in a future exchange (when its MAC address might have changed) with that AP or another AP in the ESS to help the AP identify the device. The identifier provided by the AP during association is protected so that a third party monitoring the association exchange cannot obtain the identifier. The identifier can be changed with each association so that its value to a third party attempting to track the device is limited." | Sid Thakur | Opt-in | Ready for motion |  | Revised. | Incorporate the changes in 11-23-0083r7 and 11-22-1329r17, which add behavior explanation.
48 | Robert Stacey | The order of the elements in is not ANA managed | Editorial | 23 | 9.3.3.5 | 18 | Choose a number that does not collide with numbers in the baseline. Same for 23.34.
49 | Robert Stacey | "Opt-in to providing" is cumbersome. "In the same ESS" -- there is no precedent for "same". | Technical | 26 | 12.2.11 | 8 | Change to "During association, an AP may provide an identifier to a non-AP STA. The non-AP STA may include that identifier in a future association exchange with any AP in the same ESS as the AP that originally provided the identifier. This allows the AP with which the non-AP STA is associating to recognize the non-AP STA from a prior association even though the MAC address might have changed." | Sid Thakur/Kurt Lumbatis | Opt-in | Ready for motion | 11-22/1329r15 | Revised | An AP may provide an Identifier to a non-AP STA to allow any AP in the ESS to recognize the non-AP STA when it returns to that ESS even if the non-AP STA changes its MAC Address. The non-AP STA may provide that Identifier to any AP in the same ESS upon a new association. Exchanges of the Identifier are protected from third parties. TGbh Editor: Incorporate the text changes in 11-22-1329r17 | Agreed 21 Feb, 2023 Straw Poll
50 | Robert Stacey | If inclusion of the identifier in an Association Request frame is restricted to FILS authentication then we need a shall statement to that effect. The "opt-in to using it" language is unnecessary -- this is adequately covered by the verb "may". It is not clear what distinguishes a "new identifier" from an "identifier". We need to be specific. | Technical | 26 | 12.2.11 | 19 | Replace 1st sentence of paragraph with "A non-AP STA may include the identifier in an Association Request frame if FILS authentication is used and shall not include the identifier an Association Request frame if FILS authentication is not used. An AP may include an identifier that has not previously been used in an Association Response frame if FILS authentication is used and shall not include include an identifier in an Association Response frame if FILS authentication is not used." | Sid Thakur(Kurt)/Jouni Malinen | Opt-in/New-old | Ready for motion | 11-22/1329r15 / 11-22/1329; 11-22/1078 | Revised / Revised | Modified text to clarify FILS, vs non-FILS passage of the Identifier and what the mechanisms are to pass the Identifier for both AP and non-AP STA. TGbh Editor: Incorporate the text changes in 11-22-1329r17 /(AND) Incorporate 11-22/1078r0 | Agreed 21 Feb, 2023 Straw Poll
51 | Robert Stacey | If inclusion of the identifier is restricted to the EAPOL Key messages for FT, then we need a shall statement to that effect. The "/4" (in "message 2/4", etc.) is confusing since it is not part of the actual message name. Use the actual frame name. | Technical | 26 | 12.2.11 | 22 | For FT association the following applies: - A non-AP STA may include the identifier in EAPOL-Key Message 2 frame of the initial mobility domain association - An AP may include an identifier that has not previously been used in the EAPOL-Key Message 3 frame - An identifier shall not be included in EPOL Key messages exchanged during FT protocol reassociations. | Jouni Malinen |  | Ready for motion | 11-22/1078 | Revised | Modified text to clarify FILS, vs non-FILS passage of the Identifier and what the mechanisms are to pass the Identifier for both AP and non-AP STA. TGbh Editor: Incorporate the text changes in 11-22-1329r17. Note, this also incorporates 11-22/1078r0 |  | 12
52 | Robert Stacey | "For other cases" might not be clear enough; better to enumerate. The "/4" (in "message 2/4", etc.) is confusing since it is not part of the actual message name. Use the actual frame name. | Technical | 26 | 12.2.11 | 25 | Change to "If neither FILS authentication nor FT association are used, then the following apply: - The non-AP STA may include an identifier in the EPOL Key Message 2 frame of the initial 4-way handshake. - An AP may include an identifier that has not previously been used in the EPOL Key Message 3 frame of the initial 4-way handshake. " | Jouni Malinen |  | Ready for motion | 11-22/1078 | Revised | Modified text to clarify FILS, vs non-FILS passage of the Identifier and what the mechanisms are to pass the Identifier for both AP and non-AP STA. TGbh Editor: Incorporate the text changes in 11-22-1329r17. Note, this also incorporates 11-22/1078r0 |  | 12
53 | Robert Stacey | "opaque identifier" is not defined and it is not clear how it differs from an "identifier'. Similarly, what distinguishes a "new identifier" from an "identifier" | Technical | 26 | 12.2.11 | 28 | Either substitute "opaque identifier" with something meaningful or define the term. Replace "new identifier" with "identifier that has not previously been used" (or similar) | Dan Harkins/Jouni Malinen/Kurt Lumbatis? | Device ID term/opaque | Ready for motion | 11-22/1329r15 | Revised | Removed text and replaced all with Identifier. TGbh Editor: Incorporate the text changes in 11-22-1329r17 | Agreed 21 Feb, 2023 Straw Poll
54 | Robert Stacey | "Without modification" is unnecessary; if it is modified then it is not the identifier. The identifier is the value. | Technical | 26 | 12.2.11 | 30 | Delete "without modification" | Dan Harkins |  | Resolved | 11-22/1069 | Revised | Make the same change as indicated in CID3 in document 11-22/1082r4. |  | 11
55 | Robert Stacey | "for this capability" is vague | Technical | 26 | 12.2.11 | 15 | "A non-AP STA indicates support for device ID indication in the Device ID Support subfield in the ..." | Mark Hamilton |  | Resolved |  | Revised | Replace "for this capability" with "for the Device ID capability" at P26.15 and P26.17. | Note this occurs twice. Note that another comment may change "Device ID" to a different name for the feature, and that change applies to this new text as well. | 9
56 | Robert Stacey | The item numbers in the table are not ANA managed. | Editorial | 32 | B4.4.1 | 25 | Choose yourself
57 | Robert Stacey | Clause, Figure, Table, Annex number are purely editorial; not ANA managed. | Editorial | 32 | Z | 44 | Choose next available.
58 | Robert Stacey | Here is it "device identifier", later (24.38) it is "opaque identifier" elsewhere is is just "identifier". | Technical | 24 | 9.4.2.296a | 24 | Decide which it is and use the term consistently | Antonio DeLaOlivaDelgado | Device ID term/opaque | Ready for motion |  | Revised. | Incorporate the changes in 11-23-0083r7 and 11-22-1329r17, which add behavior explanation.
59 | Robert Stacey | "The Element ID, Length, and Element ID Extension fields are defined in 9.4.2.1 (General)" -- they are not, but they should be. | Technical | 24 | 9.4.2.296a | 35 | Add Device ID element to the table in 9.4.2.1. Given its definition it is not extensible. | Mark Hamilton |  | Resolved |  | Rejected | The Element ID and Element ID Extension are in the Draft in 9.4.2.1, P23.56. The Length field follows the general description already in the baseline in 9.4.2.1. |  | 9
60 | Robert Stacey | The purpose and meaning of "from an AP in the ESS" is not clear and "the ESS" has no precedent (which ESS?) | Technical | 24 | 9.4.2.296a | 38 | Delete "from an AP in the ESS" | Jay Yang |  | Resolved | 11-22/1082 | Accepted |  |  | 9
61 | Mark Hamilton | With majority support for a STA-generated device ID (for example, Motion #3, although not 75% on a particular proposal, yet) and evidence that both network-generated and STA-generated can coexist (cf 11-22/0908), add a STA generated ID variant. | Technical |  |  |  | Add a STA-generated Device ID variant, and appropriate mechanism (if needed) to select an operating mode. | Jay Yang | non-AP STA-generated |  | 11-22/1079 |  |  | Way forward?
62 | Mark Hamilton | PICS updates are missing | Technical |  | B |  | Add the PICS statements | Mark Hamilton | PICS |  |  | Revised | Incorpoate the changes in 11-23/0461r0 for subclause B.4.4.1.
63 | Mark Hamilton | Clarify "and the non-AP STA may opt-in" | Technical | 26 | 12.2.11 | 9 | Replace "STA may opt-in to providing" with "STA may provide". Replace "opts-in to using it" with "chooses to use it", at P26.19, P26.22 and P26.26. At P17.17, replace "can opt-in" with "can choose". At P26.13, add a "NOTE--It is recommended that the non-AP STA device provide the end user or administrator with a mechanism to control when the device will choose an identifer, or provide no identifier, for a given network. | Sid Thakur/Kurt Lumbatis? | Opt-in | Ready for motion | 11-22/1329r15 | Revised. | Incorporate the changes in 11-23-0083r7 and 11-22-1329r17, which add behavior explanation. | Agreed 21 Feb, 2023 Straw Poll; updated during March plenary
64 | Jarkko Kneckt | The 802.11bh should define a protocol that allows STA to provide STA ID that the STA uses to identify itself to the AP in the following authentications/associations. | Technical | 27 | 12.7.6.3 | 40 | Please allow STA to have a possibility to provide to AP the STA Identifier that is used to identify the STA. | Jay Yang | non-AP STA-generated |  | 11-22/1079 |  |  | Way forward?
65 | Jarkko Kneckt | The STA Identifier should be taken into use only if the STA opts-in to use the identifier. Currently AP may just push a STA ID for the STA even if the STA does not want to have it. | Technical | 26 | 12.2.11 | 6 | Please allow the STA to have control on whether it desires to use STA identifier in the following authentications and associations. | Jay Yang | non-AP STA-generated | Ready for motion | 11-22/1329r15 | Revised | Added the following: A STA shall not send an Identifier to any STA that does not indicate Device ID is active. TGbh Editor: Incorporate the text changes in 11-22-1329r17 | Agreed 21 Feb, 2023 Straw Poll
Status = Discuss (submission is ready)
Status = Ready for motion
Status = Resolved