## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-22/1433r0
Venue Date: | Aug 2022
First Author: | Yujin Noh
Subject: | Third SA ballot - Comment Collection on D6.0
Full Date: | 2022-08-31
Author(s): | Yujin Noh
| Company: | LG Electronics
| email: | yujin.noh@lge.com
Abstract: | Second SA ballot - comments on D6.0

## Revision History
Revision | Date | Description
0 | 2022-08-31 | Initial export from DB.
1 | 2022-09-02 | Initial comment assignment completed
2 | 2022-09-15 | all comments are resolved and ready for motion

## All Comments
CID | Commenter | Must Be Satisfied | Clause Number(C) | Page(C) | Line(C) | Category | Clause | Page | Comment | Proposed Change | Ad-hoc | Comment Group | Ad-hoc Notes | Status | Assignee | Submission | Resn Status | Resolution | Ready For Motion | Motion Number | Edit Status | Edited in Draft | Edit Notes | Last Updated | Last Updated By
7000 | Sand, Stephan | No | B.4.37 | 130 | 59 | T | B.4.37 | 130.59 | In 11az D6.0 "Next Generation Positioning" has been changed to "Enhanced Positioning" and "NGP" to "EP". Please update all references in 11bd D6.0 accoringly. Note this comment might be out of scope as it addresses an issue with 11az D6.0, but 11bd D6.0 is still based on 11az D4.0. | As in comment |  |  |  | Ready for motion | Editor | 22/1458r2 | V | REVISED [09/15/2022, EDITOR] To TGbd Editor: “Next Generation Positioning” is updated to “Enhanced Positioning” at P130L59 “NGP” is updated to “EP” at P130L62. “NGPM4.1” is updated to “EPM4.1” at P130L65 and P131L6. Option 2) Rejected. This comment will be passed to the IEEE-SA editor for consideration during publication editing. (https://mentor.ieee.org/802.11/dcn/22/11-22-1458-02-00bd-resolutions-to-editorial-comments-in-sa3.docx) under CID7000. | Yes |  |  |  |  | 2022-09-14 06:58
7001 | Sand, Stephan | No | 9.4.2.298 | 39 | 46 | T | 9.4.2.298 | 39.46 | While 11bd defines values for the "Format and Bandwidth subfield" of the "Ranging Parameter element", it does not define corresponding values for the "Format and Banwidth subfield" in Table 9-280. Please add two values 44 and 45 for NGV and 10 or 20 MHz channel bandwidth. | As in comment |  |  |  | Ready for motion | Stephan Sand | 22/1569r0 | J | REJECTED [09/15/2022, EDITOR] 11az D4.0 specifies in Subclauses 11.21.6.3.1 (P126L27) and 11.21.6.3.3 (P130L36) that - “This IFTM frame shall include either a (#2133) Fine Timing Measurement Parameters element or a Ranging Parameters element.” - “For TB and non-TB ranging measurement exchange the IFTM frame shall include a Ranging Parameters element containing either the Non-TB Specific subelement or the TB Specific subelement.” As 11bd only supports non-TB ranging in the 5.9 GHz band, there is no need to specify the "Format and Bandwidth subfield" in Table 9-280 for enhanced distributed channel access (EDCA) based ranging. (https://mentor.ieee.org/802.11/dcn/22/11-22-1569-00-00bd-3rd-sa-ballot-cr-11bd-d6-0-ngv-ranging.docx) under CID 7001 | Yes |  |  |  |  | 2022-09-14 06:54
7002 | Sand, Stephan | No | 0 | 1 | 7 | G | 0 | 1.07 | 11bd D6.0 is currently based on 11az D4.0. However, 11az is curently on D6.0 and D5.0 has been available for some months. Please update 11bd so that it refers to the latest version of 11az D6.0 | As in comment |  |  |  | Ready for motion | Editor | 22/1458r2 | A | ACCEPTED [09/15/2022, EDITOR] (https://mentor.ieee.org/802.11/dcn/22/11-22-1458-02-00bd-resolutions-to-editorial-comments-in-sa3.docx) under CID7002. | Yes |  |  |  |  | 2022-09-14 06:58
7003 | An, Song-Haur | No | 31.5 | 68 | 23 | E | 31.5 | 68.23 | The capabilities of a transmit STA should be compatible to those of the addressed STA (i.e., the receiving STA) | Add "common between the transmit and the receive STA" to the end of the sentence. |  |  |  | Ready for motion | Editor | 22/1458r2 | J | REJECTED [09/15/2022, EDITOR] Higher layer aspects are out of the scope of this standard. Due to the vehicular environment, we may not know which NGV STAs are around to receive packets. Therefore, most packets will be broadcast. The higher layer may learn through a local dynamic map (LDM), which stations are around and obtain their capabilities and decide to which other stations it may communicate or not. So there is the possibility that it may communicate to a subgroup but not to all NGV STAs in its vicinity. This change may exclude this possibility as not all NGV STAs may have the same capabilities. (https://mentor.ieee.org/802.11/dcn/22/11-22-1458-02-00bd-resolutions-to-editorial-comments-in-sa3.docx) under CID7003. | Yes |  |  |  |  | 2022-09-14 06:59