## Cover
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-22/1929r0
Venue Date: | November 2022
First Author: | Claudio da Silva
Subject: | Comment resolution status per comment group
Full Date: | 11/08/2022
Author(s): | Claudio da Silva
| Company: | Meta Platforms
Address
Phone:
Fax:
email:
Abstract: | This document contains SPs ("ready for motion") and motions made towards the resolution of CC40 comments.

## Nov. 8th
| Submitted | Ready for Motion | Approved | RfM+A
Editorial | 239 | 2 | 233 | 235 | 2 ANA comments, will close them after D1.0 motion passes Osama will handle last 2 CIDS (Annexes) @ Nov. meeting
CSI | 2 | 0 | 0 | 0 | Both CIDs have been closed by other resolutions
DMG11 | 52 | 1 | 31 | 32 | Progress expected @ Nov. meeting, but only expected to close all/most in Jan. Some topics entered in the priority list
DMG9 | 73 | 0 | 67 | 67 | Most/all CIDs expected to be closed in Nov.
Frames | 11 | 3 | 4 | 7 | Most CIDs expected to be closed in Nov. One CID may take longer.
Instance | 147 | 15 | 41 | 56 | Progress being made, expect number CIDs to close @ Nov. meeting Number of CIDs depend on NDP format.
MLME | 47 | 1 | 26 | 27 | Most/all CIDs expected to be closed in Nov.
NDP | 10 | 0 | 0 | 0 | Group has converged on NDP format. PDT writing may take longer than Nov. meeting
NDPA | 6 | 0 | 0 | 0 | Initial contribution expected to close @ Nov. meeting (Junghoon). Rajat will close CIDs after convergence/Nov. meeting.
R2R | 13 | 0 | 0 | 0 | Initial technical contribution expected in Nov. (Dong). PDT may require more time.
SBP | 74 | 14 | 26 | 40 | Progress expected in Nov; likely close most/all if agenda permits.
Setup | 171 | 59 | 63 | 122 | Progress expected in Nov; but extra time (Jan) may be needed.
Termination | 26 | 5 | 21 | 26
Threshold | 25 | 5 | 9 | 14 | Most CIDs already on motion queue, only 2 left. Resolution expected at/immediately after Nov.
Trigger | 16 | 14 | 1 | 15 | Only 1 CID left. Resolution expected at/immediately after Nov.