## Cover Page
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-22/1971r4
First Author: | Edward Au (Huawei Technologies)
Subject: | REVme EDITOR2 ad-hoc comments on Working Group letter ballots
Full Date: | 2022-12-16
Author(s): | Name(s) | Edward Au
| Company | Huawei Technologies
| Address | 400-303 Terry Fox Drive, Ottawa, Ontario, Canada, K2K 3J1
Phone:
Fax:
| email: | edward.ks.au@gmail.com
Abstract:
This document contains comments in the "ED2" group, submitted on P802.11REVme recirculation Working Group letter ballot on D2.0.

## Revision History
Revision | Date | Description
0 | 2022-11-13 | 102 comments assigned to ED2 ad-hoc from the recirculation Working Group Letter Ballot on D2.0
1 | 2022-11-16 | 13 comments are ready for motion. For details, please refer to "Motion ED2-270-01".
2 | 2022-12-04 | 35 comments are ready for motion. For details, please refer to "Motion ED2-270-02" and "Motion ED2-270-03".
3 | 2022-12-07 | 18 additional comments are ready for motion. For details, please refer to "Motion ED2-270-04".
4 | 2022-12-16 | 2 comments are ready for motion. For details, please refer to "Motion ED2-270-05".

## Motion ED2-270-05
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3111 | Joseph Levy | 270 | 2 |  | 3043 | 48 | E | N | 3043 | 48 |  |  | V | Mark Rison |  |  | Key Replay Counter "field" is missing its noun in multiple locations. | Replace: "Verify that the Key Replay Counter has not yet been seen before, ..." with: "Verify that the Key Replay Counter field value has not yet been seen before, ..." Also the following similar changes should be made: At 3044.15 Replace "The Key Replay Counter shall ..." with "The Key Replay Counter field shall ..." At 3044.44 Replace "Verify that the Key Replay Counter field value matches ..." with "Verify that the Key Replay Counter value matches ..." 3044.48 Replace "...new Mesh Group Key Inform frame with a new Key Replay Counter value." with "... new Mesh Group Key Inform frame with a new Key Replay Counter field value." At 3044.51 Replace ".... a new Mesh Group Key Inform frame with a new Key Replay Counter value." with ".... a new Mesh Group Key Inform frame with a new Key Replay Counter field value." | Original text at 3043.48 in D2.0: Change “the Key Replay Counter” with “the Key Replay Counter field”. Original text at 3044.15 in D2.0: Change “The Key Replay Counter” with “The Key Replay Counter field”. Original text at 3044.44 in D2.0: Change “the Key Replay Counter value” with “the Key Replay Counter field”. Original text at 3044.48 in D2.0: Change “a new Key Replay Counter value” with “a new Key Replay Counter field”. Original text at 3044.51 in D2.0: Change “a new Key Replay Counter value” with “a new Key Replay Counter field”. | ED2 | Motion ED2-270-05 | Ready for Motion | ED2: 2022-12-16 19:28:17Z - status set to: Ready for Motion ED2: 2022-12-16 19:19:49Z - status set to: More Work Required ED2: 2022-12-07 16:50:18Z - status set to: Ready for Motion ED2: 2022-12-07 14:21:17Z - status set to: Review |  |  |  | 2022-12-16 19:28 | ED2
3022 | Abhishek Patil | 270 | 2 | 11.21.15 | 2602 | 54 | E | N | 2602 | 54 | 11.21.15 |  | V | Mark Rison |  |  | The field name is incorrect | Fix the field name (see P987L6). Also on P2603L11, the same field name should have first letters upper case (per style guide). | REVISED (ED2: 2022-12-16 19:29:20Z) At 2603.11, replace “off-channel TWT scheduling support bit” with “Off-channel TWT Scheduling Support field”. At 2602.54, change "Off-channel Scheduling TWT Support field" to "Off-channel TWT Scheduling Support field". | ED2 | Motion ED2-270-05 | Ready for Motion | ED2: 2022-12-16 19:29:09Z - status set to: Ready for Motion ED2: 2022-12-16 19:20:25Z - status set to: More Work Required ED2: 2022-12-07 16:34:49Z - status set to: Ready for Motion ED2: 2022-11-15 12:08:59Z - status set to: Review: Further work is needed per the discussion on November 15, 2022. ED2: 2022-11-15 07:42:43Z - status set to: Review |  |  |  | 2022-12-16 19:31 | ED2

## Motion ED2-270-04
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3475 | Mark RISON | 270 | 2 | 20 |  |  | E | Y |  |  | 20 |  | A | Edward Au | 22/2071r3 | 90 | "of a received PPDU" in 8.3.5.14.2 (570.3) and 28.3.9.2 (4315.14) should be "of the received PPDU"; in Table 20-1 (3336.22) and 23-1 (3574.11) and 28-1 (4248.35) it should be "of the current PPDU" | As it says in the comment | ACCEPTED (ED2: 2022-12-07 16:45:46Z) | ED2 | Motion ED2-270-04 | Resolved | ED2: 2022-12-07 16:45:49Z - status set to: Ready for Motion ED2: 2022-11-28 22:33:39Z - status set to: Review |  |  |  | 2022-12-07 16:46 | ED2
3109 | Joseph Levy | 270 | 2 | 11.2.3.12 | 2391 | 1 | E | N | 2391 | 1 | 11.2.3.12 |  | A | Edward Au | 22/2071r3 | 90 | There are several locations where "Awake Window Slot Counter" is used, this phrase should not be capitalized as the counter in not a field or element name. | Replace: "Awake Window Slot Counter" with "awake window slot counter". At the following locations: 2391.1, 2391.5, 2391.8, 2391.13, 2391.19 | ACCEPTED (ED2: 2022-12-07 16:44:46Z) | ED2 | Motion ED2-270-04 | Resolved | ED2: 2022-12-07 16:44:50Z - status set to: Ready for Motion ED2: 2022-11-28 20:35:11Z - status set to: Review |  |  |  | 2022-12-07 16:45 | ED2
3207 | Mark RISON | 270 | 2 | 3 |  |  | E | Y |  |  | 12.4 |  | V | Edward Au | 22/2071r3 | 90 | Why is PWE sometimes or always italic and bold in e.12.4.4.2.2, 12.4.5.2/3/4, 12.4.8.6.3? | Make it nonbold roman in all cases | REVISED (ED2: 2022-12-07 16:50:36Z) At 2812.35, 2812.53, 2812.58, 2812.61 (x2), 2812.62, 2813.1, 2813.37, 2813.40, 2819.62, 2820.23, 2820.29, 2820.40, 2820.45, 2821.40, 2831.37, and 2831.55, update the style of PWE from bold and italic to nonbold and nonitalic. | ED2 | Motion ED2-270-04 | Resolved | ED2: 2022-12-07 16:50:40Z - status set to: Ready for Motion ED2: 2022-12-07 14:29:35Z - status set to: Review |  |  |  | 2022-12-07 16:51 | ED2
3239 | Mark RISON | 270 | 2 | 15.2.3 | 3113 | 46 | E | Y | 3113 | 46 | 15.2.3 |  | A | Edward Au | 22/2071r3 | 90 | "SIGNAL shall represent the data rate at which the current PPDU was received. " should be "The SIGNAL parameter represents ..." Also below should be "The X parameter ..." | Change 3113.46-62 to The SIGNAL parameter represents the data rate at which the current PPDU was received. The SERVICE parameter shall be null. The SQ parameter provides to the MAC entity the signal quality of the DSSS PHY PN code correlation. The signal quality shall be sampled when the DSSS PHY achieves code lock and shall be held until the next code lock acquisition. The signal quality may be used in conjunction with RSSI as part of a CCA scheme. The RX_ANTENNA parameter reports the antenna used by the PHY for reception of the most recent PPDU. (#1373)The RX_START_FRAME_OFFSET parameter is an estimate of the offset (in 10 ns units) from the point in time at which the start of the preamble (#14)of the PPDU arrived at the receive antenna connector to the point in time at which this primitive is issued to the MAC. | ACCEPTED (ED2: 2022-12-07 16:45:09Z) | ED2 | Motion ED2-270-04 | Resolved | ED2: 2022-12-07 16:45:08Z - status set to: Ready for Motion ED2: 2022-11-28 20:41:14Z - status set to: Review |  |  |  | 2022-12-07 16:45 | ED2
3245 | Mark RISON | 270 | 2 | 12.7.9.4 | 2934 | 17 | E | Y | 2934 | 17 | 12.7.9.4 |  | A | Edward Au | 22/2071r3 | 90 | "CheckMIC(). he Supplicant invokes "; "336 bits such that he" (also 390 below); first row of Table 27-53--HE PHY MIB attributes; ""he Transmit MCS supported by the PHY" | Change "he" to "The" at 2934.17, 3360.27/40, 5320.31. At 4190.23 change it to "he(14)" | ACCEPTED (ED2: 2022-12-07 16:48:12Z) | ED2 | Motion ED2-270-04 | Resolved | ED2: 2022-12-07 16:48:17Z - status set to: Ready for Motion ED2: 2022-12-07 13:23:01Z - status set to: Review |  |  |  | 2022-12-07 16:48 | ED2
3270 | Mark RISON | 270 | 2 | 12 |  |  | E | Y |  |  | 12 |  | V | Edward Au | 22/2071r3 | 90 | sometimes it's "ciphersuite", sometimes "cipher-suite", sometimes "cipher suite" | Pick one ("cipher suite" is by far the most popular) and change the others (I can provide locations) | REVISED (ED2: 2022-12-07 16:46:35Z) At 2888.65, 2889.52, 2891.39, 2891.48, 2927.62, 3041.27, replace “cipher-suite” with “cipher suite”. At 754.19 [x2], 3045.4, 4957.26, replace “ciphersuite” with “cipher suite”. At 2913.31 and 2916.7, replace “Cipher-suite” with “Cipher suite”. | ED2 | Motion ED2-270-04 | Resolved | ED2: 2022-12-07 16:46:40Z - status set to: Ready for Motion ED2: 2022-12-01 19:32:34Z - status set to: Review |  |  |  | 2022-12-07 16:47 | ED2
3274 | Mark RISON | 270 | 2 | 10 |  |  | E | Y |  |  | 10 |  | A | Edward Au | 22/2063r2 | 90 | "receives a valid frame" and "received any valid frame" -- frames are either received or not received | Delete "valid" in "An S1G STA that receives a valid frame " at 1775.44, "receives a valid frame" at 2059.58, 2060.6, 2254.4, "receive a valid frame" at 2252.50, 2253.62 | ACCEPTED (ED2: 2022-12-07 16:39:41Z) | ED2 | Motion ED2-270-04 | Resolved | ED2: 2022-12-07 16:39:47Z - status set to: Ready for Motion ED2: 2022-11-28 16:00:25Z - status set to: Review |  |  |  | 2022-12-07 16:40 | ED2
3423 | Mark RISON | 270 | 2 | 22.2.4 | 3524 | 50 | E | Y | 3524 | 50 | 22.2.4 |  | A | Edward Au | 22/2071r3 | 90 | "Non-HT PPDU format is same as in Figure 17-1 (PPDU format). Overview of the PPDU encoding process is defined in 17.3.2.2 (Overview of the PPDU encoding process) except for following modifications: " is grotesquely garbled ("format is same as figure"? Missing articles) | Change to "Non-HT PPDU format is shown in Figure 17-1 (PPDU format). The PPDU encoding process is defined in 17.3.2.2 (Overview of the PPDU encoding process) except for the following modifications: " | ACCEPTED (ED2: 2022-12-07 16:45:29Z) | ED2 | Motion ED2-270-04 | Resolved | ED2: 2022-12-07 16:45:33Z - status set to: Ready for Motion ED2: 2022-11-28 20:45:35Z - status set to: Review |  |  |  | 2022-12-07 16:51 | ED2
3115 | Joseph Levy | 270 | 2 | 11.2.3.14.3 | 2395 | 33 | E | N | 2395 | 33 | 11.2.3.14.3 |  | V | Edward Au | 22/2063r2 | 90 | There are locations where the counters are referred to using the field name capitalization. This is not in line with the style of the 802.11 specification. Counters should use lower case names, Fields and elements using the term "Counter' in their name should be capitalized. | Replace "...the FMS Counter ID assigned ..." with "...the FMS counter ID assigned ..." | REVISED (ED2: 2022-12-07 16:42:02Z) At 1105.64 and 2395.33, replace “Counter” with “counter”. | ED2 | Motion ED2-270-04 | Resolved | ED2: 2022-12-07 16:42:09Z - status set to: Ready for Motion ED2: 2022-11-28 17:08:03Z - status set to: Review |  |  |  | 2022-12-07 16:42 | ED2
3483 | Mark RISON | 270 | 2 | 26.11.10 | 3949 | 8 | E | Y | 3949 | 8 | 26.11.10 |  | V | Edward Au | 22/2063r2 | 90 | "the power boost factor POWER_BOOST_FACTOR" should be "the POWER_BOOST_FACTOR parameter"; at line 18 "the POWER_BOOST_FACTOR" -> "the POWER_BOOST_FACTOR parameter" (3x) | As it says in the comment | REVISED (ED2: 2022-12-07 16:40:33Z) At 3949.8, replace “the power boost factor POWER_BOOST_FACTOR” with “the POWER_BOOST_FACTOR parameter”. At 3949.12, 3949.14, and 3914.18, replace “the POWER_BOOST_FACTOR” with “the POWER_BOOST_FACTOR parameter”. | ED2 | Motion ED2-270-04 | Resolved | ED2: 2022-12-07 16:40:39Z - status set to: Ready for Motion ED2: 2022-11-28 16:05:24Z - status set to: Review |  |  |  | 2022-12-07 16:41 | ED2
3487 | Mark RISON | 270 | 2 | 10.23.5.1 | 1922 | 26 | E | Y | 1922 | 26 | 10.23.5.1 |  | A | Edward Au | 22/2071r3 | 90 | "concatenating the Page Index subfield and the RAW Start AID in the RAW Group subfield" should be "concatenating the Page Index subfield and the RAW Start AID subfield in the RAW Group subfield". Ditto add " subfield" after "RAW End AID" on the next line | As it says in the comment | ACCEPTED (ED2: 2022-12-07 16:47:35Z) | ED2 | Motion ED2-270-04 | Resolved | ED2: 2022-12-07 16:47:39Z - status set to: Ready for Motion ED2: 2022-12-07 12:38:04Z - status set to: Review |  |  |  | 2022-12-07 16:48 | ED2
3532 | Mark RISON | 270 | 2 | 12 |  |  | E | Y |  |  | 12 |  | V | Mark Rison | 22/2069r0 | 90 | The row ordering in Table 12-7--Cipher suite key lengths seems haphazard | Sort alphabetically | REVISED (ED2: 2022-12-07 14:45:15Z) Incorporate the changes as shown in 22/2069r0 athttps://mentor.ieee.org/802.11/dcn/22/11-22-2069-00-000m-resolutions-for-some-comments-on-11me-d2-0-lb270.docx | ED2 | Motion ED2-270-04 | Resolved | ED2: 2022-12-02 17:15:25Z - status set to: Submission Required ED2: 2022-11-25 14:32:16Z - status set to: Review |  |  |  | 2022-12-07 14:46 | ED2
3626 | Mark RISON | 270 | 2 |  |  |  | E | Y |  |  |  |  | V | Edward Au | 22/2071r3 | 90 | "The <blah> PPDU is composed of <blah>. This is shown in <blah>." has high risk of spec rot/inconsistency | Change to "The DMG control mode PPDU is composed of the Preamble, Header, Data field, and possibly AGC and TRN subfields. This is shown in Figure 20-6 (DMG control mode PPDU format)." to "The DMG control mode PPDU is shown in Figure 20-6 (DMG control mode PPDU format)." at 3653.50 and make similar changes for other instances of "PPDU is composed of"s | REVISED (ED2: 2022-12-07 16:46:12Z) Incorporate the changes as shown in 11-22/2071r3 (https://mentor.ieee.org/802.11/dcn/22/11-22-2071-03-000m-proposed-resolution-for-miscellaneous-lb270-comments-part-3.docx). | ED2 | Motion ED2-270-04 | Resolved | ED2: 2022-12-07 16:46:17Z - status set to: Ready for Motion ED2: 2022-11-28 23:09:17Z - status set to: Review |  |  |  | 2022-12-07 16:46 | ED2
3633 | Mark RISON | 270 | 2 | 12 |  |  | E | Y |  |  | 12 |  | V | Edward Au | 22/20715 | 90 | "= Not present" is weird | Change to "not present" and then put the "=" later on if needed, e.g. "Key MIC = Not present when using an AEAD cipher; otherwise, MIC(KCK, EAPOL) - MIC computed over the body of this EAPOL-Key frame with the Key MIC field first initialized to 0" -> "Key MIC not present when using an AEAD cipher; otherwise = MIC(KCK, EAPOL) - MIC computed over the body of this EAPOL-Key frame with the Key MIC field first initialized to 0" (I can provide locations) | REVISED (ED2: 2022-12-07 20:31:56Z) Incorporate the changes as shown in the document 11-22/2071r5 (https://mentor.ieee.org/802.11/dcn/22/11-22-2071-05-000m-proposed-resolution-for-miscellaneous-lb270-comments-part-3.docx). | ED2 | Motion ED2-270-04 | Resolved | ED2: 2022-12-07 20:31:55Z - status set to: Ready for Motion ED2: 2022-12-07 16:47:52Z - status set to: More Work Required ED2: 2022-12-07 13:14:54Z - status set to: Review |  |  |  | 2022-12-07 20:34 | ED2
3702 | Mark RISON | 270 | 2 |  |  |  | E | Y |  |  |  |  | J | Edward Au | 22/2071r3 | 90 | "Std" is haphazardly present after "IEEE" and before "802" | I can provide locations if I'm told what the rule is for when it's needed | REJECTED (ED2: 2022-12-07 16:49:46Z) The IEEE publication editor reviews the draft to ensure “Std” is used in the appropriate places. | ED2 | Motion ED2-270-04 | Resolved | ED2: 2022-12-07 16:49:52Z - status set to: Ready for Motion ED2: 2022-12-07 13:52:55Z - status set to: Review |  |  |  | 2022-12-07 16:50 | ED2
3311 | Mark RISON | 270 | 2 | 11.21.15 |  |  | E | Y |  |  | 11.21.15 |  | V | Edward Au | 22/2071r3 | 90 | "Channel Usage" should be lowercase | Lowercase (except C if at start of sentence etc.) at 375.20, 387.55 (rightmost), 397.32 (rightmost), 1636.42, 2109.13, 2602.36/37/40(2x)/59/61/63/64, 2603.24, 2604.2(2x)/28, 4774.61, 4988.12/25/26, 5770.32 | REVISED (ED2: 2022-12-07 16:47:13Z) Replace “Channel Usage” with “channel usage” at 387.55 (rightmost), 397.32 (rightmost), 1636.42, 2109.13, 2602.36/37/40(2x)/59/61/63/64, 2603.24, 2604.2(2x)/28, 4988.12/25/26, 5770.32. Replace “Channel Usage” with “Channel usage” at 375.20 and 4774.61. Note to the commenter: These are the exact locations provided by the commenter. | ED2 | Motion ED2-270-04 | Resolved | ED2: 2022-12-07 16:47:17Z - status set to: Ready for Motion ED2: 2022-12-07 12:34:02Z - status set to: Review |  |  |  | 2022-12-07 16:47 | ED2

## Motion ED2-270-03
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3692 | Mark RISON | 270 | 2 |  |  |  | E | Y |  |  |  |  | J | Edward Au | 22/2063r1 | 91 | It is weird that the feature is "TIM broadcast" but the frames are just "TIM" frames | Rename TIM frames to TIM Broadcast frames (I can provide locations) | REJECTED (ED2: 2022-12-02 17:25:22Z) While it may be weird that the feature is “TIM broadcast” but the corresponding frames are “TIM frames”, there is no concern to continue using “TIM frames”. | ED2 | Motion ED2-270-03 | Resolved | ED2: 2022-12-05 20:03:22Z - status set to: Ready for Motion ED2: 2022-11-25 18:50:35Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2

## Motion ED2-270-02
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3229 | Mark RISON | 270 | 2 | 12.6.1.2.2 | 2861 | 29 | E | Y | 2861 | 29 | 12.6.1.2.2 |  | A | Edward Au | 22/2001r3 | 90 | "uses the Open System authentication" should be "uses Open System authentication" | As it says in the comment | ACCEPTED (ED2: 2022-12-02 17:11:03Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 13:19:02Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3814 | Yoshio Urabe | 270 | 2 | 29.6.2 | 4556 | 45 | E | N | 4556 | 45 | 29.6.2 |  | A | Edward Au | 22/2001r3 | 90 | In "after transmitting the Beacon frame and non-GCR-SP group addressed if ...", something is missing after "group addressed". | Add "BUs" after "group addressed". | ACCEPTED (ED2: 2022-12-02 17:06:45Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 13:02:09Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3335 | Mark RISON | 270 | 2 | 27.4.4 | 4198 | 50 | E | Y | 4198 | 50 | 27.4.4 |  | A | Edward Au | 22/2063r1 | 90 | "See (#2369)10.12.2 (A-MPDU length limit rules) and 9.2.4.6.1 (General)" should be "and 9.2.4.8.1" | As it says in the comment | ACCEPTED (ED2: 2022-12-02 17:23:51Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 18:23:48Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3320 | Mark RISON | 270 | 2 | 11.4.4.4 |  |  | E | Y |  |  | 11.4.4.4 |  | A | Edward Au | 22/2001r3 | 90 | "TPSEC" and "TSEC" should be "TSPEC" | Fix at 2454.45 (2x) and 5685.58 | ACCEPTED (ED2: 2022-12-02 17:14:58Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 14:22:38Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3308 | Mark RISON | 270 | 2 | 26.8.4.4 | 3918 |  | E | Y | 3918 |  | 26.8.4.4 |  | A | Edward Au | 22/2001r3 | 90 | "that contains a TWT Flow Identifier" -- missing "field" | Add " field" after the cited text on lines 44, 50, 55, 62 | ACCEPTED (ED2: 2022-12-02 17:14:44Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 14:19:27Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3260 | Mark RISON | 270 | 2 | 12 |  |  | E | Y |  |  | 12 |  | A | Edward Au | 22/2063r1 | 90 | "TK bits" should be "TK_bits" | Change at 2957.13 (3x), 2957.14, 2957.15 (2x), 2957.47 (3x) | ACCEPTED (ED2: 2022-12-02 17:28:35Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 21:16:33Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3251 | Mark RISON | 270 | 2 | 14.10.9.3 | 3068 | 28 | E | Y | 3068 | 28 | 14.10.9.3 |  | A | Edward Au | 22/2063r1 | 90 | "For the per target fields (Per Target Flags, Target Address, Target HWMP Sequence Number) assume" -- font size changes. Also in "Where A-MPDU aggregation is employed, HT-immediate block ack is assumed". Also at 2753.55 | Use uniform font size at referenced location and also in "Where A-MPDU aggregation is employed, HT-immediate block ack is assumed." at 5679.55 and "nonzero" at 2753.55 and "is not SUCCESS(#1277) or SAE_HASH_TO_ELEMENT" at 2831.43 | ACCEPTED (ED2: 2022-12-02 17:27:42Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 19:59:14Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3363 | Mark RISON | 270 | 2 | 12.7.2 | 2906 | 1 | E | Y | 2906 | 1 | 12.7.2 |  | A | Edward Au | 22/2063r1 | 90 | "IPN corresponds to" should be "IPN field contains" | As it says in the comment | ACCEPTED (ED2: 2022-12-02 17:27:05Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 19:28:09Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3240 | Mark RISON | 270 | 2 | 12.7.8.4.2 | 2929 | 9 | E | Y | 2929 | 9 | 12.7.8.4.2 |  | A | Edward Au | 22/2001r3 | 90 | "pairwise cipher suite list field" needs uppercasing | Change to "Pairwise Cipher Suite List field" | ACCEPTED (ED2: 2022-12-02 17:11:21Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 13:22:05Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3387 | Mark RISON | 270 | 2 | 11.30.5 | 2687 | 21 | E | Y | 2687 | 21 | 11.30.5 |  | A | Edward Au | 22/2001r3 | 90 | "non-contiguous" (2x) | Delete hyphen at 2687.21 and 5287.14 | ACCEPTED (ED2: 2022-12-02 17:12:08Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 13:33:49Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3201 | Mark RISON | 270 | 2 | 11.20.1 | 2554 | 15 | E | Y | 2554 | 15 | 11.20.1 |  | A | Edward Au | 22/2001r3 | 90 | "Note that " should be "NOTE---" since it is not something particularly noteworthy, but rather a gentle reminder | Change "Note that the TDLS Discovery Response frame is not a TDLS frame but a Public Action frame." to "NOTE---The TDLS Discovery Response frame is not a TDLS frame but a Public Action frame." | ACCEPTED (ED2: 2022-12-02 17:14:22Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 14:14:26Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3196 | Mark RISON | 270 | 2 | 11.1.3.8.4 |  |  | E | Y |  |  | 11.1.3.8.4 |  | V | Edward Au | 22/2063r1 | 90 | "identified by an Element ID and Element ID Extension (if applicable)" -- missing "field" (also other locations) | Identify locations where "field" is missing | REVISED (ED2: 2022-12-02 17:23:28Z) At 2348.24 and 2348.43, replace “an Element ID and Element ID Extension” with “Element ID and Element ID Extension fields”. At 2348.45, replace “the same Element ID and Element ID Extension” with “the same Element ID and Element ID Extension fields”. | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 18:17:27Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3195 | Mark RISON | 270 | 2 | 11.1.3.8.4 |  |  | E | Y |  |  | 11.1.3.8.4 |  | A | Edward Au | 22/2063r1 | 90 | "identified by an Element ID and Element ID Extension (if applicable)" -- missing "field" (also other locations) | 2x on referenced page change "an Element ID and Element ID Extension" to "Element ID and Element ID Extension fields" and 1x change "same Element ID and Element ID Extension" to "same Element ID and Element ID Extension fields" | ACCEPTED (ED2: 2022-12-02 17:23:20Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 18:17:14Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3092 | John Wullert | 270 | 2 | 26.3.1 | 3833 | 55 | E | N | 3833 | 55 | 26.3.1 |  | A | Edward Au | 22/2001r3 | 90 | Missing comma - there should be a comma between "10.2.7 (Fragmentation/ defragmentation overview)" and "10.4 (MSDU, (11ax)A-MSDU, and MMPDU fragmentation)," | Add comma in the indicated position. | ACCEPTED (ED2: 2022-12-02 17:13:59Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 14:07:42Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3797 | Xiangxin Gu | 270 | 2 | B.4.10 | 4721 | 53 | E | N | 4721 | 53 | B.4.10 |  | V | Edward Au | 22/2001r3 | 90 | 11.6.2 (Procedure at the STA) is not the right reference | change to 11.8.3 Quieting channels for testing | REVISED (ED2: 2022-12-02 17:08:42Z) At 4721.53, 4721.63, and 4722.13, replace the reference 11.6.2 (Procedure at the STA)” with 11.8.3 (Quieting channels for testing). Note to the Editors: Delete “EMPTY” at 4721.46 and 4765.6 (HTP2.12). | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 13:13:22Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3815 | Yoshio Urabe | 270 | 2 | 21.3.8.3.3 | 3435 | 9 | E | N | 3435 | 9 | 21.3.8.3.3 |  | A | Edward Au | 22/2001r3 | 90 | In the text (... relative to the non-HT signal field), the abbreviation "L-SIG" is preferrable instead of "non-HT singal field". Otherwise "signal" should be capitalized. | Replace "non-HT signal field" with "L-SIG". | ACCEPTED (ED2: 2022-12-02 17:08:29Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 13:06:00Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3250 | Mark RISON | 270 | 2 | 11.2.3.4 | 2379 | 18 | E | Y | 2379 | 18 | 11.2.3.4 |  | A | Edward Au | 22/2001r3 | 90 | "under the assumptions that a DTIM is transmitted once every three TIMs" -- that's a single assumption | Change "assumptions" to "assumption" | ACCEPTED (ED2: 2022-12-02 17:11:31Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 13:27:34Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3474 | Mark RISON | 270 | 2 | 16.3.8.6 |  |  | E | Y |  |  | 16.3.8.6 |  | A | Edward Au | 22/2063r1 | 90 | "SYNC field of the received frame" in 16.3.8.6 (3163.51) should be "SYNC field of the received PPDU"; ditto "STF or the CEF field of the received frame" frame->PPDU in 25.3.13 (3762.56) | As it says in the comment | ACCEPTED (ED2: 2022-12-02 17:30:00Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-28 13:30:52Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3728 | Mark RISON | 270 | 2 |  |  |  | E | Y |  |  |  |  | V | Edward Au | 22/2063r1 | 90 | "-- The "Channel starting frequency" column in Table E-4 (Global operating classes) is greater than or equal to 5.925 and less than or equal to 7.125" -- columns don't have values, cells do. And it would be better to give units (though it's true the cell itself doesn't) | As it says in the comment | REVISED (ED2: 2022-12-02 17:31:28Z) Incorporate the changes as shown in 11-22/2063r1 at https://mentor.ieee.org/802.11/dcn/22/11-22-2063-01-000m-proposed-resolution-for-miscellaneous-lb270-comments-part-2.docx At 868.16, updated the text (highlighted in red, bold, and underline for convenience) as follows: The value in the “Channel starting frequency (GHz)” column in Table E-4 (Global operating classes) is greater than or equal to 5.925 and less than or equal to 7.125 for the operating class indicated in the Operating Class field. At 868.20, updated the text as follows: The value in the “Channel spacing (MHz)” column in Table E-4 (Global operating classes) is greater than or equal to 40 MHz for the operating class indicated in the Operating Class field. | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-28 15:11:05Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3721 | Mark RISON | 270 | 2 |  |  |  | E | Y |  |  |  |  | J | Edward Au | 22/2063r1 | 90 | "Tx" v "TX" inconsistency | Pick one and change the others to that. I can provide locations | REJECTED (ED2: 2022-12-02 17:26:17Z) While there is inconsistency on the terms “TX” and “Tx”, such inconsistency does not result in any issue. | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 19:23:43Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3703 | Mark RISON | 270 | 2 | 1.4 |  |  | E | Y |  |  | 1.4 |  | V | Edward Au | 22/2063r1 | 90 | "The construction "between x and y", "x to y" or "x-y"" should have x and y in italics. Also the hyphen should be a minus or en dash (but in other places hyphens or em dashes are also sometimes used) | Change "The construction "between x and y", "x to y" or "x-y"" to have x and y in italics, and the hyphen as a minus (or en dash if that is within the available glyphs) | REVISED (ED2: 2022-12-02 17:26:02Z) At 171.37, replace the hyphen of “x-y” with an en dash. At 171.38, replace the hyphen of “Bx-By” with an en dash. At 171.39, italize “x”. | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 18:57:32Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3550 | Mark RISON | 270 | 2 | 10 |  |  | E | Y |  |  | 10 |  | J | Edward Au | 22/2063r1 | 90 | Figure 10-21 gains nothing from the pseudo-3D | Make it 2D | REJECTED (ED2: 2022-12-02 17:24:57Z) The commenter fails to identify an issue of the figure. | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 18:39:52Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3505 | Mark RISON | 270 | 2 | 11 |  |  | E | Y |  |  | 11 |  | V | Edward Au | 22/2063r1 | 90 | OCVC stands for "operating channel validation capable" so "OCVC capable" doesn't make sense | Change "OCVC capability" to "OCVC" throughout (I can provide locations); see CID 1459 | REVISED (ED2: 2022-12-02 17:31:02Z) At 249.23 (subclause 3.4): Change “OCVC operating channel validation capable” to “OCVC operating channel validation capable or operating channel validation capability” At 2785.44, delete “capable”. At 2400.53, 2401.20, 2401.35, 2488.4, 2488.5, 2496.46, 2536.44, 2536.51, 2536.55, 2537.3, 2773.50 (x2), 2785.43, 2785.47, 2786.1, 2786.16, 2915.7, 2917.32, 2924.16, 2925.16, 2958.37, 2959.43, 2960.56, 2961.59, 2986.9, 2968.57, 2991.44, 2992.37, 3035.44, and 3036.49, delete “capability”. | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-28 14:47:06Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3496 | Mark RISON | 270 | 2 | 12.7.2 | 2901 | 14 | E | Y | 2901 | 14 | 12.7.2 |  | A | Edward Au | 22/2063r1 | 90 | "in which case the Request (bit 11) is also set to 1" should not have "the" (my mistake in reviewing) | As it says in the comment | ACCEPTED (ED2: 2022-12-02 17:30:42Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-28 14:09:13Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3360 | Mark RISON | 270 | 2 | 1.5 |  |  | E | Y |  |  | 1.5 |  | A | Edward Au | 22/2063r1 | 90 | log_10 should not be subscript 10; also in text below (CID 2379) | Desubscriptify log_10 to log10 at 1455.6 (2x), 1455.29, 4315.48. Also add parens around N_PSRT,nonpunc at 3939.10 | ACCEPTED (ED2: 2022-12-02 17:28:52Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 21:21:17Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3476 | Mark RISON | 270 | 2 | 23.3.18.7 | 3682 | 38 | E | Y | 3682 | 38 | 23.3.18.7 |  | A | Edward Au | 22/2063r1 | 90 | "within the specific dynamic range of the receiver" should be "within the specified dynamic range of the receiver" | As it says in the comment | ACCEPTED (ED2: 2022-12-02 17:30:11Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-28 13:32:55Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3729 | Mark RISON | 270 | 2 |  |  |  | E | Y |  |  |  |  | V | Edward Au | 22/2063r1 | 90 | In 9.6.x, the first subsubsubclause is sometimes "General", sometimes "<blah> Action field" | Pick one and change the others to that. I can provide locations | REVISED (ED2: 2022-12-02 17:26:35Z) Replace the title of 9.6.2 from “Spectrum Management Action frames” to “Spectrum Management Action frame details”. Replace the title of 9.6.2.1 from “General” to “Spectrum Management Action field”. Replace the title of 9.6.3.1 from “General” to “QoS Action field”. Replace the title of 9.6.4.1 from “General” to “Block Ack Action field”. Replace the title of 9.6.5 from “Vendor-specific action details” to “Vendor-specific Action frame details”. Replace the title of 9.6.6 from “Radio Measurement action details” to “Radio Measurement Action frame details”. Replace the title of 9.6.6.1 from “General” to “Radio Measurement Action field”. Replace the title of 9.6.7 from “Public Action details” to “Public Action frame details”. Replace the title of 9.6.7.1 from “Public Action frames” to “Public Action field”. Replace the title of 9.6.8.1 from “General” to “FT Action field”. Replace the title of 9.6.9.1 from “General” to “SA Query Action field”. Replace the title of 9.6.10 from “Protected Dual of Public Action frames” to “Protected Dual of Public Action frame details”. Replace the title of 9.6.12.1 from “General” to “TDLS Action field”. Replace the title of 9.6.13 from “WNM Action details” to “WNM Action frame details”. Replace the title of 9.6.13.1 from “WNM Action fields” to “WNM Action field”. Replace the title of 9.6.14 from “Unprotected WNM Action details” to “Unprotected WNM Action frame details”. Replace the title of 9.6.14.1 from “Unprotected WNM Action fields” to “Unprotected WNM Action field”. Replace the title of 9.6.15.1 from “General” to “Self-protected Action field”. Replace the title of 9.6.16.1 from “Mesh Action fields” to “Mesh Action field”. Replace the title of 9.6.17.1 from “Multihop Action fields” to “Multihop Action field”. Replace the title of 9.6.18.1 from “General” to “Robust AV Streaming Action field”. Replace the title of 9.6.23.1 from “General” to “FILS Action field”. | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 19:24:45Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3464 | Mark RISON | 270 | 2 | 12.7.2 | 2904 | 56 | E | Y | 2904 | 56 | 12.7.2 |  | A | Edward Au | 22/2063r1 | 90 | "the EAPOL protocol version field" should be "the Protocol Version field of the EAPOL PDU (see Figure 12-33 (EAPOL-Key frame format))" | As it says in the comment | ACCEPTED (ED2: 2022-12-02 17:28:14Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 20:12:34Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3441 | Mark RISON | 270 | 2 | C.3 |  |  | E | Y |  |  | C.3 |  | A | Edward Au | 22/2063r1 | 90 | "STATUS Deprecated" should be "STATUS deprecated" (16x) | Change throughout C.3 | ACCEPTED (ED2: 2022-12-02 17:29:27Z) Note to the Editors: The 16 locations in D2.0 are listed as follows for your convenience, namely, 4902.13, 4918.63, 4976.64, 4979.39, 4984.53, 5086.47, 5091.37, 5193.35, 5220.64, 5221.28, 5221.41, 5221.54, 5450.39, 5452.21, 5460.48, and 5475.63. | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-28 13:27:42Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3426 | Mark RISON | 270 | 2 | 12.7.10.3 | 2941 | 58 | E | Y | 2941 | 58 | 12.7.10.3 |  | A | Edward Au | 22/2063r1 | 90 | "When (#1571)an EAPOL-Key request frame is received, then" -- spurious "then" | Delete the "then" | ACCEPTED (ED2: 2022-12-02 17:28:02Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 20:02:36Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3416 | Mark RISON | 270 | 2 | 12.7.2 | 2906 | 13 | E | Y | 2906 | 13 | 12.7.2 |  | A | Edward Au | 22/2063r1 | 90 | "The following (#1836)EAPOL-Key PDUs are used to implement the" is missing a word | Append " handshakes" | ACCEPTED (ED2: 2022-12-02 17:24:31Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 18:32:49Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3412 | Mark RISON | 270 | 2 | 15.2.3 | 3113 | 40 | E | Y | 3113 | 40 | 15.2.3 |  | A | Edward Au | 22/2063r1 | 90 | "This RSSI parameter" -> "The RSSI parameter" | As it says in the comment | ACCEPTED (ED2: 2022-12-02 17:24:19Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 19:31:54Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3391 | Mark RISON | 270 | 2 | 11.21.15 | 2603 | 8 | E | Y | 2603 | 8 | 11.21.15 |  | A | Edward Au | 22/2063r1 | 90 | "in the HE Capabilities element, that it transmits," spurious commas | Delete commas at 2603.8 | ACCEPTED (ED2: 2022-12-02 17:24:08Z) | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-25 18:26:27Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2
3482 | Mark RISON | 270 | 2 | 27.2.2 | 4006 | 35 | E | Y | 4006 | 35 | 27.2.2 |  | A | Edward Au | 22/2063r1 | 90 | "the range of 0.5 to 2" should be "the range 0.5 to 2" | Change all the "the range of <n> to <m>" to "the range <n> to <m>" | ACCEPTED (ED2: 2022-12-02 17:30:28Z) Note to the Editors, the locations in D2.0 are listed as follows for your convenience: At 755.12, change “the range of 1 to 2007” to “the range 1 to 2007”. At 755.15, change “the range of 1 to 8191” to “the range 1 to 8191”. At 858.49, change “the range of 0 to 30” to “the range 0 to 30”. At 2283.40, change “the range of 0 to 30” to “the range 0 to 30”. At 2283.42, change “the range of 0 to 30” to “the range 0 to 30”. At 2298.52, change “the range of 1 to 15” to “the range 1 to 15”. At 2368.35, change “the range of 0 to 255” to “the range 0 to 255”. At 2917.15, change “the range of 0 to 1” to “the range 0 to 1”. At 3875.64, change “the range of 0 and OCW” to “the range 0 to OCW”. At 3991.19, change “the range of 1 to 4095” with “the range 1 to 4095”. At 3997.35, change “the range of 0 to aPSDUMaxLength octets” to “the range 0 to aPSDUMaxLength octets”. At 4006.35, change “the range of 0.5 to 2” to “the range 0.5 to 2”. At 4073.55, change “the range of 4 to 7” to “the range 4 to 7”. At 4073.56, change “the range of 4 to 7” to “the range 4 to 7”. At 4133.22, change “the range of 0 ≤ k ≤ NSD – 1” with “the range 0 ≤ k ≤ NSD – 1”. At 4133.22, change “the range of NSD ≤ q(k) ≤ 2NSD – 1” to “the range NSD ≤ q(k) ≤ 2NSD – 1”. At 4133.24, change “the range of 0 ≤ k ≤ NSD/2 – 1” with “the range 0 ≤ k ≤ NSD/2 – 1”. At 4133.24, change “the range of NSD/2 ≤ k ≤ NSD – 1” with “the range NSD/2 ≤ k ≤ NSD – 1”. At 4241.26, change “the range of 14 to 1023” to “the range 14 to 1023”. At 4243.17, change “the range of 1 to 8” to “the range 1 to 8”. At 4243.28, change “the range of 1 to 8” to “the range 1 to 8”. At 4440.42, change “the range of 0 to 255” to “the range 0 to 255”. At 4440.56, change “the range of 0 to 255” to “the range 0 to 255”. At 4582.48, change “the range of 0 to aMPDUMaxLength octets” to “the range 0 to aMPDUMaxLength octets”. | ED2 | Motion ED2-270-02 | Resolved | ED2: 2022-11-28 14:06:52Z - status set to: Review |  |  |  | 2022-12-05 20:03 | ED2

## Motion ED2-270-01
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3452 | Mark RISON | 270 | 2 | E.2.7 | 5523 | 1 | E | Y | 5523 | 1 | E.2.7 |  | A | Edward Au | 22/2001r1 | 88 | "Regulatory Client EIRP PSD" should be lowercase client | As it says in the comment | ACCEPTED (ED2: 2022-11-15 12:05:01Z) | ED2 | Motion ED2-270-01 | Resolved | ED2: 2022-11-15 12:05:02Z - status set to: Ready for Motion ED2: 2022-11-15 02:25:34Z - status set to: Review |  |  |  | 2022-11-15 12:06 | ED2
3403 | Mark RISON | 270 | 2 | 11.12 |  |  | E | Y |  |  | 11.12 |  | A | Edward Au | 22/2001r1 | 88 | "matches its own" -- delete the "own" | Delete "own" at 2535.27, 3679.52, 3681.2, 1915.10, 2535.21/43, 3024.4, 3074.54/56 | ACCEPTED (ED2: 2022-11-15 12:03:37Z) | ED2 | Motion ED2-270-01 | Resolved | ED2: 2022-11-15 12:03:39Z - status set to: Ready for Motion ED2: 2022-11-15 02:11:07Z - status set to: Review |  |  |  | 2022-11-15 12:06 | ED2
3279 | Mark RISON | 270 | 2 | 30 |  |  | E | Y |  |  | 30 |  | A | Edward Au | 22/2001r1 | 88 | "using contiguous 13 subcarriers" should be "using 13 contiguous subcarriers" (2x) | Change at 4579.55 and 4603.60 | ACCEPTED (ED2: 2022-11-15 12:04:22Z) | ED2 | Motion ED2-270-01 | Resolved | ED2: 2022-11-15 12:04:24Z - status set to: Ready for Motion ED2: 2022-11-15 02:13:46Z - status set to: Review |  |  |  | 2022-11-15 12:06 | ED2
3210 | Mark RISON | 270 | 2 | AC | 5795 | 54 | E | Y | 5795 | 54 | AC |  | A | Edward Au | 22/2001r1 | 88 | "Example 3 in AC-2" should be "Example 3 in Table AC-2", and at 5796.61 "AC-2" should be "Table AC-2" | As it says in the comment | ACCEPTED (ED2: 2022-11-15 12:04:42Z) | ED2 | Motion ED2-270-01 | Resolved | ED2: 2022-11-15 12:04:43Z - status set to: Ready for Motion ED2: 2022-11-15 02:16:49Z - status set to: Review |  |  |  | 2022-11-15 12:06 | ED2
3198 | Mark RISON | 270 | 2 | 11.21.4.1 | 2574 | 22 | E | Y | 2574 | 22 | 11.21.4.1 |  | A | Edward Au | 22/2001r1 | 88 | What is "the essDetectionInterval value"? | Change to "the ESS detection interval" | ACCEPTED (ED2: 2022-11-15 12:05:51Z) | ED2 | Motion ED2-270-01 | Resolved | ED2: 2022-11-15 12:05:49Z - status set to: Ready for Motion ED2: 2022-11-15 07:36:16Z - status set to: Review |  |  |  | 2022-11-15 12:06 | ED2
3197 | Mark RISON | 270 | 2 | 11 |  |  | E | Y |  |  | 11 |  | A | Edward Au | 22/2001r1 | 88 | "ESS Detection Interval" should be "ESS detection interval" when not followed by "field" | Change at 2566.55, 2570.37, 2576.36 | ACCEPTED (ED2: 2022-11-15 12:06:46Z) | ED2 | Motion ED2-270-01 | Resolved | ED2: 2022-11-15 12:06:45Z - status set to: Ready for Motion ED2: 2022-11-15 08:03:28Z - status set to: Review |  |  |  | 2022-11-15 12:07 | ED2
3188 | Mark RISON | 270 | 2 | B.4 | 4662 | 60 | E | Y | 4662 | 60 | B.4 |  | V | Edward Au | 22/2001r1 | 88 | FR45 "Clause 9" is not very precise | Give a more precise xref | REVISED (ED2: 2022-11-15 12:08:25Z) At 4662.60, replace “Clause 9 (Frame formats)” with “9.3.4.3 (S1G Beacon frame format), 11.1.3 (Maintaining synchronization)”. | ED2 | Motion ED2-270-01 | Resolved | ED2: 2022-11-15 12:08:28Z - status set to: Ready for Motion ED2: 2022-11-15 07:59:35Z - status set to: Review |  |  |  | 2022-11-15 12:09 | ED2
3142 | Kazuto Yano | 270 | 2 | 10.23.2.12.1 | 1907 | 50 | E | N | 1907 | 50 | 10.23.2.12.1 |  | A | Edward Au | 22/2001r1 | 88 | "Thhe" must be "The". | Please fix the typo. | ACCEPTED (ED2: 2022-11-15 12:08:12Z) | ED2 | Motion ED2-270-01 | Resolved | ED2: 2022-11-15 12:08:09Z - status set to: Ready for Motion ED2: 2022-11-15 07:52:54Z - status set to: Review |  |  |  | 2022-11-15 12:08 | ED2
3062 | Hiroyuki Motozuka | 270 | 2 | B.4.24.1 | 4792 | 30 | E | N | 4792 | 30 | B.4.24.1 |  | A | Edward Au | 22/2001r1 | 88 | The reference for DMG-M2 (Signaling of DMG operation) is incorrect. | Change the reference "9.4.2.127.7 (TDD Capability Information field(11ay))" to "9.4.2.128 (DMG Operation element)" | ACCEPTED (ED2: 2022-11-15 12:05:31Z) | ED2 | Motion ED2-270-01 | Resolved | ED2: 2022-11-15 12:05:30Z - status set to: Ready for Motion ED2: 2022-11-15 07:30:30Z - status set to: Review |  |  |  | 2022-11-15 12:06 | ED2
3132 | Jouni Malinen | 270 | 2 | 12.4.5.4 | 2820 | 61 | E | Y | 2820 | 61 | 12.4.5.4 |  | V | Edward Au | 22/2001r1 | 88 | PWE stands for "password element"; not "password identifier", | At P2820 L61, replace "password identifier (PWE)" with "password identifier". | REVISED (ED2: 2022-11-15 12:07:49Z) Incorporate the changes for CID 3132 as shown in https://mentor.ieee.org/802.11/dcn/22/11-22-2001-01-000m-proposed-resolution-for-miscellaneous-lb270-comments.docx | ED2 | Motion ED2-270-01 | Resolved | ED2: 2022-11-15 12:08:00Z - status set to: Ready for Motion ED2: 2022-11-15 07:51:12Z - status set to: Review |  |  |  | 2022-11-15 12:08 | ED2
3127 | Jouni Malinen | 270 | 2 | 12.2.2 | 2780 | 42 | E | Y | 2780 | 42 | 12.2.2 |  | A | Edward Au | 22/2001r1 | 88 | The reference for the description of TKIP is pointing to an incorrect clause (CCMP). | At P2780 L42, replace "TKIP, described in 12.5.2" with "TKIP, described in 12.3.4" | ACCEPTED (ED2: 2022-11-15 12:07:38Z) | ED2 | Motion ED2-270-01 | Resolved | ED2: 2022-11-15 12:07:35Z - status set to: Ready for Motion ED2: 2022-11-15 07:48:46Z - status set to: Review |  |  |  | 2022-11-15 12:08 | ED2
3125 | Jouni Malinen | 270 | 2 | 12.2.4 | 2781 | 17 | E | Y | 2781 | 17 | 12.2.4 |  | A | Edward Au | 22/2001r1 | 88 | Missing space between words. | At P2781 L17, replace "anRSNA" with "an RSNA". | ACCEPTED (ED2: 2022-11-15 12:07:21Z) | ED2 | Motion ED2-270-01 | Resolved | ED2: 2022-11-15 12:07:23Z - status set to: Ready for Motion ED2: 2022-11-15 07:46:34Z - status set to: Review |  |  |  | 2022-11-15 12:07 | ED2
3065 | John Coffey | 270 | 2 | 30.1 | 4579 | 36 | E | Y | 4579 | 36 | 30.1 |  | A | Edward Au | 22/2001r1 | 88 | Missing period at end of sentence. | Add period. | ACCEPTED (ED2: 2022-11-15 12:07:07Z) | ED2 | Motion ED2-270-01 | Resolved | ED2: 2022-11-15 12:07:08Z - status set to: Ready for Motion ED2: 2022-11-15 07:44:25Z - status set to: Review |  |  |  | 2022-11-15 12:07 | ED2

## Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3022 | Abhishek Patil | 270 | 2 | 11.21.15 | 2602 | 54 | E | N | 2602 | 54 | 11.21.15 |  | V | Mark Rison |  |  | The field name is incorrect | Fix the field name (see P987L6). Also on P2603L11, the same field name should have first letters upper case (per style guide). | REVISED (ED2: 2022-12-16 19:29:20Z) At 2603.11, replace “off-channel TWT scheduling support bit” with “Off-channel TWT Scheduling Support field”. At 2602.54, change "Off-channel Scheduling TWT Support field" to "Off-channel TWT Scheduling Support field". | ED2 | Motion ED2-270-05 | Ready for Motion | ED2: 2022-12-16 19:29:09Z - status set to: Ready for Motion ED2: 2022-12-16 19:20:25Z - status set to: More Work Required ED2: 2022-12-07 16:34:49Z - status set to: Ready for Motion ED2: 2022-11-15 12:08:59Z - status set to: Review: Further work is needed per the discussion on November 15, 2022. ED2: 2022-11-15 07:42:43Z - status set to: Review |  |  |  | 2022-12-16 19:31 | ED2
3062 | Hiroyuki Motozuka | 270 | 2 | B.4.24.1 | 4792 | 30 | E | N | 4792 | 30 | B.4.24.1 |  | A | Edward Au | 22/2001r1 | 88 | The reference for DMG-M2 (Signaling of DMG operation) is incorrect. | Change the reference "9.4.2.127.7 (TDD Capability Information field(11ay))" to "9.4.2.128 (DMG Operation element)" | ACCEPTED (ED2: 2022-11-15 12:05:31Z) | ED2 | 20221117 Approved | Resolved | ED2: 2022-11-15 12:05:30Z - status set to: Ready for Motion ED2: 2022-11-15 07:30:30Z - status set to: Review |  |  |  | 2022-11-17 19:25 | EDITOR
3065 | John Coffey | 270 | 2 | 30.1 | 4579 | 36 | E | Y | 4579 | 36 | 30.1 |  | A | Edward Au | 22/2001r1 | 88 | Missing period at end of sentence. | Add period. | ACCEPTED (ED2: 2022-11-15 12:07:07Z) | ED2 | 20221117 Approved | Resolved | ED2: 2022-11-15 12:07:08Z - status set to: Ready for Motion ED2: 2022-11-15 07:44:25Z - status set to: Review |  |  |  | 2022-11-17 19:25 | EDITOR
3081 | John Wullert | 270 | 2 | 4.3.5.1 | 259 | 12 | T | N | 259 | 12 | 4.3.5.1 |  | V |  |  | 88 | The first, two-sentence paragragh in clause 4.3.5.1 seems out of place. According to the clause and parent clause headings, the text should provide an overview of Distribution System concepts, and this initial paragraph talks about PHY limitations and coverage. | Delete these two sentences. | REVISED (GEN: 2022-11-16 09:38:07Z) Merge the first two paragraphs of 4.3.5.1. | ED2 | 20221117 Approved | Resolved | GEN: 2022-11-16 09:38:11Z - status set to: Ready for Motion |  |  |  | 2022-11-17 19:25 | EDITOR
3085 | John Wullert | 270 | 2 | 9.3.3.2 | 694 | 15 | G | N | 694 | 15 | 9.3.3.2 |  | A |  |  | 88 | Note text associated with Channel Switch Announcement is unclear, where it only seems to assign a value to one of two options. (Other Notes in same table assign value for each variable.) | Revise to "The Channel Switch Announcement element is optionally present if dot11SpectrumManagementRequired is true or dot11ExtendedChannelSwitchActivated is true" | ACCEPTED (GEN: 2022-11-16 09:37:24Z) | ED2 | 20221117 Approved | Resolved | GEN: 2022-11-16 09:37:29Z - status set to: Ready for Motion |  |  |  | 2022-11-17 19:25 | EDITOR
3087 | John Wullert | 270 | 2 | 9.3.3.11 | 721 | 43 | G | N | 721 | 43 | 9.3.3.11 |  | A |  |  | 88 | Note text associated with Channel Switch Announcement is unclear, where it only seems to assign a value to one of two variables. (Other Notes in same table assign value for each variable.) | Revise to "The Channel Switch Announcement element is optionally present if dot11SpectrumManagementRequired is true or dot11ExtendedChannelSwitchActivated is true" | ACCEPTED (GEN: 2022-11-16 09:36:18Z) | ED2 | 20221117 Approved | Resolved | GEN: 2022-11-16 09:36:21Z - status set to: Ready for Motion |  |  |  | 2022-11-17 19:25 | EDITOR
3111 | Joseph Levy | 270 | 2 |  | 3043 | 48 | E | N | 3043 | 48 |  |  | V | Mark Rison |  |  | Key Replay Counter "field" is missing its noun in multiple locations. | Replace: "Verify that the Key Replay Counter has not yet been seen before, ..." with: "Verify that the Key Replay Counter field value has not yet been seen before, ..." Also the following similar changes should be made: At 3044.15 Replace "The Key Replay Counter shall ..." with "The Key Replay Counter field shall ..." At 3044.44 Replace "Verify that the Key Replay Counter field value matches ..." with "Verify that the Key Replay Counter value matches ..." 3044.48 Replace "...new Mesh Group Key Inform frame with a new Key Replay Counter value." with "... new Mesh Group Key Inform frame with a new Key Replay Counter field value." At 3044.51 Replace ".... a new Mesh Group Key Inform frame with a new Key Replay Counter value." with ".... a new Mesh Group Key Inform frame with a new Key Replay Counter field value." | Original text at 3043.48 in D2.0: Change “the Key Replay Counter” with “the Key Replay Counter field”. Original text at 3044.15 in D2.0: Change “The Key Replay Counter” with “The Key Replay Counter field”. Original text at 3044.44 in D2.0: Change “the Key Replay Counter value” with “the Key Replay Counter field”. Original text at 3044.48 in D2.0: Change “a new Key Replay Counter value” with “a new Key Replay Counter field”. Original text at 3044.51 in D2.0: Change “a new Key Replay Counter value” with “a new Key Replay Counter field”. | ED2 | Motion ED2-270-05 | Ready for Motion | ED2: 2022-12-16 19:28:17Z - status set to: Ready for Motion ED2: 2022-12-16 19:19:49Z - status set to: More Work Required ED2: 2022-12-07 16:50:18Z - status set to: Ready for Motion ED2: 2022-12-07 14:21:17Z - status set to: Review |  |  |  | 2022-12-16 19:28 | ED2
3116 | Joseph Levy | 270 | 2 | 29.9.3 | 4568 | 35 | E | N | 4568 | 35 | 29.9.3 | [5 empty] | There are locations where the counters are referred to using the field name capitalization. This is not in line with the style of the 802.11 specification. Counters should use lower case names, Fields and elements using the term "Counter' in their name should be capitalized. | Replace "A WUR AP shall maintain a BSS Parameter Update Counter. The WUR AP shall increase the BSS Parameter Update Counter if a critical update ..." with "A WUR AP shall maintain a BSS parameter update counter. The WUR AP shall increase the BSS parameter update counter if a critical update ..." Also the following similar changes should be made: 4568.58 Replace "... the current value of the BSS Parameter Update Counter in ..." with "... the current value of the BSS parameter update counter in ..." 4568.60 Replace "... if the Counter value in the WUR Operation element ..." with "... if the Counter subfield value in the WUR Operation element ..." 4568.63 Replace "A WUR non-AP STA shall maintain a BSS Parameter Update Counter. The WUR non-AP STA shall update its BSS Parameter Update Counter to the Counter subfield contained in the latest WUR Operation element ..." with "A WUR non-AP STA shall maintain a BSS parameter update counter. The WUR non-AP STA shall update its BSS parameter update counter to the Counter subfield contained in the latest WUR Operation element ..." 4570.4 Replace "... different from its BSS Parameter Update Counter shall follow ..." with "... different from its BSS parameter update counter shall follow ..." |  | ED2 | [6 empty] | 2022-11-12 16:38 | EDITOR
3117 | Joseph Levy | 270 | 2 | B.4.4.1 | 4639 | 56 | E | N | 4639 | 56 | B.4.4.1 | [5 empty] | There are locations where the counters are referred to using the field name capitalization. This is not in line with the style of the 802.11 specification. Counters should use lower case names, Fields and elements using the term "Counter' in their name should be capitalized. | Replace: "(#1912)Counter Mode with cipherblock chaining message authentication code protocol (CCMP) data confidentiality protocol using CCMP-128" With: "(#1912)Counter mode with cipherblock chaining message authentication code protocol (CCMP) data confidentiality protocol using CCMP-128" Also the following similar changes should be made: 4640.30 Replace: "(#1912)Galois/Counter Mode protocol (GCMP)" with "(#1912)Galois/counter mode protocol (GCMP)" |  | ED2 | [6 empty] | 2022-11-12 16:38 | EDITOR
3125 | Jouni Malinen | 270 | 2 | 12.2.4 | 2781 | 17 | E | Y | 2781 | 17 | 12.2.4 |  | A | Edward Au | 22/2001r1 | 88 | Missing space between words. | At P2781 L17, replace "anRSNA" with "an RSNA". | ACCEPTED (ED2: 2022-11-15 12:07:21Z) | ED2 | 20221117 Approved | Resolved | ED2: 2022-11-15 12:07:23Z - status set to: Ready for Motion ED2: 2022-11-15 07:46:34Z - status set to: Review |  |  |  | 2022-11-17 19:25 | EDITOR
3127 | Jouni Malinen | 270 | 2 | 12.2.2 | 2780 | 42 | E | Y | 2780 | 42 | 12.2.2 |  | A | Edward Au | 22/2001r1 | 88 | The reference for the description of TKIP is pointing to an incorrect clause (CCMP). | At P2780 L42, replace "TKIP, described in 12.5.2" with "TKIP, described in 12.3.4" | ACCEPTED (ED2: 2022-11-15 12:07:38Z) | ED2 | 20221117 Approved | Resolved | ED2: 2022-11-15 12:07:35Z - status set to: Ready for Motion ED2: 2022-11-15 07:48:46Z - status set to: Review |  |  |  | 2022-11-17 19:25 | EDITOR
3132 | Jouni Malinen | 270 | 2 | 12.4.5.4 | 2820 | 61 | E | Y | 2820 | 61 | 12.4.5.4 |  | V | Edward Au | 22/2001r1 | 88 | PWE stands for "password element"; not "password identifier", | At P2820 L61, replace "password identifier (PWE)" with "password identifier". | REVISED (ED2: 2022-11-15 12:07:49Z) Incorporate the changes for CID 3132 as shown in https://mentor.ieee.org/802.11/dcn/22/11-22-2001-01-000m-proposed-resolution-for-miscellaneous-lb270-comments.docx | ED2 | 20221117 Approved | Resolved | ED2: 2022-11-15 12:08:00Z - status set to: Ready for Motion ED2: 2022-11-15 07:51:12Z - status set to: Review |  |  |  | 2022-11-17 19:25 | EDITOR
3135 | Jouni Malinen | 270 | 2 | 12.7.3 | 2910 | 24 | T | Y | 2910 | 24 | 12.7.3 |  | V |  |  | 88 | The recently added AKM 00-0F-AC:25 (FT/SAE with variable key length) made parsing of the first Authentication frame in the FT protocol case inconvenient since the AP receiving this frame may not have been part of the SAE authentication exchange with the non-AP STA and as such, it does not yet know which finite cyclic group was used with SAE and as such, does not know the length of the MIC field. However, this AP needs to be able to parse the FTE in this frame and, in particular, find the subelements from the FTE after the variable length MIC field. This cannot be done robustly without knowing the length of the MIC field (and the 8 octet length of the likely first subelement makes this even more inconvenient since that happens to be the difference between possible MIC field lengths). | Specify the lengtg of the MIC field in the FTE for the new AKM: - at P1037 L8 (Figure 9-418), add a new subfield "MIC Length" for B1..B3 (3 bits), leaving B4..B7 (4 bits) as the new size for Reserved - at P1036 L18 add a new paragraph: "The MIC Length subfield defines the length of the MIC field when using AKM 00-0F-AC:25. The value of this subfield is not applicable for other AKMs. Table 9-<new> defines the available values for this." - at P1036 L18 add a new table "Table 9-<new>--MIC length" with columns "Value" and "MIC field length in octets" and values "0 = 16 or not applicable", "1 = 24", "2 = 32", "3-7 = Reserved". | REVISED (SEC: 2022-11-14 09:48:40Z) Incorporate the changes in https://mentor.ieee.org/802.11/dcn/22/11-22-1991-02-000m-proposed-resolutions-to-some-lb270-comments.docx, which implements the changes proposed by the commenter. | ED2 | 20221117 Approved | Resolved | SEC: 2022-11-14 09:59:01Z - status set to: Ready for Motion |  |  |  | 2022-11-17 19:25 | EDITOR
3142 | Kazuto Yano | 270 | 2 | 10.23.2.12.1 | 1907 | 50 | E | N | 1907 | 50 | 10.23.2.12.1 |  | A | Edward Au | 22/2001r1 | 88 | "Thhe" must be "The". | Please fix the typo. | ACCEPTED (ED2: 2022-11-15 12:08:12Z) | ED2 | 20221117 Approved | Resolved | ED2: 2022-11-15 12:08:09Z - status set to: Ready for Motion ED2: 2022-11-15 07:52:54Z - status set to: Review |  |  |  | 2022-11-17 19:25 | EDITOR
3188 | Mark RISON | 270 | 2 | B.4 | 4662 | 60 | E | Y | 4662 | 60 | B.4 |  | V | Edward Au | 22/2001r1 | 88 | FR45 "Clause 9" is not very precise | Give a more precise xref | REVISED (ED2: 2022-11-15 12:08:25Z) At 4662.60, replace “Clause 9 (Frame formats)” with “9.3.4.3 (S1G Beacon frame format), 11.1.3 (Maintaining synchronization)”. | ED2 | 20221117 Approved | Resolved | ED2: 2022-11-15 12:08:28Z - status set to: Ready for Motion ED2: 2022-11-15 07:59:35Z - status set to: Review |  |  |  | 2022-11-17 19:25 | EDITOR
3197 | Mark RISON | 270 | 2 | 11 |  |  | E | Y |  |  | 11 |  | A | Edward Au | 22/2001r1 | 88 | "ESS Detection Interval" should be "ESS detection interval" when not followed by "field" | Change at 2566.55, 2570.37, 2576.36 | ACCEPTED (ED2: 2022-11-15 12:06:46Z) | ED2 | 20221117 Approved | Resolved | ED2: 2022-11-15 12:06:45Z - status set to: Ready for Motion ED2: 2022-11-15 08:03:28Z - status set to: Review |  |  |  | 2022-11-17 19:25 | EDITOR
3198 | Mark RISON | 270 | 2 | 11.21.4.1 | 2574 | 22 | E | Y | 2574 | 22 | 11.21.4.1 |  | A | Edward Au | 22/2001r1 | 88 | What is "the essDetectionInterval value"? | Change to "the ESS detection interval" | ACCEPTED (ED2: 2022-11-15 12:05:51Z) | ED2 | 20221117 Approved | Resolved | ED2: 2022-11-15 12:05:49Z - status set to: Ready for Motion ED2: 2022-11-15 07:36:16Z - status set to: Review |  |  |  | 2022-11-17 19:25 | EDITOR
3200 | Mark RISON | 270 | 2 | C.3 |  |  | E | Y |  |  | C.3 |  |  | Mark Rison |  |  | "The default is" should not appear in the DESCRIPTION, but in a DEFVAL | As it says in the comment |  | ED2 | Submission Required | Submission Required | ED2: 2022-11-25 13:15:46Z - status set to: Submission Required |  |  |  | 2022-11-25 13:16 | ED2
3208 | Mark RISON | 270 | 2 | 12.4.8.1 | 2827 | 37 | E | Y | 2827 | 37 | 12.4.8.1 | [5 empty] | "Zero(Rc)" should be "zero(Rc)" in Figure 12-15--SAE finite state machine. Ditto "Big(" should be lowercase | As it says in the comment |  | ED2 | [6 empty] | 2022-11-12 16:38 | EDITOR
3210 | Mark RISON | 270 | 2 | AC | 5795 | 54 | E | Y | 5795 | 54 | AC |  | A | Edward Au | 22/2001r1 | 88 | "Example 3 in AC-2" should be "Example 3 in Table AC-2", and at 5796.61 "AC-2" should be "Table AC-2" | As it says in the comment | ACCEPTED (ED2: 2022-11-15 12:04:42Z) | ED2 | 20221117 Approved | Resolved | ED2: 2022-11-15 12:04:43Z - status set to: Ready for Motion ED2: 2022-11-15 02:16:49Z - status set to: Review |  |  |  | 2022-11-17 19:25 | EDITOR
3234 | Mark RISON | 270 | 2 | 12.7.2 | 2901 | 29 | E | Y | 2901 | 29 | 12.7.2 | [5 empty] | Material on behaviour on reception of an receives an EAPOL-Key request frame should be moved to the subclause on rekeying (12.6.21) | Move lines 29-58 on page 2901 to the end of 12.6.21 |  | ED2 | [6 empty] | 2022-11-12 16:38 | EDITOR
3241 | Mark RISON | 270 | 2 | 12.7.8.4 |  |  | E | Y |  |  | 12.7.8.4 | [5 empty] | RSNE fields should be referred to by their name, not by paraphrasing | As it says in the comment |  | ED2 | [6 empty] | 2022-11-12 16:38 | EDITOR
3279 | Mark RISON | 270 | 2 | 30 |  |  | E | Y |  |  | 30 |  | A | Edward Au | 22/2001r1 | 88 | "using contiguous 13 subcarriers" should be "using 13 contiguous subcarriers" (2x) | Change at 4579.55 and 4603.60 | ACCEPTED (ED2: 2022-11-15 12:04:22Z) | ED2 | 20221117 Approved | Resolved | ED2: 2022-11-15 12:04:24Z - status set to: Ready for Motion ED2: 2022-11-15 02:13:46Z - status set to: Review |  |  |  | 2022-11-17 19:25 | EDITOR
3295 | Mark RISON | 270 | 2 | 11.20.3 | 2555 | 29 | E | Y | 2555 | 29 | 11.20.3 | [5 empty] | MLME-DLSSETUP in Figure 11-35--TDLS direct-link establishment should be MLME-TDLSSETUP | As it says in the comment |  | ED2 | [6 empty] | 2022-11-12 16:38 | EDITOR
3382 | Mark RISON | 270 | 2 | 3.2 |  |  | T | Y |  |  | 3.2 |  | V |  |  | 88 | It would be helpful to have a definition of SM Power Save in 3.2 | Add "spatial multiplexing (SM) power save: A mode of operation that allows a station (STA) to listen using one radio frequency (RF) chain some of the time, then switch on additional RF chains for subsequent single-user multiple input, multiple output (SU-MIMO) operation." | REVISED (GEN: 2022-11-16 09:48:14Z) Add "spatial multiplexing (SM) power save: A mode of operation that allows a station (STA) to listen using one radio frequency (RF) chain, then switch on additional RF chains for subsequent single-user multiple input, multiple output (SU-MIMO) operation." | ED2 | 20221117 Approved | Resolved | GEN: 2022-11-16 09:48:01Z - status set to: Ready for Motion |  |  |  | 2022-11-17 19:25 | EDITOR
3403 | Mark RISON | 270 | 2 | 11.12 |  |  | E | Y |  |  | 11.12 |  | A | Edward Au | 22/2001r1 | 88 | "matches its own" -- delete the "own" | Delete "own" at 2535.27, 3679.52, 3681.2, 1915.10, 2535.21/43, 3024.4, 3074.54/56 | ACCEPTED (ED2: 2022-11-15 12:03:37Z) | ED2 | 20221117 Approved | Resolved | ED2: 2022-11-15 12:03:39Z - status set to: Ready for Motion ED2: 2022-11-15 02:11:07Z - status set to: Review |  |  |  | 2022-11-17 19:25 | EDITOR
3413 | Mark RISON | 270 | 2 | 27.3.11.8.5 | 4095 | 31 | E | Y | 4095 | 31 | 27.3.11.8.5 |  |  | Edward Au | 22/2063r3 |  | "NSD is 52 and 26 if the HE-SIG-B DCM field in the HE-SIG-A field is 0 and 1, respectively." should be or ... or | As it says in the comment |  | ED2 | More Work Required | More Work Required | ED2: 2022-12-07 20:34:04Z - status set to: More Work Required ED2: 2022-12-02 17:29:04Z - status set to: Review ED2: 2022-11-25 21:25:57Z - status set to: Review |  |  |  | 2022-12-07 20:34 | ED2
3418 | Mark RISON | 270 | 2 | 6 |  |  | T | Y |  |  | 6 |  | V |  |  | 88 | Why is the valid range for NAVSyncDelay N/A? | Change "N/A" to ">= 1" (with a >= glyph) at 411.15 and 480.16 | REVISED (GEN: 2022-11-16 09:49:56Z) – Change “N/A” to “>=0’ (with a >= glyph) at 411.15 and 480.16. | ED2 | 20221117 Approved | Resolved | GEN: 2022-11-16 09:50:02Z - status set to: Ready for Motion |  |  |  | 2022-11-17 19:25 | EDITOR
3452 | Mark RISON | 270 | 2 | E.2.7 | 5523 | 1 | E | Y | 5523 | 1 | E.2.7 |  | A | Edward Au | 22/2001r1 | 88 | "Regulatory Client EIRP PSD" should be lowercase client | As it says in the comment | ACCEPTED (ED2: 2022-11-15 12:05:01Z) | ED2 | 20221117 Approved | Resolved | ED2: 2022-11-15 12:05:02Z - status set to: Ready for Motion ED2: 2022-11-15 02:25:34Z - status set to: Review |  |  |  | 2022-11-17 19:25 | EDITOR
3461 | Mark RISON | 270 | 2 | 11.20.6.1 | 2560 | 36 | E | Y | 2560 | 36 | 11.20.6.1 | [5 empty] | The "DL"s in Figure 11-35--Events occurring for a TDLS direct link channel switch(#1356) are confusing because they don't mean downlink, they mean direct link | Change to "direct link"s at lines 36 and 52 |  | ED2 | [6 empty] | 2022-11-12 16:38 | EDITOR
3506 | Mark RISON | 270 | 2 | 1.5 |  |  | E | Y |  |  | 1.5 |  |  | Edward Au | 22/2001r3 |  | L() is not very descriptive (cf. Truncate-n()) | Rename to Slice(). I can provide a list of locations |  | ED2 | More Work Required | Review | ED2: 2022-12-07 16:35:10Z - status set to: Review. Further work is needed per the discussion on December 7, 2022. ED2: 2022-12-02 17:13:03Z - status set to: Review ED2: 2022-11-25 13:55:49Z - status set to: Review |  |  |  | 2022-12-07 16:36 | ED2
3507 | Mark RISON | 270 | 2 | 1.5 |  |  | E | Y |  |  | 1.5 |  |  | Edward Au | 22/2001r3 |  | L() is not very descriptive (cf. Truncate-n()) | Provide a cross-reference to an RFC or similar where L() is defined as the slice operator |  | ED2 | More Work Required | More Work Required | ED2: 2022-12-07 16:35:37Z - status set to: Review. Further work is needed per the discussion on December 7, 2022. ED2: 2022-12-02 17:13:18Z - status set to: More Work Required ED2: 2022-11-25 13:56:46Z - status set to: Review |  |  |  | 2022-12-07 16:36 | ED2
3520 | Mark RISON | 270 | 2 | 12 |  |  | T | Y |  |  | 12 |  | V |  |  | 88 | CID 1881 was marked ready for motion, but then subsequently incorrectly changed from REVISED to REJECTED | Implement the changes agreed for CID 1881 | REVISED (SEC: 2022-11-14 09:39:57Z) Make the changes shown under “Proposed changes” for CID 1881 in https://mentor.ieee.org/802.11/dcn/22/11-22-0353-02-000m-resolutions-for-some-comments-on-11me-d1-0-lb258.docx, which make the changes proposed by the commenter, with minor editorial tweaks. Note: This comment CID 1881 in the previous LB was incorrectly marked as rejected and the previously approved changes are incorporated here. | ED2 | 20221117 Approved | Resolved | SEC: 2022-11-14 09:39:57Z - status set to: Ready for Motion |  |  |  | 2022-12-07 16:37 | ED2
3544 | Mark RISON | 270 | 2 | 20 |  |  | E | Y |  |  | 20 |  |  | Mark Rison |  |  | "header field[s]" in Clause 20 and children clauses should be "Header field" | I can provide locations |  | ED2 | Submission Required | Submission Required | ED2: 2022-11-25 14:32:52Z - status set to: Submission Required |  |  |  | 2022-11-25 14:40 | ED2
3576 | Mark RISON | 270 | 2 | 1.4 |  |  | E | Y |  |  | 1.4 | [5 empty] | "beacon report" should be "Beacon report" -- and maybe for other kinds of report too (e.g. "neighbor report") | Refer to <x> Request/Report with an uppercase R, per the conventions in 1.4 and 9.4.2.21.1 |  | ED2 | [6 empty] | 2022-11-12 16:38 | EDITOR
3630 | Mark RISON | 270 | 2 |  |  |  | E | Y | [8 empty] | Figure 19-27--PHY receive state machine and Figure 23-53--PHY receive state machine and Figure 21-37--PHY receive state machine and Figure 27-63--PHY receive state machine if midambles are not present have >1 "End of Wait" states | Number each of the End of Wait states, so no state appears twice |  | ED2 | [6 empty] | 2022-11-12 16:40 | EDITOR
3640 | Mark RISON | 270 | 2 | 12.7 |  |  | E | Y |  |  | 12.7 | [5 empty] | There are various editorial issues in 12.7.6 and 12.7.7 and 12.7.4 | Make the changes shown under "Proposed changes" under CIDs 179/180 in 21/0829 (latest revision) |  | ED2 | [6 empty] | 2022-11-12 16:38 | EDITOR
3659 | Mark RISON | 270 | 2 |  |  |  | E | Y | [5 empty] | Mark Rison |  |  | Sometimes fields described as "(optional)" in their defining figure don't say ", if present," in their description | I ought to be able to provide locations |  | ED2 | Submission Required | Submission Required | ED2: 2022-11-25 13:59:53Z - status set to: Submission Required |  |  |  | 2022-11-25 14:00 | ED2
3661 | Mark RISON | 270 | 2 | 12 |  |  | E | Y |  |  | 12 | [5 empty] | Figure 12-23--CCMP decapsulation block diagram is still fuzzy | De-fuzz it (or take the GCMP one and adapt it for GCMP) |  | ED2 | [6 empty] | 2022-11-12 16:38 | EDITOR
3667 | Mark RISON | 270 | 2 |  |  |  | E | Y | [5 empty] | Mark Rison |  |  | Don't use hyphens for minuses | Change hyphens that represent subtraction to a minus glyph |  | ED2 | Submission Required | Submission Required | ED2: 2022-11-25 14:01:52Z - status set to: Submission Required |  |  |  | 2022-11-25 14:02 | ED2
3668 | Mark RISON | 270 | 2 |  |  |  | E | Y | [5 empty] | Mark Rison |  |  | Figures should not have xrefs unless they will automatically be updated when the xref number changes, otherwise there will be spec rot | Either remove xrefs from figures and make the xref in the body text that refers to the figure, or find a way to include real xrefs in figures (maybe can overlay a text box with the xref?) |  | ED2 | Submission Required | Submission Required | ED2: 2022-11-25 14:02:09Z - status set to: Submission Required |  |  |  | 2022-11-25 14:02 | ED2
3677 | Mark RISON | 270 | 2 | B.4 |  |  | E | Y |  |  | B.4 |  |  | Mark Rison |  |  | Some of the PICS selectors have unnecessary outside parens | I can provide locations |  | ED2 | Submission Required | Submission Required | ED2: 2022-11-25 13:14:02Z - status set to: Submission Required |  |  |  | 2022-11-25 13:16 | ED2
3679 | Mark RISON | 270 | 2 | C.3 |  |  | E | Y |  |  | C.3 |  |  | Mark Rison |  |  | Things like "See 11.22.2.4 (Peer-to-peer link" should not be in DESCRIPTIONs unless there is a REFERENCE line to give the revision. Actually should be entirely in the REFERENCE line | Move all xrefs to REFERENCE lines |  | ED2 | Submission Required | Submission Required | ED2: 2022-11-25 13:14:34Z - status set to: Submission Required |  |  |  | 2022-11-25 13:17 | ED2
3681 | Mark RISON | 270 | 2 |  |  |  | E | Y | [5 empty] | Mark Rison |  |  | "vendor-specific element" (case-insensitively) should be "Vendor Specific element" and otherwise "vendor-specific" should be "vendor specific" (case-preservingly) | I can provide locations |  | ED2 | Submission Required | Submission Required | ED2: 2022-11-25 14:02:23Z - status set to: Submission Required |  |  |  | 2022-11-25 14:02 | ED2
3683 | Mark RISON | 270 | 2 |  |  |  | E | Y | [8 empty] | "drop" is not clear in the context of a frame | Use "discard" for frames, and "ignore" for everything else |  | ED2 | [6 empty] | 2022-11-12 16:40 | EDITOR
3686 | Mark RISON | 270 | 2 | 12 |  |  | E | Y |  |  | 12 | [5 empty] | "Length", including in "KDF-Hash-Length", in 12.7.1.6.3 PMK-R0 should be italic, also in 12.7.1.6.4 PMK-R1, 12.7.1.6.5 PTK, 12.7.8.2 TPK handshake; in .6.4 and .8.2 Length should be explicitly defined too; in .8.2. "that uses Hash to generate a key whose length is TK_bits + 128" should be "using the hash algorithm identified by the AKM suite selector (see Table 9-151 (AKM suite selectors))" | As it says in the comment |  | ED2 | [6 empty] | 2022-11-12 16:38 | EDITOR
3693 | Mark RISON | 270 | 2 |  |  |  | E | Y | [5 empty] | Mark Rison |  |  | The whole "field" v. "subfield" thing is just a big inconsistent mess (e.g. in the subclause for Reduced Neighbor Report element some things in the Neighbor AP Information field are fields and some are subfields, and the TBTT Information Set [sub!]field contains one or more TBTT Information fields). There is no value in trying to make the distinction, because (a) the distinction is not made reliably (b) it's not possible to make the distinction, because some things are subfields of X but are also the field that contains subfield Y (c) it doesn't tell you anything of particular significance | Change "subfield" to "field" throughout (I can provide locations) |  | ED2 | More Work Required | More Work Required | ED2: 2022-12-07 16:48:32Z - status set to: More Work Required; reassaign to Mark Rison. ED2: 2022-12-07 13:30:20Z - status set to: Review |  |  |  | 2022-12-07 20:34 | ED2
3700 | Mark RISON | 270 | 2 |  |  |  | E | Y | [5 empty] | Mark Rison |  |  | The use of "or both" (~77x) implies that uses of "or" without and "or both" are exclusive, but this is not the case | Delete "or both" throughout (I can provide locations) |  | ED2 | Submission Required | Submission Required | ED2: 2022-11-25 14:03:35Z - status set to: Submission Required |  |  |  | 2022-11-25 14:04 | ED2
3701 | Mark RISON | 270 | 2 |  |  |  | E | Y | [5 empty] | Mark Rison |  |  | Should not have a comma before a modal verb (when not the end of a subclause or list) | Delete the comma in ", may" or ", should" or ", shall", except where this comma delineates the end of a (grammatical) subclause or list. I can provide locations |  | ED2 | Submission Required | Submission Required | ED2: 2022-11-25 14:03:51Z - status set to: Submission Required |  |  |  | 2022-11-25 14:04 | ED2
3705 | Mark RISON | 270 | 2 |  |  |  | E | Y | [5 empty] | Mark Rison |  |  | There are many editorial issues with the description of subelements | Fix as suggested in 19/0856 |  | ED2 | Submission Required | Submission Required | ED2: 2022-11-25 14:33:24Z - status set to: Submission Required |  |  |  | 2022-11-25 14:41 | ED2
3723 | Mark RISON | 270 | 2 |  |  |  | E | Y | [5 empty] | Mark Rison |  |  | "Key ID" should be "key ID" when not at the start of a sentence etc. and not followed by "field" etc. | I can provide locations |  | ED2 | Submission Required | Submission Required | ED2: 2022-11-25 14:33:54Z - status set to: Submission Required |  |  |  | 2022-11-25 14:41 | ED2
3724 | Mark RISON | 270 | 2 |  |  |  | E | Y | [8 empty] | Some field/frame figures' boxes have overhangs or missing corner bits, e.g. Figure 9-2 and Table 9-5 | Get a joiner to make more accurate joins |  | ED2 | [6 empty] | 2022-11-12 16:40 | EDITOR
3725 | Mark RISON | 270 | 2 |  |  |  | E | Y | [8 empty] | "Channel Center Frequency Segment 0" is confusing because it actually gives a channel number not a channel frequency (which requires the channel starting factor to be known) | Rename to "Channel Center Index Segment 0" |  | ED2 | [6 empty] | 2022-11-12 16:40 | EDITOR
3726 | Mark RISON | 270 | 2 | C.3 |  |  | E | Y |  |  | C.3 |  |  | Mark Rison |  |  | Even within C.3 there is confusion as to whether MIB things are variables or attributes | Refer to them as MIB attributes throughout |  | ED2 | More Work Required | More Work Required | ED2: 2022-12-07 16:41:16Z - status set to: More Work Required; reassigned to Mark Rison. ED2: 2022-11-28 17:05:51Z - status set to: Review |  |  |  | 2022-12-07 16:42 | ED2
3727 | Mark RISON | 270 | 2 | 13.9.3.1 | 2997 | 41 | E | Y | 2997 | 41 | 13.9.3.1 | [5 empty] | "PTK= Calc FT-PTK ()" should be "PTK = Calc FT-PTK ()" (space before =) | Add space before = |  | ED2 | [6 empty] | 2022-11-12 16:38 | EDITOR
3733 | Mark RISON | 270 | 2 |  |  |  | E | Y | [5 empty] | Mark Rison |  |  | Delete "(bit <n>)" when it just duplicates info already in a figure or table | I can provide locations |  | ED2 | Submission Required | Submission Required | ED2: 2022-11-25 14:34:23Z - status set to: Submission Required |  |  |  | 2022-11-25 14:41 | ED2
3735 | Mark RISON | 270 | 2 |  |  |  | E | Y | [5 empty] | Mark Rison |  |  | "Classifier Parameter" is sometimes spuriously capitalised. Also "the Classifier.". Also "Classifier Type" and words after it inconsistent too | I can provide locations |  | ED2 | Submission Required | Submission Required | ED2: 2022-11-25 14:34:34Z - status set to: Submission Required |  |  |  | 2022-11-25 14:41 | ED2
3766 | Robert Stacey | 270 | 2 | 3.2 | 196 | 6 | T | N | 196 | 6 | 3.2 |  | V |  |  | 89 | This definition for "6 GHz band" it is not very intuitive and excludes channel 2 (operating class 136). | Define "6 GHz band" in a more intuitive way: e.g., "The frequency band that includes channels with a channel center frequency between 5.95 GHz and 7.125 GHz." | REVISED (GEN: 2022-11-16 09:46:37Z) Redefine "6 GHz band" as " The frequency band between 5.925 GHz and 7.125 GHz”. | ED2 | 20221117 Approved | Resolved | GEN: 2022-11-17 09:51:36Z - status set to: Resolved GEN: 2022-11-17 09:46:02Z - Pulled from Motion #88 GEN: 2022-11-16 09:46:50Z - status set to: Ready for Motion |  |  |  | 2022-11-17 19:25 | EDITOR
3771 | Robert Stacey | 270 | 2 | 3.2 | 218 | 46 | T | N | 218 | 46 | 3.2 |  | V |  |  | 88 | The term "multicarrier signal" is used exactly twice; at 218.43 and 4579.54. It does not deserve an entry in 3.2 and as a more broadly used term would overlap with OFDM. | Delete the definition at 218.43. Replace "multicarrier signal" at 4579.54 with "signal constructed from multiple subcarriers". At 218.43, change "where the multicarrier signal" to "where a signal constructed from multiple subcarriers" (note definite article to indefinite article change). | REVISED (GEN: 2022-11-16 09:44:02Z) Delete the definition at 218.43. Replace "multicarrier signal" at 4579.54 with "signal constructed from multiple subcarriers" (first occurrence) and delete "multicarrier" in the second occurrence. At 218.43, change "where the multicarrier signal" to "where a signal constructed from multiple subcarriers" (note definite article to indefinite article change). | ED2 | 20221117 Approved | Resolved | GEN: 2022-11-16 09:44:38Z - status set to: Ready for Motion |  |  |  | 2022-11-17 19:25 | EDITOR