## Cover
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-22/2092r1
Venue Date: | December 2022
First Author: | Claudio da Silva
Subject: | D0.5 TBDs
Full Date: | 12/19/2022
Author(s): | Claudio da Silva
| Company: | Meta Platforms
Address
Phone:
Fax:
email:
Abstract: | This document contains a list of TBDs present in D0.5 and volunteers assigned to resolve them.
TBDs not resolved by the time TGbf approves the release of D1.0 will be removed from the draft and submitted as comments in the D1.0 Letter Ballot by the editor.

## TBDs
78.20 | Claudio/Steve | (Encoding of CW subfield is TBD) | 22/2115r0, motion pending
94.12 | Assaf | maximum supported Doppler
94.16 | Assaf | minimum supported Doppler resolution
103.36 | Assaf | DMG Sensing Report element format
109.7 | Assaf | Axis #1, #2, #3 and #4 subfields
109.23 | Assaf | Beam Index is defined in TBD.
113.1 | Assaf | The Report Type subfield is defined in TBD (DMG)
124.19 | Solomon | SBP Termination frame
124.21
124.39
148.41 | Cheng | The Dialog Token field in a TBD frame may… | 22/2051r2, motion 215
149.16 | Naren | Order TF/NDPA sounding
176.30 | Assaf | Sensing Instance SN
177.19 | Ning | DMG Sensing Request frame, coordinated monostatic
177.28 | Ning | Monostatic PPDU
180.3 | Solomon | DMG sensing measurement setup termination | 22/2142r1, motion pending
180.8 | Solomon | DMG sensing session termination | 22/2142r1, motion pending