## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-23/0834r7
Venue Date: | July 2023
First Author: | Emily Qi (Intel Corporation)
Subject: | REVme WG LB273 EDITOR1 ad-hoc Comments
Full Date: | 2023-07-13
Author(s): | Name(s) | Emily Qi
| Company | Intel Corporation
Address
Phone:
Fax:
| email: | emily.h.qi@intel.com
Abstract:
|  |  | Tab Name | Number | Description
|  |  | All Comments (for EDITOR1 ad hoc) | 71 | All LB273 editorial comments in ED1 adhoc
|  |  | Trivial Editorial Comments | 27 | Trivial editorial comments, ready for motion.
|  |  | Motion-EDITOR1-3A | 17 | Reviewed in the TGme teleconference in June. Ready for motion.
|  |  | Motion-EDITOR1-3B | 9 | Reviewed in the TGme teleconference in June. Ready for motion
|  |  | Motion-EDITOR1-3C | 6 | Reviewed in the July Plenary by the end of Wednesday. Ready for motion
|  |  | Motion-EDITOR1-3D | 7 | Reviewed in the July Plenary Thursday AM2. Ready for motion
|  |  | Submission Required | 3
Review - A comment with a proposed resolution that could be considered by the TG and gives clear direction to Editors on the implementation of the proposed change.
Discuss - A comment with a proposed resolution that gives clear direction to Editors on the implementation of the proposed change, but looks as if it needs discussion in the group (e.g. the change doesn't look right or may be controversial)
Submission Required - A comment with a proposed resolution that does not give clear direction to the Editors on the implementation of the proposed change. (i.e. someone has to do work to prepare a contribution for the TG to consider). An assignee, typically the commenter, needs to provide a contribution.
More Work Required - A comment that the TG has reviewed where there was no agreement on a resolution. For these comments, someone is assigned to do more work on the proposed resolution and to prepare a contribution. A date will be associated with the CID for follow-up with the TG.
This document contains comments in the "EDITOR1 ad hoc" group, submitted on REVme WG LB273 on REVme D3.0.

## Revision History
Revision | Date | Description
0 | 2023-05-14 | 71 comments assigned to Editor1 ad-hoc from LB273 on Draft 3.0 and added a new tab "Trivial Editorial Comments".
1 | 2023-05-17 | Added CID 4124 and updated CID 4088 in the tab "Trivial Editorial Comments".
2 | 2023-06-14 | Added a tab for "Motion-EDITOR1-3A".
3 | 2023-06-15 | updated CID 4364 with additional changes.
4 | 2023-06-15 | Updated CID 4216
5 | 2023-07-09 | Added a tab for "Motion-EDITOR1-3B" for the ready for motion comments in June.
6 | 2023-07-12 | Added a tab for "Motion-EDITOR1-3C" for the ready for motion comments by the end of Wednesday.
7 | 2023-07-13 | Added tabs for "Motion-EDITOR1-3D" and "Submission Required"

## Submission Required
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4208 | Mark RISON | 273 | 3 | 10.25 |  |  | E | N |  |  | 10.25 |  |  | Mark Rison |  |  | 10.25 and 11.5 sometimes use "set up" and sometimes use "establish". It would be better to use a single term | As it says in the comment [needs direction] |  | ED1 | Submission Required | Submission Required | ED1: 2023-07-13 10:10:19Z - status set to: Submission Required ED1: 2023-06-02 14:23:32Z - status set to: More Work Required ED1: 2023-06-02 14:23:14Z - commenter decided to go with establish. ED1: 2023-05-27 00:22:06Z - status set to: Submission Required ED1: 2023-05-12 23:54:06Z - status set to: Discuss |  |  |  | 2023-07-13 10:11 | ED1
4217 | Mark RISON | 273 | 3 | 9 |  |  | E | N |  |  | 9 |  |  | Mark RISON |  |  | "query response" v "Query Response" | Should be lowercase if not name of field etc. |  | ED1 | Submission Required | Submission Required | ED1: 2023-05-12 23:55:44Z - status set to: Submission Required |  |  |  | 2023-07-13 10:11 | ED1
4242 | Mark RISON | 273 | 3 | 3 |  |  | E | N |  |  | 3 |  |  | Mark RISON |  |  | We should only have one abbreviation for each item in Clause 3 (see 22/1993 for the instances and counts) | As it says in the comment [confirm direction] |  | ED1 | Submission Required | Submission Required | ED1: 2023-05-27 00:21:41Z - status set to: Submission Required ED1: 2023-05-12 23:58:47Z - status set to: Discuss |  |  |  | 2023-07-13 10:11 | ED1

## Motion-EDITOR1-3D
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4199 | Mark RISON | 273 | 3 | 9.6 |  |  | E | N |  |  | 9.6 |  | V | Mark Rison |  |  | There are 7 "Action field is set"s in 9.6 that should just be "The <blah> Action field is defined in 9.6.<blah>.1." | As it says in the comment [I can provide locations if needed; confirm direction] | REVISED (ED1: 2023-07-13 10:02:19Z)- Make the changes shown under “Proposed changes” for CID 4199 in https://mentor.ieee.org/802.11/dcn/23/11-23-0933-05-000m-resolutions-for-some-comments-on-11me-d3-0-lb273.docx, which ensure that consistent wording is used throughout 9.6. | ED1 | Motion-EDITOR1-3D | Ready for Motion | ED1: 2023-07-13 10:02:30Z - status set to: Ready for Motion ED1: 2023-06-02 14:18:34Z - status set to: More Work Required ED1: 2023-05-27 00:22:16Z - status set to: Submission Required ED1: 2023-05-12 23:53:47Z - status set to: Discuss |  |  |  | 2023-07-13 10:03 | ED1
4201 | Mark RISON | 273 | 3 | 10 |  |  | E | N |  |  | 10 |  | V | Mark Rison |  |  | There are a few "successfully negotiated"s, which implies that the other "negotiated"s include unsuccessful negotiation | Delete "successfully" in each case [I can provide locations if needed; confirm direction] | REVISED (ED1: 2023-07-13 09:47:10Z) Revised. Delete “successfully”/”a successful” at: 1871.23: An AP may transmit an SPP A-MSDU for a GCR group address if it has successfully negotiated RSNA (re)associations with all associated STAs that have an active GCR agreement for this group address. 1953.43: (11ay)An EDMG STA that has successfully negotiated a block ack agreement shall obey the following rules as a recipient in addition to the rules specified in 10.25.6 (HT-immediate block ack extensions). 1954.1: (11ay)An EDMG STA that has successfully negotiated a block ack agreement shall obey the following rules as an originator in addition to rules specified in 10.25.6 (HT-immediate block ack extensions). 1973.62: A block ack agreement that is successfully negotiated between two PBAC STAs is a protected block ack agreement. 1974.1: A block ack agreement that is successfully negotiated between two STAs when either or both of the STAs is not a PBAC STA is a block ack agreement that is not a protected block ack agreement. 1974.10: A STA that has successfully negotiated a protected block ack agreement shall obey the following rule as a block ack originator in addition to rules specified in 10.25.6.7 (Originator’s behavior) and 10.25.6.8 (Maintaining block ack state at the originator): 1974.18: A STA that has successfully negotiated a protected block ack agreement shall obey the following rules for that agreement(#1014) as a block ack recipient in addition to rules specified from(#1014) 10.25.6.3 (Scoreboard context control during full-state operation) to 10.25.6.6 (Receive reordering buffer control operation): | ED1 | Motion-EDITOR1-3D | Ready for Motion | ED1: 2023-07-13 09:47:24Z - status set to: Ready for Motion ED1: 2023-06-02 14:21:51Z - status set to: More Work Required ED1: 2023-05-27 00:22:11Z - status set to: Submission Required ED1: 2023-05-12 23:53:58Z - status set to: Discuss therer were concerns about changes in clause 12 and 13. |  |  |  | 2023-07-13 09:48 | ED1
4303 | Mark RISON | 273 | 3 | 9 |  |  | E | N |  |  | 9 |  | V | Mark RISON |  |  | "Service period request (SPR) frame", "Sector sweep (SSW) frame", "Sector sweep feedback (SSW-Feedback) frame", "Sector sweep Ack (SSW-Ack) frame" -- frames should have just one name | As it says in the comment [confirm direction] | REVISED (ED1: 2023-07-13 09:59:30Z)- Make the changes shown under “Proposed changes” for CID 4303 in https://mentor.ieee.org/802.11/dcn/23/11-23-0933-05-000m-resolutions-for-some-comments-on-11me-d3-0-lb273.docx, which ensure that frames/fields related to SPR/SSW have only one name. | ED1 | Motion-EDITOR1-3D | Ready for Motion | ED1: 2023-07-13 09:51:48Z - status set to: Ready for Motion ED1: 2023-06-02 14:51:18Z - status set to: More Work Required ED1: 2023-05-27 00:21:26Z - status set to: Submission Required ED1: 2023-05-13 00:01:11Z - status set to: Discuss |  |  |  | 2023-07-13 10:01 | ED1
4318 | Mark RISON | 273 | 3 | 3.2 |  |  | E | N |  |  | 3.2 |  | J | Mark RISON |  |  | CID 3772: the improvements to "mask PPDU" definitions should be made for S1G, mass-market PHYs and DMG too | As it says in the comment | REJECTED (ED1: 2023-07-13 08:46:08Z)- Reject Reason: The remaining mask PPDU definitions in Clause 3.2 cannot be further simplified. | ED1 | Motion-EDITOR1-3D | Ready for Motion | ED1: 2023-07-13 08:46:34Z - status set to: Ready for Motion ED1: 2023-05-13 00:01:46Z - status set to: Submission Required |  |  |  | 2023-07-13 08:59 | ED1
4340 | Mark RISON | 273 | 3 | 3 |  |  | E | N |  |  | 3 |  | V | Mark Rison |  |  | Any frame names in definitions need to be lowercase in Clause 3, per CID 1630. E.g. "time priority Management frame:" should be "time priority management frame:" | As it says in the comment [confirm direction] | REVISED (ED1: 2023-07-13 09:21:09Z)- Lowercase the following in Clause 3, except the material in parentheses: mesh Data frame: non-high-throughput (non-HT) SIGNAL field (L-SIG) transmit opportunity (TXOP) protection: robust Action frame: robust Management frame: time priority Management frame: | ED1 | Motion-EDITOR1-3D | Ready for Motion | ED1: 2023-07-13 09:22:18Z - status set to: Ready for Motion ED1: 2023-06-02 14:52:42Z - status set to: More Work Required ED1: 2023-05-27 00:21:14Z - status set to: Submission Required ED1: 2023-05-13 00:02:43Z - status set to: Discuss |  |  |  | 2023-07-13 09:22 | ED1
4356 | Mark RISON | 273 | 3 | 9 |  |  | E | N |  |  | 9 |  | V | Mark Rison |  |  | Is the field "Comeback Delay" or "GAS Comeback Delay"? Also sometimes missing "frame" | As it says in the comment | REVISED (ED1: 2023-07-13 09:50:34Z) Make the changes shown under “Proposed changes” for CID 4356 in https://mentor.ieee.org/802.11/dcn/23/11-23-0933-05-000m-resolutions-for-some-comments-on-11me-d3-0-lb273.docx, which add “GAS” and “frame” where missing, and other minor editorial tweaks. | ED1 | Motion-EDITOR1-3D | Ready for Motion | ED1: 2023-07-13 09:50:45Z - status set to: Ready for Motion ED1: 2023-06-02 14:54:25Z - status set to: More Work Required ED1: 2023-05-27 00:20:56Z - status set to: Submission Required ED1: 2023-05-13 00:03:03Z - status set to: Discuss- there is no location. Assigned to the commenter for leading the discussion. |  |  |  | 2023-07-13 09:51 | ED1
4367 | Mark RISON | 273 | 3 | 9 |  |  | E | N |  |  | 9 |  | V | Mark RISON |  |  | The field is now called EOF/Tag but there are ~9 instances of "EOF (sub)field" | Add "/Tag" to the errant instances | REVISED (ED1: 2023-07-13 09:42:28Z)- Add “/Tag” after “EOF” at 206.57, 230.18, 1725.43, 1726.18, 1812.15, 1875.40, 1876.6/36, 1877.20, 3580.16. At 1726.1 change “The” to “The”. | ED1 | Motion-EDITOR1-3D | Ready for Motion | ED1: 2023-07-13 09:42:48Z - status set to: Ready for Motion ED1: 2023-05-13 00:10:30Z - status set to: Submission Required |  |  |  | 2023-07-13 09:43 | ED1

## Motion-EDITOR1-3C
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4008 | Abhishek Patil | 273 | 3 | 9.6 | 1531 | 10 | E | N | 1531 | 10 | 9.6 |  | J | Abhi PATIL |  |  | Tables in clause 9.6 describe the 'Action' field for each type of 'action' frame. However, the corresponding frames are several pages away. When reviewing content from different frames, it requires a lot of back-n-forth navigation. It will greatly help if each row under the 'Description' column provides a reference to the corresponding frame format (for example, in Table 9-431, for the row corresponding to value 0, update the Description text to say: "Spectrum Measurement Request (see 9.6.2.2 (Spectrum Measurement Request frame format))". This will be similar to how clause 9.4.2.1 provides reference to respective subclauses for each element listed in Table 9-128. | As in comment | REJECTED (ED1: 2023-07-10 15:50:46Z) - The comment was withdrawn by the commenter. | ED1 | Motion-EDITOR1-3C | Ready for Motion | ED1: 2023-07-10 15:52:07Z - status set to: Ready for Motion ED1: 2023-05-15 17:14:59Z - status set to: Submission Required ED1: 2023-05-12 23:40:11Z - status set to: Review |  |  |  | 2023-07-12 16:10 | ED1
4122 | Mark Hamilton | 273 | 3 | 9.4.2.231.1 | 1348 | 42 | E | Y | 1348 | 42 | 9.4.2.231.1 |  | V | Mark HAMILTON |  |  | Missing ".". Also, should there be a space? Misc other related typos. | P1348.42 has "PHY-CCA indication (IDLE)" (no ".", and a space). Add the dot, for sure. (Same thing at P1349.41.) The space seems to be inconsistent: P568.15 has space, P568.63 does not. Which should it be? (This applies to all the primitive types, "request, indication, response, confirm", which are all inconsistent.) Another issue: P2366.10 has "busy" instead of "BUSY". And, finally, P2768.30 has "PHY-CCA.INDICATION" ("indication" should be lower case). | REVISED (ED1: 2023-07-10 14:38:08Z)- Incorporate the changes in https://mentor.ieee.org/802.11/dcn/23/11-23-1059-01-000m-revme-cids-4270-4107-4114-4122.docx under (for) CID 4122. | ED1 | Motion-EDITOR1-3C | Ready for Motion | ED1: 2023-07-10 14:38:43Z - status set to: Ready for Motion ED1: 2023-05-26 21:49:54Z - status set to: More Work Required ED1: 2023-05-13 00:14:08Z - status set to: Review |  |  |  | 2023-07-12 16:10 | ED1
4219 | Mark RISON | 273 | 3 | 10.5 | 2285 | 30 | E | N | 2285 | 30 | 10.5 |  | V | Mark RISON |  |  | "include a Page Slice Number that matches its Page Slice Number and a page index that matches its Page index" has bogus capitalisation and missing "field"s | As it says in the comment [needs submission] | REVISED (ED1: 2023-07-12 10:28:57Z)- Revised. Change the para at the referenced location to: An S1G STA for which dot11PageSlicingImplemented is true shall process all received TIM elements that include a Page Slice Number field that matches its page slice number and a Page Index field that matches its page index At 2286.3/10/20, 2378.48/50 change “Page Slice Number” to “Page Slice Number field”. | ED1 | Motion-EDITOR1-3C | Ready for Motion | ED1: 2023-07-12 10:29:07Z - status set to: Ready for Motion ED1: 2023-05-15 17:19:43Z - status set to: Submission Required ED1: 2023-05-12 23:56:30Z - status set to: Review |  |  |  | 2023-07-12 16:10 | ED1
4220 | Mark RISON | 273 | 3 |  |  |  | T | N |  |  |  |  | V | Mark Rison |  |  | Shouldn't say values are reserved for the WFA, as then they would not be allowed to be used by 802.11 STAs. Just say used/defined by the WFA | As it says in the comment [needs discussion] | REVISED (ED1: 2023-07-12 10:26:49Z)- Revised. Make the changes shown under “Proposed changes” for CID 4220 in https://mentor.ieee.org/802.11/dcn/23/11-23-0933-04-000m-resolutions-for-some-comments-on-11me-d3-0-lb273.docx, which describe fields/values as being allocated to the WFA rather than reserved. | ED1 | Motion-EDITOR1-3C | Ready for Motion | ED1: 2023-07-12 10:26:56Z - status set to: Ready for Motion ED1: 2023-06-02 14:42:41Z - status set to: More Work Required ED1: 2023-05-27 00:21:47Z - status set to: Submission Required ED1: 2023-05-12 23:56:47Z - status set to: Discuss |  |  |  | 2023-07-12 16:10 | ED1
4278 | Mark RISON | 273 | 3 | 1.4 |  |  | E | N |  |  | 1.4 |  | V | Mark RISON |  |  | We should have something in 1.4 to say that e.g. "beacon" refers to a Beacon, DMG Beacon or S1G Beacon frame | As it says in the comment [needs discussion] | REVISED (ED1: 2023-07-12 10:25:24Z)- Revised. At 173.17 add a para “References in this standard to a “beacon” (with a lowercase initial letter) are to be understood as being to a Beacon, DMG Beacon or S1G Beacon frame, as the context permits.” | ED1 | Motion-EDITOR1-3C | Ready for Motion | ED1: 2023-07-12 10:25:51Z - status set to: Ready for Motion ED1: 2023-06-02 14:46:23Z - status set to: More Work Required ED1: 2023-05-27 00:21:34Z - status set to: Submission Required ED1: 2023-05-12 23:59:37Z - status set to: Discuss |  |  |  | 2023-07-12 16:10 | ED1
4357 | Mark RISON | 273 | 3 | 3.2 |  |  | E | Y |  |  | 3.2 |  | V | Youhan KIM |  |  | Incorporation of the CID 1948 resolution into D2.0 wasn't done correctly: REVISED (GEN: 2022-06-15 14:29:50Z) Add the following definition in Clause 3.2: non-high-efficiency (non-HE) physical layer (PHY) protocol data unit (PPDU): A PPDU that is transmitted by a Clause 15 (DSSS PHY specification for the 2.4 GHz band designated for ISM applications), Clause 16 (High rate direct sequence spread spectrum (HR/DSSS) PHY specification), Clause 17 (Orthogonal frequency division multiplexing (OFDM) PHY specification), or Clause 18 (Extended Rate PHY (ERP) specification) PHY, or not using a TXVECTOR FORMAT parameter equal to HE. And change non-high-thought (non-HT) physical layer (PHY) protocol data unit (PPDU): non-high-throughput (non-HT) physical layer (PHY) protocol data unit (PPDU): A PPDU that is transmitted by a Clause 15 (DSSS PHY specification for the 2.4 GHz band designated for ISM applications), Clause 16 (High rate direct sequence spread spectrum (HR/DSSS) PHY specification), Clause 17 (Orthogonal frequency division multiplexing (OFDM) PHY specification), or Clause 18 (Extended Rate PHY (ERP) specification) PHY, or not using a TXVECTOR FORMAT parameter equal to HT_MF, HT_GF, VHT. or HE | Implement the CID 1948 resolution as directed | REVISED (ED1: 2023-07-12 15:40:03Z)- Instruction to TGme Editor: Implement the proposed text updates for CIDs 4343 and 4357 in https://mentor.ieee.org/802.11/dcn/23/11-23-1127-08-000m-lb273- misc-cids.docx Note that CIDs 4343 and 4357 have the same resolution and text updates. | ED1 | Motion-EDITOR1-3C | Ready for Motion | ED1: 2023-07-12 15:40:13Z - status set to: Ready for Motion ED1: 2023-06-23 15:48:29Z - status set to: More Work Required ED1: 2023-05-27 00:00:37Z - status set to: Discuss ED1: 2023-05-15 17:22:25Z - status set to: Submission Required ED1: 2023-05-13 00:20:27Z - status set to: Review |  |  |  | 2023-07-12 16:10 | ED1

## Motion-EDITOR1-3B
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4114 | Mark Hamilton | 273 | 3 | 4.9.1 | 322 | 35 | E | Y | 322 | 35 | 4.9.1 |  | V | Mark HAMILTON |  |  | The PHY is a complete layer, not a sublayer. | Change "PHY Sublayer" to "PHY Layer" in Figure 4-24 (2x), and also in Figure 4-25 (2x). | REVISED (ED1: 2023-06-26 14:34:11Z) - Change "PHY Sublayer" to "PHY Layer" in Figure 4-24 (2x), and in Figure 4-25 (2x), and also in text at locations: P3130.23, P3132.39, P3137.37, P3156.33, P3161.12, P3166.12, P3195.56, P3198.28, P3203.34, P3221.28, P3225.53, P3532.1, P3585.20, P4677.38, P4693.29. Note to Editor: some of instances should be: Change "PHY sublayer" to "PHY layer" | ED1 | Motion-EDITOR1-3B | Ready for Motion | ED1: 2023-06-26 14:37:20Z - status set to: Ready for Motion ED1: 2023-05-26 21:49:16Z - status set to: More Work Required ED1: 2023-05-13 00:13:48Z - status set to: Review |  |  |  | 2023-07-09 21:59 | ED1
4156 | Mark RISON | 273 | 3 | 9 |  |  | E | N |  |  | 9 |  | J |  |  |  | The Greek letters in Table 9-114--Order of... are different from those in Table 9-89--Order of..., which makes it hard to search for references to the angles | Use the same Greek letter glyphs everywhere. Specifically, use the Unicode Greek letter glyphs (9-89 and 9-114 seems to use some proprietary horror; 9-99 seems to use some proprietary horror for phi but not for psi!) | REJECTED (ED1: 2023-06-23 15:55:27Z) Reject Reason: The standard will be professionally edited prior to publication. The Greek letter glyphs usage will be referred to the publication editor for consideration during preparation for publication. | ED1 | Motion-EDITOR1-3B | Ready for Motion | ED1: 2023-06-23 15:56:41Z - status set to: Ready for Motion ED1: 2023-05-26 23:56:41Z - status set to: Discuss ED1: 2023-05-15 17:15:34Z - status set to: Submission Required ED1: 2023-05-12 23:41:45Z - status set to: Review |  | will be referred to the publication editor |  | 2023-07-09 21:59 | ED1
4169 | Mark RISON | 273 | 3 | 9.8 |  |  | E | N |  |  | 9.8 |  | A |  |  |  | "an SID" should be "a SID" (12x) | As it says in the comment [I can provide locations if needed; confirm direction] | ACCEPTED (ED1: 2023-06-23 15:57:09Z) Note to editor: 12 instances. | ED1 | Motion-EDITOR1-3B | Ready for Motion | ED1: 2023-06-23 15:57:23Z - status set to: Ready for Motion ED1: 2023-05-12 23:43:27Z - status set to: Discuss |  |  |  | 2023-07-09 21:59 | ED1
4181 | Mark RISON | 273 | 3 | 9 |  |  | E | N |  |  | 9 |  | A |  |  |  | "[see" should be "(see" and similarly for closing ] (~18x) | As it says in the comment [I can provide locations if needed; confirm direction] | ACCEPTED (ED1: 2023-06-23 15:57:34Z) | ED1 | Motion-EDITOR1-3B | Ready for Motion | ED1: 2023-06-23 15:57:37Z - status set to: Ready for Motion ED1: 2023-05-15 17:16:47Z - status set to: Discuss ED1: 2023-05-12 23:50:38Z - status set to: Review |  |  |  | 2023-07-09 21:59 | ED1
4210 | Mark RISON | 273 | 3 | 9 |  |  | E | N |  |  | 9 |  | J |  |  |  | "A field or subfield within the figure depiction of a frame format that includes a decimal value within parentheses indicates that this field or subfield is set to the indicated value upon transmission." -- in the teleconf on 2023-01-06 it was stated by the Editor that figures should not have numeric field values | Delete all such parentheticals [big item] | REJECTED (ED1: 2023-06-23 16:07:15Z) Reject Reason: It is okay to have numeric values in a field or subfield as indicated in 9.2.2. | ED1 | Motion-EDITOR1-3B | Ready for Motion | ED1: 2023-06-23 16:07:45Z - status set to: Ready for Motion ED1: 2023-05-26 23:59:26Z - status set to: Discuss ED1: 2023-05-15 19:22:22Z - status set to: Submission Required ED1: 2023-05-12 23:54:56Z - status set to: Discuss |  |  |  | 2023-07-09 21:59 | ED1
4336 | Mark RISON | 273 | 3 | 9 |  |  | E | N |  |  | 9 |  | J |  |  |  | "Operating Class and Channel field" sounds like two fields, not one field, so is very confusing | Change "and" to "And" throughout (in 9.4.1.22 Operating Class and Channel field, 9.4.2.69.3 Location Indication Channels subelement, 9.4.2.84 Channel Usage element, 9.9.3.3 WUR Discovery frame format, 11.21.15 Channel usage procedures) | REJECTED (ED1: 2023-06-23 15:54:22Z) - Reject Reason: “Operating Class and Channel field" is legacy text and remains unchanged. For any new field name definition, all words in the name (excluding acronyms) should be capitalized, including prepositions and conjunctions, as it stated in https://mentor.ieee.org/802.11/dcn/09/11-09-1034-20-0000-802-11-editorial-style-guide.docx. | ED1 | Motion-EDITOR1-3B | Ready for Motion | ED1: 2023-06-23 15:54:45Z - status set to: Ready for Motion ED1: 2023-05-15 17:21:43Z - status set to: Discuss ED1: 2023-05-13 00:02:33Z - status set to: Review |  |  |  | 2023-07-09 21:59 | ED1
4359 | Mark RISON | 273 | 3 | 9.4.2.199.2 | 1297 | 8 | E | N | 1297 | 8 | 9.4.2.199.2 |  | A |  |  |  | Sometimes the N in N_STS,total is italicised, sometimes not | Italicised is far more popular, so fix in Table 9-343--Subfields of the S1G Capabilities Information field | ACCEPTED (ED1: 2023-06-23 15:47:01Z) At 1297.8, Italicised N in N_STS,total. | ED1 | Motion-EDITOR1-3B | Ready for Motion | ED1: 2023-06-23 15:47:30Z - status set to: Ready for Motion ED1: 2023-05-27 00:02:32Z - status set to: Discuss ED1: 2023-05-15 17:23:48Z - status set to: Submission Required ED1: 2023-05-13 00:04:13Z - status set to: Review |  |  |  | 2023-07-09 21:59 | ED1
4406 | Yoshio Urabe | 273 | 3 | 9.4.2.198 | 1283 | 13 | E | N | 1283 | 13 | 9.4.2.198 |  | V |  |  |  | The location of this paragraph is not appropriate because the NDP Paging field exists only in the Individual TWT Parameter Set field explained in the next page. | Put the definition of NDP Paging Indicator field instead of the paragraph. For example, "The NDP Paging Indicator field is set to 1 to indicate that the NDP Paging field exists in the Individual TWT Parameter Set field; otherwise it is set to 0." Alternatively, the definition applies only when the Broadcast field is set to 0; and the NDP Paging Indicator field is reserved when the Broadcast field is set to 1. Further, move the current paragraph to P1291L62, after the paragraph of "The TWT Channel field ..." with a slight changes. For example, "The NDP Paging field is present in the Individual TWT Parameter Set field if the NDP Paging Indicator subfield in the Control field is equal to 1; otherwise, the NDP Paging field is not present. | REVISED (ED1: 2023-06-23 15:46:18Z)- At 1283.13, Change “The NDP Paging field is present if the NDP Paging Indicator subfield is equal to 1; otherwise, the NDP Paging field is not present.” To “The NDP Paging Indicator subfield is set to 1 to indicate that the NDP Paging field is present; otherwise, it is set to 0.” | ED1 | Motion-EDITOR1-3B | Ready for Motion | ED1: 2023-06-23 15:46:33Z - status set to: Ready for Motion ED1: 2023-05-27 00:06:02Z - status set to: Discuss ED1: 2023-05-15 17:13:29Z - status set to: Submission Required ED1: 2023-05-12 23:25:38Z - status set to: Review |  |  |  | 2023-07-09 21:59 | ED1
4416 | Alfred Asterjadhi | 273 | 3 |  |  |  | E | Y | 2002 | 38 | 10.29 |  | A | Alfred Asterjadhi |  |  | QoS null entry is missing. It was added by IEEE802.11ax. | Please add the entry for QoS Null. I have noticed a couple of entries missing out. So please check that proposed changes from IEEE802.11ax make it to baseline. | ACCEPTED (ED1: 2023-07-09 21:24:49Z) Note to editor: Insert a new bullet “QoS Null” in P2002L39 of IEEE802.11REVme D3.0. | ED1 | Motion-EDITOR1-3B | Ready for Motion | ED1: 2023-07-09 21:25:26Z - status set to: Ready for Motion ED1: 2023-05-15 17:24:54Z - status set to: Submission Required ED1: 2023-05-13 00:15:58Z - status set to: Review |  |  |  | 2023-07-09 21:59 | ED1

## Motion-EDITOR1-3A
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4013 | Brian Hart | 273 | 3 | 9.2.4.8.1 | 621 | 1 | E | N | 621 | 1 | 9.2.4.8.1 |  | V |  |  |  | Table 9-34expresses units in the title of the table, which is non-traditional (i.e., easy to miss) and not as precise as could be | Dete "(octets)" and "in microseconds" from table header, and instead add these as labels to each row (i.e. all rows are octets except the last which is microseconds) | REVISED (ED1: 2023-05-26 21:45:54Z)- Change the table title to “Maximum data unit sizes and durations” Change “size” in the first column to “size (in octets)” Change “duration” in the first column to “duration (in microseconds)”. Note: this comment was discussed on 6/12. The resolution is aligned with the resolution above. | ED1 | Motion-EDITOR1-3A | Ready for Motion | ED1: 2023-05-26 21:46:18Z - status set to: Ready for Motion ED1: 2023-05-12 23:16:31Z - status set to: Review |  |  |  | 2023-06-14 20:27 | ED1
4025 | Chaoming Luo | 273 | 3 | 10.11 | 1871 | 20 | E | N | 1871 | 20 | 10.11 |  | V |  |  |  | Since the term RSNA has been defined, it's better to use 'non-RSNA' instead of 'non-RSN association' | as in comment. | REVISED (ED1: 2023-05-26 21:46:50Z) - At 1871.20, Change “non-RSN association” to “non-RSNA” At 2864.24, change “RSN association” to “RSNA”. At 1871.23, change “RSNA (re)association” to “RSNA”. | ED1 | Motion-EDITOR1-3A | Ready for Motion | ED1: 2023-05-26 21:47:08Z - status set to: Ready for Motion ED1: 2023-05-14 22:29:18Z - status set to: Review ED1: 2023-05-12 23:25:09Z - status set to: Ready for Motion |  |  |  | 2023-06-14 20:27 | ED1
4096 | Lisa Ward | 273 | 3 | 9.3.3.10 | 725 | 50 | E | N | 725 | 50 | 9.3.3.10 |  | A |  |  |  | I think the sentence "The TVHT Operation element is present for a TVHT STA when dot11TVHTOptionImplemented is true; otherwise it is not present" should just say: "The TVHT Operation element is present for a STA when dot11TVHTOptionImplemented is true; otherwise it is not present" | delete 'TVHT' before STA in the sentence so it reads: "The TVHT Operation element is present for a STA when dot11TVHTOptionImplemented is true; otherwise it is not present" | ACCEPTED (ED1: 2023-05-26 21:47:17Z) | ED1 | Motion-EDITOR1-3A | Ready for Motion | ED1: 2023-05-26 21:47:21Z - status set to: Ready for Motion ED1: 2023-05-12 23:21:21Z - status set to: Review |  |  |  | 2023-06-14 20:27 | ED1
4106 | Mark Hamilton | 273 | 3 | 3.2 | 202 | 22 | E | Y | 202 | 22 | 3.2 |  | A |  |  |  | "nonenhanced" (EDMG) does not have a hyphen, but in the 2.16+2.16 PPDU definition, and 4.32+4.32 PPDU definition, there is a hyphen. | replace "non-enhanced" with "nonenhanced" | ACCEPTED (ED1: 2023-05-26 21:47:37Z) Note to editor: locations are: 202.22 and 202.56. | ED1 | Motion-EDITOR1-3A | Ready for Motion | ED1: 2023-05-26 21:47:49Z - status set to: Ready for Motion ED1: 2023-05-13 00:11:25Z - status set to: Review |  |  |  | 2023-06-14 20:27 | ED1
4125 | Mark Hamilton | 273 | 3 | 10.11 | 1868 | 21 | E | Y | 1868 | 21 | 10.11 |  | J |  |  |  | We don't refer to fields so informally | Change "SAs are all the same" to "SA fields are all the same". Same thing for DAs on that same line. | REJECTED (ED1: 2023-05-26 21:50:21Z) Reject reason: The SA and DA are associated with an MSDU, but are not fields (rather they are parameters in the MA-UNITDATA.request (where they are called "source/destination address")). The current text is accurate. | ED1 | Motion-EDITOR1-3A | Ready for Motion | ED1: 2023-05-26 21:50:36Z - status set to: Ready for Motion ED1: 2023-05-13 00:15:47Z - status set to: Review |  |  |  | 2023-06-14 20:27 | ED1
4170 | Mark RISON | 273 | 3 | 9.4 |  |  | E | Y |  |  | 9.4 |  | A |  |  |  | Saying in text that a field "is 2 octets" duplicates the figure | Delete "The length of the Authentication Algorithm Number field is 2 octets." in 9.4.1.1, "The length of the Authentication Transaction Sequence Number field is 2 octets." in 9.4.1.2, "The length of the Beacon Interval field is 2 octets." in 9.4.1.3, "The length of the Capability Information field is 2 octets." in 9.4.1.4, "The length of the Listen Interval field is 2 octets." in 9.4.1.6, "The length of the Reason Code field is 2 octets." in 9.4.1.7, "The length of the AID field is 2 octets." in 9.4.1.8, "The length of the Block Ack Parameter Set field is 2 octets." in 9.4.1.13, "The length of the Block Ack Timeout Value field is 2 octets." in 9.4.1.14, "The length of the Originator Preferred MCS field is 2 octets." in 9.4.1.15, "The length of the DELBA Parameter Set field is 2 octets." in 9.4.1.16, "The length of the RSN Capabilities field is 2 octets." in 9.4.2.23.4, "is 2 octets and" in 9.4.2.46, | ACCEPTED (ED1: 2023-05-26 21:51:07Z) | ED1 | Motion-EDITOR1-3A | Ready for Motion | ED1: 2023-05-26 21:51:10Z - status set to: Ready for Motion ED1: 2023-05-12 23:47:01Z - status set to: Review |  |  |  | 2023-06-14 20:27 | ED1
4209 | Mark RISON | 273 | 3 | 9.2.2 | 572 | 44 | E | N | 572 | 44 | 9.2.2 |  | V |  |  |  | "A field or subfield within the figure depiction of a frame format that includes a decimal value within parentheses indicates that this field or subfield is set to the indicated value upon transmission." -- doesn't account for textual cases, e.g. "(Control)" in Figure 9-37--Frame Control field subfield values within Control frames carried in a non-S1G PPDU and Figure 9-1212--Frame Control field subfield values within PV1 Control frames (are there any parentheticals that are actually part of the field name?) | Delete "decimal" in the cited text | REVISED (ED1: 2023-05-26 21:51:25Z) Replace "includes a decimal value" with "includes a value (decimal, if numeric)" | ED1 | Motion-EDITOR1-3A | Ready for Motion | ED1: 2023-05-26 21:52:02Z - status set to: Ready for Motion ED1: 2023-05-12 23:54:17Z - status set to: Review |  |  |  | 2023-06-14 20:27 | ED1
4216 | Mark RISON | 273 | 3 | 9 |  |  | E | N |  |  | 9 |  | J | Mark Rison |  |  | "wake-up" should be "wakeup" | As it says in the comment [needs discussion] | REJECTED (ED1: 2023-06-15 17:44:16Z) - REJECTED (ED1: 2023-06-02 14:30:33Z)- insufficial details. The comment fails to identify a specific issue to be addressed. It fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | ED1 | Motion-EDITOR1-3A | Ready for Motion | ED1: 2023-06-02 14:55:45Z - status set to: Ready for Motion ED1: 2023-06-02 14:31:43Z - status set to: Resolved ED1: 2023-05-27 00:22:00Z - status set to: Submission Required ED1: 2023-05-12 23:55:13Z - status set to: Discuss "wake-up" is defined in WUR and widely used in the draft. I found 406 instance. |  |  |  | 2023-06-15 17:45 | ED1
4238 | Mark RISON | 273 | 3 | 6.4 | 370 | 34 | E | N | 370 | 34 | 6.4 |  | A |  |  |  | "TDLS peer U-APSD" in Table 6-1 should be "TDLS peer U-APSD (TPU)" | As it says in the comment | ACCEPTED (ED1: 2023-05-26 21:52:13Z) | ED1 | Motion-EDITOR1-3A | Ready for Motion | ED1: 2023-05-26 21:52:16Z - status set to: Ready for Motion ED1: 2023-05-12 23:58:22Z - status set to: Review |  |  |  | 2023-06-14 20:27 | ED1
4296 | Mark RISON | 273 | 3 | 9.2.4.1.4 | 580 | 1 | E | N | 580 | 1 | 9.2.4.1.4 |  | A |  |  |  | "QMF Management frame" in Table 9-4--Combinations of To DS and From DS subfields in Management frames is weird because "QMF" stands for "QoS Management frame" | In that table change "QMF Management frames" to "QMFs" and "Non-QMF Management frames" to "Management frames that are not QMFs" | ACCEPTED (ED1: 2023-05-26 21:52:23Z) | ED1 | Motion-EDITOR1-3A | Ready for Motion | ED1: 2023-05-26 21:52:26Z - status set to: Ready for Motion ED1: 2023-05-12 23:59:58Z - status set to: Review |  |  |  | 2023-06-14 20:27 | ED1
4301 | Mark RISON | 273 | 3 | 9.3.1.8.9 | 650 | 48 | E | N | 650 | 48 | 9.3.1.8.9 |  | A |  |  |  | "one EDMG Multi-TID BlockAck" should be "one EDMG Multi-TID BlockAck frame" | As it says in the comment | ACCEPTED (ED1: 2023-05-26 21:52:36Z) | ED1 | Motion-EDITOR1-3A | Ready for Motion | ED1: 2023-05-26 21:52:39Z - status set to: Ready for Motion ED1: 2023-05-13 00:00:48Z - status set to: Review |  |  |  | 2023-06-14 20:27 | ED1
4310 | Mark RISON | 273 | 3 | 9.4.2.240 | 1357 | 12 | E | Y | 1357 | 12 | 9.4.2.240 |  | A |  |  |  | "SAE hash-to-element field" should be "SAE Hash-to-element field". Also, at 2817.61 change " SAE hash-to-element bit" to " SAE Hash-to-element bit" and at 2811.44 change "SAE Hash-to-element(#3178) method" to "SAE hash-to-element(#3178) method" | As it says in the comment | ACCEPTED (ED1: 2023-05-26 21:52:45Z) | ED1 | Motion-EDITOR1-3A | Ready for Motion | ED1: 2023-05-26 21:52:47Z - status set to: Ready for Motion ED1: 2023-05-13 00:01:27Z - status set to: Review |  |  |  | 2023-06-14 20:27 | ED1
4333 | Mark RISON | 273 | 3 | 9 | 854 | 53 | E | N | 854 | 53 | 9 |  | A |  |  |  | There should be no "element" (except in the xref caption) in the non-heading cells of the first column of Table 9-128--Element IDs | Change "AKM Suite Selector element (See" to "AKM Suite Selector (see" | ACCEPTED (ED1: 2023-05-26 21:52:58Z) Note to editor: also change “See” to “see”. | ED1 | Motion-EDITOR1-3A | Ready for Motion | ED1: 2023-05-26 21:53:14Z - status set to: Ready for Motion ED1: 2023-05-13 00:02:06Z - status set to: Review |  |  |  | 2023-06-14 20:27 | ED1
4362 | Mark RISON | 273 | 3 | 9.4.2.228.3 | 1342 | 24 | E | N | 1342 | 24 | 9.4.2.228.3 |  | V |  |  |  | "MaximumA - PPDUULenghtExponent" has a typo in "Length" and in "PPDUU" | As it says in the comment | REVISED (ED1: 2023-05-26 00:21:49Z)- In the Encoding column, replace "MaximumA -PPDUULenghtExponent" with "Maximum AMPDU Length Exponent". | ED1 | Motion-EDITOR1-3A | Ready for Motion | ED1: 2023-05-26 00:22:12Z - status set to: Ready for Motion ED1: 2023-05-13 00:07:44Z - status set to: Review |  |  |  | 2023-06-14 20:27 | ED1
4364 | Mark RISON | 273 | 3 | 9.4.2.228.3 | 1342 | 23 | E | N | 1342 | 23 | 9.4.2.228.3 |  | V |  |  |  | "Maximum AMPDU Length" is missing a hyphen after A (2x locations). Also "AMPDU" at 5098.3 | As it says in the comment | ED1: 2023-06-15 14:39:24Z - REVISED (ED1: 2023-05-26 00:23:01Z) -In the Encoding column, replace "MaximumA -PPDUULenghtExponent" with "Maximum AMPDU Length Exponent". At 5098.3, change "AMPDU" to "A-MPDU". | ED1 | Motion-EDITOR1-3A | Ready for Motion | ED1: 2023-05-26 00:23:14Z - status set to: Ready for Motion ED1: 2023-05-13 00:10:01Z - status set to: Review |  |  |  | 2023-06-15 14:41 | ED1
4381 | RUI YANG | 273 | 3 | 9.3.1.19 | 660 | 38 | E | N | 660 | 38 | 9.3.1.19 |  | J |  |  |  | Saying "A subchannel lies within a bandwidth" doesn't make sense, but "a subchannel lies within a channel" does. Suggest replace "BSS bandwidth" by "BSS channel", which has been used in D3.0, e.g., the title of subclause 10.45.3 is "BSS channel selection methods". | Change the sentence to "The lowest numbered bit of the Disallowed Subchannel Bitmap subfield corresponds to the 20 MHz subchannel that lies within the BSS channel and that has the lowest frequency of the set of all 20 MHz subchannels within the BSS channel." | REJECTED (ED1: 2023-05-26 00:27:27Z)- The term BSS channel might be confused with the Primary 20 MHz channel number. And the term BSS bandwidth is used extensively in the standard. | ED1 | Motion-EDITOR1-3A | Ready for Motion | ED1: 2023-05-26 00:27:47Z - status set to: Ready for Motion ED1: 2023-05-12 23:38:11Z - status set to: Review |  |  |  | 2023-06-14 20:27 | ED1
4387 | Sigurd Schelstraete | 273 | 3 | 4.5.3.3 | 308 | 24 | E | N | 308 | 24 | 4.5.3.3 |  | A |  |  |  | "To deliver an MSDU within an ESS via the DS, the DS needs to know which AP within the ESS to deliver the MSDU, ". Looks like "to" is missing after "the MSDU" | Change sentence to "(...) needs to know which AP within the ESS to deliver the MSDU to, " | ACCEPTED (ED1: 2023-05-26 21:54:57Z) | ED1 | Motion-EDITOR1-3A | Ready for Motion | ED1: 2023-05-26 21:55:00Z - status set to: Ready for Motion ED1: 2023-05-12 23:29:09Z - status set to: Review |  |  |  | 2023-06-14 20:27 | ED1

## Trivial Editorial Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4007 | Abhishek Patil | 273 | 3 | 9.4.2.198 | 1287 | 60 | E | N | 1287 | 60 | 9.4.2.198 |  | A |  |  |  | The paragraph describing Broadcast TWT Recommendation subfield should be on its own. | Split the paragraph such that the description for Broadcast TWT Recommendation subfield is covered in a separate paragraph. | ACCEPTED (ED1: 2023-05-12 23:39:33Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-13 00:20:57Z - status set to: Ready for Motion ED1: 2023-05-12 23:39:53Z - status set to: Read for Motion |  |  |  | 2023-05-14 22:29 | ED1
4044 | Jay Yang | 273 | 3 | 9.4.1.7 | 751 | 55 | E | N | 751 | 55 | 9.4.1.7 |  | A |  |  |  | Table 9-77 should be put in the blow the sentence of "The reason codes are defined in Table 9-77(Reason codes) " in the line 55/56 of page 751. The current position of Table 9-77 truncates the description of AID field in the subclause 9.4.1.8 | as the comments | ACCEPTED (ED1: 2023-05-12 23:18:21Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:18:36Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4083 | Kazuto Yano | 273 | 3 | 3.1 | 188 | 14 | E | N | 188 | 14 | 3.1 |  | A |  |  |  | An acronym "mesh STA" is given for "mobile station". The acronym must be "mobile STA". | As in comment. | ACCEPTED (ED1: 2023-05-12 23:29:45Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:29:53Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4084 | Kazuto Yano | 273 | 3 | 3.1 | 188 | 49 | E | N | 188 | 49 | 3.1 |  | A |  |  |  | "[MM-SMEComponent" must be "[MM-SME] Component". | Please fix this typo. | ACCEPTED (ED1: 2023-05-12 23:30:31Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:30:39Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4085 | Kazuto Yano | 273 | 3 | 3.2 | 199 | 53 | E | N | 199 | 53 | 3.2 |  | A |  |  |  | "An" is missing before "HT AP 2G4". | Please fix this typo. | ACCEPTED (ED1: 2023-05-12 23:31:14Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:31:21Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4086 | Kazuto Yano | 273 | 3 | 4.9.3 | 323 | 63 | E | N | 323 | 63 | 4.9.3 |  | A |  |  |  | Figures 4-26 and 4-27 appear in this order. | Please reorder these figures in the ascending order. | ACCEPTED (ED1: 2023-05-12 23:31:42Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:31:50Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4087 | Kazuto Yano | 273 | 3 | 6.7.6.2 | 543 | 18 | E | N | 543 | 18 | 6.7.6.2 |  | A |  |  |  | A comma is missing after "TXTIME". | Please add the comma. | ACCEPTED (ED1: 2023-05-12 23:32:26Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:32:32Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4088 | Kazuto Yano | 273 | 3 | 8.3.5.12.2 | 543 | 63 | E | N | 543 | 63 | 8.3.5.12.2 |  | V |  |  |  | A comma is missing after "per20bitmap". | Please add the comma. | REVISED (ED1: 2023-05-15 13:22:54Z) - At 560.63, change "per20bitmap" to "per20bitmap,". At 551.52, change "(IDLE, [per20bitmap])" to "(IDLE[, per20bitmap]). | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:34:01Z - status set to: Ready for Motion |  |  |  | 2023-05-15 13:27 | ED1
4089 | Kazuto Yano | 273 | 3 | 9.2.5.2 | 628 | 18 | E | N | 628 | 18 | 9.2.5.2 |  | V |  |  |  | "3189" seems to be a comment number. If so, please fix the notation. Otherwise, please remove it. | As in comment. | REVISED (ED1: 2023-05-12 23:34:34Z)- remove "3189". | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:34:55Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4090 | Kazuto Yano | 273 | 3 | 9.4.1.8 | 754 | 20 | E | N | 754 | 20 | 9.4.1.8 |  | A |  |  |  | "group cipeh rsuite" must be "group cipher suite". | Please fix this typo. | ACCEPTED (ED1: 2023-05-12 23:35:09Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:35:18Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4091 | Kazuto Yano | 273 | 3 | 9.4.2.25 | 987 | 49 | E | N | 987 | 49 | 9.4.2.25 |  | A |  |  |  | "101-n" must be "102-n". | Please fix this typo. | ACCEPTED (ED1: 2023-05-12 23:35:39Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:35:46Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4092 | Kazuto Yano | 273 | 3 | 9.6.7.14 | 1566 | 1 | E | N | 1566 | 1 | 9.6.7.14 |  | A |  |  |  | Please remove the unnecessary opening parenthesis in the caption of Table 9-458. | As in comment. | ACCEPTED (ED1: 2023-05-12 23:36:11Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:36:20Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4093 | Kazuto Yano | 273 | 3 | 10.41.6.3.2 | 2166 | 63 | E | N | 2166 | 63 | 10.41.6.3.2 |  | A |  |  |  | Figures 10-99 and 10-98 appear in this order. | Please reorder these figures in the ascending order. | ACCEPTED (ED1: 2023-05-12 23:36:39Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:36:44Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4098 | Mark Hamilton | 273 | 3 | 4.9.5 | 328 | 20 | E | Y | 328 | 20 | 4.9.5 |  | A |  |  |  | Figure 4-30 has "black box" problems | Correct the "black boxes" across the bottom of the figure, to be horizonatl brackets. | ACCEPTED (ED1: 2023-05-13 00:13:15Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-13 00:13:23Z - status set to: Ready for Motion ED1: 2023-05-13 00:10:58Z - status set to: Review |  |  |  | 2023-05-14 22:29 | ED1
4113 | Mark Hamilton | 273 | 3 | 4.5.9.2.2 | 317 | 45 | E | Y | 317 | 45 | 4.5.9.2.2 |  | A |  |  |  | Figure 4-20 has the "black boxes" problem | Correct the "black boxes" in Figure 4-20. | ACCEPTED (ED1: 2023-05-13 00:13:31Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-13 00:13:38Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4124 | Mark Hamilton | 273 | 3 | 3.4 | 244 | 21 | E | Y | 244 | 21 | 3.4 |  | A |  |  |  | Stray "(" | Delete "(" at the end of this line | ACCEPTED (ED1: 2023-05-15 13:12:31Z). Note to Editor: The location is 243.14. It has the same resolution as CID 4388. | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-15 13:15:18Z - status set to: Ready for Motion ED1: 2023-05-13 00:15:24Z - status set to: Review- Location is incorrect. |  |  |  | 2023-05-15 13:18 | ED1
4128 | Mark RISON | 273 | 3 | 9.4.2.258 | 1397 | 25 | E | N | 1397 | 25 | 9.4.2.258 |  | A |  |  |  | "(see9.4.2.27" | Add space after "see" | ACCEPTED (ED1: 2023-05-12 23:40:30Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:40:40Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4130 | Mark RISON | 273 | 3 | 9.3.3.2 | 696 | 26 | E | N | 696 | 26 | 9.3.3.2 |  | A |  |  |  | "The Extended BSS Load element is optionally present if dot11QBSSLoadImplemented, and dot11VHTOptionImplemented are true." -- spurious comma | Delete the comma | ACCEPTED (ED1: 2023-05-12 23:41:04Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:41:11Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4172 | Mark RISON | 273 | 3 | 5 |  |  | E | N |  |  | 5 |  | A |  |  |  | In Figures 5-1/2/7 "De-aggregation" should be "Deaggregation" (2x in each case). Ditto in the para at 2334.13 (2x also) | As it says in the comment | ACCEPTED (ED1: 2023-05-12 23:49:46Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:49:54Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4188 | Mark RISON | 273 | 3 | 9.4.2.258 | 1396 | 39 | E | N | 1396 | 39 | 9.4.2.258 |  | A |  |  |  | "are defined in 9.4.2.1" should be a hyperlink | (Maybe in other locations too) | ACCEPTED (ED1: 2023-05-12 23:50:55Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:51:03Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4193 | Mark RISON | 273 | 3 | 10.11 | 1869 | 52 | E | N | 1869 | 52 | 10.11 |  | A |  |  |  | " its BlockAck Parameter Set field " should be " the Block Ack Parameter Set field " (space and "the") | As it says in the comment | ACCEPTED (ED1: 2023-05-12 23:53:24Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:53:31Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4236 | Mark RISON | 273 | 3 | 9.4.1.58 | 817 | 1 | E | N | 817 | 1 | 9.4.1.58 |  | A |  |  |  | "Requested" in Figure 9-186--TWT Information field format has wrong font size for the "d" in the second cell | Fix the font | ACCEPTED (ED1: 2023-05-12 23:57:33Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:57:42Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4377 | Robert Sosack | 273 | 3 | 9.2.5.2 | 628 | 18 | E | N | 628 | 18 | 9.2.5.2 |  | A |  |  |  | extra characters in the word "Frame" | replace Fr3189ame with Frame | ACCEPTED (ED1: 2023-05-12 23:19:35Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:19:46Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4378 | Robert Sosack | 273 | 3 | 9.4.1.8 | 754 | 20 | E | N | 754 | 20 | 9.4.1.8 |  | A |  |  |  | space in wrong place | replace ciphe rsuite with cipher suite | ACCEPTED (ED1: 2023-05-12 23:20:32Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:20:38Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4388 | Stephan Sand | 273 | 3 | 3.4 | 243 | 14 | E | N | 243 | 14 | 3.4 |  | A |  |  |  | There is an extra "(" at the end of the line of the DL MU-MIMO acronym definition | Remove "(" at the end of the line | ACCEPTED (ED1: 2023-05-12 23:25:59Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:26:07Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4389 | Stephan Sand | 273 | 3 | 9.2.5.2 | 628 | 18 | E | N | 628 | 18 | 9.2.5.2 |  | A |  |  |  | "Fr3189ame Control field" | Delete "3189" | ACCEPTED (ED1: 2023-05-12 23:26:11Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:26:24Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1
4393 | Stephan Sand | 273 | 3 | 9.4.2.235 | 1352 | 46 | E | N | 1352 | 46 | 9.4.2.235 |  | A |  |  |  | Due to editorial changes from CID 3333, there is an extra "or one of the center frequency indices from the row" at the beginnin of the pargarph | Please delete "or one of the center frequency indices from the row" | ACCEPTED (ED1: 2023-05-12 23:27:38Z) | ED1 | Trivial editorial comments | Ready for Motion | ED1: 2023-05-12 23:28:13Z - status set to: Ready for Motion |  |  |  | 2023-05-14 22:29 | ED1

## All LB273 ED1 Comments
11-23-0834-00-000m | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4007 | Abhishek Patil | 273 | 3 | 9.4.2.198 | 1287 | 60 | E | N | 1287 | 60 | 9.4.2.198 | [5 empty] | The paragraph describing Broadcast TWT Recommendation subfield should be on its own. | Split the paragraph such that the description for Broadcast TWT Recommendation subfield is covered in a separate paragraph. |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4008 | Abhishek Patil | 273 | 3 | 9.6 | 1531 | 10 | E | N | 1531 | 10 | 9.6 | [5 empty] | Tables in clause 9.6 describe the 'Action' field for each type of 'action' frame. However, the corresponding frames are several pages away. When reviewing content from different frames, it requires a lot of back-n-forth navigation. It will greatly help if each row under the 'Description' column provides a reference to the corresponding frame format (for example, in Table 9-431, for the row corresponding to value 0, update the Description text to say: "Spectrum Measurement Request (see 9.6.2.2 (Spectrum Measurement Request frame format))". This will be similar to how clause 9.4.2.1 provides reference to respective subclauses for each element listed in Table 9-128. | As in comment |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4013 | Brian Hart | 273 | 3 | 9.2.4.8.1 | 621 | 1 | E | N | 621 | 1 | 9.2.4.8.1 | [5 empty] | Table 9-34expresses units in the title of the table, which is non-traditional (i.e., easy to miss) and not as precise as could be | Dete "(octets)" and "in microseconds" from table header, and instead add these as labels to each row (i.e. all rows are octets except the last which is microseconds) |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4025 | Chaoming Luo | 273 | 3 | 10.11 | 1871 | 20 | E | N | 1871 | 20 | 10.11 | [5 empty] | Since the term RSNA has been defined, it's better to use 'non-RSNA' instead of 'non-RSN association' | as in comment. |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4044 | Jay Yang | 273 | 3 | 9.4.1.7 | 751 | 55 | E | N | 751 | 55 | 9.4.1.7 | [5 empty] | Table 9-77 should be put in the blow the sentence of "The reason codes are defined in Table 9-77(Reason codes) " in the line 55/56 of page 751. The current position of Table 9-77 truncates the description of AID field in the subclause 9.4.1.8 | as the comments |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4083 | Kazuto Yano | 273 | 3 | 3.1 | 188 | 14 | E | N | 188 | 14 | 3.1 | [5 empty] | An acronym "mesh STA" is given for "mobile station". The acronym must be "mobile STA". | As in comment. |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4084 | Kazuto Yano | 273 | 3 | 3.1 | 188 | 49 | E | N | 188 | 49 | 3.1 | [5 empty] | "[MM-SMEComponent" must be "[MM-SME] Component". | Please fix this typo. |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4085 | Kazuto Yano | 273 | 3 | 3.2 | 199 | 53 | E | N | 199 | 53 | 3.2 | [5 empty] | "An" is missing before "HT AP 2G4". | Please fix this typo. |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4086 | Kazuto Yano | 273 | 3 | 4.9.3 | 323 | 63 | E | N | 323 | 63 | 4.9.3 | [5 empty] | Figures 4-26 and 4-27 appear in this order. | Please reorder these figures in the ascending order. |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4087 | Kazuto Yano | 273 | 3 | 6.7.6.2 | 543 | 18 | E | N | 543 | 18 | 6.7.6.2 | [5 empty] | A comma is missing after "TXTIME". | Please add the comma. |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4088 | Kazuto Yano | 273 | 3 | 8.3.5.12.2 | 543 | 63 | E | N | 543 | 63 | 8.3.5.12.2 | [5 empty] | A comma is missing after "per20bitmap". | Please add the comma. |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4089 | Kazuto Yano | 273 | 3 | 9.2.5.2 | 628 | 18 | E | N | 628 | 18 | 9.2.5.2 | [5 empty] | "3189" seems to be a comment number. If so, please fix the notation. Otherwise, please remove it. | As in comment. |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4090 | Kazuto Yano | 273 | 3 | 9.4.1.8 | 754 | 20 | E | N | 754 | 20 | 9.4.1.8 | [5 empty] | "group cipeh rsuite" must be "group cipher suite". | Please fix this typo. |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4091 | Kazuto Yano | 273 | 3 | 9.4.2.25 | 987 | 49 | E | N | 987 | 49 | 9.4.2.25 | [5 empty] | "101-n" must be "102-n". | Please fix this typo. |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4092 | Kazuto Yano | 273 | 3 | 9.6.7.14 | 1566 | 1 | E | N | 1566 | 1 | 9.6.7.14 | [5 empty] | Please remove the unnecessary opening parenthesis in the caption of Table 9-458. | As in comment. |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4093 | Kazuto Yano | 273 | 3 | 10.41.6.3.2 | 2166 | 63 | E | N | 2166 | 63 | 10.41.6.3.2 | [5 empty] | Figures 10-99 and 10-98 appear in this order. | Please reorder these figures in the ascending order. |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4096 | Lisa Ward | 273 | 3 | 9.3.3.10 | 725 | 50 | E | N | 725 | 50 | 9.3.3.10 | [5 empty] | I think the sentence "The TVHT Operation element is present for a TVHT STA when dot11TVHTOptionImplemented is true; otherwise it is not present" should just say: "The TVHT Operation element is present for a STA when dot11TVHTOptionImplemented is true; otherwise it is not present" | delete 'TVHT' before STA in the sentence so it reads: "The TVHT Operation element is present for a STA when dot11TVHTOptionImplemented is true; otherwise it is not present" |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4098 | Mark Hamilton | 273 | 3 | 4.9.5 | 328 | 20 | E | Y | 328 | 20 | 4.9.5 | [5 empty] | Figure 4-30 has "black box" problems | Correct the "black boxes" across the bottom of the figure, to be horizonatl brackets. |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4106 | Mark Hamilton | 273 | 3 | 3.2 | 202 | 22 | E | Y | 202 | 22 | 3.2 | [5 empty] | "nonenhanced" (EDMG) does not have a hyphen, but in the 2.16+2.16 PPDU definition, and 4.32+4.32 PPDU definition, there is a hyphen. | replace "non-enhanced" with "nonenhanced" |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4113 | Mark Hamilton | 273 | 3 | 4.5.9.2.2 | 317 | 45 | E | Y | 317 | 45 | 4.5.9.2.2 | [5 empty] | Figure 4-20 has the "black boxes" problem | Correct the "black boxes" in Figure 4-20. |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4114 | Mark Hamilton | 273 | 3 | 4.9.1 | 322 | 35 | E | Y | 322 | 35 | 4.9.1 | [5 empty] | The PHY is a complete layer, not a sublayer. | Change "PHY Sublayer" to "PHY Layer" in Figure 4-24 (2x), and also in Figure 4-25 (2x). |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4122 | Mark Hamilton | 273 | 3 | 9.4.2.231.1 | 1348 | 42 | E | Y | 1348 | 42 | 9.4.2.231.1 | [5 empty] | Missing ".". Also, should there be a space? Misc other related typos. | P1348.42 has "PHY-CCA indication (IDLE)" (no ".", and a space). Add the dot, for sure. (Same thing at P1349.41.) The space seems to be inconsistent: P568.15 has space, P568.63 does not. Which should it be? (This applies to all the primitive types, "request, indication, response, confirm", which are all inconsistent.) Another issue: P2366.10 has "busy" instead of "BUSY". And, finally, P2768.30 has "PHY-CCA.INDICATION" ("indication" should be lower case). |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4124 | Mark Hamilton | 273 | 3 | 3.4 | 244 | 21 | E | Y | 244 | 21 | 3.4 | [5 empty] | Stray "(" | Delete "(" at the end of this line |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4125 | Mark Hamilton | 273 | 3 | 10.11 | 1868 | 21 | E | Y | 1868 | 21 | 10.11 | [5 empty] | We don't refer to fields so informally | Change "SAs are all the same" to "SA fields are all the same". Same thing for DAs on that same line. |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4128 | Mark RISON | 273 | 3 | 9.4.2.258 | 1397 | 25 | E | N | 1397 | 25 | 9.4.2.258 | [5 empty] | "(see9.4.2.27" | Add space after "see" |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4130 | Mark RISON | 273 | 3 | 9.3.3.2 | 696 | 26 | E | N | 696 | 26 | 9.3.3.2 | [5 empty] | "The Extended BSS Load element is optionally present if dot11QBSSLoadImplemented, and dot11VHTOptionImplemented are true." -- spurious comma | Delete the comma |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4156 | Mark RISON | 273 | 3 | 9 |  |  | E | N |  |  | 9 | [5 empty] | The Greek letters in Table 9-114--Order of... are different from those in Table 9-89--Order of..., which makes it hard to search for references to the angles | Use the same Greek letter glyphs everywhere. Specifically, use the Unicode Greek letter glyphs (9-89 and 9-114 seems to use some proprietary horror; 9-99 seems to use some proprietary horror for phi but not for psi!) |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4169 | Mark RISON | 273 | 3 | 9.8 |  |  | E | N |  |  | 9.8 | [5 empty] | "an SID" should be "a SID" (12x) | As it says in the comment [I can provide locations if needed; confirm direction] |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4170 | Mark RISON | 273 | 3 | 9.4 |  |  | E | Y |  |  | 9.4 | [5 empty] | Saying in text that a field "is 2 octets" duplicates the figure | Delete "The length of the Authentication Algorithm Number field is 2 octets." in 9.4.1.1, "The length of the Authentication Transaction Sequence Number field is 2 octets." in 9.4.1.2, "The length of the Beacon Interval field is 2 octets." in 9.4.1.3, "The length of the Capability Information field is 2 octets." in 9.4.1.4, "The length of the Listen Interval field is 2 octets." in 9.4.1.6, "The length of the Reason Code field is 2 octets." in 9.4.1.7, "The length of the AID field is 2 octets." in 9.4.1.8, "The length of the Block Ack Parameter Set field is 2 octets." in 9.4.1.13, "The length of the Block Ack Timeout Value field is 2 octets." in 9.4.1.14, "The length of the Originator Preferred MCS field is 2 octets." in 9.4.1.15, "The length of the DELBA Parameter Set field is 2 octets." in 9.4.1.16, "The length of the RSN Capabilities field is 2 octets." in 9.4.2.23.4, "is 2 octets and" in 9.4.2.46, |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4172 | Mark RISON | 273 | 3 | 5 |  |  | E | N |  |  | 5 | [5 empty] | In Figures 5-1/2/7 "De-aggregation" should be "Deaggregation" (2x in each case). Ditto in the para at 2334.13 (2x also) | As it says in the comment |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4181 | Mark RISON | 273 | 3 | 9 |  |  | E | N |  |  | 9 | [5 empty] | "[see" should be "(see" and similarly for closing ] (~18x) | As it says in the comment [I can provide locations if needed; confirm direction] |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4188 | Mark RISON | 273 | 3 | 9.4.2.258 | 1396 | 39 | E | N | 1396 | 39 | 9.4.2.258 | [5 empty] | "are defined in 9.4.2.1" should be a hyperlink | (Maybe in other locations too) |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4193 | Mark RISON | 273 | 3 | 10.11 | 1869 | 52 | E | N | 1869 | 52 | 10.11 | [5 empty] | " its BlockAck Parameter Set field " should be " the Block Ack Parameter Set field " (space and "the") | As it says in the comment |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4199 | Mark RISON | 273 | 3 | 9.6 |  |  | E | N |  |  | 9.6 | [5 empty] | There are 7 "Action field is set"s in 9.6 that should just be "The <blah> Action field is defined in 9.6.<blah>.1." | As it says in the comment [I can provide locations if needed; confirm direction] |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4201 | Mark RISON | 273 | 3 | 10 |  |  | E | N |  |  | 10 | [5 empty] | There are a few "successfully negotiated"s, which implies that the other "negotiated"s include unsuccessful negotiation | Delete "successfully" in each case [I can provide locations if needed; confirm direction] |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4208 | Mark RISON | 273 | 3 | 10.25 |  |  | E | N |  |  | 10.25 | [5 empty] | 10.25 and 11.5 sometimes use "set up" and sometimes use "establish". It would be better to use a single term | As it says in the comment [needs direction] |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4209 | Mark RISON | 273 | 3 | 9.2.2 | 572 | 44 | E | N | 572 | 44 | 9.2.2 | [5 empty] | "A field or subfield within the figure depiction of a frame format that includes a decimal value within parentheses indicates that this field or subfield is set to the indicated value upon transmission." -- doesn't account for textual cases, e.g. "(Control)" in Figure 9-37--Frame Control field subfield values within Control frames carried in a non-S1G PPDU and Figure 9-1212--Frame Control field subfield values within PV1 Control frames (are there any parentheticals that are actually part of the field name?) | Delete "decimal" in the cited text |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4210 | Mark RISON | 273 | 3 | 9 |  |  | E | N |  |  | 9 | [5 empty] | "A field or subfield within the figure depiction of a frame format that includes a decimal value within parentheses indicates that this field or subfield is set to the indicated value upon transmission." -- in the teleconf on 2023-01-06 it was stated by the Editor that figures should not have numeric field values | Delete all such parentheticals [big item] |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4216 | Mark RISON | 273 | 3 | 9 |  |  | E | N |  |  | 9 | [5 empty] | "wake-up" should be "wakeup" | As it says in the comment [needs discussion] |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4217 | Mark RISON | 273 | 3 | 9 |  |  | E | N |  |  | 9 | [5 empty] | "query response" v "Query Response" | Should be lowercase if not name of field etc. |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4219 | Mark RISON | 273 | 3 | 10.5 | 2285 | 30 | E | N | 2285 | 30 | 10.5 | [5 empty] | "include a Page Slice Number that matches its Page Slice Number and a page index that matches its Page index" has bogus capitalisation and missing "field"s | As it says in the comment [needs submission] |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4220 | Mark RISON | 273 | 3 |  |  |  | T | N | [8 empty] | Shouldn't say values are reserved for the WFA, as then they would not be allowed to be used by 802.11 STAs. Just say used/defined by the WFA | As it says in the comment [needs discussion] |  | ED1 | [6 empty] | 2023-05-08 18:44 | EDITOR
4236 | Mark RISON | 273 | 3 | 9.4.1.58 | 817 | 1 | E | N | 817 | 1 | 9.4.1.58 | [5 empty] | "Requested" in Figure 9-186--TWT Information field format has wrong font size for the "d" in the second cell | Fix the font |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4238 | Mark RISON | 273 | 3 | 6.4 | 370 | 34 | E | N | 370 | 34 | 6.4 | [5 empty] | "TDLS peer U-APSD" in Table 6-1 should be "TDLS peer U-APSD (TPU)" | As it says in the comment |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4242 | Mark RISON | 273 | 3 | 3 |  |  | E | N |  |  | 3 | [5 empty] | We should only have one abbreviation for each item in Clause 3 (see 22/1993 for the instances and counts) | As it says in the comment [confirm direction] |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4278 | Mark RISON | 273 | 3 | 1.4 |  |  | E | N |  |  | 1.4 | [5 empty] | We should have something in 1.4 to say that e.g. "beacon" refers to a Beacon, DMG Beacon or S1G Beacon frame | As it says in the comment [needs discussion] |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4296 | Mark RISON | 273 | 3 | 9.2.4.1.4 | 580 | 1 | E | N | 580 | 1 | 9.2.4.1.4 | [5 empty] | "QMF Management frame" in Table 9-4--Combinations of To DS and From DS subfields in Management frames is weird because "QMF" stands for "QoS Management frame" | In that table change "QMF Management frames" to "QMFs" and "Non-QMF Management frames" to "Management frames that are not QMFs" |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4301 | Mark RISON | 273 | 3 | 9.3.1.8.9 | 650 | 48 | E | N | 650 | 48 | 9.3.1.8.9 | [5 empty] | "one EDMG Multi-TID BlockAck" should be "one EDMG Multi-TID BlockAck frame" | As it says in the comment |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4303 | Mark RISON | 273 | 3 | 9 |  |  | E | N |  |  | 9 | [5 empty] | "Service period request (SPR) frame", "Sector sweep (SSW) frame", "Sector sweep feedback (SSW-Feedback) frame", "Sector sweep Ack (SSW-Ack) frame" -- frames should have just one name | As it says in the comment [confirm direction] |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4310 | Mark RISON | 273 | 3 | 9.4.2.240 | 1357 | 12 | E | Y | 1357 | 12 | 9.4.2.240 | [5 empty] | "SAE hash-to-element field" should be "SAE Hash-to-element field". Also, at 2817.61 change " SAE hash-to-element bit" to " SAE Hash-to-element bit" and at 2811.44 change "SAE Hash-to-element(#3178) method" to "SAE hash-to-element(#3178) method" | As it says in the comment |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4318 | Mark RISON | 273 | 3 | 3.2 |  |  | E | N |  |  | 3.2 | [5 empty] | CID 3772: the improvements to "mask PPDU" definitions should be made for S1G, mass-market PHYs and DMG too | As it says in the comment |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4333 | Mark RISON | 273 | 3 | 9 | 854 | 53 | E | N | 854 | 53 | 9 | [5 empty] | There should be no "element" (except in the xref caption) in the non-heading cells of the first column of Table 9-128--Element IDs | Change "AKM Suite Selector element (See" to "AKM Suite Selector (see" |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4334 | Mark RISON | 273 | 3 | 9.6.5 |  |  | E | N |  |  | 9.6.5 | [5 empty] | Change "9.6.5 Vendor-specific Action frame details" to "9.6.5 Vendor-specific frame details", since VS frames are not a family of frames identified by an Action field, unlike other Action frames | As it says in the comment |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4336 | Mark RISON | 273 | 3 | 9 |  |  | E | N |  |  | 9 | [5 empty] | "Operating Class and Channel field" sounds like two fields, not one field, so is very confusing | Change "and" to "And" throughout (in 9.4.1.22 Operating Class and Channel field, 9.4.2.69.3 Location Indication Channels subelement, 9.4.2.84 Channel Usage element, 9.9.3.3 WUR Discovery frame format, 11.21.15 Channel usage procedures) |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4340 | Mark RISON | 273 | 3 | 3 |  |  | E | N |  |  | 3 | [5 empty] | Any frame names in definitions need to be lowercase in Clause 3, per CID 1630. E.g. "time priority Management frame:" should be "time priority management frame:" | As it says in the comment [confirm direction] |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4356 | Mark RISON | 273 | 3 | 9 |  |  | E | N |  |  | 9 | [5 empty] | Is the field "Comeback Delay" or "GAS Comeback Delay"? Also sometimes missing "frame" | As it says in the comment |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4357 | Mark RISON | 273 | 3 | 3.2 |  |  | E | Y |  |  | 3.2 | [5 empty] | Incorporation of the CID 1948 resolution into D2.0 wasn't done correctly: REVISED (GEN: 2022-06-15 14:29:50Z) Add the following definition in Clause 3.2: non-high-efficiency (non-HE) physical layer (PHY) protocol data unit (PPDU): A PPDU that is transmitted by a Clause 15 (DSSS PHY specification for the 2.4 GHz band designated for ISM applications), Clause 16 (High rate direct sequence spread spectrum (HR/DSSS) PHY specification), Clause 17 (Orthogonal frequency division multiplexing (OFDM) PHY specification), or Clause 18 (Extended Rate PHY (ERP) specification) PHY, or not using a TXVECTOR FORMAT parameter equal to HE. And change non-high-thought (non-HT) physical layer (PHY) protocol data unit (PPDU): non-high-throughput (non-HT) physical layer (PHY) protocol data unit (PPDU): A PPDU that is transmitted by a Clause 15 (DSSS PHY specification for the 2.4 GHz band designated for ISM applications), Clause 16 (High rate direct sequence spread spectrum (HR/DSSS) PHY specification), Clause 17 (Orthogonal frequency division multiplexing (OFDM) PHY specification), or Clause 18 (Extended Rate PHY (ERP) specification) PHY, or not using a TXVECTOR FORMAT parameter equal to HT_MF, HT_GF, VHT. or HE | Implement the CID 1948 resolution as directed |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4359 | Mark RISON | 273 | 3 | 9.4.2.199.2 | 1297 | 8 | E | N | 1297 | 8 | 9.4.2.199.2 | [5 empty] | Sometimes the N in N_STS,total is italicised, sometimes not | Italicised is far more popular, so fix in Table 9-343--Subfields of the S1G Capabilities Information field |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4361 | Mark RISON | 273 | 3 | 10.11 | 1870 | 8 | E | N | 1870 | 8 | 10.11 | [5 empty] | "The length of an A-MSDU transmitted in a VHT PPDU or HE PPDU(11ax) is limited by the maximum MPDU size supported by the recipient STA (see 10.12.5 (Transport of A-MPDU by the PHY data service))." looks like a stale xref | Put in the correct xref |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4362 | Mark RISON | 273 | 3 | 9.4.2.228.3 | 1342 | 24 | E | N | 1342 | 24 | 9.4.2.228.3 | [5 empty] | "MaximumA - PPDUULenghtExponent" has a typo in "Length" and in "PPDUU" | As it says in the comment |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4364 | Mark RISON | 273 | 3 | 9.4.2.228.3 | 1342 | 23 | E | N | 1342 | 23 | 9.4.2.228.3 | [5 empty] | "Maximum AMPDU Length" is missing a hyphen after A (2x locations). Also "AMPDU" at 5098.3 | As it says in the comment |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4367 | Mark RISON | 273 | 3 | 9 |  |  | E | N |  |  | 9 | [5 empty] | The field is now called EOF/Tag but there are ~9 instances of "EOF (sub)field" | Add "/Tag" to the errant instances |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4377 | Robert Sosack | 273 | 3 | 9.2.5.2 | 628 | 18 | E | N | 628 | 18 | 9.2.5.2 | [5 empty] | extra characters in the word "Frame" | replace Fr3189ame with Frame |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4378 | Robert Sosack | 273 | 3 | 9.4.1.8 | 754 | 20 | E | N | 754 | 20 | 9.4.1.8 | [5 empty] | space in wrong place | replace ciphe rsuite with cipher suite |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4381 | RUI YANG | 273 | 3 | 9.3.1.19 | 660 | 38 | E | N | 660 | 38 | 9.3.1.19 | [5 empty] | Saying "A subchannel lies within a bandwidth" doesn't make sense, but "a subchannel lies within a channel" does. Suggest replace "BSS bandwidth" by "BSS channel", which has been used in D3.0, e.g., the title of subclause 10.45.3 is "BSS channel selection methods". | Change the sentence to "The lowest numbered bit of the Disallowed Subchannel Bitmap subfield corresponds to the 20 MHz subchannel that lies within the BSS channel and that has the lowest frequency of the set of all 20 MHz subchannels within the BSS channel." |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4387 | Sigurd Schelstraete | 273 | 3 | 4.5.3.3 | 308 | 24 | E | N | 308 | 24 | 4.5.3.3 | [5 empty] | "To deliver an MSDU within an ESS via the DS, the DS needs to know which AP within the ESS to deliver the MSDU, ". Looks like "to" is missing after "the MSDU" | Change sentence to "(...) needs to know which AP within the ESS to deliver the MSDU to, " |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4388 | Stephan Sand | 273 | 3 | 3.4 | 243 | 14 | E | N | 243 | 14 | 3.4 | [5 empty] | There is an extra "(" at the end of the line of the DL MU-MIMO acronym definition | Remove "(" at the end of the line |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4389 | Stephan Sand | 273 | 3 | 9.2.5.2 | 628 | 18 | E | N | 628 | 18 | 9.2.5.2 | [5 empty] | "Fr3189ame Control field" | Delete "3189" |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4393 | Stephan Sand | 273 | 3 | 9.4.2.235 | 1352 | 46 | E | N | 1352 | 46 | 9.4.2.235 | [5 empty] | Due to editorial changes from CID 3333, there is an extra "or one of the center frequency indices from the row" at the beginnin of the pargarph | Please delete "or one of the center frequency indices from the row" |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4406 | Yoshio Urabe | 273 | 3 | 9.4.2.198 | 1283 | 13 | E | N | 1283 | 13 | 9.4.2.198 | [5 empty] | The location of this paragraph is not appropriate because the NDP Paging field exists only in the Individual TWT Parameter Set field explained in the next page. | Put the definition of NDP Paging Indicator field instead of the paragraph. For example, "The NDP Paging Indicator field is set to 1 to indicate that the NDP Paging field exists in the Individual TWT Parameter Set field; otherwise it is set to 0." Alternatively, the definition applies only when the Broadcast field is set to 0; and the NDP Paging Indicator field is reserved when the Broadcast field is set to 1. Further, move the current paragraph to P1291L62, after the paragraph of "The TWT Channel field ..." with a slight changes. For example, "The NDP Paging field is present in the Individual TWT Parameter Set field if the NDP Paging Indicator subfield in the Control field is equal to 1; otherwise, the NDP Paging field is not present. |  | ED1 | [6 empty] | 2023-05-08 18:29 | EDITOR
4416 | Alfred Asterjadhi | 273 | 3 |  |  |  | E | Y | 2002 | 38 | 10.29 | [5 empty] | QoS null entry is missing. It was added by IEEE802.11ax. | Please add the entry for QoS Null. I have noticed a couple of entries missing out. So please check that proposed changes from IEEE802.11ax make it to baseline. |  | ED1 | [6 empty] | 2023-05-09 18:42 | EDITOR