## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-23/2032r10
Venue Date: | May 2024
First Author: | Mark Hamilton, Ruckus/CommScope
Subject: | REVmd Working Group Comments for MAC ad-hoc
Full Date: | 2024-05-16
Author(s): | Name(s) | Mark Hamilton
| Company | Ruckus/CommScope
Address
Phone:
Fax:
| email: | mark.hamilton@commscope.com
Abstract:
This document contains comments in the "MAC ad hoc" group, submitted on REVme SA Ballots on the published IEEE Std 802.11-2020 and subsequent amendments.

## Revision History
Revision | Date | Description
0 | 2023-11-11 | Initial revision after Initial SA ballot on D4.0, and Ad Hoc Status and Assignments done.
1 | 2023-11-11 | Minor updates (some assignments, typos, etc.)
2 | 2023-11-16 | CIDs ready for motion during November session on Motion MAC-BI tab: 6001, 6002, 6004, 6005, 6171, 6338.
3 | 2023-12-08 | CIDs ready for motion since November through December ad hoc F2F, on Motion MAC-BJ tab: 6388, 6219, 6222, 6258, 6261, 6265, 6311, 6326, 6551, 6387, 6183, 6413, 6452, 6509, 6588, 6593, 6546, 6549, 6338, 6060, 6068, 6072, 6075, 6289, 6016, 6017, 6185, 6064, 6136, 6137, 6138, 6139, 6142, 6169, 6032, 6029.
4 | 2024-01-14 | CIDs ready for motion since December ad hoc, on Motion MAC-BK tab and Motion MAC 6509 tab.
5 | 2024-01-18 | CIDs ready for motion on tabs (separate motions on each): Motion MAC 6509, Motion MAC 6087, Motion MAC 6071, Motion MAC-BK, Submission Required, More Work Required.
6 | 2024-03-08 | Comments from second SA ballot (first recirc) added, Ad Hoc Status and Assignments done.
7 | 2024-03-13 | Updates per Denver (March '24) F2F, through Wednesday.
8 | 2024-04-11 | 19 CIDs ready for motion on Motion MAC-BM tab. 3 CIDs in "Review" status, for review during ad hoc. 12 that need discussion, probably at ad hoc. 7 are "More work required" and scheduled for the ad hoc. 26 are assigned with Submission Required, and pending action from the assignee.
9 | 2024-04-27 | 41 CIDs total, now ready for motion on Motion MAC-BM tab, after San Diego ad hoc meetings.
10 | 2024-05-16 | At end of Warsaw F2F, 21 CIDs ready for motion on "Motion MAC-BN" tab, 1 CID on a separate tab "Motoin MAC 7159" and 6 CIDs on the "Submission Required" tab are planned to be rejected for lack of sufficient detail, and the assigned Submission was never provided.

## Motion MAC-BN
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
7105 | Hamilton, Mark | 1002 | 5 | 9.3.3.5 | 738 | 20 | T | Yes | 738 | 20 | 9.3.3.5 |  | J | Mark HAMILTON |  |  | What does "ought" mean in this context? "Should"?? "Shall"?? Something non-normative?? Yes, clause 9 is generally not supposed to use normative verbs, but here the intent is now entirely unclear. | Replace "ought" with understandable phrasing. Same thing at P738.31, P741.57, P742.11, P746.48, P746.59, P752.17, P752.28, P757.16, P757.29, P760.16, and P761.11. | REJECTED (MAC: 2024-05-15 09:46:19Z): The commenter does not provide sufficient details to determine a satisfactory resolution. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-15 09:47:17Z - status set to: Ready for Motion MAC: 2024-04-18 02:51:26Z - status set to: More Work Required MAC: 2024-04-17 18:20:34Z - status set to: More work required. Bring back at May interim. MAC: 2024-03-07 20:43:42Z - status set to: Discuss |  |  |  | 2024-05-15 09:47 | MAC
7142 | Levy, Joseph | 1002 | 5 | 9.4.2.69.2 | 1145 | 25 | T | Yes | 1145 | 25 | 9.4.2.69.2 |  | V | Joseph Levy |  |  | The text: "The exact criteria and mechanism to detect motion is out of scope for this standard." this has nothing to do with the format of the Location Indication Parameters subelement. | Delete: "The exact criteria and mechanism to detect motion is out of scope for this standard." | REVISED (MAC: 2024-05-15 09:58:41Z): Move the cited sentence to P2692.39 (following bullet (2)), as a NOTE-- | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-15 09:59:18Z - status set to: Ready for Motion MAC: 2024-04-18 02:51:30Z - status set to: More Work Required. Bring back at May interim. MAC: 2024-04-17 18:52:35Z - status set to: More work required. MAC: 2024-04-17 18:51:21Z - Started to say: REJECTED (MAC: 2024-04-17 18:48:58Z): This paragraph appears within text that discusses reported detected motion, so noting that the details of how such detection is done is appropriate here. But, considered moving the sentence to a normative clause instead. MwR, assign to Joseph. Bring back at May interim. MAC: 2024-03-07 21:28:42Z - The cited sentence seems to be in the midst of several paragraph that talk about reporting motion, and the "In-Motion…" fields. MAC: 2024-03-07 21:27:45Z - status set to: Discuss |  |  |  | 2024-05-15 09:59 | MAC
7224 | RISON, Mark | 1002 | 5 | 9 |  |  | T | Yes |  |  | 9 |  | V | Mark Rison |  |  | Units for Length fields should be specified (typically octets) | Fix in Cookie Length in 9.4.2.306, Emergency Call Number in 9.4.5.5, Redict URL in 9.4.5.6, NAI Realm Data Field Length in 9.4.5.10 | REVISED (MAC: 2024-04-29 14:51:14Z): Incorporate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0702-03-000m-resolutions-for-some-comments-on-11me-d5-0-sa2.docx, for CID 7224. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-04-29 14:57:18Z - status set to: Ready for Motion MAC: 2024-04-18 02:51:21Z - status set to: More Work Required MAC: 2024-04-17 18:02:56Z - status set to: More work required. Bring back on May 6. MAC: 2024-03-07 20:29:33Z - status set to: Discuss |  |  |  | 2024-04-29 14:57 | MAC
7213 | RISON, Mark | 1002 | 5 | 11.5.3.4 | 2588 | 63 | T | Yes | 2588 | 63 | 11.5.3.4 |  | V | Mark Rison | 11-24/0702 |  | "a) Discard all MPDUs that have not been acknowledged, up to and including the last (highest in sequence number space) MPDU transmitted, and b) Set the sequence number of the next MPDU to be transmitted outside the block ack agreement to the sequence number immediately after that of the last (highest in sequence number space) MPDU transmitted." should allow last one to be retxed, i.e. a) to allow not last if not acked and b) to say use that SN if retxing | Commenter to bring specific wording proposal | REVISED (MAC: 2024-04-18 20:38:42Z): Incorporate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0702-03-000m-resolutions-for-some-comments-on-11me-d5-0-sa2.docx for CID 7213. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-04-19 04:34:41Z - status set to: Ready for Motion MAC: 2024-03-08 18:59:05Z - status set to: Submission Required |  |  |  | 2024-04-29 15:14 | MAC
7203 | RISON, Mark | 1002 | 5 | 9.4.1.51 | 851 | 12 | T | Yes | 851 | 12 | 9.4.1.51 |  | J | Mark Rison |  |  | Table 9-110--Subfield values of the Operating Mode field "Channel Width If the Rx NSS Type subfield is 0, indicates the supported channel width:" has lost the encodings for width for non-VHT HT STAs! | Restore from previous draft | REJECTED (MAC: 2024-05-16 07:34:46Z): Operating Mode was introduced by 11ac, and thus not parsed by non-VHT HT STAs. Therefore, there is no need to define encoding for non-VHT HT STAs. Furthermore, prior REVme drafts did not have encoding for non-VHT HT STAs. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-16 07:35:44Z - status set to: Ready for Motion MAC: 2024-03-07 21:08:11Z - Not been present since -2016. If it's valid to be present, this need explanation and submission. MAC: 2024-03-07 21:08:05Z - status set to: Submission Required |  |  |  | 2024-05-16 07:36 | MAC
7195 | RISON, Mark | 1002 | 5 | 11 |  |  | T | Yes |  |  | 11 |  | J | Mark Rison |  |  | The term "BSS configuration" is used but not defined | Define it | REJECTED (MAC: 2024-05-15 13:21:26Z): The comment fails to provide sufficient details so that a resolution can be identified that would satisfy the commenter. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-15 13:22:19Z - status set to: Ready for Motion MAC: 2024-04-18 20:10:23Z - status set to: More Work Required. Bring back at May interim. MAC: 2024-03-07 20:43:26Z - status set to: Submission Required |  |  |  | 2024-05-15 13:22 | MAC
7160 | RISON, Mark | 1002 | 5 | 9.6.7.7 |  |  | T | Yes |  |  | 9.6.7.7 |  | V | Mark Rison | 11-24/0702 |  | It should be possible to specify a Max Channel Switch Time in an ECSA frame | At the end of Figure 9-1191—Extended Channel Switch Announcement frame Action field format add a cell "Max Channel Switch Time element" with "Zero or more" above and "6" below. Ditto in Figure 9-1178—Channel Switch Announcement frame Action field format | REVISED (MAC: 2024-04-18 20:25:07Z): Incorporate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0702-02-000m-resolutions-for-some-comments-on-11me-d5-0-sa2.docx for CID 7160. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-13 15:11:04Z - status set to: Ready for Motion MAC: 2024-04-18 20:27:15Z - status set to: More Work Required. Bring back at May interim. (There was a request for more time to review off-line, by Youhan.) MAC: 2024-03-07 20:33:06Z - status set to: Submission Required |  |  |  | 2024-05-13 15:11 | MAC
7151 | RISON, Mark | 1002 | 5 | 9.4.2.261 | 1455 | 41 | T | Yes | 1455 | 41 | 9.4.2.261 |  | V | Mark Rison |  |  | "The Short SSID List field contains the one or more four octet Short SSID fields" -- but "The Short SSID field is defined in 9.4.2.169.3 (Calculating the short SSID)." and that defines the size | Delete " four octet" | REVISED (MAC: 2024-04-29 14:58:24Z): Incorporate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0702-03-000m-resolutions-for-some-comments-on-11me-d5-0-sa2.docx, for CID 7151. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-04-29 15:06:47Z - status set to: Ready for Motion MAC: 2024-04-18 02:51:41Z - status set to: More Work Required MAC: 2024-04-17 18:57:00Z - status set to: More work required. Bring back at May 6 telecon. MAC: 2024-03-07 21:35:38Z - 9.4.2.169.3 does not define a format, only that the calculation results in a 32-bit value. 9.4.2.169.3 is a stretching a bit to talk about the/a Short SSID _field_, without a clear cite of which example(s) of this field this is referencing. The wording around P1680.53 (D5.0) adds to this messiness, without a clear specification of length here, either. MAC: 2024-03-07 21:35:36Z - status set to: Discuss |  |  |  | 2024-04-29 15:07 | MAC
7063 | Qi, Emily | 1002 | 5 | 9.4.2.84 | 1168 | 14 | T | Yes | 1168 | 14 | 9.4.2.84 |  | V | Emily Qi | 11-24/0695 |  | "The Channel Usage element defines the channel usage information for (#6071)channel-usage-aidable BSSs or an off channel TDLS direct link." is not correct. For example, the capability notification can be used for any BSS, not only for "channel-usage-aidable BSS". | delete "The Channel Usage element defines the channel usage information for (#6071)channel-usage-aidable BSSs or an off channel TDLS direct link". | REVISED (MAC: 2024-05-16 07:26:54Z): Change: “The Channel Usage element defines the channel usage information for (#6071) channel-usage-aidable BSSs or an off channel TDLS direct link. “ To: “The Channel Usage element defines channel usage information for a list of channels used in a BSS or an off channel TDLS direct link.” | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-16 07:27:12Z - status set to: Ready for Motion MAC: 2024-04-18 02:51:36Z - status set to: More Work Required MAC: 2024-04-17 21:41:50Z - status set to: More work required. Bring back at May interim. (Several straw polls, none got a clear direction.) MAC: 2024-04-17 18:54:19Z - status set to: Submission Required MAC: 2024-03-08 19:24:44Z - Suggest we have a quick discussion with Channel Usage experts to confirm. MAC: 2024-03-07 21:30:57Z - status set to: Discuss |  |  |  | 2024-05-16 07:27 | MAC
7146 | Levy, Joseph | 1002 | 5 | 11.45.3.2 | 2958 | 50 | T | No | 2958 | 50 | 11.45.3.2 |  | A | Joseph Levy |  |  | The normative verb is missing. | Replace " … the AP discards the HLP packet(s)." With " … the AP shall discard the HLP packet(s)." | ACCEPTED (MAC: 2024-05-15 10:01:28Z) Note to Editor, the location is P2943.50 | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-15 10:01:31Z - status set to: Ready for Motion MAC: 2024-04-18 22:19:45Z - Bring back on May 6 MAC: 2024-03-25 15:56:30Z - Expand the work to the surrounding (and preceeding) paragraphs, and bullet lists. MAC: 2024-03-25 15:56:28Z - status set to: More Work Required. Bring back at ad hoc. MAC: 2024-03-08 19:13:28Z - status set to: Review |  |  |  | 2024-05-15 10:05 | MAC
7108 | Hamilton, Mark | 1002 | 5 | 9.4.2.35 | 1067 | 64 | T | Yes | 1067 | 64 | 9.4.2.35 |  | V | Mark HAMILTON |  |  | What exactly is the meaning of "DMG positioning". This should be a defined term or better description of when to set this bit. | Define "DMG positioning" term. | REVISED (MAC: 2024-05-14 09:45:51Z): Replace “the AP supports DMG positioning” with “the reported AP is a DMG AP and supports FTM measurement (see 11.21.6.4.2.2 (DMG general measurement exchange)).” | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-14 09:45:56Z - status set to: Ready for Motion MAC: 2024-03-07 21:24:28Z - status set to: Submission Required |  |  |  | 2024-05-14 09:46 | MAC
7001 | Adachi, Tomoko | 1002 | 5 | 11.21.15 |  |  | T | No |  |  | 11.21.15 |  | V | Tomoko Adachi | 11-24/732 |  | The Channel Usage Respose frame can include a Transmit Power Envelope element (9.6.13.25). This element is an optional field but it needs to be used when channel usage procedure targeting especially 6 GHz in order for a STA to meet regulatory requirements therein. However, in 11.21.15, there is no description of a Transmit Power Envelope element. | Change the second parent item under the paragraph starting with "Upon receipt of a Channel Usage element in the Probe Response or Channel Usage Response frame, the receiving STA may use the following:" in 11.21.15 from "The Power Constraint element, if present, ..." to "The Power Constraint element or the Transmit Power Envelope element, if present, …". Change "The Transmit Power Envelope element field is defined in 9.4.2.160 (Transmit Power Envelope element)." in 9.6.13.25 to "The Transmit Power Envelope Element field includes zero or one Transmit Power Envelope elements described in 9.4.2.160 (Transmit Power Envelope element). The use of the Transmit Power Envelope element included in the Transmit Power Envelope Element field is described in 11.21.15 (Channel usage procedures)." Change "Transmit Power Envelope element (optional)" in Figure 9-1293 to "Transmit Power Envelope Element (optional)". | REVISED (MAC: 2024-05-13 14:55:09Z): Incorporate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0732-01-000m-resolution-for-cid-7001.docx. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-13 15:02:22Z - status set to: Ready for Motion MAC: 2024-03-12 23:58:28Z - status set to: More work Required. Schedule for May interim. MAC: 2024-03-07 20:26:56Z - status set to: Review |  |  |  | 2024-05-13 15:03 | MAC
7091 | Kneckt, Jarkko | 1002 | 5 | 10.23.2.9 | 2022 | 15 | T | Yes | 2022 | 15 | 10.23.2.9 |  | J | Reza Hedayat |  |  | Current spec allows tarnsmitter to exceed TXOP limit for initial transmission of an MSDU under a block ack agreement. However, for some cases, although a device tries to establish a block ack agreement with a peer, the peer device may reject it. It’d make sense to extend the allowance (under “Initial transmission of an MSDU …") to also be applicable to the cases where a block ack agreement is not set. | Remove “under a block ack agreement” from the bullet: "Initial transmission of an MSDU under a block ack agreement, where the MSDU is not in an A-MPDU consisting of more than one MPDU and the MSDU is not in an A-MSDU." | REJECTED (MAC: 2024-05-14 14:57:56Z): No consensus. Discussion included whether we believe Fragmentation is never used in practice, and if so should we decprate it? Concern that if this change is made, TXOP Limit will have no practical meaning anymore, because almost everything can be excepted from the rule. A Straw Poll was held to Accept the Proposed Change, result: 3-6-2, failed | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-16 07:06:29Z - status set to: Ready for Motion MAC: 2024-03-25 15:03:24Z - status set to: More Work Required. Bring back at the ad hoc. MAC: 2024-03-08 18:46:08Z - status set to: Review |  |  |  | 2024-05-16 07:07 | MAC
7084 | Asterjadhi, Alfred | 1002 | 5 | 26.8.3.3 |  |  | T | Yes |  |  | 26.8.3.3 |  | V | Alfred Asterjadhi |  |  | Similar comment to the AP side, now on the STA side. If the obtained TWT from a TWT parameter set is pointing to a value in the past (as opposed to the future) then this is because the frame containing the TWT field has been waiting in the queue for enough time to cause the partial TSF value rotation. Hence the STA needs to ensure that the correct value is determined (i.e., in the future rather than the past). | Clarify that if the obtained TWT from frames that contain partial TWT information is referring to the past then the actual value is the one that is obtained by assuming a 12 bit rotation (i.e., MSB of the main TWT is increased by one). Check that this issue is fixed for all fields that contain a future time in the format of a partial TSF (e.g., TACT, STACK, TWT infor, TSPECT, etc). Refer to 11-23/2155 for an example resolution. | REVISED (MAC: 2024-04-17 17:17:10Z): Agree in principle with the comment. Proposed resolution clarifies the wording on the AP side behavior and addresses the ambiguity at the STA side by adding a note and declarative descriptions regarding how to obtain the subsequent TWTs based on the TWT and TWT wake interval fields. Went over STACK, TACK, TSPEC, and TWT INFORMATION frames and add a similar note wherever applicable. This is aligned with the proposal in 11-23/2155r1, which was also discussed. Tgme editor: Incorporate the changes as shown in https://mentor.ieee.org/802.11/dcn/24/11-24-0705-02-000m-cr-for-assigned-cid-on-twt.docx under all headings that include CID 7084. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-04-29 14:49:31Z - status set to: Ready for Motion MAC: 2024-04-18 02:50:59Z - status set to: More Work Required MAC: 2024-04-18 02:45:28Z - status set to: More work required. Bring back at May 6 telecon. MAC: 2024-03-07 20:43:09Z - status set to: Submission Required |  |  |  | 2024-04-29 14:50 | MAC
7083 | Asterjadhi, Alfred | 1002 | 5 | 26.8.3.2 |  |  | T | Yes |  |  | 26.8.3.2 |  |  | Alfred Asterjadhi |  |  | Since the TWT contains a partial TSF value it is possible that when the STA schedules for transmission the frame the TWT value might refer to a time that has actually passed when the frame is actually transmitted (16 bit rotation happens between the queueing and actual transmission). I think this may be an issue for different functionalities that are relying on partial TSFs and intend to signal a future value. | Please fix the issue for TWT field in B-TWT, and also check the cases of STACK, TACK, TSPEC, TWT Information frame, etc. Refer to 11-23/2155 for an example resolution | REVISED (MAC: 2024-04-17 17:15:30Z): Agree in principle with the comment. Proposed resolution clarifies the wording on the AP side behavior and addresses the ambiguity at the STA side by adding a note and declarative descriptions regarding how to obtain the subsequent TWTs based on the TWT and TWT wake interval fields. Went over STACK, TACK, TSPEC, and TWT INFORMATION frames and add a similar note wherever applicable. This is aligned with the proposal in 11-23/2155r1, which was also discussed. Tgme editor: Incorporate the changes as shown in https://mentor.ieee.org/802.11/dcn/24/11-24-0705-02-000m-cr-for-assigned-cid-on-twt.docx under all headings that include CID 7083. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-04-29 14:48:58Z - status set to: Ready for Motion MAC: 2024-04-18 02:50:47Z - status set to: More Work Required MAC: 2024-04-18 02:44:59Z - status set to: More work required. Bring back at May 6 telecon MAC: 2024-03-07 20:26:09Z - status set to: Submission Required |  |  |  | 2024-04-29 14:49 | MAC
7077 | Qi, Emily | 1002 | 5 | 11.1.4.7 | 2487 | 13 | T | Yes | 2487 | 13 | 11.1.4.7 |  | V | Mark HAMILTON | 11-24/566 |  | Clause 6 issue - couldn’t find 6.3.128.5 | as in comment. | REVISED (MAC: 2024-04-29 14:44:34Z): Incorproate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0747-01-000m-resolution-of-cid-7077.docx | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-04-29 14:47:24Z - status set to: Ready for Motion MAC: 2024-04-19 04:45:04Z - status set to: More Work Required MAC: 2024-04-18 18:50:52Z - status set to: More Work Required. Bring back at April 29. ACTION: (Mark HAMILTON): Do something with the table in 6.3.128.5.2 (in 11bd), to not need this in clause 6 (and also fix up the cross-references at the same time). MAC: 2024-03-08 19:27:46Z - Assign to Emily to find a volunteer. MAC: 2024-03-08 18:56:46Z - status set to: Submission Required |  |  |  | 2024-05-13 15:59 | MAC
7076 | Qi, Emily | 1002 | 5 | 10.23.2.8 | 2019 | 32 | T | Yes | 2019 | 32 | 10.23.2.8 |  | V | Stephen Sand |  |  | 11bd work item -11bd instructs TGme editor to insert new items after the item beginning “A Ranging NDP Announcement frame followed after a SIFS by an HE Ranging NDP…” (inserted by IEEE Std 802.11az-2022) at the end of the dashed list after the first paragraph of 10.23.2.8 as follows. However, the cited location cannot be identified in D4.0 | as in comment. | REVISED (MAC: 2024-05-06 15:28:24Z): Incorporate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0771-02-000m-sa-ballot-cid-7076-comment-resolution.docx | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-06 15:29:09Z - status set to: Ready for Motion MAC: 2024-03-08 19:27:08Z - Assign to Emily to find a volunteer. MAC: 2024-03-08 18:43:21Z - status set to: Submission Required |  |  |  | 2024-05-16 07:28 | MAC
7075 | Qi, Emily | 1002 | 5 | 10.23.2.8 | 2019 | 28 | T | Yes | 2019 | 28 | 10.23.2.8 |  | V | Jonathan Segev | 11-24/690 |  | 11az work item - 11az instructs TGme editor to insert new item after the item beginning “A BFRP Trigger frame…” at the end of the dashed list after the first paragraph of 10.23.2.8. However, the cited location cannot be identified in D4.0. | as in comment. | REVISED (MAC: 2024-05-14 09:19:33Z): Incorporate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0865-01-000m-cid-7075.docx. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-14 09:40:55Z - status set to: Ready for Motion MAC: 2024-04-18 02:51:46Z - status set to: More Work Required MAC: 2024-04-17 23:30:18Z - status set to: More work required. Bring back at the May interim. MAC: 2024-03-08 19:26:43Z - Assign to Emily to find a volunteer. MAC: 2024-03-08 18:43:14Z - status set to: Submission Required |  |  |  | 2024-05-14 09:41 | MAC
7071 | Qi, Emily | 1002 | 5 | 10.2.3.2 | 1756 | 65 | T | Yes | 1756 | 65 | 10.2.3.2 |  | J | Graham Smith | 11-24/566 |  | 6.3.55(Timing measurement) was deleted in D2.0. The reference needs to be updated. | as in comment. | REJECTED (MAC: 2024-05-16 07:31:03Z): No such reference at D5.0 L1756L65. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-16 07:31:13Z - status set to: Ready for Motion MAC: 2024-04-18 18:58:56Z - Also note CID 7067. MAC: 2024-03-07 21:54:23Z - The (bad?) reference no longer appears (was removed as part of the clause 6.3 clean-up?), so the CRC will need help with a reminder what the reference is, to be able to update it. Similar text/change appears on P1674.47. This appears to be intentional. But, the [fine] timing measurement figures seem to be gone; were they supposed to be moved? MAC: 2024-03-07 21:54:20Z - status set to: Submission Required |  |  |  | 2024-05-16 07:31 | MAC
7024 | Wang, Xiaofei | 1002 | 5 | 26.1 | 4047 | 7 | T | Yes | 4047 | 7 | 26.1 |  | V | Xiaofei Wang | 11-24/718 |  | The spec needs to clearly define what the word "supports" means. Traditional if a STA "supports" a feature or functionality, it means that it implements it. However, this sentence "An HE STA supports the MAC and MLME functions defined in Clause 26 (High-efficiency (HE) MAC specification(11ax)) in addition to the MAC functions defined in Clause 10 (MAC sublayer functional description), the MLME functions defined in Clause 11 (MLME), and the security functions defined in Clause 12 (Security), except when the functions in Clause 26 (High-efficiency (HE) MAC specification(11ax)) supersede the functions in Clause 10 (MAC sublayer functional description) or Clause 11 (MLME)." causes confusion since a STA clearly does not always "support" all the functions defined in all these clauses. This sentence in RevME has been used as a base for rejecting another occurrence of the word "support" for a later amendment claiming that this sentence implies that "supports feature A" does not always mean a device will implement feature A. | either define "supports" can mean optionally implement, or use a different words to convey the meaning. | REVISED (MAC: 2024-05-13 15:03:44Z): Incorporate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0718-03-000m-cr-for-cid-7024.docx. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-13 15:06:48Z - status set to: Ready for Motion MAC: 2024-04-18 02:51:54Z - status set to: More Work Required MAC: 2024-04-17 20:21:04Z - status set to: More work required. Bring back at May interim. MAC: 2024-04-17 20:17:44Z - "An HE STA [shall?] support [/implement?] [all?] the *mandatory* MAC and MLME functions defined in Clause 26 …" MAC: 2024-03-08 19:14:22Z - status set to: Discuss |  |  |  | 2024-05-13 15:07 | MAC
7137 | Levy, Joseph | 1002 | 5 | 9.9.3.4 | 1879 | 40 | T | No | 1879 | 40 | 9.9.3.4 |  | J | Joseph Levy |  |  | WUR uses term "ID field" to describe the WUR 12 bit ID field, this is very confusing as the term ID field is used throughout the specification and is not a 12 bit field and is usually better named: e.g., Fragment ID field, Band ID field, Element ID field, etc.. Where the WUR text refers to the "WUR ID field" as simply the "ID field" should be corrected to eliminate any possible confusion. | Replace "ID field" with "WUR ID field" at the following locations: 1874.20,22,31,48 1876.50 1877.4,17 1878.12,59 1879.40 4807.6,56.62 4808.4(2),15,18,56 4809.20 4819.62 4820.1,5,13 4825.60 219.13 227.53 | REJECTED (MAC: 2024-05-15 12:08:47Z): The comment was withdran by the commenter | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-15 12:09:08Z - status set to: Ready for Motion MAC: 2024-04-18 22:20:21Z - Bring back on May 6 MAC: 2024-03-25 14:36:34Z - status set to: More Work Required. Bring back at the ad hoc. MAC: 2024-03-08 18:15:06Z - status set to: Review |  |  |  | 2024-05-15 12:09 | MAC

## Motion MAC 7159
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
7159 | RISON, Mark | 1002 | 5 | 21.3.20 | 3709 | 63 | T | Yes | 3709 | 63 | 21.3.20 |  | V | Mark Rison |  |  | It is not clear what action causes transition out of the End Of Wait state in the PHY receive state machines (the location given is just one example) | Have a statement at the start of every subclause with PHY receive state machines: "If no condition is shown for a transition, the transition is unconditional and immediate." | REVISED (MAC: 2024-05-14 16:02:53Z): At the end of Subclause 1.4 add a para: “Where a transition is shown a state machine figure, but no transition condition is shown, the transition occurs as soon as all the state actions have been performed.” | MAC | Motion MAC 7159 | Ready for Motion | MAC: 2024-05-14 16:03:00Z - status set to: Ready for Motion MAC: 2024-04-18 02:51:50Z - status set to: More Work Required MAC: 2024-04-17 19:01:00Z - status set to: More work required. Bring back at May interim. MAC: 2024-03-08 19:14:06Z - status set to: Discuss |  |  |  | 2024-05-16 07:20 | MAC

## Submission Required
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
7086 | Kneckt, Jarkko | 1002 | 5 | 11.21.15 | 2782 | 1 | T | Yes | 2782 | 1 | 11.21.15 |  |  | Jarkko Kneckt |  |  | What happens if a P2P TWT SP overlaps with a normal TWT SP; what would be the behavior of the AP and the STA? | Clarify the AP/STA behaviors in the described event as follows: An AP shall assume STA unavailability during a P2P TWT SP regardless of partially/fully overlapping I/BC/R (not a P2P) TWT SP. i.e. The P2P TWT SP (STA non-availability) has "higher priority" than I/BC/R TWT SPs. |  | MAC | Submission Required | Ready for Motion | MAC: 2024-05-16 07:36:11Z - status set to: Ready for Motion MAC: 2024-03-08 19:02:08Z - status set to: Submission Required |  |  |  | 2024-05-16 07:36 | MAC
7087 | Kneckt, Jarkko | 1002 | 5 | 11.21.15 | 2784 | 20 | T | Yes | 2784 | 20 | 11.21.15 |  |  | Jarkko Kneckt |  |  | Currently BA transmission rules with P2P TWT SPs are not clear. Spec says that BA should be transmitted regardless of the NAV, but also spec says that no transmissions can be made during the P2P TWT SP. | Please clarify that If STA has transmitted UL frames soliciting ACK/BA, then AP shall send ACK /BA even if the STA's negotiated P2P TWT SP starts during or before the BA/ACK transmission. |  | MAC | Submission Required | Ready for Motion | MAC: 2024-05-16 07:36:17Z - status set to: Ready for Motion MAC: 2024-03-08 19:10:54Z - status set to: Submission Required |  |  |  | 2024-05-16 07:36 | MAC
7088 | Kneckt, Jarkko | 1002 | 5 | 11.21.15 | 2784 | 20 | T | Yes | 2784 | 20 | 11.21.15 |  |  | Jarkko Kneckt |  |  | Currently BA transmission rules with P2P TWT SPs are not clear. Spec says that BA should be transmitted regardless of the NAV, but also spec says that no transmissions can be made during the P2P TWT SP. | Please clarify that If AP is transmitting DL frame to STA when P2P TWT SP starts, then STA may send ACK /BA to the AP even if the STA's negotiated P2P TWT SP has started during/before BA/ACK transmission. |  | MAC | Submission Required | Ready for Motion | MAC: 2024-05-16 07:36:22Z - status set to: Ready for Motion MAC: 2024-03-08 19:10:50Z - status set to: Submission Required |  |  |  | 2024-05-16 07:36 | MAC
7089 | Kneckt, Jarkko | 1002 | 5 | 11.21.15 | 2781 | 37 | T | Yes | 2781 | 37 | 11.21.15 |  |  | Jarkko Kneckt |  |  | Peer-to-Peer(P2P) TWT is a promising method to help the coex between infrastructure network and other network activities that the STA is participating in. However, in reality, the P2P clock can drift against the infrastructure BSS clock. The STA should be able to indicate to the AP an uncertainty window around the scheduled p2p TWT SP start time. So at any time in such uncertainty window, the AP should take into account that the p2p activity may have started already. | Please include uncertainty window to the P2P TWT SPs as defined in the comment. |  | MAC | Submission Required | Ready for Motion | MAC: 2024-05-16 07:36:02Z - status set to: Ready for Motion MAC: 2024-03-08 19:00:58Z - status set to: Submission Required |  |  |  | 2024-05-16 07:36 | MAC
7090 | Kneckt, Jarkko | 1002 | 5 | 11.21.15 | 2781 | 37 | T | Yes | 2781 | 37 | 11.21.15 |  |  | Jarkko Kneckt |  |  | The P2P clock can drift against the infrastructure BSS clock.This may cause poor alignment of the P2P TWT SPs operated in A) infrastructure network and B) P2P network. The P2P TWT should have a mechanism to update the P2P TWT SP start time to avoid cumulative clock drift error to exceed certain threshold error duration. | Please provide tools for STA to adjust the P2P TWT SP start time. |  | MAC | Submission Required | Ready for Motion | MAC: 2024-05-16 07:36:06Z - status set to: Ready for Motion MAC: 2024-03-08 19:01:12Z - status set to: Submission Required |  |  |  | 2024-05-16 07:36 | MAC

## Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
7001 | Adachi, Tomoko | 1002 | 5 | 11.21.15 |  |  | T | No |  |  | 11.21.15 |  | V | Tomoko Adachi | 11-24/732 |  | The Channel Usage Respose frame can include a Transmit Power Envelope element (9.6.13.25). This element is an optional field but it needs to be used when channel usage procedure targeting especially 6 GHz in order for a STA to meet regulatory requirements therein. However, in 11.21.15, there is no description of a Transmit Power Envelope element. | Change the second parent item under the paragraph starting with "Upon receipt of a Channel Usage element in the Probe Response or Channel Usage Response frame, the receiving STA may use the following:" in 11.21.15 from "The Power Constraint element, if present, ..." to "The Power Constraint element or the Transmit Power Envelope element, if present, …". Change "The Transmit Power Envelope element field is defined in 9.4.2.160 (Transmit Power Envelope element)." in 9.6.13.25 to "The Transmit Power Envelope Element field includes zero or one Transmit Power Envelope elements described in 9.4.2.160 (Transmit Power Envelope element). The use of the Transmit Power Envelope element included in the Transmit Power Envelope Element field is described in 11.21.15 (Channel usage procedures)." Change "Transmit Power Envelope element (optional)" in Figure 9-1293 to "Transmit Power Envelope Element (optional)". | REVISED (MAC: 2024-05-13 14:55:09Z): Incorporate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0732-01-000m-resolution-for-cid-7001.docx. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-13 15:02:22Z - status set to: Ready for Motion MAC: 2024-03-12 23:58:28Z - status set to: More work Required. Schedule for May interim. MAC: 2024-03-07 20:26:56Z - status set to: Review |  |  |  | 2024-05-13 15:03 | MAC
7024 | Wang, Xiaofei | 1002 | 5 | 26.1 | 4047 | 7 | T | Yes | 4047 | 7 | 26.1 |  | V | Xiaofei Wang | 11-24/718 |  | The spec needs to clearly define what the word "supports" means. Traditional if a STA "supports" a feature or functionality, it means that it implements it. However, this sentence "An HE STA supports the MAC and MLME functions defined in Clause 26 (High-efficiency (HE) MAC specification(11ax)) in addition to the MAC functions defined in Clause 10 (MAC sublayer functional description), the MLME functions defined in Clause 11 (MLME), and the security functions defined in Clause 12 (Security), except when the functions in Clause 26 (High-efficiency (HE) MAC specification(11ax)) supersede the functions in Clause 10 (MAC sublayer functional description) or Clause 11 (MLME)." causes confusion since a STA clearly does not always "support" all the functions defined in all these clauses. This sentence in RevME has been used as a base for rejecting another occurrence of the word "support" for a later amendment claiming that this sentence implies that "supports feature A" does not always mean a device will implement feature A. | either define "supports" can mean optionally implement, or use a different words to convey the meaning. | REVISED (MAC: 2024-05-13 15:03:44Z): Incorporate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0718-03-000m-cr-for-cid-7024.docx. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-13 15:06:48Z - status set to: Ready for Motion MAC: 2024-04-18 02:51:54Z - status set to: More Work Required MAC: 2024-04-17 20:21:04Z - status set to: More work required. Bring back at May interim. MAC: 2024-04-17 20:17:44Z - "An HE STA [shall?] support [/implement?] [all?] the *mandatory* MAC and MLME functions defined in Clause 26 …" MAC: 2024-03-08 19:14:22Z - status set to: Discuss |  |  |  | 2024-05-13 15:07 | MAC
7063 | Qi, Emily | 1002 | 5 | 9.4.2.84 | 1168 | 14 | T | Yes | 1168 | 14 | 9.4.2.84 |  | V | Emily Qi | 11-24/0695 |  | "The Channel Usage element defines the channel usage information for (#6071)channel-usage-aidable BSSs or an off channel TDLS direct link." is not correct. For example, the capability notification can be used for any BSS, not only for "channel-usage-aidable BSS". | delete "The Channel Usage element defines the channel usage information for (#6071)channel-usage-aidable BSSs or an off channel TDLS direct link". | REVISED (MAC: 2024-05-16 07:26:54Z): Change: “The Channel Usage element defines the channel usage information for (#6071) channel-usage-aidable BSSs or an off channel TDLS direct link. “ To: “The Channel Usage element defines channel usage information for a list of channels used in a BSS or an off channel TDLS direct link.” | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-16 07:27:12Z - status set to: Ready for Motion MAC: 2024-04-18 02:51:36Z - status set to: More Work Required MAC: 2024-04-17 21:41:50Z - status set to: More work required. Bring back at May interim. (Several straw polls, none got a clear direction.) MAC: 2024-04-17 18:54:19Z - status set to: Submission Required MAC: 2024-03-08 19:24:44Z - Suggest we have a quick discussion with Channel Usage experts to confirm. MAC: 2024-03-07 21:30:57Z - status set to: Discuss |  |  |  | 2024-05-16 07:27 | MAC
7071 | Qi, Emily | 1002 | 5 | 10.2.3.2 | 1756 | 65 | T | Yes | 1756 | 65 | 10.2.3.2 |  | J | Graham Smith | 11-24/566 |  | 6.3.55(Timing measurement) was deleted in D2.0. The reference needs to be updated. | as in comment. | REJECTED (MAC: 2024-05-16 07:31:03Z): No such reference at D5.0 L1756L65. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-16 07:31:13Z - status set to: Ready for Motion MAC: 2024-04-18 18:58:56Z - Also note CID 7067. MAC: 2024-03-07 21:54:23Z - The (bad?) reference no longer appears (was removed as part of the clause 6.3 clean-up?), so the CRC will need help with a reminder what the reference is, to be able to update it. Similar text/change appears on P1674.47. This appears to be intentional. But, the [fine] timing measurement figures seem to be gone; were they supposed to be moved? MAC: 2024-03-07 21:54:20Z - status set to: Submission Required |  |  |  | 2024-05-16 07:31 | MAC
7075 | Qi, Emily | 1002 | 5 | 10.23.2.8 | 2019 | 28 | T | Yes | 2019 | 28 | 10.23.2.8 |  | V | Jonathan Segev | 11-24/690 |  | 11az work item - 11az instructs TGme editor to insert new item after the item beginning “A BFRP Trigger frame…” at the end of the dashed list after the first paragraph of 10.23.2.8. However, the cited location cannot be identified in D4.0. | as in comment. | REVISED (MAC: 2024-05-14 09:19:33Z): Incorporate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0865-01-000m-cid-7075.docx. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-14 09:40:55Z - status set to: Ready for Motion MAC: 2024-04-18 02:51:46Z - status set to: More Work Required MAC: 2024-04-17 23:30:18Z - status set to: More work required. Bring back at the May interim. MAC: 2024-03-08 19:26:43Z - Assign to Emily to find a volunteer. MAC: 2024-03-08 18:43:14Z - status set to: Submission Required |  |  |  | 2024-05-14 09:41 | MAC
7076 | Qi, Emily | 1002 | 5 | 10.23.2.8 | 2019 | 32 | T | Yes | 2019 | 32 | 10.23.2.8 |  | V | Stephen Sand |  |  | 11bd work item -11bd instructs TGme editor to insert new items after the item beginning “A Ranging NDP Announcement frame followed after a SIFS by an HE Ranging NDP…” (inserted by IEEE Std 802.11az-2022) at the end of the dashed list after the first paragraph of 10.23.2.8 as follows. However, the cited location cannot be identified in D4.0 | as in comment. | REVISED (MAC: 2024-05-06 15:28:24Z): Incorporate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0771-02-000m-sa-ballot-cid-7076-comment-resolution.docx | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-06 15:29:09Z - status set to: Ready for Motion MAC: 2024-03-08 19:27:08Z - Assign to Emily to find a volunteer. MAC: 2024-03-08 18:43:21Z - status set to: Submission Required |  |  |  | 2024-05-16 07:28 | MAC
7077 | Qi, Emily | 1002 | 5 | 11.1.4.7 | 2487 | 13 | T | Yes | 2487 | 13 | 11.1.4.7 |  | V | Mark HAMILTON | 11-24/566 |  | Clause 6 issue - couldn’t find 6.3.128.5 | as in comment. | REVISED (MAC: 2024-04-29 14:44:34Z): Incorproate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0747-01-000m-resolution-of-cid-7077.docx | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-04-29 14:47:24Z - status set to: Ready for Motion MAC: 2024-04-19 04:45:04Z - status set to: More Work Required MAC: 2024-04-18 18:50:52Z - status set to: More Work Required. Bring back at April 29. ACTION: (Mark HAMILTON): Do something with the table in 6.3.128.5.2 (in 11bd), to not need this in clause 6 (and also fix up the cross-references at the same time). MAC: 2024-03-08 19:27:46Z - Assign to Emily to find a volunteer. MAC: 2024-03-08 18:56:46Z - status set to: Submission Required |  |  |  | 2024-05-13 15:59 | MAC
7083 | Asterjadhi, Alfred | 1002 | 5 | 26.8.3.2 |  |  | T | Yes |  |  | 26.8.3.2 |  |  | Alfred Asterjadhi |  |  | Since the TWT contains a partial TSF value it is possible that when the STA schedules for transmission the frame the TWT value might refer to a time that has actually passed when the frame is actually transmitted (16 bit rotation happens between the queueing and actual transmission). I think this may be an issue for different functionalities that are relying on partial TSFs and intend to signal a future value. | Please fix the issue for TWT field in B-TWT, and also check the cases of STACK, TACK, TSPEC, TWT Information frame, etc. Refer to 11-23/2155 for an example resolution | REVISED (MAC: 2024-04-17 17:15:30Z): Agree in principle with the comment. Proposed resolution clarifies the wording on the AP side behavior and addresses the ambiguity at the STA side by adding a note and declarative descriptions regarding how to obtain the subsequent TWTs based on the TWT and TWT wake interval fields. Went over STACK, TACK, TSPEC, and TWT INFORMATION frames and add a similar note wherever applicable. This is aligned with the proposal in 11-23/2155r1, which was also discussed. Tgme editor: Incorporate the changes as shown in https://mentor.ieee.org/802.11/dcn/24/11-24-0705-02-000m-cr-for-assigned-cid-on-twt.docx under all headings that include CID 7083. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-04-29 14:48:58Z - status set to: Ready for Motion MAC: 2024-04-18 02:50:47Z - status set to: More Work Required MAC: 2024-04-18 02:44:59Z - status set to: More work required. Bring back at May 6 telecon MAC: 2024-03-07 20:26:09Z - status set to: Submission Required |  |  |  | 2024-04-29 14:49 | MAC
7084 | Asterjadhi, Alfred | 1002 | 5 | 26.8.3.3 |  |  | T | Yes |  |  | 26.8.3.3 |  | V | Alfred Asterjadhi |  |  | Similar comment to the AP side, now on the STA side. If the obtained TWT from a TWT parameter set is pointing to a value in the past (as opposed to the future) then this is because the frame containing the TWT field has been waiting in the queue for enough time to cause the partial TSF value rotation. Hence the STA needs to ensure that the correct value is determined (i.e., in the future rather than the past). | Clarify that if the obtained TWT from frames that contain partial TWT information is referring to the past then the actual value is the one that is obtained by assuming a 12 bit rotation (i.e., MSB of the main TWT is increased by one). Check that this issue is fixed for all fields that contain a future time in the format of a partial TSF (e.g., TACT, STACK, TWT infor, TSPECT, etc). Refer to 11-23/2155 for an example resolution. | REVISED (MAC: 2024-04-17 17:17:10Z): Agree in principle with the comment. Proposed resolution clarifies the wording on the AP side behavior and addresses the ambiguity at the STA side by adding a note and declarative descriptions regarding how to obtain the subsequent TWTs based on the TWT and TWT wake interval fields. Went over STACK, TACK, TSPEC, and TWT INFORMATION frames and add a similar note wherever applicable. This is aligned with the proposal in 11-23/2155r1, which was also discussed. Tgme editor: Incorporate the changes as shown in https://mentor.ieee.org/802.11/dcn/24/11-24-0705-02-000m-cr-for-assigned-cid-on-twt.docx under all headings that include CID 7084. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-04-29 14:49:31Z - status set to: Ready for Motion MAC: 2024-04-18 02:50:59Z - status set to: More Work Required MAC: 2024-04-18 02:45:28Z - status set to: More work required. Bring back at May 6 telecon. MAC: 2024-03-07 20:43:09Z - status set to: Submission Required |  |  |  | 2024-04-29 14:50 | MAC
7086 | Kneckt, Jarkko | 1002 | 5 | 11.21.15 | 2782 | 1 | T | Yes | 2782 | 1 | 11.21.15 |  |  | Jarkko Kneckt |  |  | What happens if a P2P TWT SP overlaps with a normal TWT SP; what would be the behavior of the AP and the STA? | Clarify the AP/STA behaviors in the described event as follows: An AP shall assume STA unavailability during a P2P TWT SP regardless of partially/fully overlapping I/BC/R (not a P2P) TWT SP. i.e. The P2P TWT SP (STA non-availability) has "higher priority" than I/BC/R TWT SPs. |  | MAC | Submission Required | Ready for Motion | MAC: 2024-05-16 07:36:11Z - status set to: Ready for Motion MAC: 2024-03-08 19:02:08Z - status set to: Submission Required |  |  |  | 2024-05-16 07:36 | MAC
7087 | Kneckt, Jarkko | 1002 | 5 | 11.21.15 | 2784 | 20 | T | Yes | 2784 | 20 | 11.21.15 |  |  | Jarkko Kneckt |  |  | Currently BA transmission rules with P2P TWT SPs are not clear. Spec says that BA should be transmitted regardless of the NAV, but also spec says that no transmissions can be made during the P2P TWT SP. | Please clarify that If STA has transmitted UL frames soliciting ACK/BA, then AP shall send ACK /BA even if the STA's negotiated P2P TWT SP starts during or before the BA/ACK transmission. |  | MAC | Submission Required | Ready for Motion | MAC: 2024-05-16 07:36:17Z - status set to: Ready for Motion MAC: 2024-03-08 19:10:54Z - status set to: Submission Required |  |  |  | 2024-05-16 07:36 | MAC
7088 | Kneckt, Jarkko | 1002 | 5 | 11.21.15 | 2784 | 20 | T | Yes | 2784 | 20 | 11.21.15 |  |  | Jarkko Kneckt |  |  | Currently BA transmission rules with P2P TWT SPs are not clear. Spec says that BA should be transmitted regardless of the NAV, but also spec says that no transmissions can be made during the P2P TWT SP. | Please clarify that If AP is transmitting DL frame to STA when P2P TWT SP starts, then STA may send ACK /BA to the AP even if the STA's negotiated P2P TWT SP has started during/before BA/ACK transmission. |  | MAC | Submission Required | Ready for Motion | MAC: 2024-05-16 07:36:22Z - status set to: Ready for Motion MAC: 2024-03-08 19:10:50Z - status set to: Submission Required |  |  |  | 2024-05-16 07:36 | MAC
7089 | Kneckt, Jarkko | 1002 | 5 | 11.21.15 | 2781 | 37 | T | Yes | 2781 | 37 | 11.21.15 |  |  | Jarkko Kneckt |  |  | Peer-to-Peer(P2P) TWT is a promising method to help the coex between infrastructure network and other network activities that the STA is participating in. However, in reality, the P2P clock can drift against the infrastructure BSS clock. The STA should be able to indicate to the AP an uncertainty window around the scheduled p2p TWT SP start time. So at any time in such uncertainty window, the AP should take into account that the p2p activity may have started already. | Please include uncertainty window to the P2P TWT SPs as defined in the comment. |  | MAC | Submission Required | Ready for Motion | MAC: 2024-05-16 07:36:02Z - status set to: Ready for Motion MAC: 2024-03-08 19:00:58Z - status set to: Submission Required |  |  |  | 2024-05-16 07:36 | MAC
7090 | Kneckt, Jarkko | 1002 | 5 | 11.21.15 | 2781 | 37 | T | Yes | 2781 | 37 | 11.21.15 |  |  | Jarkko Kneckt |  |  | The P2P clock can drift against the infrastructure BSS clock.This may cause poor alignment of the P2P TWT SPs operated in A) infrastructure network and B) P2P network. The P2P TWT should have a mechanism to update the P2P TWT SP start time to avoid cumulative clock drift error to exceed certain threshold error duration. | Please provide tools for STA to adjust the P2P TWT SP start time. |  | MAC | Submission Required | Ready for Motion | MAC: 2024-05-16 07:36:06Z - status set to: Ready for Motion MAC: 2024-03-08 19:01:12Z - status set to: Submission Required |  |  |  | 2024-05-16 07:36 | MAC
7091 | Kneckt, Jarkko | 1002 | 5 | 10.23.2.9 | 2022 | 15 | T | Yes | 2022 | 15 | 10.23.2.9 |  | J | Reza Hedayat |  |  | Current spec allows tarnsmitter to exceed TXOP limit for initial transmission of an MSDU under a block ack agreement. However, for some cases, although a device tries to establish a block ack agreement with a peer, the peer device may reject it. It’d make sense to extend the allowance (under “Initial transmission of an MSDU …") to also be applicable to the cases where a block ack agreement is not set. | Remove “under a block ack agreement” from the bullet: "Initial transmission of an MSDU under a block ack agreement, where the MSDU is not in an A-MPDU consisting of more than one MPDU and the MSDU is not in an A-MSDU." | REJECTED (MAC: 2024-05-14 14:57:56Z): No consensus. Discussion included whether we believe Fragmentation is never used in practice, and if so should we decprate it? Concern that if this change is made, TXOP Limit will have no practical meaning anymore, because almost everything can be excepted from the rule. A Straw Poll was held to Accept the Proposed Change, result: 3-6-2, failed | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-16 07:06:29Z - status set to: Ready for Motion MAC: 2024-03-25 15:03:24Z - status set to: More Work Required. Bring back at the ad hoc. MAC: 2024-03-08 18:46:08Z - status set to: Review |  |  |  | 2024-05-16 07:07 | MAC
7105 | Hamilton, Mark | 1002 | 5 | 9.3.3.5 | 738 | 20 | T | Yes | 738 | 20 | 9.3.3.5 |  | J | Mark HAMILTON |  |  | What does "ought" mean in this context? "Should"?? "Shall"?? Something non-normative?? Yes, clause 9 is generally not supposed to use normative verbs, but here the intent is now entirely unclear. | Replace "ought" with understandable phrasing. Same thing at P738.31, P741.57, P742.11, P746.48, P746.59, P752.17, P752.28, P757.16, P757.29, P760.16, and P761.11. | REJECTED (MAC: 2024-05-15 09:46:19Z): The commenter does not provide sufficient details to determine a satisfactory resolution. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-15 09:47:17Z - status set to: Ready for Motion MAC: 2024-04-18 02:51:26Z - status set to: More Work Required MAC: 2024-04-17 18:20:34Z - status set to: More work required. Bring back at May interim. MAC: 2024-03-07 20:43:42Z - status set to: Discuss |  |  |  | 2024-05-15 09:47 | MAC
7108 | Hamilton, Mark | 1002 | 5 | 9.4.2.35 | 1067 | 64 | T | Yes | 1067 | 64 | 9.4.2.35 |  | V | Mark HAMILTON |  |  | What exactly is the meaning of "DMG positioning". This should be a defined term or better description of when to set this bit. | Define "DMG positioning" term. | REVISED (MAC: 2024-05-14 09:45:51Z): Replace “the AP supports DMG positioning” with “the reported AP is a DMG AP and supports FTM measurement (see 11.21.6.4.2.2 (DMG general measurement exchange)).” | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-14 09:45:56Z - status set to: Ready for Motion MAC: 2024-03-07 21:24:28Z - status set to: Submission Required |  |  |  | 2024-05-14 09:46 | MAC
7137 | Levy, Joseph | 1002 | 5 | 9.9.3.4 | 1879 | 40 | T | No | 1879 | 40 | 9.9.3.4 |  | J | Joseph Levy |  |  | WUR uses term "ID field" to describe the WUR 12 bit ID field, this is very confusing as the term ID field is used throughout the specification and is not a 12 bit field and is usually better named: e.g., Fragment ID field, Band ID field, Element ID field, etc.. Where the WUR text refers to the "WUR ID field" as simply the "ID field" should be corrected to eliminate any possible confusion. | Replace "ID field" with "WUR ID field" at the following locations: 1874.20,22,31,48 1876.50 1877.4,17 1878.12,59 1879.40 4807.6,56.62 4808.4(2),15,18,56 4809.20 4819.62 4820.1,5,13 4825.60 219.13 227.53 | REJECTED (MAC: 2024-05-15 12:08:47Z): The comment was withdran by the commenter | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-15 12:09:08Z - status set to: Ready for Motion MAC: 2024-04-18 22:20:21Z - Bring back on May 6 MAC: 2024-03-25 14:36:34Z - status set to: More Work Required. Bring back at the ad hoc. MAC: 2024-03-08 18:15:06Z - status set to: Review |  |  |  | 2024-05-15 12:09 | MAC
7142 | Levy, Joseph | 1002 | 5 | 9.4.2.69.2 | 1145 | 25 | T | Yes | 1145 | 25 | 9.4.2.69.2 |  | V | Joseph Levy |  |  | The text: "The exact criteria and mechanism to detect motion is out of scope for this standard." this has nothing to do with the format of the Location Indication Parameters subelement. | Delete: "The exact criteria and mechanism to detect motion is out of scope for this standard." | REVISED (MAC: 2024-05-15 09:58:41Z): Move the cited sentence to P2692.39 (following bullet (2)), as a NOTE-- | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-15 09:59:18Z - status set to: Ready for Motion MAC: 2024-04-18 02:51:30Z - status set to: More Work Required. Bring back at May interim. MAC: 2024-04-17 18:52:35Z - status set to: More work required. MAC: 2024-04-17 18:51:21Z - Started to say: REJECTED (MAC: 2024-04-17 18:48:58Z): This paragraph appears within text that discusses reported detected motion, so noting that the details of how such detection is done is appropriate here. But, considered moving the sentence to a normative clause instead. MwR, assign to Joseph. Bring back at May interim. MAC: 2024-03-07 21:28:42Z - The cited sentence seems to be in the midst of several paragraph that talk about reporting motion, and the "In-Motion…" fields. MAC: 2024-03-07 21:27:45Z - status set to: Discuss |  |  |  | 2024-05-15 09:59 | MAC
7146 | Levy, Joseph | 1002 | 5 | 11.45.3.2 | 2958 | 50 | T | No | 2958 | 50 | 11.45.3.2 |  | A | Joseph Levy |  |  | The normative verb is missing. | Replace " … the AP discards the HLP packet(s)." With " … the AP shall discard the HLP packet(s)." | ACCEPTED (MAC: 2024-05-15 10:01:28Z) Note to Editor, the location is P2943.50 | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-15 10:01:31Z - status set to: Ready for Motion MAC: 2024-04-18 22:19:45Z - Bring back on May 6 MAC: 2024-03-25 15:56:30Z - Expand the work to the surrounding (and preceeding) paragraphs, and bullet lists. MAC: 2024-03-25 15:56:28Z - status set to: More Work Required. Bring back at ad hoc. MAC: 2024-03-08 19:13:28Z - status set to: Review |  |  |  | 2024-05-15 10:05 | MAC
7151 | RISON, Mark | 1002 | 5 | 9.4.2.261 | 1455 | 41 | T | Yes | 1455 | 41 | 9.4.2.261 |  | V | Mark Rison |  |  | "The Short SSID List field contains the one or more four octet Short SSID fields" -- but "The Short SSID field is defined in 9.4.2.169.3 (Calculating the short SSID)." and that defines the size | Delete " four octet" | REVISED (MAC: 2024-04-29 14:58:24Z): Incorporate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0702-03-000m-resolutions-for-some-comments-on-11me-d5-0-sa2.docx, for CID 7151. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-04-29 15:06:47Z - status set to: Ready for Motion MAC: 2024-04-18 02:51:41Z - status set to: More Work Required MAC: 2024-04-17 18:57:00Z - status set to: More work required. Bring back at May 6 telecon. MAC: 2024-03-07 21:35:38Z - 9.4.2.169.3 does not define a format, only that the calculation results in a 32-bit value. 9.4.2.169.3 is a stretching a bit to talk about the/a Short SSID _field_, without a clear cite of which example(s) of this field this is referencing. The wording around P1680.53 (D5.0) adds to this messiness, without a clear specification of length here, either. MAC: 2024-03-07 21:35:36Z - status set to: Discuss |  |  |  | 2024-04-29 15:07 | MAC
7159 | RISON, Mark | 1002 | 5 | 21.3.20 | 3709 | 63 | T | Yes | 3709 | 63 | 21.3.20 |  | V | Mark Rison |  |  | It is not clear what action causes transition out of the End Of Wait state in the PHY receive state machines (the location given is just one example) | Have a statement at the start of every subclause with PHY receive state machines: "If no condition is shown for a transition, the transition is unconditional and immediate." | REVISED (MAC: 2024-05-14 16:02:53Z): At the end of Subclause 1.4 add a para: “Where a transition is shown a state machine figure, but no transition condition is shown, the transition occurs as soon as all the state actions have been performed.” | MAC | Motion MAC 7159 | Ready for Motion | MAC: 2024-05-14 16:03:00Z - status set to: Ready for Motion MAC: 2024-04-18 02:51:50Z - status set to: More Work Required MAC: 2024-04-17 19:01:00Z - status set to: More work required. Bring back at May interim. MAC: 2024-03-08 19:14:06Z - status set to: Discuss |  |  |  | 2024-05-16 07:20 | MAC
7160 | RISON, Mark | 1002 | 5 | 9.6.7.7 |  |  | T | Yes |  |  | 9.6.7.7 |  | V | Mark Rison | 11-24/0702 |  | It should be possible to specify a Max Channel Switch Time in an ECSA frame | At the end of Figure 9-1191—Extended Channel Switch Announcement frame Action field format add a cell "Max Channel Switch Time element" with "Zero or more" above and "6" below. Ditto in Figure 9-1178—Channel Switch Announcement frame Action field format | REVISED (MAC: 2024-04-18 20:25:07Z): Incorporate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0702-02-000m-resolutions-for-some-comments-on-11me-d5-0-sa2.docx for CID 7160. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-13 15:11:04Z - status set to: Ready for Motion MAC: 2024-04-18 20:27:15Z - status set to: More Work Required. Bring back at May interim. (There was a request for more time to review off-line, by Youhan.) MAC: 2024-03-07 20:33:06Z - status set to: Submission Required |  |  |  | 2024-05-13 15:11 | MAC
7195 | RISON, Mark | 1002 | 5 | 11 |  |  | T | Yes |  |  | 11 |  | J | Mark Rison |  |  | The term "BSS configuration" is used but not defined | Define it | REJECTED (MAC: 2024-05-15 13:21:26Z): The comment fails to provide sufficient details so that a resolution can be identified that would satisfy the commenter. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-15 13:22:19Z - status set to: Ready for Motion MAC: 2024-04-18 20:10:23Z - status set to: More Work Required. Bring back at May interim. MAC: 2024-03-07 20:43:26Z - status set to: Submission Required |  |  |  | 2024-05-15 13:22 | MAC
7203 | RISON, Mark | 1002 | 5 | 9.4.1.51 | 851 | 12 | T | Yes | 851 | 12 | 9.4.1.51 |  | J | Mark Rison |  |  | Table 9-110--Subfield values of the Operating Mode field "Channel Width If the Rx NSS Type subfield is 0, indicates the supported channel width:" has lost the encodings for width for non-VHT HT STAs! | Restore from previous draft | REJECTED (MAC: 2024-05-16 07:34:46Z): Operating Mode was introduced by 11ac, and thus not parsed by non-VHT HT STAs. Therefore, there is no need to define encoding for non-VHT HT STAs. Furthermore, prior REVme drafts did not have encoding for non-VHT HT STAs. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-05-16 07:35:44Z - status set to: Ready for Motion MAC: 2024-03-07 21:08:11Z - Not been present since -2016. If it's valid to be present, this need explanation and submission. MAC: 2024-03-07 21:08:05Z - status set to: Submission Required |  |  |  | 2024-05-16 07:36 | MAC
7213 | RISON, Mark | 1002 | 5 | 11.5.3.4 | 2588 | 63 | T | Yes | 2588 | 63 | 11.5.3.4 |  | V | Mark Rison | 11-24/0702 |  | "a) Discard all MPDUs that have not been acknowledged, up to and including the last (highest in sequence number space) MPDU transmitted, and b) Set the sequence number of the next MPDU to be transmitted outside the block ack agreement to the sequence number immediately after that of the last (highest in sequence number space) MPDU transmitted." should allow last one to be retxed, i.e. a) to allow not last if not acked and b) to say use that SN if retxing | Commenter to bring specific wording proposal | REVISED (MAC: 2024-04-18 20:38:42Z): Incorporate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0702-03-000m-resolutions-for-some-comments-on-11me-d5-0-sa2.docx for CID 7213. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-04-19 04:34:41Z - status set to: Ready for Motion MAC: 2024-03-08 18:59:05Z - status set to: Submission Required |  |  |  | 2024-04-29 15:14 | MAC
7224 | RISON, Mark | 1002 | 5 | 9 |  |  | T | Yes |  |  | 9 |  | V | Mark Rison |  |  | Units for Length fields should be specified (typically octets) | Fix in Cookie Length in 9.4.2.306, Emergency Call Number in 9.4.5.5, Redict URL in 9.4.5.6, NAI Realm Data Field Length in 9.4.5.10 | REVISED (MAC: 2024-04-29 14:51:14Z): Incorporate the changes in https://mentor.ieee.org/802.11/dcn/24/11-24-0702-03-000m-resolutions-for-some-comments-on-11me-d5-0-sa2.docx, for CID 7224. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-04-29 14:57:18Z - status set to: Ready for Motion MAC: 2024-04-18 02:51:21Z - status set to: More Work Required MAC: 2024-04-17 18:02:56Z - status set to: More work required. Bring back on May 6. MAC: 2024-03-07 20:29:33Z - status set to: Discuss |  |  |  | 2024-04-29 14:57 | MAC

## Alfred Asterjadhi
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
7083 | Asterjadhi, Alfred | 1002 | 5 | 26.8.3.2 |  |  | T | Yes |  |  | 26.8.3.2 |  |  | Alfred Asterjadhi |  |  | Since the TWT contains a partial TSF value it is possible that when the STA schedules for transmission the frame the TWT value might refer to a time that has actually passed when the frame is actually transmitted (16 bit rotation happens between the queueing and actual transmission). I think this may be an issue for different functionalities that are relying on partial TSFs and intend to signal a future value. | Please fix the issue for TWT field in B-TWT, and also check the cases of STACK, TACK, TSPEC, TWT Information frame, etc. Refer to 11-23/2155 for an example resolution | REVISED (MAC: 2024-04-17 17:15:30Z): Agree in principle with the comment. Proposed resolution clarifies the wording on the AP side behavior and addresses the ambiguity at the STA side by adding a note and declarative descriptions regarding how to obtain the subsequent TWTs based on the TWT and TWT wake interval fields. Went over STACK, TACK, TSPEC, and TWT INFORMATION frames and add a similar note wherever applicable. This is aligned with the proposal in 11-23/2155r1, which was also discussed. Tgme editor: Incorporate the changes as shown in https://mentor.ieee.org/802.11/dcn/24/11-24-0705-02-000m-cr-for-assigned-cid-on-twt.docx under all headings that include CID 7083. | MAC | Motion MAC-BN | Ready for Motion | MAC: 2024-04-29 14:48:58Z - status set to: Ready for Motion MAC: 2024-04-18 02:50:47Z - status set to: More Work Required MAC: 2024-04-18 02:44:59Z - status set to: More work required. Bring back at May 6 telecon MAC: 2024-03-07 20:26:09Z - status set to: Submission Required |  |  |  | 2024-04-29 14:49 | MAC

## Jarkko Kneckt
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
7086 | Kneckt, Jarkko | 1002 | 5 | 11.21.15 | 2782 | 1 | T | Yes | 2782 | 1 | 11.21.15 |  |  | Jarkko Kneckt |  |  | What happens if a P2P TWT SP overlaps with a normal TWT SP; what would be the behavior of the AP and the STA? | Clarify the AP/STA behaviors in the described event as follows: An AP shall assume STA unavailability during a P2P TWT SP regardless of partially/fully overlapping I/BC/R (not a P2P) TWT SP. i.e. The P2P TWT SP (STA non-availability) has "higher priority" than I/BC/R TWT SPs. |  | MAC | Submission Required | Ready for Motion | MAC: 2024-05-16 07:36:11Z - status set to: Ready for Motion MAC: 2024-03-08 19:02:08Z - status set to: Submission Required |  |  |  | 2024-05-16 07:36 | MAC
7087 | Kneckt, Jarkko | 1002 | 5 | 11.21.15 | 2784 | 20 | T | Yes | 2784 | 20 | 11.21.15 |  |  | Jarkko Kneckt |  |  | Currently BA transmission rules with P2P TWT SPs are not clear. Spec says that BA should be transmitted regardless of the NAV, but also spec says that no transmissions can be made during the P2P TWT SP. | Please clarify that If STA has transmitted UL frames soliciting ACK/BA, then AP shall send ACK /BA even if the STA's negotiated P2P TWT SP starts during or before the BA/ACK transmission. |  | MAC | Submission Required | Ready for Motion | MAC: 2024-05-16 07:36:17Z - status set to: Ready for Motion MAC: 2024-03-08 19:10:54Z - status set to: Submission Required |  |  |  | 2024-05-16 07:36 | MAC
7088 | Kneckt, Jarkko | 1002 | 5 | 11.21.15 | 2784 | 20 | T | Yes | 2784 | 20 | 11.21.15 |  |  | Jarkko Kneckt |  |  | Currently BA transmission rules with P2P TWT SPs are not clear. Spec says that BA should be transmitted regardless of the NAV, but also spec says that no transmissions can be made during the P2P TWT SP. | Please clarify that If AP is transmitting DL frame to STA when P2P TWT SP starts, then STA may send ACK /BA to the AP even if the STA's negotiated P2P TWT SP has started during/before BA/ACK transmission. |  | MAC | Submission Required | Ready for Motion | MAC: 2024-05-16 07:36:22Z - status set to: Ready for Motion MAC: 2024-03-08 19:10:50Z - status set to: Submission Required |  |  |  | 2024-05-16 07:36 | MAC
7089 | Kneckt, Jarkko | 1002 | 5 | 11.21.15 | 2781 | 37 | T | Yes | 2781 | 37 | 11.21.15 |  |  | Jarkko Kneckt |  |  | Peer-to-Peer(P2P) TWT is a promising method to help the coex between infrastructure network and other network activities that the STA is participating in. However, in reality, the P2P clock can drift against the infrastructure BSS clock. The STA should be able to indicate to the AP an uncertainty window around the scheduled p2p TWT SP start time. So at any time in such uncertainty window, the AP should take into account that the p2p activity may have started already. | Please include uncertainty window to the P2P TWT SPs as defined in the comment. |  | MAC | Submission Required | Ready for Motion | MAC: 2024-05-16 07:36:02Z - status set to: Ready for Motion MAC: 2024-03-08 19:00:58Z - status set to: Submission Required |  |  |  | 2024-05-16 07:36 | MAC
7090 | Kneckt, Jarkko | 1002 | 5 | 11.21.15 | 2781 | 37 | T | Yes | 2781 | 37 | 11.21.15 |  |  | Jarkko Kneckt |  |  | The P2P clock can drift against the infrastructure BSS clock.This may cause poor alignment of the P2P TWT SPs operated in A) infrastructure network and B) P2P network. The P2P TWT should have a mechanism to update the P2P TWT SP start time to avoid cumulative clock drift error to exceed certain threshold error duration. | Please provide tools for STA to adjust the P2P TWT SP start time. |  | MAC | Submission Required | Ready for Motion | MAC: 2024-05-16 07:36:06Z - status set to: Ready for Motion MAC: 2024-03-08 19:01:12Z - status set to: Submission Required |  |  |  | 2024-05-16 07:36 | MAC