## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: 11-24-0484-02-000m
Venue Date: | April 2024
First Author: | Jon Rosdahl (Qualcomm)
Subject: | REVme GEN ad-hoc comments on SB Recirc-1
Full Date: | 2024-04-22
Author(s): | Name(s) | Jon Rosdahl
| Company | Qualcomm Technologies, Inc.
| Address | 10871 N 5750 W Highland, UT 84003
| Phone: | +1-801-492-4023
| Fax: | +1-801-492-4023
| email: | jrosdahl@ieee.org
Abstract:
This document contains the comments assigned to GEN Adhoc from the SA Recirc-1 Ballot
As the Comment Resolutions are approved, the CIDs will be moved to the Editor, and out of this file.
There is one Tab for all GEN AdHoc Comments
There is one Tab per comment group.
There is one Tab per Assignee (to make it easy to find submission required assignments).
The Ready for Motion tabs are followed by the Technical grouped tabs followed by the individual assigned tabs.

## Revision History
Revision | Date | Description
0 | 2024-03-07 | Initial Allocation of CIDs.- Updated with initial proposed Comment Groups and Adhoc Status -
1 | 2024-03-14 | Update Status to March 13 -- 3 Motion Tabs - "GEN Motion March" (8 CIDs); "GEN Motion EBCS" (1 CID); and :"Gen Motion Amendment" (1 CID)
2 | 2024-04-22 | Update Status through April REVme AdHoc - 7 CIDS left - 2 More work Required -- 5 Submission Required -- 9 GEN Motion April - Ready for Motion
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19

## All GEN Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
7003 | Banavara, Madhusudan | 1002 | 5 |  | 379 | 26 | G | No | 379 | 26 |  |  | J |  |  |  | The use of "non" in the standards has always been confusing and has become increasingly - for example: "Non-AP STA Non-AP MLD and Non-PCP STA" etc. Takes quite a bit of time to figure out what you are referring to and we forget the core of the feature we were reading about. Please use a positive version of these instead or figure out a way to represent these network entities in a less confusing way... |  | REJECTED (GEN: 2024-04-18 23:37:02Z) The use of "non" is an unfortunately necessary naming convention that differentiates legacy features that are not included in the new features. | GEN | GEN Motion April | Ready for Motion | GEN: 2024-04-18 23:37:17Z - status set to: Ready for Motion GEN: 2024-03-08 06:38:42Z - status set to: Submission Required |  |  |  | 2024-04-19 14:56 | GEN
7051 | McCann, Stephen | 1002 | 5 | Contents | 94 | 65 | T | Yes | 94 | 65 | Contents |  | V | Emily Qi | 11-24/696r1 |  | The title of clause 34 should state "MAC specification" to align it with the title of the previous clauses. | Change "34. Enhanced broadcast services procedures(11bc)" to "34. Enhanced broadcast services procedures MAC specification (11bc)" | REVISED (GEN: 2024-04-18 17:04:58Z) - At 4953.1, change the title of clause 34 to “Enhanced broadcast services MAC specification”. | GEN | GEN Motion April | Ready for Motion | GEN: 2024-04-18 17:03:15Z - status set to: Ready for Motion Similar to CID 7059, 7056. GEN: 2024-03-12 00:00:09Z - status set to: More Work Required - Schedule April REVme AdHoc GEN: 2024-03-08 06:40:17Z - status set to: Review Proposed Resolution: Accept |  |  |  | 2024-04-18 17:07 | GEN
7056 | McCann, Stephen | 1002 | 5 | Contents | 94 | 65 | T | Yes | 94 | 65 | Contents |  | J | Emily Qi |  |  | The 11bc CID 5113 (Initial SA Ballot) suggests that clause 34 actually defines MAC sublayer behaviour, which it does. Therefore this clause should be moved to a sub clause of clause 10 and not stand alone. See 11-23-0486r0, "SAB Initial Ballot" tab to find CID 5113. | Move Clause 34 into Clause 10, as 10.71. | REJECTED (GEN: 2024-04-18 16:59:07Z) The CRC reviewed the comment. This comment is same as CID 7059. The motion to approve the resolution for CID 7059 (Move Clause 34 to a sub-clause of clause 11) failed on 3/14/2024 with the motion result of 6 Yes - 7 No - 4 abstain. The implementing proposed changes does not have task group consensus. | GEN | GEN Motion April | Ready for Motion | GEN: 2024-04-18 16:59:12Z - status set to: Ready for Motion GEN: 2024-04-17 00:32:02Z - status set to: More Work Required See CID 7059 Similar issue. Scheduled for April REVme AdHoc. GEN: 2024-03-08 06:48:43Z - status set to: Discuss |  |  |  | 2024-04-18 17:00 | GEN
7059 | Montemurro, Michael | 1002 | 5 | 34 | 4953 | 1 | T | Yes | 4953 | 1 | 34 |  | J | Emily Qi | 11-24/492 |  | During one of the later rounds of SA Ballot, the EBCS clause was moved from a sub-clause of 11 to clause 34 in response to a comment that requested that the EBCS clause be divided between clause 11 and 10. | The commenter will provide a submission to address the comment that restores the clause 11 content and possibly moves some content to clause 10. | REJECTED (GEN: 2024-04-18 16:57:43Z) The CRC reviewed the comment. The motion to approve revised changes (Move Clause 34 to a sub-clause of clause 11) failed on 3/14/2024 with the motion result of 6 Yes - 7 No - 4 abstain. The implementing revised changes does not have task group consensus. | GEN | GEN Motion April | Ready for Motion | GEN: 2024-04-18 16:58:09Z - status set to: Ready for Motion GEN: 2024-03-14 22:27:59Z - status set to: More Work Required - Schedule April REVme AdHoc GEN: 2024-03-13 03:51:45Z - status set to: Ready for Motion - Separate Motion. GEN: 2024-03-08 06:51:04Z - status set to: Submission Required - |  |  |  | 2024-04-18 16:58 | GEN
7065 | Qi, Emily | 1002 | 5 | 3 | 271 | 51 | G | Yes | 271 | 51 | 3 |  |  | Jonathan Segev |  |  | 11az work item - 11az asks to change all instances of “initial fine timing measurement request” to “IFTMR” as appropriate in the next revision of IEEE Std 802.11. Need a submission for those changes. | as in comment. |  | GEN | GEN Submission Required | Submission Required | GEN: 2024-03-08 06:37:43Z - status set to: Submission Required GEN: 2024-03-08 06:32:48Z - status set to: Needs Submission |  |  |  | 2024-03-09 19:04 | GEN
7066 | Qi, Emily | 1002 | 5 | 3 | 271 | 56 | G | Yes | 271 | 56 | 3 |  |  | Emily Qi |  |  | 11az work item - 11az asks to change all instances of “fine timing measurement” to “FTM” as appropriate in the next revision of IEEE Std 802.11. Need a submission for those changes. | as in comment. |  | GEN | GEN Submission Required | Submission Required | GEN: 2024-03-08 06:40:55Z - status set to: Submission Required |  |  |  | 2024-03-09 19:05 | GEN
7067 | Qi, Emily | 1002 | 5 | 6 |  |  | G | Yes |  |  | 6 |  |  | Graham Smith |  |  | Contents in Clause 6 of 11az, 11bd and 11bc cannot be rolled-in due to the Clause 6 structure changes in REVme. This can be resolved by a submission. | as in comment. |  | GEN | GEN Submission Required | Submission Required | GEN: 2024-03-08 06:41:28Z - status set to: Submission Required |  |  |  | 2024-03-09 19:04 | GEN
7110 | Hamilton, Mark | 1002 | 5 | 5.1.5.3 | 369 | 40 | T | Yes | 369 | 40 | 5.1.5.3 |  |  | Stephen McCann |  |  | 1) The EBCS actions only happen if this is an EBCS enabled AP. 2) This text belongs somewhere else, not in the Role-specific behavior block (which does not contain the EBCS traffic stream mapper). | 1) Add qualification that this action occurs if this is an AP operating EBCS. ("In the context of EBCS…" like in 5.1.5.2, perhaps?) 2) Move this text and the associated NOTE 2 to somewhere appropriate. |  | GEN | GEN Submission Required | Submission Required | GEN: 2024-03-08 06:45:18Z - status set to: Submission Required See also CID 7111. |  |  |  | 2024-03-13 03:42 | GEN
7111 | Hamilton, Mark | 1002 | 5 | 5.1.5.2 | 369 | 9 | T | Yes | 369 | 9 | 5.1.5.2 |  |  | Stephen McCann |  |  | 1) The Role-specific behavior (which is what is described in this subclause) doesn't include the EBCS filter. This paragraph belongs somewhere else. 2) This sentence talks about actions of the EBCS filter in DL, but the EBCS filter (per Figure 5-1) is an UL behavior. | 1) Move this text, and the associated NOTE 2, somewhere appropriate. 2) Fix this to talk about the EBCS Traffic Mapper, or change "DL" to "UL", or something?? |  | GEN | GEN Submission Required | Submission Required | GEN: 2024-03-08 06:45:45Z - status set to: Submission Required See also CID 7110. |  |  |  | 2024-03-13 03:43 | GEN
7121 | Levy, Joseph | 1002 | 5 | 6.5.5.2.2 | 442 | 6 | T | Yes | 442 | 6 | 6.5.5.2.2 |  | V | Graham Smith |  |  | The additions made in 802.11az have not been inserted. "Content of PASN Authentication Frame" is not included. | Insert "Content of PASN Authentication Frame" after "Content of FILS Authentication Frame" and before "Vendor SpecificInfo" Note this also applies to 6.5.5.3, | REVISED (GEN: 2024-04-18 20:55:23Z) Incorporate the changes in 11-24/0566r4 (https://mentor.ieee.org/802.11/dcn/24/11-24-0566-04-000m-resolutions-of-cids-7082-7071-7077.docx) for CIDs 7121 and 7122 (GEN). | GEN | GEN Motion April | Ready for Motion | GEN: 2024-04-18 20:55:32Z - status set to: Ready for Motion GEN: 2024-03-11 23:52:31Z - status set to: More Work Required GEN: 2024-03-08 06:46:10Z - status set to: Review Proposed Resolution: Accepted |  |  |  | 2024-04-18 21:05 | GEN
7122 | Levy, Joseph | 1002 | 5 | 6.5.5.2.2 | 442 | 63 | T | Yes | 442 | 63 | 6.5.5.2.2 |  | V | Graham Smith | 11-24/0566r4 |  | The additions made in 802.11az have not been inserted. "Content of PASN Authentication Frame" is not included. | Insert the Content of PASN Authentication Frame details in the table after Content of FILS Authentication Frame and before Vendor SpecificInfo details. See 802.11az-2022 page 29, 6.3.5.2.2 - for the content of the table. | REVISED (GEN: 2024-04-18 20:55:41Z) Incorporate the changes in 11-24/0566r4 (https://mentor.ieee.org/802.11/dcn/24/11-24-0566-04-000m-resolutions-of-cids-7082-7071-7077.docx) for CIDs 7121 and 7122 (GEN). | GEN | GEN Motion April | Ready for Motion | GEN: 2024-04-18 20:55:47Z - status set to: Ready for Motion GEN: 2024-03-11 23:50:37Z - status set to: More Work Required - Schedule at the April REVme AdHoc GEN: 2024-03-08 06:47:31Z - status set to: Review Proposed Resolution: Accepted |  |  |  | 2024-04-18 20:56 | GEN
7187 | RISON, Mark | 1002 | 5 | 4.3.1 | 274 | 3 | T | Yes | 274 | 3 | 4.3.1 |  | V | Mark HAMILTON | 11-24/691r1 |  | "If a STA moves out of the BSA, it can no longer directly communicate with all the other STAs present in the BSA." -- in a infra BSS it doesn't need to, it only needs to communicate with the AP | Not sure how to express this | REVISED (GEN: 2024-04-18 20:42:53Z) At P195.1, change the definition of BSA to: “The area in which the members of a basic service set (BSS) are able to communicate with each other such that necessary services of the BSS can be provided, such as synchronization and data transfer. NOTE—The extent of a given BSA is unlikely to be strictly definable, nor static. See 4.3.6 for further discussion.” | GEN | GEN Motion April | Ready for Motion | GEN: 2024-04-18 20:42:57Z - status set to: Ready for Motion GEN: 2024-04-16 23:53:15Z - status set to: Submission Required -- Similar CID assigned to Mark H. Schedule for Return with Mark H this week. CID 7187. GEN: 2024-03-08 06:32:17Z - status set to: Discuss |  |  |  | 2024-04-18 20:45 | GEN
7188 | RISON, Mark | 1002 | 5 | 4.3.1 | 274 | 1 | T | Yes | 274 | 1 | 4.3.1 |  | V | Mark HAMILTON |  |  | Is the BSA "The area containing the members of a basic service set (BSS)." per Clause 3 or is it "the coverage area within which all the member STAs of the BSS can remain in communication" per Clause 4? The latter is typically bigger than the former, since if a STA moves a little further away it will typically still be able to be heard. | Change the Clause 3 definition to be the Clause 4 definition | REVISED (GEN: 2024-04-18 22:24:10Z) At P195.1, change the definition of BSA to: “The area in which the members of a basic service set (BSS) are able to communicate with each other such that necessary services of the BSS can be provided, such as synchronization and data transfer. NOTE—The extent of a given BSA is unlikely to be strictly definable, nor static. See 4.3.6 for further discussion.” (Same resolution as CID 7187) | GEN | GEN Motion April | Ready for Motion | GEN: 2024-04-18 22:24:42Z - status set to: Ready for Motion GEN: 2024-03-11 23:43:44Z - status set to: More Work Required Schedule for April REVme AdHoc. GEN: 2024-03-08 06:25:15Z - status set to: Review Proposed Resolution: Revised; |  |  |  | 2024-04-18 22:25 | GEN
7196 | RISON, Mark | 1002 | 5 | 10.2.3.3 |  |  | G | Yes |  |  | 10.2.3.3 |  |  | Jon Rosdahl |  |  | 802.11e should be deprecated | At the start of 10.2.3.3 HCF controlled channel access (HCCA) add a para "HCCA is deprecated." |  | GEN | GEN More work Required | More Work Required | GEN: 2024-04-17 00:16:44Z - status set to: More Work Required Assign to Jon - Post to releflector with Poll results: Schedule for May 6th. GEN: 2024-03-08 06:23:35Z - status set to: Discuss |  |  |  | 2024-04-17 00:17 | GEN
7199 | RISON, Mark | 1002 | 5 | 3 |  |  | T | Yes |  |  | 3 |  | V | Mark RISON | 11-24/702r1 |  | Is it not clear whether group addressed frames are "addressed to" STAs | Clarify, maybe under the definition of group addressed in C3 | REVISED (GEN: 2024-04-18 20:23:00Z) In 9.2.2 Conventions, at the end of the para: Without further qualification, reception by the MAC sublayer implies that the frame contents are valid, and that the protocol version is supported (see 9.2.4.1.2 (Protocol Version subfield)), with no implication regarding frame addressing or regarding whether the frame type or other fields in the MAC header are meaningful to the MAC entity, where the frame is addressed to the STA (individually addressed or group addressed).(#6185) add: Unless explicitly specified, a group addressed frame might or might not, depending on the context, be considered “addressed to” a particular STA. Additionally, in certain contexts a frame individually addressed to a STA might be considered “received” by another STA (see e.g. 10.3.2.4). Note to EDITOR --This Resolution is the same resolution as CID 7200 (MAC) | GEN | GEN Motion April | Ready for Motion | GEN: 2024-04-18 20:24:11Z - status set to: Ready for Motion GEN: 2024-03-13 23:58:46Z - status set to: Submission Required GEN: 2024-03-08 06:24:01Z - status set to: Discuss |  |  |  | 2024-04-18 20:40 | GEN
7225 | RISON, Mark | 1002 | 5 |  |  |  | T | Yes | [5 empty] | Mark RISON |  |  | The term "network" is used a lot, but not actually defined. It might be equivalent to "BSS", or it might be equivalent to "ESS", or it might be something else | Define the term |  | GEN | GEN More work Required | More Work Required | GEN: 2024-03-14 18:15:31Z - status set to: More Work Required - Assign to Mark Rison. Bring back at May Interim GEN: 2024-03-08 05:46:01Z - status set to: Discuss |  |  |  | 2024-04-18 20:51 | GEN

## GEN Motion April
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
7003 | Banavara, Madhusudan | 1002 | 5 |  | 379 | 26 | G | No | 379 | 26 |  |  | J |  |  |  | The use of "non" in the standards has always been confusing and has become increasingly - for example: "Non-AP STA Non-AP MLD and Non-PCP STA" etc. Takes quite a bit of time to figure out what you are referring to and we forget the core of the feature we were reading about. Please use a positive version of these instead or figure out a way to represent these network entities in a less confusing way... |  | REJECTED (GEN: 2024-04-18 23:37:02Z) The use of "non" is an unfortunately necessary naming convention that differentiates legacy features that are not included in the new features. | GEN | GEN Motion April | Ready for Motion | GEN: 2024-04-18 23:37:17Z - status set to: Ready for Motion GEN: 2024-03-08 06:38:42Z - status set to: Submission Required |  |  |  | 2024-04-19 14:56 | GEN
7051 | McCann, Stephen | 1002 | 5 | Contents | 94 | 65 | T | Yes | 94 | 65 | Contents |  | V | Emily Qi | 11-24/696r1 |  | The title of clause 34 should state "MAC specification" to align it with the title of the previous clauses. | Change "34. Enhanced broadcast services procedures(11bc)" to "34. Enhanced broadcast services procedures MAC specification (11bc)" | REVISED (GEN: 2024-04-18 17:04:58Z) - At 4953.1, change the title of clause 34 to “Enhanced broadcast services MAC specification”. | GEN | GEN Motion April | Ready for Motion | GEN: 2024-04-18 17:03:15Z - status set to: Ready for Motion Similar to CID 7059, 7056. GEN: 2024-03-12 00:00:09Z - status set to: More Work Required - Schedule April REVme AdHoc GEN: 2024-03-08 06:40:17Z - status set to: Review Proposed Resolution: Accept |  |  |  | 2024-04-18 17:07 | GEN
7121 | Levy, Joseph | 1002 | 5 | 6.5.5.2.2 | 442 | 6 | T | Yes | 442 | 6 | 6.5.5.2.2 |  | V | Graham Smith |  |  | The additions made in 802.11az have not been inserted. "Content of PASN Authentication Frame" is not included. | Insert "Content of PASN Authentication Frame" after "Content of FILS Authentication Frame" and before "Vendor SpecificInfo" Note this also applies to 6.5.5.3, | REVISED (GEN: 2024-04-18 20:55:23Z) Incorporate the changes in 11-24/0566r4 (https://mentor.ieee.org/802.11/dcn/24/11-24-0566-04-000m-resolutions-of-cids-7082-7071-7077.docx) for CIDs 7121 and 7122 (GEN). | GEN | GEN Motion April | Ready for Motion | GEN: 2024-04-18 20:55:32Z - status set to: Ready for Motion GEN: 2024-03-11 23:52:31Z - status set to: More Work Required GEN: 2024-03-08 06:46:10Z - status set to: Review Proposed Resolution: Accepted |  |  |  | 2024-04-18 21:05 | GEN
7122 | Levy, Joseph | 1002 | 5 | 6.5.5.2.2 | 442 | 63 | T | Yes | 442 | 63 | 6.5.5.2.2 |  | V | Graham Smith | 11-24/0566r4 |  | The additions made in 802.11az have not been inserted. "Content of PASN Authentication Frame" is not included. | Insert the Content of PASN Authentication Frame details in the table after Content of FILS Authentication Frame and before Vendor SpecificInfo details. See 802.11az-2022 page 29, 6.3.5.2.2 - for the content of the table. | REVISED (GEN: 2024-04-18 20:55:41Z) Incorporate the changes in 11-24/0566r4 (https://mentor.ieee.org/802.11/dcn/24/11-24-0566-04-000m-resolutions-of-cids-7082-7071-7077.docx) for CIDs 7121 and 7122 (GEN). | GEN | GEN Motion April | Ready for Motion | GEN: 2024-04-18 20:55:47Z - status set to: Ready for Motion GEN: 2024-03-11 23:50:37Z - status set to: More Work Required - Schedule at the April REVme AdHoc GEN: 2024-03-08 06:47:31Z - status set to: Review Proposed Resolution: Accepted |  |  |  | 2024-04-18 20:56 | GEN
7056 | McCann, Stephen | 1002 | 5 | Contents | 94 | 65 | T | Yes | 94 | 65 | Contents |  | J | Emily Qi |  |  | The 11bc CID 5113 (Initial SA Ballot) suggests that clause 34 actually defines MAC sublayer behaviour, which it does. Therefore this clause should be moved to a sub clause of clause 10 and not stand alone. See 11-23-0486r0, "SAB Initial Ballot" tab to find CID 5113. | Move Clause 34 into Clause 10, as 10.71. | REJECTED (GEN: 2024-04-18 16:59:07Z) The CRC reviewed the comment. This comment is same as CID 7059. The motion to approve the resolution for CID 7059 (Move Clause 34 to a sub-clause of clause 11) failed on 3/14/2024 with the motion result of 6 Yes - 7 No - 4 abstain. The implementing proposed changes does not have task group consensus. | GEN | GEN Motion April | Ready for Motion | GEN: 2024-04-18 16:59:12Z - status set to: Ready for Motion GEN: 2024-04-17 00:32:02Z - status set to: More Work Required See CID 7059 Similar issue. Scheduled for April REVme AdHoc. GEN: 2024-03-08 06:48:43Z - status set to: Discuss |  |  |  | 2024-04-18 17:00 | GEN
7059 | Montemurro, Michael | 1002 | 5 | 34 | 4953 | 1 | T | Yes | 4953 | 1 | 34 |  | J | Emily Qi | 11-24/492 |  | During one of the later rounds of SA Ballot, the EBCS clause was moved from a sub-clause of 11 to clause 34 in response to a comment that requested that the EBCS clause be divided between clause 11 and 10. | The commenter will provide a submission to address the comment that restores the clause 11 content and possibly moves some content to clause 10. | REJECTED (GEN: 2024-04-18 16:57:43Z) The CRC reviewed the comment. The motion to approve revised changes (Move Clause 34 to a sub-clause of clause 11) failed on 3/14/2024 with the motion result of 6 Yes - 7 No - 4 abstain. The implementing revised changes does not have task group consensus. | GEN | GEN Motion April | Ready for Motion | GEN: 2024-04-18 16:58:09Z - status set to: Ready for Motion GEN: 2024-03-14 22:27:59Z - status set to: More Work Required - Schedule April REVme AdHoc GEN: 2024-03-13 03:51:45Z - status set to: Ready for Motion - Separate Motion. GEN: 2024-03-08 06:51:04Z - status set to: Submission Required - |  |  |  | 2024-04-18 16:58 | GEN
7187 | RISON, Mark | 1002 | 5 | 4.3.1 | 274 | 3 | T | Yes | 274 | 3 | 4.3.1 |  | V | Mark HAMILTON | 11-24/691r1 |  | "If a STA moves out of the BSA, it can no longer directly communicate with all the other STAs present in the BSA." -- in a infra BSS it doesn't need to, it only needs to communicate with the AP | Not sure how to express this | REVISED (GEN: 2024-04-18 20:42:53Z) At P195.1, change the definition of BSA to: “The area in which the members of a basic service set (BSS) are able to communicate with each other such that necessary services of the BSS can be provided, such as synchronization and data transfer. NOTE—The extent of a given BSA is unlikely to be strictly definable, nor static. See 4.3.6 for further discussion.” | GEN | GEN Motion April | Ready for Motion | GEN: 2024-04-18 20:42:57Z - status set to: Ready for Motion GEN: 2024-04-16 23:53:15Z - status set to: Submission Required -- Similar CID assigned to Mark H. Schedule for Return with Mark H this week. CID 7187. GEN: 2024-03-08 06:32:17Z - status set to: Discuss |  |  |  | 2024-04-18 20:45 | GEN
7188 | RISON, Mark | 1002 | 5 | 4.3.1 | 274 | 1 | T | Yes | 274 | 1 | 4.3.1 |  | V | Mark HAMILTON |  |  | Is the BSA "The area containing the members of a basic service set (BSS)." per Clause 3 or is it "the coverage area within which all the member STAs of the BSS can remain in communication" per Clause 4? The latter is typically bigger than the former, since if a STA moves a little further away it will typically still be able to be heard. | Change the Clause 3 definition to be the Clause 4 definition | REVISED (GEN: 2024-04-18 22:24:10Z) At P195.1, change the definition of BSA to: “The area in which the members of a basic service set (BSS) are able to communicate with each other such that necessary services of the BSS can be provided, such as synchronization and data transfer. NOTE—The extent of a given BSA is unlikely to be strictly definable, nor static. See 4.3.6 for further discussion.” (Same resolution as CID 7187) | GEN | GEN Motion April | Ready for Motion | GEN: 2024-04-18 22:24:42Z - status set to: Ready for Motion GEN: 2024-03-11 23:43:44Z - status set to: More Work Required Schedule for April REVme AdHoc. GEN: 2024-03-08 06:25:15Z - status set to: Review Proposed Resolution: Revised; |  |  |  | 2024-04-18 22:25 | GEN
7199 | RISON, Mark | 1002 | 5 | 3 |  |  | T | Yes |  |  | 3 |  | V | Mark RISON | 11-24/702r1 |  | Is it not clear whether group addressed frames are "addressed to" STAs | Clarify, maybe under the definition of group addressed in C3 | REVISED (GEN: 2024-04-18 20:23:00Z) In 9.2.2 Conventions, at the end of the para: Without further qualification, reception by the MAC sublayer implies that the frame contents are valid, and that the protocol version is supported (see 9.2.4.1.2 (Protocol Version subfield)), with no implication regarding frame addressing or regarding whether the frame type or other fields in the MAC header are meaningful to the MAC entity, where the frame is addressed to the STA (individually addressed or group addressed).(#6185) add: Unless explicitly specified, a group addressed frame might or might not, depending on the context, be considered “addressed to” a particular STA. Additionally, in certain contexts a frame individually addressed to a STA might be considered “received” by another STA (see e.g. 10.3.2.4). Note to EDITOR --This Resolution is the same resolution as CID 7200 (MAC) | GEN | GEN Motion April | Ready for Motion | GEN: 2024-04-18 20:24:11Z - status set to: Ready for Motion GEN: 2024-03-13 23:58:46Z - status set to: Submission Required GEN: 2024-03-08 06:24:01Z - status set to: Discuss |  |  |  | 2024-04-18 20:40 | GEN

## GEN More work Required
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
7196 | RISON, Mark | 1002 | 5 | 10.2.3.3 |  |  | G | Yes |  |  | 10.2.3.3 |  |  | Jon Rosdahl |  |  | 802.11e should be deprecated | At the start of 10.2.3.3 HCF controlled channel access (HCCA) add a para "HCCA is deprecated." |  | GEN | GEN More work Required | More Work Required | GEN: 2024-04-17 00:16:44Z - status set to: More Work Required Assign to Jon - Post to releflector with Poll results: Schedule for May 6th. GEN: 2024-03-08 06:23:35Z - status set to: Discuss |  |  |  | 2024-04-17 00:17 | GEN
7225 | RISON, Mark | 1002 | 5 |  |  |  | T | Yes | [5 empty] | Mark RISON |  |  | The term "network" is used a lot, but not actually defined. It might be equivalent to "BSS", or it might be equivalent to "ESS", or it might be something else | Define the term |  | GEN | GEN More work Required | More Work Required | GEN: 2024-03-14 18:15:31Z - status set to: More Work Required - Assign to Mark Rison. Bring back at May Interim GEN: 2024-03-08 05:46:01Z - status set to: Discuss |  |  |  | 2024-04-18 20:51 | GEN

## GEN Submission Required
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
7066 | Qi, Emily | 1002 | 5 | 3 | 271 | 56 | G | Yes | 271 | 56 | 3 |  |  | Emily Qi |  |  | 11az work item - 11az asks to change all instances of “fine timing measurement” to “FTM” as appropriate in the next revision of IEEE Std 802.11. Need a submission for those changes. | as in comment. |  | GEN | GEN Submission Required | Submission Required | GEN: 2024-03-08 06:40:55Z - status set to: Submission Required |  |  |  | 2024-03-09 19:05 | GEN
7067 | Qi, Emily | 1002 | 5 | 6 |  |  | G | Yes |  |  | 6 |  |  | Graham Smith |  |  | Contents in Clause 6 of 11az, 11bd and 11bc cannot be rolled-in due to the Clause 6 structure changes in REVme. This can be resolved by a submission. | as in comment. |  | GEN | GEN Submission Required | Submission Required | GEN: 2024-03-08 06:41:28Z - status set to: Submission Required |  |  |  | 2024-03-09 19:04 | GEN
7110 | Hamilton, Mark | 1002 | 5 | 5.1.5.3 | 369 | 40 | T | Yes | 369 | 40 | 5.1.5.3 |  |  | Stephen McCann |  |  | 1) The EBCS actions only happen if this is an EBCS enabled AP. 2) This text belongs somewhere else, not in the Role-specific behavior block (which does not contain the EBCS traffic stream mapper). | 1) Add qualification that this action occurs if this is an AP operating EBCS. ("In the context of EBCS…" like in 5.1.5.2, perhaps?) 2) Move this text and the associated NOTE 2 to somewhere appropriate. |  | GEN | GEN Submission Required | Submission Required | GEN: 2024-03-08 06:45:18Z - status set to: Submission Required See also CID 7111. |  |  |  | 2024-03-13 03:42 | GEN
7111 | Hamilton, Mark | 1002 | 5 | 5.1.5.2 | 369 | 9 | T | Yes | 369 | 9 | 5.1.5.2 |  |  | Stephen McCann |  |  | 1) The Role-specific behavior (which is what is described in this subclause) doesn't include the EBCS filter. This paragraph belongs somewhere else. 2) This sentence talks about actions of the EBCS filter in DL, but the EBCS filter (per Figure 5-1) is an UL behavior. | 1) Move this text, and the associated NOTE 2, somewhere appropriate. 2) Fix this to talk about the EBCS Traffic Mapper, or change "DL" to "UL", or something?? |  | GEN | GEN Submission Required | Submission Required | GEN: 2024-03-08 06:45:45Z - status set to: Submission Required See also CID 7110. |  |  |  | 2024-03-13 03:43 | GEN
7065 | Qi, Emily | 1002 | 5 | 3 | 271 | 51 | G | Yes | 271 | 51 | 3 |  |  | Jonathan Segev |  |  | 11az work item - 11az asks to change all instances of “initial fine timing measurement request” to “IFTMR” as appropriate in the next revision of IEEE Std 802.11. Need a submission for those changes. | as in comment. |  | GEN | GEN Submission Required | Submission Required | GEN: 2024-03-08 06:37:43Z - status set to: Submission Required GEN: 2024-03-08 06:32:48Z - status set to: Needs Submission |  |  |  | 2024-03-09 19:04 | GEN