## Remaining Editorials (Editor)
CID | Commenter | Must Be Satisfied | Clause Number(C) | Page(C) | Line(C) | Category | Clause | Page | Comment | Proposed Change | Status | Assignee | Submission | Resn Status | Resolution | Motion Number | Edit Status | Edited in Draft | Edit Notes | Last Updated | Last Updated By
1038 | Christian Berger | Yes | 9.3.1.22.1 | 16 | 10 | E | 9.3.1.22.1 | 16.10 | Table 9-29c--Trigger Type subfield encoding, outdated changes? | Editor instuctions and changes are copied from 802.11az-2022, but not clearly delineated from new changes by draft 802.11bk; suggested change: move to 802.11me Draft 4.1 as baseline |  | Roy Want |  |  | ACCEPT |  |  |  |  | 2024-01-02T18:46:04Z
1100 | Stephan Sand | No | 9.3.1.22.1 | 16 | 8 | E | 9.3.1.22.1 | 16.08 | Please remove the editor instruction on P16L8-9 and the corresponding change on P16L10-12 as it is already implement in REVme D4.1 Table 9-47 (Trigger Type subfield encoding) on P680L26-29. | As in comment |  | Roy Want |  |  | ACCEPT |  |  |  |  | 2024-01-02T18:46:04Z
1101 | Stephan Sand | No | 9.3.1.22.1 | 16 | 8 | E | 9.3.1.22.1 | 16.08 | Please remove the editor instruction on P16L8-9 and the corresponding change on P16L10-17 as it is already implement in REVme D4.1 on P680L26-29. | As in comment |  | Roy Want |  |  | ACCEPT |  |  |  |  | 2024-01-02T18:46:04Z
1102 | Stephan Sand | No | 9.3.1.22.1 | 16 | 19 | E | 9.3.1.22.1 | 16.19 | Please update the editorial instructions and Table caption as in REVme D4.1 as follows: Change the Table 9-54 in 9.3.1.22.1 as follows: Table 9-54--UL Target Receive Power subfield in Trigger frame | As in comment |  | Roy Want |  |  | ACCEPT |  |  |  |  | 2024-01-02T18:46:04Z
1104 | Stephan Sand | No | 9.3.1.22.10 | 17 | 9 | E | 9.3.1.22.10 | 17.09 | Subclause 9.3.1.22.10 is already part of REVme D4.1. See P691-692. To keep 11bk D1.0 concise The editorial instructions on P17L9 and the subsequent paragraph 9.3.1.22.10 should be update to reflect only the required changes in relation to REVme D4.1. | 1. Please update the editorial instruction as follows: Update the 5th paragraph as follows: 2. Please remove paragraphs 1 - 4 and 6-7, Figures 9-64Ia and 9-64Ib, and Table 9-30ka as there are no changes compared to REVme D4.1 |  | Roy Want |  |  | REVISED TGbk Editor: Update the 11bk draft to be aligned with the latest version of 802.11REVme. |  |  |  |  | 2024-01-02T18:46:04Z
1105 | Stephan Sand | No | 9.3.1.22a | 19 | 3 | E | 9.3.1.22a | 19.03 | References and Subclause numbers in 9.3.1.22a need to be updated from 11az D7.0 to REVme D4.1 | As in comment |  | Roy Want |  |  | REVISED TGbk Editor: Update the 11bk draft to be aligned with the latest version of 802.11REVme. |  |  |  |  | 2024-01-02T18:46:04Z
1106 | Stephan Sand | No | 9.3.1.22a.2 | 20 | 33 | E | 9.3.1.22a.2 | 20.33 | Please remove Paragraphs 1-3 and Figure 9-64Id in Subclause 9.3.1.22a.2 as no changes have been introduced compared to the baseline REVme D4.1. | As in comment |  | Roy Want |  |  | REVISED TGbk Editor: Update the Figure number 641d. The specified paragraphs that include changes that are 11bk specific cannot be omitted. |  |  |  |  | 2024-01-02T18:46:04Z
1107 | Stephan Sand | No | 9.3.1.22a.2 | 21 | 1 | E | 9.3.1.22a.2 | 21.01 | Please remove Paragraphs 2-3 and Figure 9-64Ie in Subclause 9.3.1.22a.3 as no changes have been introduced compared to the baseline REVme D4.1. | As in comment |  | Roy Want |  |  | REVISED TGbk Editor: Update the 11bk draft to be aligned with the latest version of 802.11REVme. |  |  |  |  | 2024-01-02T18:46:04Z
1108 | Stephan Sand | No | 9.3.1.22a.4 | 21 | 32 | E | 9.3.1.22a.4 | 21.32 | Please remove Paragraph 2 in Subclause 9.3.1.22a.4 as no changes have been introduced compared to the baseline REVme D4.1 | As in comment |  | Roy Want |  |  | REJECT This is a single line that is part of a complete section to promote readability. |  |  |  |  | 2024-01-02T18:46:04Z
1111 | Stephan Sand | No | 9.4.2.299 | 25 | 18 | E | 9.4.2.299 | 25.18 | In Subclause 9.6.7.33 (FTM frame format) of REVme D4.1 the FTM frame Action field format contains Secure HE-LTF Parameters element (see Figure 9-1176). Please remove "HE-" from "Secure HE-LTF Parameters"" in all occurences in Subclause 9.6.7.33. Similar, remove "HE-" from "Secure HE-LTF Parameters" in 9.6.7.49 ( Location Measurement Report (LMR) frame format). | As in comment |  | Roy Want |  |  | REVISE TGbk Editor: Change editor instructions in line 25.12 to refer to the baseline instead of 11az. |  |  |  |  | 2024-01-02T18:46:04Z
1130 | Joseph Levy | No | 3.2 | 23 | 14 | E | 3.2 | 23.14 | The base line text for the definition of Null-SAC HE LTF does not meet the style requirements for a definition. This correction should be coordinated with a correction to 802.11me D4.1 or D5.0. | Spell out all abbreviations and acronyms in the definition, and add the searchable term or terms associated with this definition, correct this definition so that it is in the current 802.11 style. (note this is really an TGme task) |  | Roy Want |  |  | REVISED TGbk Editor: Change the definition of 'Null-SAC-HE-LTF:" to "Null-sequence authentication code (SAC)-high efficiency (HE)-long training field (LTF): [Null SAC-HE-LTF]" |  |  |  |  | 2024-01-02T18:46:04Z
1144 | Hiroyuki Motozuka | Yes | 9.3.1.22.1 | 16 | 8 | E | 9.3.1.22.1 | 16.08 | The table and paragraphs in P16L8-L17 and P17L4-7 are already specified in 11az, and 11bk is not specifying any changes to them. Throughout the 11bk draft, there are lots of unnecessary paragraphs, tables and underlines that are already specified in the baseline (especially in 11az). | Remove the instruction, table and paragraph in P16L8-L17 and P17L2-L7. Similar changes are required throughout the 11bk draft. |  | Roy Want |  |  | ACCEPT |  |  |  |  | 2024-01-02T18:46:04Z
1359 | Mark Hamilton | No | 9.3.1.22.1 | 16 | 7 | E | 9.3.1.22.1 | 16.07 | The chnages shown in 9.3.1.22.1 appear to all already be in REVme (from 11az) | Remove these changes from this amendment. |  | Roy Want |  |  | ACCEPT |  |  |  |  | 2024-01-02T18:46:04Z
1364 | Mark Hamilton | Yes | 9.4.2.298 (sic) | 22 | 3 | E | 9.4.2.298 (sic) | 22.03 | Update subclause numbers and figure numbers to match baseline | Per REVme D4.1, this subclause is now 9.4.2.301. (And, for example, "Figure 11-37p" is actually Figure 11-60.) |  | Roy Want |  |  | REVISED TGbk Editor: Update the 11bk draft to be aligned with the latest version of 802.11REVme. |  |  |  |  | 2024-01-02T18:46:04Z
1365 | Mark Hamilton | Yes | 9.4.2.298 (sic) | 25 | 11 | E | 9.4.2.298 (sic) | 25.11 | Insert subclause heading | This change is actually in the next subclause, which is now (pre REVme D4.1) subclause 9.4.2.302. |  | Roy Want |  |  | REVISE TGbk Editor: Change editor instructions in line 12 to refer to baseline instead of 11az, and remove underline from lines 12-13. |  |  |  |  | 2024-01-02T18:46:04Z
1373 | Albert Petrick | No | 9.4.2.298 | 22 | 3 | E | 9.4.2.298 | 22.03 | Incorrect subclause number for Ranging Parmeters element. | Change subclause to 9.4.2.298 to align with REVme D4.1 |  | Roy Want |  |  | ACCEPT |  |  |  |  | 2024-01-02T18:46:04Z
1384 | Dong Wei | No | 9.3.1.22.1 | 16 | 8 | E | 9.3.1.22.1 | 16.08 | The insertion and modification have already been done in REVme D4.1 (see Table 9-47). | Remove Lines 8 - 11 |  | Roy Want |  |  | ACCEPT |  |  |  |  | 2024-01-02T18:46:04Z
1390 | Dong Wei | No | 9.4.2.298 | 22 | 3 | E | 9.4.2.298 | 22.03 | The clause numbers, table and figure numbers are not based on REVme D4.1. | Update the clause numbers, table and figure numbers based on REVme D4.1 (it is better to update the reference numbers throughout the entire draft) |  | Roy Want |  |  | REVISED TGbk Editor: Update the 11bk draft to be aligned with the latest version of 802.11REVme. |  |  |  |  | 2024-01-02T18:46:04Z