## Slide 1: TGbk 320MHz Positioning July Meeting Closing Report
Date: 2024-07-18
Authors:

## Slide 2: Abstract
This document is the TGbk 320MHz Positioning closing report for the IEEE 802.11 July 2024 plenary meeting.

## Slide 3: July Meeting Progress and Targets Towards the Sep. Meeting
Work completed during this meeting:
  Completed response to LB286, approved WG recirculation ballot and targeting an unchanged 802.11bk D3.0 draft in anticipation of SA ballot.
  Completed response to MDR report and approved changes incorporated to D3.0.
Chart: LB286 CR Progress
| Overall | Editorial | Technical | General
LB286 | 134 | 53 | 72 | 9
Current completion | 134 | 53 | 72 | 9
Work expected towards Sep. meeting:
  Conduct recirculation ballot on D3.0.
  Initiate and complete D3.0 CR, targeting an unchanged draft.
  Generate draft report to EC on requesting unconditional initiation of SA ballot.

## Slide 4: TGbk Projected Timeline (previous)
Q2 2024
Q1 2024
Q3 2023
Q2 2023
Q1 2023
Q4 2023
Q3 2024
Q4 2024
Formation
Framework
Framework completion
05/23
802.11bk amendment text development
Initial WG ballot
Recirc 03/24
11bk D2.0
Initial SA
07/24
Final WG ballot 7/24
11bk D3.0
MDR
MDR start
MDR cmp
D4.0
D5.0
Final SA
11/24
SA Recir.
10/24

## Slide 5: TGbk Projected Timeline (updated)
Q2 2024
Q1 2024
Q3 2023
Q2 2023
Q1 2023
Q4 2023
Q3 2024
Q4 2024
Formation
Framework
Framework completion
05/23
802.11bk amendment text development
Initial WG ballot
Recirc 03/24
11bk D2.0
Initial SA
10/24
Final WG ballot 9/24
11bk D3.0
MDR
MDR start
MDR cmp
D4.0
D5.0
Final SA
11/24
SA Recir.
11/24

## Slide 6: Scheduled TGbk telecons
  Aug. 13th 10:00 am PT/13:00 ET (2hrs)
  Aug. 20th 10:00 am PT/13:00 ET (2hrs)
  Aug. 27th 10:00 am PT/13:00 ET (2hrs).
** - meeting as part of the IEEE week, refer to WG agenda document for details.
┼ - Motion meeting, motions to be made available to chair 15 days in advance and announced to group 10 days in advance.