## revision
This spreadsheet includes a summary of reflector comments on Editorial CID resolutions in 24/952.
2024-06-19 | R0

## comment matrix
| Page | Subclause | Line | Comment | Proposed Change |  | Editor’s Proposed Resolution Text | Comments
Name
3014 | Smith, Graham | 35 | 12.2.12.1 | 60 | The paragraph at P35.58 is on PASN. It would be better to move this to Page 36 just preceeding line 20 where the PASN explanation is given. | Move paragraph to just before P36.20. | Revised. Editor to switch the order of the 3rd and 4th paragraphs in section 12.2.12.1 to group the AP-related paragraphs on PASN together. Proposed new resolution: Rejected. Comment is superceded by other changes to this section. | (Paragraphs are intended to be 13 and 14, I think?)
Agreed, but I think more should be done. I note that many paragraphs are agnostic as to which scenario/mechanism applies. Then the one at P36.50 really should be for non-PASN only, because it conflicts with the one at P36.60. So, those two should be in parallel together somewhere, that lists out all the scenario-specific points (are there any others that should go with them?) (See CID 3042 on L50 not being clear, and resolution in 11-24/0885, though, also.) Then, we have a big example of PASN, but no examples of the others (see CID 3131 suggesting to add more). And, the last paragraph is probably too important to be lost at the end like it is.
Agree that the section is a hodge-podge, but to entirely restructure it really calls for a technical submission,
3033 | Stacey, Robert | 37 | 12.2.12.2 | 50 | "Identifiable random MAC address (IRM) operation" in the title but "IRM mechanism" elsewhere. | Change title to "Identifiable random MAC address (IRM) mechanism". At 48.28, change "IRM operation" to "IRM mechanism" | Revised. Editor to remove mechanism and operation from section titles and PICs table for better aligment with baseline text including parallel clauses for Device ID. | Editor says to remove both "mechanism" and "operation" for better alignment with baseline. Is that correct? I can live with it. But, Graham (11-24/0916) changed it to "operation". Which way is it?
When I looked at sections preceding these new sections, they didn't use mechanism or operation in the section titles, so I proposed to just remove them.
3053 | Patwardhan, Gaurav | 39 | 12.2.13 | 46 | Typo. It should be ‘… shall be used as derived a part of.. “ | as in comment | Revised. Editor to change phrase to "shall be used as derived from the PTK" Revised. Editor to modify sentence to:"The KEK, as derived from the PTK (see 12.13.7), shall be used with the negotiated key wrap algorithm to encrypt the Encrypted Data field of the PASN Encrypted Data element." Also, L24 should be "KEK = L(PTK, 256, KEK_bits)" Note: check alignment with REVmeD6.0/D7.0. (L has changed). | How about "The KEK, as derived from the PTK, shall be used with the negotiated key wrap algorithm."
The sentence is a little longer. How about:
The KEK as derived from the PTK shall be used with the negotiated key wrap algorithm to encrypt the Encrypted Data field of the PASN Encrypted Data element.
Those last 2 words need to be lowercase or have "field" or something after
3060 | McCann, Stephen | 34 | 12.2.12 | 24 | TA (Transmission Address) requires an article. | Change "TA" to "a TA" at the cited location. Change "TA" to "the TA" at P34L25. | Accept. Revised: Editor to modify the sentence to: "The second mechanism, referred to as the IRM mechanism, has the non-AP STA provide a random MAC address (different from the address it is currently using as the TA for its transmissions) to the AP during association or PASN authentication and then use that MAC address as the TA for its transmissions for identification of the STA, during its next preassociation exchanges, PASN authentication, and/or association and associated exchanges with that AP." | Suggest “its TA” would be better than “a TA” (first location).
Full text: The second mechanism, referred to as the IRM mechanism, has the non-AP STA provide a random MAC address (different from the address it is currently using as its TA for its own transmissions) to the AP during association or PASN authentication and then use that MAC address as the TA for its own transmissions for identification of the STA, during its next preassociation exchanges, PASN authentication, and/or association and associated exchanges with that AP.
Maybe "its TA for its own transmissions" is a bit heavy. "the TA for its transmissions"? Graham Smith: I agree that “its” is better
3061 | McCann, Stephen | 34 | 12.2.12 | 36 | device ID requires an article. | Change "Device ID" to "The device ID" at the cited location. | Accept. | Suggest to change "IRM allows", also. And, change both to "The <xxx> feature allows…"
There are 4 more CIDs for this NOTE: 3087, 3062, 3094, 3126
Can the same person resolve them together? Graham S suggests: I would prefer “The IRM mechanism” and “The device ID mechanism” so as to be consistent.
3062 | McCann, Stephen | 34 | 12.2.12 | 37 | The sentence "If an AP and a non-AP STA both have both IRM and device ID activated..." has a couple of typos. | Change the cited sentence to "If an AP and a non-AP STA have both an IRM and a device ID activated...". | Accept. Revised, check all relevant CIDs and merge together | (Note, see CID 3061 on same text.) It is not "has an IRM", but "has [the] IRM [feature] activated" (as well as the device ID feature). So, need different fix-up to the wording.
There are 4 more CIDs for this NOTE: 3087, 3061, 3094, 3126
Can the same person resolve them together? From Graham Smith: I suggest “mechanisms” and sentence revised to read “If an AP and non-AP STA have both IRM and device ID mechanisms activated,…”
3063 | McCann, Stephen | 36 | 12.2.12.2 | 8 | The sentence "If an AP sets Device ID (sub)element or Device ID KDE with the Device ID Status field set to 1…" has a couple of typos. | Change the cited sentence to "In an AP, if the Device ID Status field in a Device ID (sub)element or Device ID KDE is equal to 1…." | Accept. Revised: Editor to modify sentence as follows: "If an AP provides a Device ID (sub)element or a Device ID KDE with the Device ID Status field set to 1, indicating Not Recognized, then the AP may also provide in that same Device ID (sub)element or Device ID KDE a new device ID, thus establishing a new shared identity." | Suggest rejecting this. This is meant to correlate to the AP at the time when it is setting the Device ID Status field (in preparation for transmitting it), that it may also provide a new device ID in the same element. Phrasing this as a test (“equal to”) of the Device ID Status field (as if it were a received field) is confusing.
The sentence is confusing as it stands. Not sure the best way to clean it up, but don't agree that rejecting the comment is the best path.
3064 | McCann, Stephen | 35 | 12.2.12.1 | 18 | In the 802.11 baseline the usual phrase is "out of scope of this standard". | Change "out of scope for this standard" to "out of scope of this standard" and also on P38L20. | Accept. | Agree with the Accepted. However, it is worth noting to the REVme folks that there are 3 instances of “out of scope for” in the REVme baseline, also.
11me/D6.0 is out for ballot now!
3123 | Lalam, Massinissa | 29 | 9.4.2.319 | 44 | Replace "The format of the PASN Encrypted Data element is shown in Figure 9-1072e (Device ID subelement format)." with "The format of the PASN Encrypted Data element when Subelement ID equals Device ID is shown in Figure 9-1072e (Device ID subelement format)." | As in comment | Accept. Revised: Editor to modify sentence to: "The format of the Device ID subelement is shown in Figure 9-1072e…" | I have a minor rewording to suggest: "The format of the Encrypted Data field when it contains a Device ID subelement is shown…" or some such.
If we do accept then it needs to be a revise, since various "field"s are missing
3124 | Lalam, Massinissa | 29 | 9.4.2.319 | 63 | Replace "The format of the IRM subelement is shown in Figure 9-1072f (IRM subelement format)." with "The format of the PASN Encrypted Data element when Subelement ID equals IRM is shown in Figure 9-1072f (IRM subelement format)." | As in comment | Accept. Reject. Current language is sufficiently descriptive in its context. | Same suggestion as CID 3123, just above.
If we do accept then it needs to be a revise, since various "field"s are missing and maybe equals needs to be indicates
3130 | Lalam, Massinissa | 51 | AF | 18 | Consider renaming "(informative) Example opaque device identifier scheme" as "(informative) Example of an opaque device identifier scheme" | As in comment | Accept. Revised: Editor to change Annex title to: (informative) Example of an opaque device identifier scheme | I’m okay with the direction (and hence the “accept in principle” conceptually), but we need specific wording – the Editor cannot just “Accept” this, as is.
I meant to accept the wording in the comment. Alternatively:
Revised: Editor to change Annex title to: (informative) Example of an opaque device identifier scheme
3136 | RISON, Mark | 45 | 12.13.7 | 38 | "a KEK and a KDK are derived" wrong verb | Change "and" to "and/or" | Accept. Reject. Current language is correct. The number of bits is dependent upon the inclusion or not of both KEK and KDK. | I’d like to discuss. I thought “and/or” was not acceptable wording.
I thought so too, but found 295 instances in the latest REVme draft. NNN is the Bits required for KCK, KEK, TK and KDK depending on the pairwise cipher and whether a KEK and a KDK are derived
3138 | RISON, Mark | 25 | 9.4.2.19.7 | 60 | "with a Length field set to 1" should be "with the Length field set to 1" | As it says in the comment | Accept. Reject. This is baseline text, please direct this comment to TGm. | This is text from the baseline. Do we (as a TG) agree that we should fix this?
3139 | RISON, Mark | 31 | 11.10.9.1.1 | 50 | " measurement request is Active" should be " Measurement request is Active" | As it says in the comment. Ditto at 32.25 | Accept. Reject. This is baseline text, please direct this comment to TGm. | This is text from the baseline. Do we (as a TG) agree that we should fix this?
3140 | RISON, Mark | 31 | 11.10.9.1.1 | 62 | "measurement request" should be "Measurement request" | As it says in the comment | Accept. Reject. The lower-case use is the convention in the baseline for referencing these frames in a general sense (not to a specific type of measurement request), and the proposed change would also be inconsistent with the existing text in this paragraph. | Suggest we reject. The lower-case use is the convention in the baseline for referencing these frames in a general sense (not to a specific type of measurement request), and the proposed change would also be inconsistent with the existing text in this paragraph.
Ah, sorry, I thought a measurement request was a specific kind of request like a Beacon request, but no it's generic. OK to reject on this basis
3141 | RISON, Mark | 32 | 11.10.9.1.1 | 17 | "measurement request" should be "Measurement request" | As it says in the comment | Accept. Reject. The lower-case use is the convention in the baseline for referencing these frames in a general sense (not to a specific type of measurement request), and the proposed change would also be inconsistent with the existing text in this paragraph. | Same as CID 3140 just above.
3150 | RISON, Mark | 18 | 4.5.4.10 | 16 | "an identifiable" has two extraneous spaces | Delete two spaces (also in nearby words; also e.g. at 39.20) | Accept. | I accept the concern, but it seems to be some sort of wide space, not two spaces. So the resolution probably needs some clarification.
Seems to depend on the tool being used. The "Accept" was to say that it will be corrected.
3160 | RISON, Mark | 28 | 9.4.2.314 | 37 | "Indicates that the IRM has not been recog-nized" -- weird word-break | Don't hyphenate | Accept. | I’m not sure I agree with the comment. This is a line break issue with a long word. I suggest we just leave such issues to the professional (IEEE editing) at time of publication.
It looks like bad formatting carried over when the text was copied from a submission. Fixing it is simple.
3163 | RISON, Mark | 30 | 9.4.2.316 | 12 | "The Length field is defined in 9.4.3." missing (Subelements) which makes me worry a xref is going to be missed | As it says in the comment | Rejected. Comment is unclear as to the desired change. Problem to be brought up to Editors meeting. | I agree with this comment (at least as I think I understand it). This is asking for the usual “(Subelements)” to be added after the subclause number, to look like the usual cross-reference (which includes the subclause title). I think it’s just to help make sure this cross-reference gets noticed and turned into a hot link correctly, during integration (in REVmf).
There are several other instances of naked section numbers and they are common in the amendments. Not comfortable fixing them in a scattershot manner.
Maybe bring up in the Editors' meeting. We already have enough problems with stale xrefs, we don't want to queue up more candidates
3165 | RISON, Mark | 31 |  |  | 9.4.1.1.1 should be 9.4.1.11 (2x) | As it says in the comment | Accept. Note to Editor: locations are P34.1 and P34.19. | Agree with the comment and Accepting it. But, to help the Editor (and others reviewing), I would explicitly mention that the locations are P34.1 and P34.19.
3170 | RISON, Mark | 43 | 12.13.2 | 32 | "When PASN AKMP" missing article | As it says in the comment | Accept. Revised. Editor to modify the text to "When the PASN AKMP…" | I would reject this. This style matches the baseline in this paragraph.
OK
Then I think they should all be fixed
3174 | RISON, Mark | 45 | 12.13.7 | 19 | "PASN with defined key wrap" missing " AKMP" | As it says in the comment | Accept. | I agree, but I also note that this duplicates CID 3172 with a resolution in 11-24/968, so we need to help the Editor keep these aligned.
3176 | RISON, Mark | 46 | 12.13.7 | 14 | "in PASN field" should be "in the PASN field" | As it says in the comment | Accept. Revised. Editor to modify the text to "KEK In PASN field". Note "KEK In PASN" is the field name. Also in Table 9-373, "The field is set to 1 when dot11KEKPASNActivated is true to indicate support for deriving a KEK for PASN." and "KEK In PASN" in Information column. Page 50.39, same change to MIB (a KEK for PASN). | No, we need to reject this. “KEK in PASN” in the name of the field.
OK
Then the field name is incredibly confusing and the "in" should be "In"
3182 | RISON, Mark | 51 | AF.2 | 49 | "is 256" has two spaces | Delete one of them | Accept. | Similar to CID 3150. This needs to be Revised. It is actually already only one space, but it appears to a "wide" (em-dash sized) space. Replace with a normal space.
Seems to depend on the tool being used. The "Accept" was to say that it will be corrected.
3205 | RISON, Mark | 37 | 12.2.12.1 | 49 | Double full stop | Delete one of them | Accept. Reject. Not found in current draft. | I can’t find this problem. I think this is Rejected, no problem found.
Agree, Reject.
Hm, I agree.
Having said that, at 42.7 the full stop in " {RSNE, GTK[N]. OCI" should be a comma
3206 | RISON, Mark | 37 | 12.2.12.1 | 48 | "or any procedure" doesn't make sense | Change to "or any other procedure" | Accept. | Agree with Accept. But, I’d add a “Note to Editor, the location is actually 37.44.”
3207 | RISON, Mark | 39 | 12.2.12.2 | 32 | "can" is the correct way to say "is able to" | As it says in the comment | Accept. Revised. Editor to modify sentence to: "If a non-AP STA has previously provided an IRM to an AP in an ESS, the APs in the ESS have retained the information, and the non-AP STA sends an Authentication frame using that IRM as the TA to any AP in the ESS, then the AP receiving the Authentication frame can identify the non-AP STA before association is started or completed." | I don’t know what this is requesting (I can’t find the location/problem), so I don’t agree with “Accept”. In general, we need to be careful substituting “can” (which explicitly means the Standard supports this as an optional behavior) for “is able to” (which is a more declarative statement of what is believed to be a fact).
Agree, Reject. Is this comment held over from another version?
No, this is on the current text: " If a non-AP STA has previously provided an IRM to an AP in as ESS, and the non-AP STA sends an Authentication frame using that IRM as the TA to any AP in the ESS, then the AP receiving the Authentication frame is able to identify the non-AP STA before association is started or completed."
"can" is not "optional behaviour" -- that's "may" -- it's "The word can is used for statements of possibility and capability." (which I've always understood as implying "based on normative text elsewhere")