## Slide 1: TGbk 320MHz Positioning Sep. Meeting Closing Report
Date: 2024-09-12
Authors:

## Slide 2: Abstract
This document is the TGbk 320MHz Positioning closing report for the IEEE 802.11 September 2024 interim meeting.

## Slide 3: Sep. Meeting Progress and Targets Towards the Nov. Meeting
Work completed the meeting week:
  Completed response to LB287 and seek approval to move to SA ballot.
  Approved report to EC on unconditional request to go to SA ballot.
Targets towards Nov. meeting:
  Receive EC approval to go SA ballot.
  Conduct initial SA ballot and move to rapid decision making.

## Slide 4: TGbk Projected Timeline (previously)
Q2 2024
Q1 2024
Q3 2023
Q2 2023
Q1 2023
Q4 2023
Q3 2024
Q4 2024
Formation
Framework
Framework completion
05/23
802.11bk amendment text development
Initial WG ballot
Recirc 03/24
11bk D2.0
Initial SA
10/24
Final WG ballot 9/24
11bk D3.0
MDR
MDR start
MDR cmp
D4.0
D5.0
Final SA
11/24
SA Recir.
11/24

## Slide 5: TGbk Projected Timeline (updated)
Q1 2025
Q4 2024
Q2 2024
Q1 2024
Q4 2023
Q3 2024
Q2 2025
Q3 2025
Initial WG ballot
Recirc 03/24
802.11bk amendment text development
11bk D2.0
Initial SA
10/24
Final WG 7/24
11bk D3.0
MDR
MDR start
MDR cmp
D4.0
D5.0
Final SA
3/25
SA Recir.
1/25
publication
D6.0
LMSC approval to go to REVcom 5/25

## Slide 6: Scheduled TGbk telecons
  Nov. 5th 10:00 am PT/13:00 ET (2hrs) *┼
* - newly announced
** - meeting as part of the IEEE week, refer to WG agenda document for details.
┼ - Motion meeting, motions to be made available to chair 15 days in advance and announced to group 10 days in advance.