## Slide 1: REVmf Closing Report – November 2024
Date: 2024-11-14
Authors:

## Slide 2: Work Completed
Established TG leadership:
  Vice Chairs: Mark Hamilton, Mark Rison
  Editors: Po-Kai Huang, Edward Au, (with Emily Qi in supervisory role)
  Secretary: Jon Rosdahl
Established initial timeline
Considered contributions on REVme D7.0

## Slide 3: Plans for January
Teleconferences scheduled
  None. Will be announced on 10 days notice if one is needed.
January: 2 sessions
Objectives:
  Discuss contributions on changes to REVme D7.0 (in advance of IEEE 802.11-2024 publication)

## Slide 4: TGmf Timeline
Nov 2024 – PAR Approval
Nov 2024 – Initial meeting, contributions on REVme D7.0
Jan/Mar 2025 – Contributions on REVme D7.0/IEEE 802.11-2024
Jan - Mar 2025 – Publication of 802.11-2024 and roll-in of TGbh and TGbe
May 2025 – Initial D1.0 WG Letter ballot
May-Nov 2025 – Roll-in TGbf and TGbk
Jan 2026 – D2.0 Recirculation LB
Jul 2026 – D3.0 Recirculation
Jan 2027 – D4.0 Initial SA Ballot – Roll-in TGbi
Jul 2027 – D5.0 Recirculation SA Ballot
Nov 2027 – D6.0 Recirculation SA Ballot
Jan 2028 – D6.0 Recirculation SA Ballot (clean recirculation)
Feb 2028 – RevCom/SASB Approval