## Slide 1: IEEE 802.11 Nov 2024 Plenary TGbp Closing Report
Chair: Bo Sun (Sanechips)
Elected Vice Chairs: Steve Shellhammer (Qualcomm)
Rakesh Taori (Infineon)
Secretary : Sebastian Max (Ericsson)
Tech Editor: Yinan Qi (OPPO)

## Slide 2: TGbp’s Progress during this week
8 TGbp meetings were planned and held during Nov plenary session, with the agenda include in the latest revision of 11-24/1671.
TGbp approved the updated FRD and SFD documents incorporating approved motions in Sep.
More than 30 tech contributions were presented and discussed, on functional requirements, PHY/MAC solutions and Wireless Power Transmission.
Lots of technical Motions for FRD/SFD were approved as captured in last revision of 11-24/1322.
The 11bp timeline was revisited without change.
2 teleconferences were arranged after Nov plenary session.
Goal of future TGbp work:
  Continue developing FRD and SFD based on consensus
  Open technical discussion

## Slide 3: TGbp Timeline Plan (Subject to change based on development progress)
  PAR approved Mar 2024
  First TG meeting May 2024
  D0.1 (ready for CC) Mar, 2025
  D1.0 Letter Ballot Feb, 2026
  D2.0 LB recirculation Nov, 2026
  Form SA Ballot Pool Mar 1 to Mar 31, 2027
  Initial SA Ballot (D4.0) Aug, 2027
  Final 802.11 WG approval Jan 2028
  802 EC approval Mar 2028
  RevCom and SASB approval May 2028

## Slide 4: TGbp Teleconference Plan
  Dec 3rd (Tuesday), 9:00am, ET, 2 hours; Webex
  Jan 7th (Tuesday), 9:00am, ET, 2 hours; Webex