## Slide 1
IEEE 802.11 TGbp Snapshot for IEEE 802 Jan Interim 2025
Chair: Bo Sun (Sanechips)
Vice Chair: Steve Shellhammer (Qualcomm)
            Rakesh Taori (Infineon)
Secretary: Sebastian Max (Ericsson)
          Tech Editor: Yinan Qi (OPPO)

## Slide 2: TGbp Snapshot for Jan 2025 IEEE 802 Interim
2 TGbp teleconfrences were held since Nov plenary session, focusing on review of updatd FRD and SFD, and open tech discussion, with agenda included in 11-24/1996 and meeting minutes included in 11-25/0054 and 11-25/2038.
8 TGbp meetings are planned during the IEEE 802 Jan interim session, with a full meeting agenda included in the latest revision of 11-24/1997:
  Notes, all TGbp meetings will be in conference room 401.
Goal for TGbp meetings in this week:
  open technical discussion and improve FRD/SFD documents based on consensus
 | Mon | Tue | Wed | Thu | Fri
AM1 (8:00~10:00) | 802.11 Opening Plenary | TGbp (PHY) | TGbp (PHY) | TGbp (MAC/WPT/Sec) | Closing Plenary
AM2 (10:30~12:30) | TGbp (Opening/FR) |  | TGbp (MAC) |  | 
PM1 (13:30~15:30) |  |  | Mid-week Plenary | TGbp (SP/Motions/Closing) | 
PM2 (16:00~18:00) | TGbp (PHY) | TGbp (PHY) |  |  | 
EVE (19:30~21:30) |  |  |  |  | 

## Slide 3: TGbp Snapshot for Jan 2025 IEEE 802 Interim
  PAR approved Mar 2024
  First TG meeting May 2024
  D0.1 (ready for CC) Mar, 2025
  D1.0 Letter Ballot Feb, 2026
  D2.0 LB recirculation Nov, 2026
  Form SA Ballot Pool Mar 1 to Mar 31, 2027
  Initial SA Ballot (D4.0) Aug, 2027
  Final 802.11 WG approval Jan 2028
  802 EC approval Mar 2028
  RevCom and SASB approval May 2028