## Slide 1: REVmf Closing Report – January 2025
Date: 2025-01-16
Authors:

## Slide 2: Work Completed
Considered contributions on modifications REVme D7.0
  Accepted two documents with proposed changes
Discussed a contribution on extend multi-link operation to support 802.11 mesh networking
Agenda doc: https://mentor.ieee.org/802.11/dcn/24/11-24-2073-04-000m-revmf-agenda-january-2025.pptx
Motion doc: https://mentor.ieee.org/802.11/dcn/24/11-24-1925-03-000m-revmf-motions.pptx

## Slide 3: Plans for March
Teleconferences scheduled
  None planned.
  Will be announced on 10 days notice if one is needed.
March: 2 sessions
Objectives:
  Discuss contributions on changes to REVme D7.0 (in advance of IEEE 802.11-2024 publication)
  Monitor publication status of REVme, 802.11bh, and 802.11be

## Slide 4: TGmf Timeline
Nov 2024 – PAR Approval
Nov 2024 – Initial meeting, contributions on REVme D7.0
Jan - Mar 2025 – Contributions on REVme D7.0/IEEE 802.11-2024
Jan - Mar 2025 – Publication of 802.11-2024 and roll-in of TGbh and TGbe
May 2025 – Initial D1.0 WG Letter ballot
May-Nov 2025 – Roll-in TGbf and TGbk
Jan 2026 – D2.0 Recirculation LB
Jul 2026 – D3.0 Recirculation
Jan 2027 – D4.0 Initial SA Ballot – Roll-in TGbi
Jul 2027 – D5.0 Recirculation SA Ballot
Nov 2027 – D6.0 Recirculation SA Ballot
Jan 2028 – D6.0 Recirculation SA Ballot (clean recirculation)
Feb 2028 – RevCom/SASB Approval