## Slide 1: IMMW for Mobile Device and TGbq timeline
Date: 2025-03-10
Authors:

## Slide 2: Introduction (IMMW PAR/CSD)
Scope of the project
  Non-standalone operation in 42-71 GHz using single-user OFDM
  11bq device is required to support at least one of sub-7.25 GHz bands
  Multi-Link Operation (MLO) defined in sub-7.25 GHz (i.e., 11be) to support non-standalone operation in 42-71 GHz
    leverage or reuse existing PHY/MAC defined for sub-7.25 GHz bands, e.g., SU PPDU format and MAC frames, and define BW mode operating in non-overlapping channels
Need for the project
  Demands of new applications (e.g. augmented and virtual reality, proximity ranging and sensing) both in terms of throughput, latency bounds and accuracy even in in the densest environments
  Cost effective manner is achieved by enabling non-standalone operation in 42-71 GHz bands

## Slide 3: IMMW SG Discussion Summary
 | Possible options/consideration | 11ad/11ay
Modified Multi-Link Operation (MLO) | Leverage 11be/11bn Multi-Link Operation Non-standalone IMMW link | -
Single User/Multi User | Single-User for implementation simplicity Multi-User for the next release | -
Reuse sub 7GHz (11be/11bn) MAC (by up-clocking) | Details to be discussed | -
Bandwidth | [320, 2560] 320, 640, 1280, 2560MHz | [2160, 8640]
Sub-carrier spacing | 2.5 MHz | (11ay) 5.12 MHz
Modulation | 16 QAM, 64 QAM, or up to 4k QAM | SC PHY (64 QAM)
Number of Spatial Streams | 1, 2 up to 4 | (11ay) Up to 4
Throughput | 1. Min 0.1 Gbps 2. “1.5-5.5 Gbps” Or “above 10 Gbps” | 8.1 / 37.9 Gbps
Latency | For XR/VR applications, a few-milliseconds latency is required | -
Sensing/Localization | Other related TG will expand 11bq amendment | -

## Slide 4: Use case and Considerations on Consumer Mobile Device
Use Case
  High throughput hotspot
  Screen mirroring: up to 8K video mirroring with wire-equivalent latency
  AR/VR application with wire-equivalent latency and proximity/gesture detection
Further considerations
  Small form-factor size with a single antenna for mmW preferred for consumer device
  Latency reduction is important to support AR/VR application with low latency traffic (e.g., 10 ms with 99-percentile wireless delay)
  Throughput bottleneck due to Application Processor (e.g., 5 Gbps with single-core) or PCIe interface capability
    5 Gbps IMMW link throughput may be enough
  User experience: low battery drain rate, reduced batter/device heating
    Absolute heat reduction is more important than J/bit metrics. High throughput or active usage of mmW Tx chain can increase heat, which may be better to be avoided
  With the benefit of small form-factor and reduced battery heating, DL-only operation in mmW (UL TX, e.g., Ack tx, in sub-7GHz) may be considered as one of implementation options
  In consideration of hand grip loss and human body disturbance, user’s mobility, a robust (re)transmission protocol design is required

## Slide 5: Other TGs’ Timelines (as a reference)
 | PAR | PAR approved | First TG meeting | WG Letter Ballots (D1.0) | SA Ballot (D3.0/4.0/5.0) | Final 802.11 WG Approval | RevCom Approval
11ad | Very High Throughput 60GHz | 2008-12-10 |  | 2010-10-24 | 2012-01-05 | 2012-07-01 | 2012-10-23
11ay | Next Generation 60GHz | 2015-03-26 |  | 2018-01-07 | 2020-01-09 | 2020-11-01 | 2021-03-01
11bf | WLAN Sensing | 2020-09-25 | 2020-08 | 2023-03-02 | 2024-06-12 |  | 
11bh | Randomized and Changing MAC Addresses | 2021-02-10 |  | 2023-07-01 | 2024-05-09 | 2024-07-01 | 
11bi | Enhanced Data Privacy | 2021-02-10 |  | 2025-01 |  |  | 
11bk | 320 MHz Positioning | 2022-12-03 |  | 2023-12-28 | 2024-11-10 |  | 
11bp | Ambient Power Communication | 2024-03-19 | 2024-05 | 2026-02 | 2027-08 | 2028-01 | 2028-05
from first TG meeting to D1.0: 1-3 years
from D1.0 to 11 WG approval: 1-2 years

## Slide 6: Proposal: TGbq Timeline Adjustment
TGbq timeline needs to be adjusted and PAR extension may be required considering the start date of TGbq (Feb. '25), sufficient technical discussions period (1-2 years), the practical letter ballot period (1-2 years), and SA ballot period (0.5 year)
  Roughly we have three options, i.e., Option 1 (maintaining PAR timeline, the expected completion time: Mar. 2027), Option 2 (an aggressive one, the expected completion time: Apr. 2028), and Option 3 (a conservative one, the expected completion time: Apr. 2029)
2024
2025
2026
2027
Break
2028
PAR/CSD
approved in WG
(Jul. '24)
IMMW SG
(Nov. '23)
34 contributions discussed
First TGbq
(Feb. '25)
Initial SA Ballot (D4.0)
(Jul. '26)
16 month
8 month
Submittal to RevCom
(Mar. '27)
12 month
D0.1 (Feb. '26)
D4.0
(Aug. '27)
Submittal to RevCom
(Apr. '28)
Option 2 (aggressive one)
6 month
8 month
D1.0
(Aug. '26)
12 month
2029
Option 1 (PAR timeline)
18 month
D1.0
(Aug. '27)
Option 3 (conservative one)
D0.1
(Aug. '26)
12 month
D4.0
(Aug. '28)
Submittal to RevCom
(Apr. '29)
8 month
12 month
D0.1
D1.0

## Slide 7: Conclusion
Various technical discussions have been studied in the IMMW SG, and now specific upper limits of spatial stream, bandwidth, and modulation need to be determined in consideration of target throughput and latency
We need a more realistic and reasonable timeline for TGbq in consideration of the other TGs’ timelines, sufficient technical discussion period and comment resolution period
  D0.1
    Discussion on target performance metrics and which specific MAC/PHY features we can reuse for TGbq to achieve them
    MAC enhancement to support Multi-Link Operation for non-standalone mmW link
  D1.0 – D4.0: comment resolution period (it typically takes 1-2 years)

## Slide 8: Reference
[1]

## Slide 9: Straw Poll #1
Do you agree with extending the timeline since the current PAR timeline is considered unrealistically tight?

## Slide 10: Straw Poll #2
Which of the following options do you think a realistic and reasonable timeline for TGbq?
  Option 1) the expected completion time (submittal to RevCom): Mar. 2027
    This option aligns with the timeline in the PAR
    Expected milestone: D1.0 (late '25 or early '26), D4.0 (Jul. '26)
  Option 2), the expected completion time: Apr. 2028
    Expected milestone: D0.1 (Feb. '26), D1.0 (Aug. '26), D4.0 (Aug. '27)
      One year of technical discussions to get D0.1
  Option 3), the expected completion time: Apr. 2029
    Expected milestone: D0.1 (Aug. '26), D1.0 (Aug. '27), D4.0 (Aug. '28)
      One and a half years of technical discussions to get D0.1
  [Note 1] If straw poll #1 is passed, then option 1 is not valid.