## Slide 1: P802.11bk Report to 802 LMSC on Conditional Approval to go to RevCom
Date: 2025-03-12
Authors:

## Slide 2: Introduction
This document contains the report to the IEEE 802 Executive Committee in support of a request for conditional approval to send IEEE P802.11bk D5.0 to RevCom.
R0 – Initial draft.
R1 – incorporate feedback from group discussion, update unsatisfied commenters list.
R2 – update typos.

## Slide 3: Standards Association (SA) Ballot Results – P802.11bk
Ballot Close Date | Title | Ballot Type | Pool | Return | %Return | Abstain | %Abstain | Approve | Disapprove | %Approve
Nov.-10-2024 | Initial SA ballot for D3.0 | Technical | 150 | 101 | 76% | 5 | 7% | 103 | 7 | 93%
Feb.-07-2025 | First Recirculation Ballot for TGbk draft 4.0 | Recirculation | 150 | 122 | 81% | 4 | 3% | 114 | 4 | 96%

## Slide 4: SA Ballot Comments – P802.11bk
Ballot Close Date | Title | Total Number of Comments received (Yes and No votes)
Nov.-10-2024 | Initial SA ballot for P802.11bk draft D3.0 | 78 (28T, 0G, 50E)
Feb.-07-2025 | First Recirculation SA Ballot for P802.11bk draft 4.0 | 21 (13T, 0G, 8E)

## Slide 5: Unsatisfied Technical comments by commenter
Voter | Initial | 1st Re | 2nd Re | Comment topic | Total
None. |  |  |  |  | 

## Slide 6: IEEE-SA Mandatory Coordination
Coordination Entity | Draft | Date | Status
IEEE-SA Editorial (MEC) | D3.0 | July 2024 | “Meets all editorial requirements.”
Quantities, Units and Letter Symbols (SCC14) |  |  | Not required
Terms and Definitions (SCC10) |  |  | Not required
Registration Authority Committee (RAC) |  |  | Not Required

## Slide 7: P802.11bk Timeline
Report to 802 LMSC for conditional approval to proceed to RevCom | 2025-03-14
2nd Recirculation on D5.0 | 2025-03-24 – 2022-04-02
Comment Response Notification | 2025-04-07
Post to RevCom by | 2025-03-28
RevCom recommendation | 2025-05-07
SASB approval | Expected prior to 2025-05-31