## All Comments
CID | Commenter | Must Be Satisfied | Clause Number(C) | Page(C) | Line(C) | Category | Clause | Page | Comment | Proposed Change | Ad-hoc | Comment Group | Ad-hoc Notes | Status | Assignee | Submission | Resn Status | Resolution | Ready For Motion | Motion Number | Edit Status | Edited in Draft | Edit Notes | Last Updated | Last Updated By
R2-1 | Stephan Sand | Yes | 9.4.2.1 | 25 | 27 | T | 9.4.2.1 | 25.27 | In Table 9-130 (Element IDs) the element "Puncture Pattern Element" with Element ID 254 is introduced. However, Table 9-130 P894L44 in 802.11REVme D7.0 the Element ID is reserved. Also Table 9-130 is in the ANA database and 11bk did not update the Table 9-130. | According to ANA database 11-0270r77 elements 245 to 252 are available. Therefore, change the Element ID for the Puncture Pattern Element to 245 in Table 9-130 and update the ANA database accordingly. | [7 empty] | REJECT The comment is not related to the project/standard being balloted. The comment is outside the scope of the ballot as it refers to the document 11-11-270r77 (ANA DB), which is outside the scope of P802.11bk. | [5 empty] | 2025-03-31 14:24 | Robert Stacey
R2-2 | Christian Berger | No | 9.6.7.49 | 34 | 16 | E | 9.6.7.49 | 34.16 | Mix of underline and not underline in new text with editor instruction "change" | Either underline the first paragraph, or remove underline from the second paragraph and change editor instruction to "add" | [7 empty] | REJECT The comments will be forwarded to the publisher. | [5 empty] | 2025-03-31 14:24 | Robert Stacey
R2-3 | Christian Berger | No | 11.21.6.4.3.1 | 43 | 3 | E | 11.21.6.4.3.1 | 43.03 | Break in the underline | Make sure all new text is underlined (underline the word "MU") | [7 empty] | REJECT The comments will be forwarded to the publisher. | [5 empty] | 2025-03-31 14:24 | Robert Stacey