## IEEEcover
August 2004 |  | IEEE P802.15-04/423r0
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | Drafting status
Date Submitted | [August 10, 2004]
Source | [James P. K. Gilb] | Voice: [(858)-485-6401]
| [Appairent Technologies] | Fax: [(858)-485-6406]
| [16990 Via Tazon, #125] | E-mail: [last name at ieee dot org]
[San Diego, CA 92127]
Re: | []
Abstract | [This spreadsheet tracks the comment drafting status for both the assignments of issues to people as well as tracking when the resolutions are applied to the draft.]
Purpose | [To track the status of comments and the application of the resolutions to the draft.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after furt
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Commentswritten
|  | Left to go | 69
|  | Total finished | 7
|  | Left to claim | 0 | Enter 'done' when comment applied
CID | Status | Heberling | ADH comments | Gilb | JPKG comments | Hall | JH comments | Sarallo | JS comments | Schrader | MKS comments | Bain | JB comments | Tally | Claimed
1 | JCB | [10 empty] | JCB | Jay to write text | 0 | 0
2 | JH |  |  |  |  | JH | Text proposed | [6 empty] | 0 | 0
3 | Done |  |  | Done | Comment rejected | [8 empty] | 1 | 0
4 | JH |  |  |  |  | JH | Text proposed | [6 empty] | 0 | 0
5 | Done |  |  | Done | Comment rejected | [8 empty] | 1 | 0
6 | JPKG |  |  | JPKG | Text in the minutes | [8 empty] | 0 | 0
7 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
8 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
9 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
10 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
11 | Done |  |  | Done | Comment rejected | [8 empty] | 1 | 0
12 | Sarallo | [6 empty] | Sarallo | Will be corrected with updates to MSCs, see CID 36 |  |  |  |  | 0 | 0
13 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
14 | Done |  |  | Done | Comment rejected | [8 empty] | 1 | 0
15 | JPKG |  |  | JPKG | Write based on minutes | [8 empty] | 0 | 0
16 | JPKG |  |  | JPKG | Write based on minutes | [8 empty] | 0 | 0
17 | JPKG |  |  | JPKG | Write based on minutes | [8 empty] | 0 | 0
18 | JPKG |  |  | JPKG | Write based on minutes | [8 empty] | 0 | 0
19 | JPKG |  |  | JPKG | Write based on minutes | [8 empty] | 0 | 0
20 | JPKG |  |  | JPKG | Write based on minutes | [8 empty] | 0 | 0
21 | Done |  |  | Done | Comment rejected | [8 empty] | 1 | 0
22 | Done |  |  | Done | Comment rejected | [8 empty] | 1 | 0
23 | Sarallo | [6 empty] | Sarallo | Need to align with new MLMEs |  |  |  |  | 0 | 0
24 | Sarallo | [6 empty] | Sarallo | Need to align with new MLMEs |  |  |  |  | 0 | 0
25 | JPKG |  |  | JPKG | Write based on minutes | [8 empty] | 0 | 0
26 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
27 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
28 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
29 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
30 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
31 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
32 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
33 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
34 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
35 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
36 | Sarallo | [6 empty] | Sarallo | The new MSCs, align with new MLMEs |  |  |  |  | 0 | 0
37 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
38 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
39 | JPKG |  |  | JPKG | New text in 15-04-0384-00 | [8 empty] | 0 | 0
40 | JPKG |  |  | JPKG | New text in 15-04-0384-00 | [8 empty] | 0 | 0
41 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
42 | JPKG |  |  | JPKG | Pending resolution, see CID 45 | [8 empty] | 0 | 0
43 | JPKG |  |  | JPKG | New text in 15-04-0384-00 | [8 empty] | 0 | 0
44 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
45 | JPKG |  |  | JPKG | Pending resolution, see CID 42 | [8 empty] | 0 | 0
46 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
47 | JPKG |  |  | JPKG | New text needed (HCS calc) | [8 empty] | 0 | 0
48 | JPKG |  |  | JPKG | New text needed (FCS calc) | [8 empty] | 0 | 0
49 | Sarallo | [6 empty] | Sarallo | Align with new MLMEs |  |  |  |  | 0 | 0
50 | Sarallo | [6 empty] | Sarallo | Need to allow fragmentation of PNC Info command |  |  |  |  | 0 | 0
51 | JPKG |  |  | JPKG | New text in 15-04-0384-00 | [8 empty] | 0 | 0
52 | JCB | [10 empty] | JCB | Jay to write text | 0 | 0
53 | JPKG |  |  | JPKG | New text in 15-04-0384-00 | [8 empty] | 0 | 0
54 | JPKG |  |  | JPKG | New text in 15-04-0384-00 | [8 empty] | 0 | 0
55 | JPKG |  |  | JPKG | New text in 15-04-0384-00 | [8 empty] | 0 | 0
56 | JPKG |  |  | JPKG | New text in 15-04-0384-00 | [8 empty] | 0 | 0
57 | JPKG |  |  | JPKG | New text in 15-04-0384-00 | [8 empty] | 0 | 0
58 | JPKG |  |  | JPKG | New text in 15-04-0384-00 | [8 empty] | 0 | 0
59 | JPKG |  |  | JPKG | New text in 15-04-0384-00 | [8 empty] | 0 | 0
60 | Done |  |  | Done | Comment rejected | [8 empty] | 1 | 0
61 | JPKG |  |  | JPKG | New text in 15-04-0384-00 | [8 empty] | 0 | 0
62 | JPKG |  |  | JPKG | New text in 15-04-0384-00 | [8 empty] | 0 | 0
63 | JPKG |  |  | JPKG | See 15-04-0131-03 | [8 empty] | 0 | 0
64 | JPKG |  |  | JPKG | Need to write annex | [8 empty] | 0 | 0
65 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
66 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
67 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
68 | JPKG |  |  | JPKG | See 15-04-0131-03 | [8 empty] | 0 | 0
69 | JPKG |  |  | JPKG | Need to propose text | [8 empty] | 0 | 0
70 | JPKG |  |  | JPKG | Need to propose text | [8 empty] | 0 | 0
71 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
72 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
73 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
74 | JPKG |  |  | JPKG | Text in database | [8 empty] | 0 | 0
75 | Sarallo | [6 empty] | Sarallo | New MLMEs |  |  |  |  | 0 | 0
76 | Sarallo | [6 empty] | Sarallo | Align with new MLMEs |  |  |  |  | 0 | 0
Total assigned |  | 0 |  | 64 |  | 2 |  | 8 |  | 0 |  | 2 |  | 76
Total resolved |  | 0 |  | 7 |  | 0 |  | 0 |  | 0 |  | 0 |  | 7
Total left to finish |  | 0 |  | 57 |  | 2 |  | 8 |  | 0 |  | 2 |  | 69

## Commentsresolved
Total left to close |  | 243 |  | Assigned to others | 241 | Assigned to Gilb | 2 | Assigned to Odman | 0 | Assigned to Schrader/Bain | 0 | PM | 0 | Pmwake | 0 | Editorials for Gilb | 0
Total left to assign |  | 243 |  |  |  | Assigned to Singer | 0 | Assigned to Heberling | 0 | Assigned to Bain | 0 | MTS | 0 | MaxCTAs | 0 | T & TR's left | 245
Comment ID | Assigned to | Closed/open | Status | Due date | Not Assigned | Assgned to Schrader | 0 | Assigned to Sarallo | 0
1 |  |  |  |  | 1
2 |  |  |  |  | 1
3 |  |  |  |  | 1
4 |  |  |  |  | 1
5 |  |  |  |  | 1
6 |  |  |  |  | 1
7 | Gilb | Closed |  |  | 0
8 |  |  |  |  | 1
9 |  |  |  |  | 1
10 |  |  |  |  | 1
11 |  |  |  |  | 1
12 |  |  |  |  | 1
13 |  |  |  |  | 1
14 |  |  |  |  | 1
15 |  |  |  |  | 1
16 |  |  |  |  | 1
17 |  |  |  |  | 1
18 |  |  |  |  | 1
19 |  |  |  |  | 1
20 |  |  |  |  | 1
21 |  |  |  |  | 1
22 |  |  |  |  | 1
23 |  |  |  |  | 1
24 |  |  |  |  | 1
25 |  |  |  |  | 1
26 |  |  |  |  | 1
27 |  |  |  |  | 1
28 |  |  |  |  | 1
29 |  |  |  |  | 1
30 |  |  |  |  | 1
31 |  |  |  |  | 1
32 |  |  |  |  | 1
33 |  |  |  |  | 1
34 |  |  |  |  | 1
35 |  |  |  |  | 1
36 |  |  |  |  | 1
37 |  |  |  |  | 1
38 |  |  |  |  | 1
39 |  |  |  |  | 1
40 |  |  |  |  | 1
41 |  |  |  |  | 1
42 |  |  |  |  | 1
43 |  |  |  |  | 1
44 |  |  |  |  | 1
45 |  |  |  |  | 1
46 |  |  |  |  | 1
47 |  |  |  |  | 1
48 |  |  |  |  | 1
49 |  |  |  |  | 1
50 |  |  |  |  | 1
51 |  |  |  |  | 1
52 |  |  |  |  | 1
53 |  |  |  |  | 1
54 |  |  |  |  | 1
55 |  |  |  |  | 1
56 |  |  |  |  | 1
57 |  |  |  |  | 1
58 |  |  |  |  | 1
59 |  |  |  |  | 1
60 |  |  |  |  | 1
61 |  |  |  |  | 1
62 |  |  |  |  | 1
63 |  |  |  |  | 1
64 |  |  |  |  | 1
65 |  |  |  |  | 1
66 |  |  |  |  | 1
67 |  |  |  |  | 1
68 |  |  |  |  | 1
69 |  |  |  |  | 1
70 |  |  |  |  | 1
71 |  |  |  |  | 1
72 |  |  |  |  | 1
73 |  |  |  |  | 1
74 |  |  |  |  | 1
75 |  |  |  |  | 1
76 |  |  |  |  | 1
77 |  |  |  |  | 1
78 |  |  |  |  | 1
79 |  |  |  |  | 1
80 |  |  |  |  | 1
81 |  |  |  |  | 1
82 |  |  |  |  | 1
83 |  |  |  |  | 1
84 |  |  |  |  | 1
85 |  |  |  |  | 1
86 |  |  |  |  | 1
87 |  |  |  |  | 1
88 |  |  |  |  | 1
89 |  |  |  |  | 1
90 |  |  |  |  | 1
91 |  |  |  |  | 1
92 |  |  |  |  | 1
93 |  |  |  |  | 1
94 |  |  |  |  | 1
95 |  |  |  |  | 1
96 |  |  |  |  | 1
97 |  |  |  |  | 1
98 |  |  |  |  | 1
99 |  |  |  |  | 1
100 |  |  |  |  | 1
101 |  |  |  |  | 1
102 |  |  |  |  | 1
103 |  |  |  |  | 1
104 |  |  |  |  | 1
105 |  |  |  |  | 1
106 |  |  |  |  | 1
107 |  |  |  |  | 1
108 |  |  |  |  | 1
109 |  |  |  |  | 1
110 |  |  |  |  | 1
111 |  |  |  |  | 1
112 |  |  |  |  | 1
113 |  |  |  |  | 1
114 |  |  |  |  | 1
115 |  |  |  |  | 1
116 |  |  |  |  | 1
117 |  |  |  |  | 1
118 |  |  |  |  | 1
119 |  |  |  |  | 1
120 |  |  |  |  | 1
121 |  |  |  |  | 1
122 |  |  |  |  | 1
123 |  |  |  |  | 1
124 |  |  |  |  | 1
125 |  |  |  |  | 1
126 |  |  |  |  | 1
127 |  |  |  |  | 1
128 |  |  |  |  | 1
129 |  |  |  |  | 1
130 |  |  |  |  | 1
131 |  |  |  |  | 1
132 |  |  |  |  | 1
133 |  |  |  |  | 1
134 |  |  |  |  | 1
135 |  |  |  |  | 1
136 |  |  |  |  | 1
137 |  |  |  |  | 1
138 |  |  |  |  | 1
139 |  |  |  |  | 1
140 |  |  |  |  | 1
141 |  |  |  |  | 1
142 |  |  |  |  | 1
143 |  |  |  |  | 1
144 |  |  |  |  | 1
145 |  |  |  |  | 1
146 |  |  |  |  | 1
147 |  |  |  |  | 1
148 |  |  |  |  | 1
149 |  |  |  |  | 1
150 |  |  |  |  | 1
151 |  |  |  |  | 1
152 |  |  |  |  | 1
153 |  |  |  |  | 1
154 |  |  |  |  | 1
155 |  |  |  |  | 1
156 |  |  |  |  | 1
157 |  |  |  |  | 1
158 |  |  |  |  | 1
159 |  |  |  |  | 1
160 |  |  |  |  | 1
161 |  |  |  |  | 1
162 |  |  |  |  | 1
163 |  |  |  |  | 1
164 |  |  |  |  | 1
165 |  |  |  |  | 1
166 |  |  |  |  | 1
167 |  |  |  |  | 1
168 |  |  |  |  | 1
169 |  |  |  |  | 1
170 |  |  |  |  | 1
171 |  |  |  |  | 1
172 |  |  |  |  | 1
173 |  |  |  |  | 1
174 |  |  |  |  | 1
175 |  |  |  |  | 1
176 |  |  |  |  | 1
177 |  |  |  |  | 1
178 |  |  |  |  | 1
179 |  |  |  |  | 1
180 |  |  |  |  | 1
181 |  |  |  |  | 1
182 |  |  |  |  | 1
183 |  |  |  |  | 1
184 |  |  |  |  | 1
185 |  |  |  |  | 1
186 |  |  |  |  | 1
187 |  |  |  |  | 1
188 |  |  |  |  | 1
189 |  |  |  |  | 1
190 |  |  |  |  | 1
191 |  |  |  |  | 1
192 |  |  |  |  | 1
193 |  |  |  |  | 1
194 |  |  |  |  | 1
195 |  |  |  |  | 1
196 |  |  |  |  | 1
197 |  |  |  |  | 1
198 |  |  |  |  | 1
199 |  |  |  |  | 1
200 |  |  |  |  | 1
201 |  |  |  |  | 1
202 |  |  |  |  | 1
203 |  |  |  |  | 1
204 |  |  |  |  | 1
205 |  |  |  |  | 1
206 |  |  |  |  | 1
207 |  |  |  |  | 1
208 |  |  |  |  | 1
209 |  |  |  |  | 1
210 |  |  |  |  | 1
211 |  |  |  |  | 1
212 |  |  |  |  | 1
213 |  |  |  |  | 1
214 |  |  |  |  | 1
215 |  |  |  |  | 1
216 |  |  |  |  | 1
217 |  |  |  |  | 1
218 |  |  |  |  | 1
219 |  |  |  |  | 1
220 |  |  |  |  | 1
221 |  |  |  |  | 1
222 |  |  |  |  | 1
223 |  |  |  |  | 1
224 |  |  |  |  | 1
225 |  |  |  |  | 1
226 |  |  |  |  | 1
227 |  |  |  |  | 1
228 |  |  |  |  | 1
229 |  |  |  |  | 1
230 |  |  |  |  | 1
231 |  |  |  |  | 1
232 |  |  |  |  | 1
233 |  |  |  |  | 1
234 |  |  |  |  | 1
235 | Gilb | Closed |  |  | 0
236 |  |  |  |  | 1
237 |  |  |  |  | 1
238 |  |  |  |  | 1
239 |  |  |  |  | 1
240 |  |  |  |  | 1
241 |  |  |  |  | 1
242 |  |  |  |  | 1
243 |  |  |  |  | 1
244 |  |  |  |  | 1
245 |  |  |  |  | 1