## Main
Priority | Direction | Related To CID | CID | CommenterName | CommenterEmail | Commenter Phone | Commenter Mobile | Commenter Company | Clause | Subclause | Page | Line | Comment Type | Comment | SuggestedRemedy | Response | Comment Status | Response Status | Topic | CreateDate | LastModDate | Dispatch Date | Written Date | Accept_Reject Date | Closed_Unsatisf Date | Voter Status
3 |  | 1 | 1 | Bain, Jay | jbain@hiwaay.net |  |  | Fearn Consulting | 06 | 6.1.2 | 28 | 25 | TR | Although the following sub-clause 6.1.2.1 Channel pages covers the addition, leaving 6.1.2 alone leaves the original but errored text in place. There is a comment that also deals with the editorial style of current 6.1.2.1. That still stands. | Make 6.1.2 a leadin that overviews the channel pages and channel numbering. Then make 6.1.2.1 contain what is currently in 6.1.2 (with some edits that specify a less absolute statement than "A total of 27 channels ..."). Then add a sub-clause 6.1.2.2 to include the channel page details. | Correct, sections 6.1.2 and 6.1.2.1 will be modified to make the text technically correct. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 2 | 2 | Bain, Jay | jbain@hiwaay.net |  |  | Fearn Consulting | 06 | multiple |  |  | TR | Request to make the aMinSIFSPeriod and aMinLIFSPeriod dependent on and specified by the PHY clauses. This removes text and table content from the body of the MAC clause. Several comments make up this request thus providing specifics on where the changes are requested. This comment addresses the several destination sub-clauses of the table for aMinSIFSPeriod and aMinLIFSPeriod suggested to be in 6.1 | For each phy type, insert a sub-clause (location TBD) that is the destination of the pointer in the new table in 6.1 (general stuff). This is the destination of the values moved from clause 7. Include the value and the unit which is symbols for the PHYs in the original 15.4 standard. | Although we understand you have a preference there is no techincal difference related to the location of this information and it does not change the implementation of the standard. The committee feels that since this is a timing issue related to the MAC it belongs in the MAC section and is appropriate for current PHY's. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 2 | 5 | Bain, Jay | jbain@hiwaay.net |  |  | Fearn Consulting | 06 | 6.1 | 27 | 17 | TR | Request to make the aMinSIFSPeriod and aMinLIFSPeriod dependent on and specified by the PHY clauses. This removes text and table content from the body of the MAC clause. Several comments make up this request thus providing specifics on where the changes are requested. This comment is the placement of the general table that in turn points to the sub-clauses in the specific band PHY | Develop a table in 6.2. Horizontal titles are aMinSIFSPeriod and aMinLIFSPeriod. Vertical titles are the specific PHY that can be pointed to. This table will be extended as part of TG4a's work. It is difficult to understand where to place this table so it is in the global area of clause 6 (6.1). I think it should be in the same area as 6.1.2 Channel assignments and numbering but am not sure. | Although we understand you have a preference there is no techincal difference related to the location of this information and it does not change the implementation of the standard. The committee feels that since this is a timing issue related to the MAC it belongs in the MAC section and is appropriate for current PHY's. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 6 | 6 | Bain, Jay | jbain@hiwaay.net |  |  | Fearn Consulting | 06 | 6.4.2 table 20 | 45 | 19 | TR | In looking at Table 20 - PHY PIB attributes, it is difficult to fully understand the "Array" on phyChannelsSupported. The description doesn't seem to indicate how to build the array and how big it is (in the channel page supported direction). Does the array null fill all possible combinations of channel pages or just the ones supported? Should there be a one 32bit field for each of the non-zero fields in the phyPagesSupported bitmap? | Change the description of phyChannelsSupported description field. Add text that notes that there is one entry in the array for each non-zero entry in the phyPagesSupported bitmap. (pick a direction to read that bit map and state it so it is obvious how to read the array.) | Add normative text: The device only needs to add the tables for the PHY it supports. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 10 | 10 | Balakrishnan, Jaiganesh | jai@ti.com |  |  | Texas Instruments | 06 | 6.1.2.1 | 28 |  | TR | Channel page scheme results in too much overhead (ie number of bits). | Should just pre-append 3 bits to the channel number in order to define page. This will result in an octet describing both the channel page and channel number. | These changes were needed to address new regulatory bands and the addition of the new sub 1 GHz PHY's. The proposed remedy is not backwards compatible where as the solution in the new table is. Only the tables that you would use would be needed. Add informative text to table. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 11 | 11 | Balakrishnan, Jaiganesh | jai@ti.com |  |  | Texas Instruments | 06 | 6.7.2.2 | 52 |  | TR | There is a potential to add either 14 or 4 zero pad bits to the end of every packet. These zeros could potentially cause problems (DC offset), non-white spectrum, etc. | Add a scrambler to whiten the pad bits. | Add informative text: These zero pad bits will also be spread via the PSSS encoding to keep the over the air signaling as random as possible. | X | O |  | 2005-03-11 | 2005-03-11
1 |  | 12 | 12 | Balakrishnan, Jaiganesh | jai@ti.com |  |  | Texas Instruments | 06 | 6.7.4.1 | 56 |  | TR | A new preamble is defined for the optional PHY. How do legacy (mandatory PHYs in the 868/915 MHz band) interoperate or coexist with the optional PHY? | Please describe mechanisms, such as CTS/RTS reservations, such as the ones used in 802.11g. | Add normative text: Network formation is addressed in section 7.5.2. The PAN coordinator starts in whatever mode it instructed to and is not intended to switch dynamically. New sub GHz PHY's will be required to use either Mode 1 or Mode 3 CCA. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 10 | 13 | Batra, Anuj | batra@ieee.org |  |  | Texas Instruments | 06 | 6.1.2.1 | 28 |  | TR | Channel page scheme results in too much overhead (i.e., number of bits). | Should just pre-append 3 bits to the channel number in order to define page. This will result in an octet describing both the channel page and channel number. | see CID10. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 11 | 14 | Batra, Anuj | batra@ieee.org |  |  | Texas Instruments | 06 | 6.7.2.2 | 52 |  | TR | There is a potential to add either 14 or 4 zero pad bits to the end of every packet. These zeros could potentially cause problems (DC offset), non-white spectrum, etc. | Add a scrambler to whiten the pad bits. | see CID11. | X | O |  | 2005-03-11 | 2005-03-11
1 |  | 12 | 15 | Batra, Anuj | batra@ieee.org |  |  | Texas Instruments | 06 | 6.7.4.1 | 56 |  | TR | A new preamble is defined for the optional PHY. How do legacy devices (mandatory PHYs in the 868/915 MHz band) interoperate or coexist with the optional PHY? | Please describe mechanisms, such as CTS/RTS reservations, such as the ones used in 802.11g. | see CID12. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 709 | 709 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | 6.3.1.1 | 43 | 19 | TR | The last sentence of 6.3.1.1 is no longer correct. | Two options: (1) Replace last sentence with, "The preamble fields are described in each PHY section." Then add preamble sections to each PHY description. (2) Replace last sentence with, "For all PHY's except the optional PSSS PHY's, the preamble field shall be composed of 32 binary zeros. The PSSS preamble format is described in 6.7.4.1." | Correct, will accept remedy #2 - "For all PHY's except the optional PSSS PHY's, the preamble field shall be composed of 32 binary zeros. The PSSS preamble format is described in 6.7.4.1". | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 710 | 710 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | 6.3.1.2 | 43 | 24 | TR | The text for SFD may need to change depending on how PSSS encodes the SFD, which is not clear from section 6.7.4.2, and is the subject of another comment. | Review text from 6.3.1.2 in conjunction with PSSS SFD format in 6.7.4.2. | The proposed and accepted PSSS changes regarding the preamble and the SFD address this comment wholly. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 711 | 711 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | 6.7.4.2 | 56 | 43 | TR | The last sentence is incorrect. Table 18 shows valid frame length values, not SFD format. Also, it is not clear from 6.7.4.2 how the SFD is formatted. Does it use 26-chip sequences (like the preamble), or does it use BPSK modulation of a 32-chip sequence (like the data)? | Clarify specification of PSSS SFD. | The proposed and accepted PSSS changes regarding the preamble and the SFD address this comment wholly. Additionally normative text will be added to Section 6.3.1 referencing the sub-sections in 6.7 describing the differences of the preamble and SFD for PSSS. Also add a table summarizing preamble length in chips/symbols and time (the settled upon 320 uS). | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 715 | 715 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | 6.7.2.4 | 54 | 46 | TR | The chip rate for the 915 MHz band is specified here as 1600 kchip/s, but this is inconsistent with the symbol rate specified in 6.7.3.3. (62500 symb/sec)x(32 chip/symb) = 2000 kchip/sec. Perhaps the symbol rate in 6.7.3.3 is inocrrect, since Table 1 shows 50 ksymb/sec. | Make appropriate correction. | Correct, the data rate in Section 6.7.3.3 should be 50ksymbols/sec for the 915MHz signaling. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 716 | 716 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | Equation 7 | 54 |  | TR | The denominator in the equation for root-raised-cosine should have the form K(1-x^2) instead of K(x^2-1). As written, the pulse has a peak of -1 instead of +1. | Make appropriate change. | Correct, equation will be changed to reflect proper phase. | X | O |  | 2005-03-11 | 2005-03-11
2 | Add informative text: Outlining the tradeoffs between the 2 PHY's in Clause 5 or Clause 6 or both. | 963 | 963 | Richard Roberts | rrober14@harris.com |  |  | Harris Corporation | 06 | Table 1 | 27 |  | TR | There are two 868/915 MHz optional modes: PSSS and O-QPSK. These modes are running basically the same data rate in nearly the same bandwidth. I think that the committee needs to pick one mode or the other. While I appreciate compromise, in this case I think the committee needs to make a choice between one or the other. | Continue technical debate and chose only one high bit rate mode for use in the 868/915 MHz bands. | Add informative text: Two optional high data rate PHY's are proposed offering a tradeoff between complexity and data rate. The optional PSSS PHY offers data rates in both the 868MHz and 915MHz bands equal to that of the current 2.4GHz band PHY. The optional O-QPSK PHY offers a data rate in the 915MHz band equal to that of the current 2.4GHz band PHY and a data rate in the 868MHz band not quite as high as that of the current 2.4GHz band PHY. The optional O-QPSK PHY however, offer a signalling scheme identical to that of the current 2.4GHz band PHY. Both optional PHYs offer a data rate much higher than that of the current 868MHz and 915MHz band PHY's. | X | O |  | 2005-03-11 | 2005-03-11
1 |  | 12 | 965 | Richard Roberts | rrober14@harris.com |  |  | Harris Corporation | 06 | Table 1 | 27 |  | TR | In regards to the PHY options at 868/915 MHz, it is not clear what is the mandatory mode for communications between a PSSS and a O-QPSK radio. Is it required that all PANs in the 868/915 band start at 20 kbps/40 kbps before switching to the high speed option. How is that done? I didn't see it but may be I overlooked it in the draft. | Add a section to clause 6.6 that points the reader to a discussion of how a PSSS and a O-QPSK radio interoperate at some lower mandatory rate. How is the PAN started? At what data rate? Does it always form at the low mandatory rate and then shift to the high rate? If the material is missing then it needs to be added into the draft. | see CID12. | X | O |  | 2005-03-11 | 2005-03-11
1 |  | 12 | 1150 | Wineinger, Gerald | gww@ieee.org |  |  | Texas Instruments | 06 | 6.7.4.1 | 56 |  | TR | A new preamble is defined for the optional PHY. How do legacy (mandatory PHYs in the 868/915 MHz band) interoperate or coexist with the optional PHY? | Use the descriptionsof mechanisms, such as CTS/RTS reservations, the ones used in 802.11g. | see CID12. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 10 | 1153 | Wright, Tracy | t-wright@ti.com |  |  | Texas Instruments | 06 | 6.1.2.1 | 28 |  | TR | Channel page scheme results in too much overhead (ie number of bits). | Should just pre-append 3 bits to the channel number in order to define page. This will result in an octet describing both the channel page and channel number. | see CID10. | X | O |  | 2005-03-11 | 2005-03-11 |  |  |  |  | O
3 |  | 11 | 1154 | Wright, Tracy | t-wright@ti.com |  |  | Texas Instruments | 06 | 6.7.2.2 | 52 |  | TR | There is a potential to add either 14 or 4 zero pad bits to the end of every packet. These zeros could potentially cause problems (DC offset), non-white spectrum, etc. | Add a scrambler to whiten the pad bits. | see CID11. | X | O |  | 2005-03-11 | 2005-03-11 |  |  |  |  | O
1 |  | 12 | 1155 | Wright, Tracy | t-wright@ti.com |  |  | Texas Instruments | 06 | 6.7.4.1 | 56 |  | TR | A new preamble is defined for the optional PHY. How do legacy (mandatory PHYs in the 868/915 MHz band) interoperate or coexist with the optional PHY? | Please describe mechanisms, such as CTS/RTS reservations, such as the ones used in 802.11g. | see CID12. | X | O |  | 2005-03-11 | 2005-03-11 |  |  |  |  | O
3 |  | 10 | 1158 | Yamaguchi, Hirohisa | h-yamaguchi4@ti.com |  |  | Texas Instruments | 06 | 6.1.2.1 | 28 |  | TR | Channel page scheme results in too much overhead (ie number of bits). | Should just pre-append 3 bits to the channel number in order to define page. This will result in an octet describing both the channel page and channel number. | see CID10. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 10 | 1159 | Yamaguchi, Hirohisa | h-yamaguchi4@ti.com |  |  | Texas Instruments | 06 | 6.7.2.2 | 52 |  | TR | There is a potential to add either 14 or 4 zero pad bits to the end of every packet. These zeros could potentially cause problems (DC offset), non-white spectrum, etc. | Add a scrambler to whiten the pad bits. | see CID11. | X | O |  | 2005-03-11 | 2005-03-11
1 |  | 12 | 1160 | Yamaguchi, Hirohisa | h-yamaguchi4@ti.com |  |  | Texas Instruments | 06 | 6.7.4.1 | 56 |  | TR | A new preamble is defined for the optional PHY. How do legacy (mandatory PHYs in the 868/915 MHz band) interoperate or coexist with the optional PHY? | Please describe mechanisms, such as CTS/RTS reservations, such as the ones used in 802.11g. | see CID12. | X | O |  | 2005-03-11 | 2005-03-11
1 |  | 12 | 1170 | Dabak, Anand | dabak@ti.com |  |  | Texas Instruments | 06 | 6.7.4.1 | 56 |  | TR | A new preamble is defined for the optional PHY. How do legacy (mandatory PHYs in the 868/915 MHz band) interoperate or coexist with the optional PHY? | Please describe mechanisms, such as CTS/RTS reservations, such as the ones used in 802.11g. | see CID12. | X | O |  | 2005-03-11 | 2005-03-11 |  |  |  |  | O
3 |  | 10 | 26 | Beecher, Phil | pbeecher@compxs.com |  |  | CompXs Ltd | 06 | 6.1.2.1 | 30 |  | T | Channel page / channel number selection is not atomic - resulting in possible invalid channel / page combinations. | set channel page causes default channel within page to be selected. | see CID10. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 269 | 269 | Bourgeois Brown, Monique | m.bourgeois@motorola.com |  |  | Motorola, Inc. | 06 | 6.1.2.1 | 28 | 48 | T | The text says the upper 5 MSBs are currently reserved. If they are reserved, they cannot be defined. Or does this mean that they were previously reserved in 802.15.4-2003 and are now being defined? | Clarify usage of 5 MSBs. | Add informative text: The 5 upper MSB's which were previously reserved in 802.15.4-2003 are now being defined. | X | O |  | 2005-03-11 | 2005-03-11
2 |  | 282 | 282 | Bray, Jennifer | Jennifer.Bray@csr.com |  |  | CSR | 06 | 6.2.1.1.3 | 32 | 43 | T | Looking at 6.2.1.2.2 it seems that any value of PD-DATA.confirm other than SUCCESS does not result in transmission of a PPDU. However 6.2.1.1.3 begins "The receipt of the PD-DATA.request primitive by the PHY entity will cause the transmission of the supplied PSDU." This opening sentence seems to imply that if the transmitter is not enabled the PPDU is buffered at the PHY layer and then transmitted when the transmitter is enabled. The clause then goes on to exhaustively describe return values of PD-DATA.confirm, but the actual behaviour of the transmitter (whether or not the PPDU is transmitted) is not described. If it is correct that the PPDU will not be transmitted if the transmitter is not enabled then the opening of this subclause needs clarification. | Change first paragraph to: The receipt of the PD-DATA.request primitive by the PHY entity when the transmitter is enabled will cause the transmission of the supplied PSDU. If the transmitter is enabled (TX_ON state), the PHY will first construct a PPDU, containing the supplied PSDU, and then transmit the PPDU. When the PHY entity has completed the transmission, it will issue the PD-DATA.confirm primitive with a status of SUCCESS. If the transmitter is not enabled the PHY entity will discard the PPDU. |  | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 284 | 284 | Bray, Jennifer | Jennifer.Bray@csr.com |  |  | CSR | 06 | Table 17 | 42 | 27 | T | SUCCESS has the value 0x07 Usually SUCCESS has the value zero. This enables shorter simpler code to test for SUCCESS. | Change the enumeration to make SUCCESS 0x00 (OK, I realise you're not likely to change enumerations at this stage in development, but at least try to think about it next time! ) |  | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 315 | 315 | Callaway, Ed | ed.callaway@motorola.com |  |  | Motorola | 06 | Table 20 | 45 | 20 | T | Something is wrong in the description of phyChannelsSupported. The description seems to describe an element of the array, and not the array itself. What happens if a device supports more than two PHY channels? Also, there is a typo (I think) at the end of the description: "channelk". | Add an introductory sentence: "The array is composed of one or more rows, each of which is a bit string with the following properties: The 5 most significant bits...". Also change the "Range" entry to be "A R x 32 bit array, where R ranges from 1 to 32." Finally, change "channelk" to "channel k" at the end. | Correct - text will be modified as per commenters suggested remedy. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 317 | 317 | Callaway, Ed | ed.callaway@motorola.com |  |  | Motorola | 06 | 6.7.2.2 | 52 | 39 | T | It seems like the MAC will need to round up in its calculations of message symbol times to account for the bit padding added at the PHY layer for transmitted PSSS symbols (which contain 5 or 15 bits each). I don't know that that is captured anywhere in clause 7. | Make a note in clause 7 somewhere (at least in 7.5.1, and maybe elsewhere) that symbol timing will have to be rounded up when PSSS is used. | This will be passed to the MAC team since the issue & remedy are in Clause 7. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 537 | 537 | Gifford, Ian | giffordi@ieee.org |  |  | Freescale | 06 | Table 31 | 57 |  | T | Is there another chip PN-sequence (different length, etc.) that meets all the requirements, but in using it increases the data rate from 100kps to 200kbps or more for the 868 - 868.6 band. | Look at other possible codes and lenghts to try to achieve this. |  | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 564 | 564 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.1.2 | 30 | 17 | T | There is no need to indicate how the new channel pages will be used. Whent the TG needs them, they can use them however they want. For now, devices don't need to worry about them. | Delete the sentence "New pages will also ... like Channel page 0." | Add normative text: Use of the currently reserved channel pages will be determined and defined by the task group as needed. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 565 | 565 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.1.2 | 30 | 22 | T | The paragraph indicates things that "will have to be added" and "will be modified" and "will be described". I trust that the TG has already done these things before it sent out the draft, so these should be replaced with past tense. | Change "will have to be added" to be "have been added", change "will be modified" to be "has been modified" and chnage "will be described" to be "is described" | Correct, text in 6.1.2 and 6.1.2.1 should be integrated and tenses will have been corrected. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 566 | 566 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.1.6 | 31 | 5 | T | "detected correctly" is not well defined. | I assume that what is meant here is "correctly received" as defined either in Clause 7 or, because this only involves the PHY, frames that pass FCS check. | Will change text from "detected correctly" to "correctly received". | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 570 | 570 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.2.1.3.1 | 34 | 10 | T | LQ and LQI are used interchangeably throughout the standard, yet they appear to mean slightly different things. This is confusing to the reader because, near as I can tell, they both mean the same thing. | Pick one, either LQ or LQI and change the draft so that only one is used. | Will search entire draft and correct so that all have LQI. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 572 | 572 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.2.2.6.1 | 38 | 20 | T | Table 12: This looks like a cut-n-paste error, most likely due to an using and old Elmer's glue stick (TM) that has had its cap left off. In any event, the descriptions are for things that were requested, not for things that are "to get" | Change "to get" to be "that was requested" in two places. Also, there seemes to be an extra carriage return in the description for PIBAttributeValue, so please remove it. Most importantly, buy a new glue stick to prevent further cut-n-paste errors. | Correct, "to get" will be changed to "that was requested" in both places. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 573 | 573 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.2.2.6.2 | 38 | 35 | T | The text reads wrong, it would be better to use the same text as in Table 7. | change "will be set to length zero." to be "will have zero length." | Correct, "will be set to length zero" will be changed to "will have zero length" in both places. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 574 | 574 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.2.3 | 42 | 10 | T | The hex notation should not have spaces around the "x". Other places in the draft use "0x0a", which I am pretty sure is the correct way. | Remove the spaces in this and all tables, e.g., change "0 x 00" to be "0x00". Table 20, for example, aslo has this problem. Also, in this table, the last row has column separators that are too thick. I can assist if you need help in fixing this one. | Correct, "0 x 00" will be changed to "0x00" in both tables 17 and 20. Column separators will also be fixed. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 575 | 575 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.5.2.2 | 46 | 1 | T | The last sentence is redundant as this requirement is more than adequately described in the first sentence of this paragraph. As we all know, redundancy is the root of all evil in standards (aside from the 75% requirement, of course). | Delete the sentence "Within each octet ... is processed second." | Correct, the sentence will be deleted. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 576 | 576 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.6.2.4.1 | 50 | 21 | T | Tc isn't defined. I am pretty sure it is the chip period, but that needs to be explicitly stated and that it is the inverse of the chip rate. | Add the definition to this subclause. | We will refer the commenter to page 47 line 32 for the definiton. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 577 | 577 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.7 | 51 | 38 | T | It seems both redundant and annoying to say "868/915 MHz band optional PSSS PHY" everywhere when you could just say 868/915 MHz PSS PHY. It is almost as if you are saying "868/915 MHz band we didn't want to put it in but here it is anyway PSSS PHY". Aren't all the PHYs optional, you just have to choose one to implement? I see from the PICs that operation in the 868/915 MHz band requires the older PHY, but the MAC has no support for different modulations schemes to be used among devices. How do devices determine which modulation scheme they can use with another device? Can a coordinator send beacons using an optional PHY? Can a PAN operate at all times using an optional PHY? Are all DEVs required | Even if they are optional, it isn't really necessary to say so in the name. However, the apparent inability of the MAC to handle multiple PHYs at the same time seems like a show stopper. | The use of the word optional with in the clauses 6.7 and 6.8 will be removed, however the headers will remain with opition in parentheses. Parentheses will also be added to Table 1 and Table C4. Will clean up text in Table C4. Will also add text after Clause 6.7 and 6.8 describing the mandatory BPSK modes and that each of these are optional and refer to Table C4 as well. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 578 | 578 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.7.2.3 | 53 | 4 | T | Fig. 23: The picture looks like it is proposing a matrix multiplication, i.e., a column vector multiplying a square matrix, which wouldn't work because the matrix sizes don't match up. | Re-do the figure to use separate boxes for each of the rows (with vertical elipses between them to show the variable size). I can sketch out a version that I think would be more clear. | Correct, will change figure per commenters suggestion. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 581 | 581 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.7.2.4 | 54 | 44 | T | The ASK section is pretty short, it isn't immediately clear how to map the modulation. I know how to map positive numbers into amplitude, but how do you map negative numbers into amplitude? Does this imply that this is an antipodal modulation? | Describe how to map P"(m) into amplitude levels. A sample calculation for a few symbols using the 5 code table would be really helpful. | An explanation and example will be added. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 582 | 582 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.7.2.4.2 | 55 | 1 | T | A roll off factor of 0.1 is extremely sharp and the performance of an implementation will depend greatly on the number of taps and the precision of the calculation. Is the implementer really just trying to shoot for the spectral mask or is it important that it is an RRC filter? | If the RRC characteristic is important, then the PHY needs to either specify the minimum number of taps and the minimum precision of the calculations or a TX signal quality measure (EVM is traditionally used for PSK and QAM modulations, a version of it might apply to ASK as well). If the RRC characteristic is not necessary, then the draft should make clear that RRC equation is simply a suggestion and not a requirement. | This has since been relaxed to 0.2 and the purpose of specifying a roll-off factor is to allow for an optimum reception in the presence of an AWGN channel. The combination of the roll off factor and EVM requirement effectively sets the minimum system performance. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 583 | 583 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.8 | 56 | 47 | T | The requirements for this subclause, not surprisingly, closely mirror those for the 2.4 GHz O-QPSK PHY. However, much of the text is a repeat of the prior text, and as such, is redundant (and therefore evil). While it is equally redundant (and therefore evil) for the commenter to repeat that redundant information leads to unsynchronized text and difficulties in maintenance, I would suggest that much of this text and all of the figures could be cross referenced instead of repeated. 802.11g took this approach with the 2.4 GHz OFDM PHY, most of the specification is simply a cross-reference to clause 17 (aka, 802.11a). | Replace as much of the text and figures with cross-references to the previous definition. Use 802.11g as an example of how to do this. I would be happy to offer more detailed suggestions if the group desires. |  | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 588 | 588 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.9.1 | 60 | 50 | T | The standard uses both packet and frame to refer to data. For example, in the Clause 5, there is a figure that has a title "Schematic view of the beacon frame", yet it has the PHY packet format shown as well. Is it the intent of the editor to use packet to refer to the PHY layer grouping of data (e.g., the PPDU or PHY Protocol Data Unit) and frame to refer to the MAC layer grouping of data? | I think the standard should use only one, either frame or packet. But if the two indicated different items, then figures like those in Clause 5 need to be changed to show that part of the picture is a frame and the other part is a packet. |  | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 589 | 589 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.9.2 | 61 | 2 | T | For the RX-to-TX turnaround time, the next frame (or packet) could e either an ACK or any other frame, depending on where in the protocol the device is operating. Is there any reason here to restrict this specification to be only for the transmission of an ACK? Furthermore, the PHY doesn't know that a packet is a beacon frame, command frame, data frame or ACK frame. It is just bits to the PHY. | Change "resulting acknowledgement." to be "next PHY packet." | Correct, will change "resulting acknowledgement" to "next PHY packet". | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 591 | 591 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.9.7 | 62 | 35 | T | Received power cannot be measured in decibels, it has to be decibels relative to a power level, e.g., dBm or dBW. In addition, the mapping doesn't indicate what the mapping is. For example, is a value of 0x01 mean that the power is equal to 10 dB above the reference sensitivity +/- 6 dB? Where is the step size of the ED mapping defined? It appears that 4 steps of 10 dB with +/-3 dB accuracy is as valid of an implementation as 4 15 dB steps with +/- 6 dB accuracy. However, the mapping to ED levels would be different, 0x04 would be 40 dB in one case and 60 dB in the other. | Specify the mapping from ED measured power to the 8 bit integer or provide a PHY PIB variable that defines the step size and possibly one that defines the value for 0x01 (as the reference for a dB measurement). |  | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 570 | 592 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.9.8 | 62 | 48 | T | The draft uses both LQ and LQI pretty much interchangeably. Is there supposed to be a difference between them? In this sentence, both LQI and LQ refer to the same thing. | Pick one or the other and stick with it. |  | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 705 | 705 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | E | E.3.1.8 | 247 | 21 | T | Equation 6 is for IEEE P802.15.3 at 22 Mb/s, not 11 Mb/s. In addition, the standards should probably be referred to as "IEEE Std 802.15.3-2003", etc. for each of the other ones. Alternatively, just "802.15.3" is also acceptable. | Change as indicated. | Will correct both. | X | O |  | 2005-03-11 | 2005-03-11
2 |  | 708 | 708 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | Table 20 | 45 |  | T | Some of the PIB values appear to be "read only": phyChannelsSupported, phyTransmitPower, phyCCAmode, phyPagesSupported. | Consider adding an "access" column to Table 20 (as is done in 802.15.3-2003) to indicate read-only where appropriate. Also add text to 6.2.2.9.3 to indicate that not all PIB attributes are settable (refer to 6.2.4.2 in 802.15.3-2003). | Add column and get MAC team inputs on correct access assignment for each PIB entry. | X | O |  | 2005-03-11 | 2005-03-11
1 |  | 721 | 721 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | 6.8.3.2 | 59 | 38 | T | Is is necessary (or desired) to specify the filter with "shall", or could we just recommend the filter with "may". If the 868 band widens in the future and the regulatory emission limits are relaxed, a different filter may be more desirable. Seems like the EVM spec (6.9.3) would govern any pulse shape distortion due to use of different filters. If the filter in eq. (9) is required (with "shall"), does it effectively reduce the amount of modulation distortion (EVM) permitted from other sources, such as phase noise, or does the EVM test measure error with respect to the composite pulse shape resluting from the half sine filter and the raised-cosine filter? | Consider replacing "shall" with "may". Add text clarifying the impact, if any, of this filtering on EVM testing. | For interoperability the specification of the pulse shaping filter, for instance to allow the opportunity for optimum reception in an AWGN channel, is deemed to be necessary by the committee. | X | O |  | 2005-03-11 | 2005-03-11
2 |  | 722 | 722 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | 6.8.3.4 | 60 | 9 | T | Given that the Eb/No and bit rate is similar to 2.4 GHz PHY, sensitivity should be roughly the same (-85 dBm). For low-complexity designs, noise figures of 15 dB appear to be common for both 900 MHz and 2.4 GHz, so why penalize 900 MHz band products by requiring noise figure to be 5 dB better? The fact that 15.4 is a low-complexity standard seems to be getting lost at times. Why prevent people from developing low-cost, low-complexity devices? The same comment goes for the PSSS sensitivity in 6.7.3.4. | Consider relaxing sensitivity to -85 dBm. | Agree, will change sensitivity to -85dBm. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 725 | 725 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | 6.8.3.2 | 59 | 47 | T | This section refers to the "highest average spectral power measured within +/- 1 MHz of the carrier freuqency fc." The other 915 MHz band masks use +/- 600 kHz. Perhaps the 1 MHz value was inadvertently copied form the 2.4 GHz PHY. | Consider replacing 1 MHz with 600 kHz. | Correct, will change text to +/- 600kHz. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 726 | 726 | Grohmann, Bernd | bernd.grohmann@danfoss.com |  |  | Danfoss A/S | 06 | 6.8.2.5 | 58 |  | T | Simulations presented in TG4b have shown that no version of COBI discussed meets the requirements of the PSD mask defined by ETSI for the COBI 868 MHz mode . This is also true for the COBI 868 MHz PHY mode in P802.15-REVb/D1. I feel IEEE802.15 should not release a PHY specification without having reviewed simulation results (full PHY PDU, with preamble, FD, and data, considering non-linearity and crystal drift - i.e. as agreed in TG4b in November 2004) demonstrating ETSI compliance. | Fix COBI specification to comply with ETSI PSD mask and present simulation results per agreement in TG4b about simulations (November 2004 meeting). | Roll-off factor was changed from 0.6 to 0.2. The PSD now meets the ETSI mask. See document 15-05-0061-06-004b for simulations results. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 726 | 727 | Grohmann, Bernd | bernd.grohmann@danfoss.com |  |  | Danfoss A/S | 06 | 6.8.2.5 | 58 |  | T | Pulse shaping for O-QPSK can be expected to visibly reduce RF performance. RF performance figures from simulations presented for COBI PHY modes did not take pulse shaping into consideration. | Present simulation results (entire PHY PDU, including preamble, FD, data) and review in TG4b. | see CID 726. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 728 | 728 | Grohmann, Bernd | bernd.grohmann@danfoss.com |  |  | Danfoss A/S | 06 | 6.8.2.4 | 58 |  | T | I/Q imbalances in the implementation can influence both the RF performance of the COBI PHY modes as well as effect compliance to FCC and especially ETSI PSD mask specifications. It is unclear what I/Q imbalance COBI tolerates and what resulting implementation complexity this causes. | Present simulation results (entire PHY PDU, including preamble, FD, data) that show that this does not impede cost and review in TG4b. | The committee states that the EVM specification covers the impact of transmit I/Q imbalance. The commentor accepts the comment. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 730 | 730 | Grohmann, Bernd | bernd.grohmann@danfoss.com |  |  | Danfoss A/S | 06 | 6.7 | 51 |  | T | Although from a technical and application perspective, the specified 206 kbit/s for PSSS 868 MHz are fully sufficient, marketing of solutions may be eased by having a single, universal bitrate of 250 kbit/s in the new PHY modes. | Review options and tradeoffs to operate PSSS at 868 MHz with 250 kbit/s in TG4b. | The opportunity was given to Dr. Wolf to present modifications to PSSS that will allow for a (more) integer based bit rate technique. In addition to this the preamble and SFD sequences were modified as well. Both proposed modifications were accepted by the commmittee. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 1 | 802 | Janbu, Øyvind | o.janbu@chipcon.com |  |  | Chipcon | 06 | 6.1.2.1 | 28 | 48 | T | The text in this section indicates that the 5 MSBs of the channel bitmap are used as an integer value to specify 32 pages. However, a separate PIB attribute used for the purpose of specifying the PHY channel page is also defined, as phyCurrentPage / phyPagesSupported in Table 20. The specification has a "double definition" of this. | Remove the text which states that the 5 MSB of the 32-bit channel bitmap is used to specify the page. | see CID1. | X | O |  | 2005-03-11 | 2005-03-11 |  |  |  |  | O
3 |  | 806 | 806 | Janbu, Øyvind | o.janbu@chipcon.com |  |  | Chipcon | 06 | Table 18 | 43 | 49 | T | The last row of Table 18 indicates that there exists an MPDU of length 8. However, the shortest MPDU length with exception of 5, is 9. There are no compliant MPDU lengths of 8. | Change the text in the table to state "9 to aMaxPHYPacketSize" | Correct, will change "8" to "9". | X | O |  | 2005-03-11 | 2005-03-11 |  |  |  |  | O
3 | Will attempt to correct using commenters remedy. | 807 | 807 | Janbu, Øyvind | o.janbu@chipcon.com |  |  | Chipcon | 06 | Figure 16 | 43 | 6 | T | Figure 16 states that the number of octets in the preamble shall be 4. This violates section 6.7.4.1 which states that the preamble is generated by repeating a 26-chip sequence 8 times. | Change Figure 16 or explicitely exclude PSSS from the requirement to have a 4 octet preamble. | The preamble time for the 868/915MHz O-QPSK and PSSS PHY's will be 320uS, resulting in different #'s of chips being transmitted for each PHY in each of the bands. This difference will be captured in a separate figure in Clause 6.3.1. | X | O |  | 2005-03-11 | 2005-03-11 |  |  |  |  | O
3 |  | 806 | 808 | Janbu, Øyvind | o.janbu@chipcon.com |  |  | Chipcon | 06 | 6.3.1.4 | 44 | 4 | T | The section states that "for all packet types of legnth 5 octets or greater than seven octets" ... However, the shortest MPDU length with exception of 5, is 9. There are no compliant MPDU lengths of 8. | Change the text to "for all packet types of length 5 octets or greater than eight octets" | see CID806. | X | O |  | 2005-03-11 | 2005-03-11 |  |  |  |  | O
3 | Once CID 10 is resolved then the text will be reviewed. | 10 | 809 | Janbu, Øyvind | o.janbu@chipcon.com |  |  | Chipcon | 06 | Table 20 | 45 |  | T | The phyChannelsSupported description states "The 5 most significant bits (MSBs) (b27,... ,b31) of phyChannelsSupported shall indicate the channel page supported," This text is not clear. Does this mean that the 5 MSBs are a copy of the phyCurrentPage? If so, why is the same information provided twice? Why not completely remove the page / page support from this attribute? | Remove the text about pages supported from the definition of phyChannelsSupported. |  | X | O |  | 2005-03-11 | 2005-03-11 |  |  |  |  | O
3 |  | 865 | 865 | Janbu, Øyvind | o.janbu@chipcon.com |  |  | Chipcon | 06 | Table 22 | 48 |  | T | To allow designs with external power amplifiers, outputting significantly more than the 0 dBm, it could make sense to only include a relative limit in Table 22. | Change table 22 so that in stead of having a relative limit of -20 dB and an absolute limit of -30 dBm, there is only a relative limit of -30 dB. Also change the text in 6.5.3.1 to only talk about relative limits (not absolute limits). | For interoperability and coexistence, the absolute limits need to remain. | X | O |  | 2005-03-11 | 2005-03-11 |  |  |  |  | O
3 |  | 963 | 870 | Kinney, Patrick | pat.kinney@ieee.org |  |  | Kinney Consulting LLC | 06 | Table 1 | 27 | 38-40 | T | There are too many options for modulations with similar data ratese.g. PSSS and COBI-16. The IEEE 802 rules state: one solution for one problem. | Remove COBI-16 from the 868-868.6 MHz band and remove PSSS from the 902-928 MHz band | see CID963. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 875 | 875 | Liang, Li | liang.li@helicomm.com |  |  | wxzj Inc | 06 |  | 40 | 7 | T | Not necessary BUSY_RX, BUSY_TX |  | The indication is useful to the MAC. Changing this could impact legacy devices. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 876 | 876 | Liang, Li | liang.li@helicomm.com |  |  | wxzj Inc | 06 |  | 52 | 8 | T | The BPSK block should be moved |  | Withdrawn by commentor. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 877 | 877 | Liang, Li | liang.li@helicomm.com |  |  | wxzj Inc | 06 |  | 57 | 43 | T | We recommend the use of new code sequences from WXZJ. |  | The symmetry characteristics lost in gaining the additional 0.5dB performance would not allow for the lowest cost/complexity architecture. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 10 | 886 | Naeve, Marco | marconaeve@eaton.com |  |  | Eaton Corporation | 06 | 6.1.2 | 28 | 23 | T | The descrition of the channel assignment mechnism is inconsistent. Clause 6.1.2 describes the channel assignment for page 0 only but for instance never mentions that there are channel pages. Sub-clause 6.1.2.1 explains upper 5MSB text but never mentions the lower 27 bits anywhere. | Modify entire subclause. Under 6.1.2 describe that there are 32 pages with 26 channels each. Delete the first 2 paragraphs of 6.2.1, don't need to explain why there are channel pages or that the 5 MSBs are used. 6.1.2.1 Describe the channel page assignment. (simmilar to the text currently under 6.2.1) add 6.1.2.2 Channel assignment for page 0 (copy text currently under 6.1.2) Add 6.1.2.3 and 6.1.2.4 explaining channel assignment of page 1 and 2 similar to text currently under 6.1.2. | see CID10. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 960 | 960 | Powell, Clinton | clinton.powell@freescale.com |  |  | Freescale | 06 | Table 31 | 57 |  | T | Is there another chip PN-sequence (different length, etc.) that meets all the requirements, but in using it increases the data rate from 100kps to 200kbps or more for the 868 - 868.6 band. | Look at other possible codes and lenghts to try to achieve this. | Withdrawn by commenter. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 960 | 1059 | Vaitonis, Robin | robin.vaitonis@freescale.com |  |  | Freescale Semiconductor | 06 | Table 31 | 57 |  | T | Is there another chip PN-sequence (different length, etc.) that meets all the requirements, but in using it increases the data rate from 100kps to 200kbps or more for the 868 - 868.6 band. | Look at other possible codes and lenghts to try to achieve this. | Withdrawn by commenter. | X | O |  | 2005-03-11 | 2005-03-11 |  |  |  |  | O
3 | It is not clear what the concern is. Will contact commenter for clarification. |  | 1062 | van Leeuwen, Hans | hvl@integration.com |  |  | Integration Associates | 06 | 00 | i | 1 | T | The amplitude between the preamble and payload is 6dB different . For low cost implementation this should be the same. (I only verified the PSSS proposal, but it holds for Cobi as well) | This is only true for PSSS. However the RMS value for preamble and payload are the same. This will be left as an implementation issue. |  | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 1174 | 1174 | Grohmann, Bernd | bernd.grohmann@danfoss.com |  |  | Danfoss A/S | 06 | 6.8 | 56 |  | T | Simulations shown for COBI PHY modes were based on earlier variants of the COBI PHY specification. Since then, significant changes have been made to the COBI PHY specifications including a replacement of the coding table used, chiprates, and the resulting PHY bitrate. Furthermore, the performance of the entire PHY PDU (i.e. including preamble, FD, data) has not been reviewed in TG4b for the COBI modes that are in the P802.15-REVb/D1 specification. | Provide simulations as agreed in TG4b (November 2004 meeting) and review in TG4b. | Will refer commenter to document 15-05-0061-06-004b for simulations results to see if this suffices. | X | O |  | 2005-03-11 | 2005-03-11
2 | Need to talk with original spec. authors to understand the motivation for setting the spec. this way. | 1179 | 1179 | Kinney, Patrick | pat.kinney@ieee.org |  |  | Kinney Consulting LLC | 06 | Table 22 | 48 | 9 | T | The absolute limit for emissions using the 2.4 GHz band is set to -30 dBm, which basically makes transmit powers of > 6 dBm non-compliant due to the inherent noise powers of the signal. This limit must be reduced to that limit adopted by the 868 to 928 MHz band.~change to: absolute limit -20 dBm |  |  | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 807 | 1182 | Liang, Li | liang.li@helicomm.com |  |  | wxzj Inc | 06 |  | 56 | 42 | T | As stated, SFD is composed of 8 bits, but it is not clear whether the 8 bits will be mapped to sequences (chips) first. In line 23 of this page, it is stated preamble and SFD should both be modulated by BPSK. In table 31, preamble is clearly defined as 8 sequences, each with 26 chips, but SFD is not defined. If the 8 bits are directly mapped to 8 chips, the length of SFD may be too short. If the 8 bits are mapped to of the 32-chip sequences as it is done in the data field, the bit number is not very suitable, because in 900MHz band each symbol represents 5 bits while in 868MHz band each symbol represents 15 bits. In both cases, 8 isn't their integer multiple. |  | see CID807. | X | O |  | 2005-03-11 | 2005-03-11
3 |  | 730 | 1191 | van Leeuwen, Hans | hvl@integration.com |  |  | Integration | 06 |  |  |  | T | 250kbps in 868MHz, 915MHz and 2400MHz would make the standard better. The adoptions for applications, Network and MAC over different bands is then gone and makes a market acceptance larger and dual (or triple) band receivers easier. |  | see CID730. | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 7 | Bain, Jay | jbain@hiwaay.net |  |  | Fearn Consulting | 06 | 6.1.2.1 | 28 | 44 | E | Would it be possible to make this sub-clause more formal. I actually like the read of it but not as a standard. There is another comment that is technical in nature that applies to the 6.1.2 structure and content. | I leave it to the technical editor to adjust the text as this is only of an editoral nature. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 23 | Beecher, Phil | pbeecher@compxs.com |  |  | CompXs Ltd | 06 | 6.1.2.1 | 28 | 4850 | E | The upper 5 MSBs, which are currently reserved, of 32 bit channel bitmap will be used as an integer value to specify 32 channel pages. | The upper 5 MSBs of 32 bit channel bitmap are used to specify 32 channel pages. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 24 | Beecher, Phil | pbeecher@compxs.com |  |  | CompXs Ltd | 06 | Table 17 | 42 | 36 | E | border style inconsistent within table |  |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 268 | Bourgeois Brown, Monique | m.bourgeois@motorola.com |  |  | Motorola, Inc. | 06 | 6.1.1 | 27 | 50 | E | Reference to 802.15.4 should be replaced by a reference to this standard. |  |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 270 | Bourgeois Brown, Monique | m.bourgeois@motorola.com |  |  | Motorola, Inc. | 06 | table 2 | 2930 |  | E | Replace all the reserved rows with one reserved row. Let channel page decimal= 3-31 and channel page binary = 0011-1111. |  |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 271 | Bourgeois Brown, Monique | m.bourgeois@motorola.com |  |  | Motorola, Inc. | 06 | 6.1.2.1 | 30 | 21 | E | Replace "2 new" with "two new". Same comment for line 23. |  |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 272 | Bourgeois Brown, Monique | m.bourgeois@motorola.com |  |  | Motorola, Inc. | 06 | table 19 | 44 |  | E | aTurnaroundTime should be in italics. |  |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 283 | Bray, Jennifer | Jennifer.Bray@csr.com |  |  | CSR | 06 | Table 10 |  |  | E | The Energy level parameter will not be the ED level for the current channel if the status is anything other than SUCCESS. Should there be a default value? | Change Description for Energy level to If status is set to SUCCESS this is the ED level for the current channel, otherwise this parameter is zero. OR If status is set to SUCCESS this is the ED level for the current channel, otherwise the value of this parameter is not meaningful. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 308 | Callaway, Ed | ed.callaway@motorola.com |  |  | Motorola | 06 | Table 2 | 29 | 19 | E | All the "reserved" entries are unnecessary. | Just write, "pages 3-31 reserved". |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 309 | Callaway, Ed | ed.callaway@motorola.com |  |  | Motorola | 06 | 6.1.2 | 30 | 13 | E | The example uses a reserved channel page. All reserved channel pages, like other reserved fields and values, should be set to zero. | Use channel page 0, channel 2 as an example (for example). |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 310 | Callaway, Ed | ed.callaway@motorola.com |  |  | Motorola | 06 | 6.1.2 | 30 | 17 | E | The second sentence ("New pages will also have ...") is irrelevant in this standard, since the mapping is not specified. | Delete sentence. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 311 | Callaway, Ed | ed.callaway@motorola.com |  |  | Motorola | 06 | 6.1.2 | 30 | 21 | E | Paragraph uses the future tense. | "To support the use of the channel page and channel numbering scheme 2 new PHY PIB attributes, phyPagesSupported and phyCurrentPage, are used in Table 20 (PHY PIB attributes). See 6.4.2." |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 312 | Callaway, Ed | ed.callaway@motorola.com |  |  | Motorola | 06 | 6.1.6 | 30 | 48 | E | "...regarding receiver sensitivity" is superfluous. | Delete the phrase. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 313 | Callaway, Ed | ed.callaway@motorola.com |  |  | Motorola | 06 | 6.2.1 | 31 | 47 | E | Text is plural, but there is only one entry in Table 4. | "Table 4 lists the sole primitive supported by the PD-SAP. This primitive is discussed in the subclauses referenced in the table." |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 314 | Callaway, Ed | ed.callaway@motorola.com |  |  | Motorola | 06 | Table 18 | 43 | 47 | E | Unless I am miscounting, frame length values 6-8 should be reserved, and frame length value 9 to aMaxPHYPacketSize should be used for MPDUs. See 5.4.3 and Figures 10-13. | Change Reserved frame length values to "6-8", and MPDU values to "9 to aMaxPHYPacketSize". |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 316 | Callaway, Ed | ed.callaway@motorola.com |  |  | Motorola | 06 | Table 17 | 42 | 7 | E | vertical line missing between Value and Description. | Add vertical line. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 318 | Callaway, Ed | ed.callaway@motorola.com |  |  | Motorola | 06 | 6.7.2.3 | 54 | 32 | E | "symmetric to zero" is an ambiguous phrase, also used in line 38. | Is "symbol symmetric about zero with respect to the current PSSS symbol" what was intended? I really don't know. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 319 | Callaway, Ed | ed.callaway@motorola.com |  |  | Motorola | 06 | 6.7.4.1 | 56 | 30 | E | The left-most chip number is "1". (Its *value* is "0".) | Change to read, "The left-most chip number "1" in the diagram, with a value of "0", is transmitted first." |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 320 | Callaway, Ed | ed.callaway@motorola.com |  |  | Motorola | 06 | 6.9.3 | 61 | 39 | E | 15.4-2003 reference. | "The EVM shall be defined as...." |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 321 | Callaway, Ed | ed.callaway@motorola.com |  |  | Motorola | 06 | 6.9.3.1 | 62 | 3 | E | 15.4 reference. | "A transmitter shall have..." |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 322 | Callaway, Ed | ed.callaway@motorola.com |  |  | Motorola | 06 | 6.9.5 | 62 | 14 | E | 15.4 reference. | "A transmitter shall be...." |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 323 | Callaway, Ed | ed.callaway@motorola.com |  |  | Motorola | 06 | 6.9.6 | 62 | 22 | E | 15.4 reference. | "A receiver shall have...." |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 349 | Callaway, Ed | ed.callaway@motorola.com |  |  | Motorola | 07 | Table 71 | 160 | 31 | E | "Ghz" and "Mhz". Also, are the range values still appropriate for the new PHYs? | Change to "GHz" and "MHz". |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 376 | Callaway, Ed | ed.callaway@motorola.com |  |  | Motorola | E |  | 241 | 1 | E | Entire Annex needs to be updated to 15.4b. | Make updates. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 377 | Callaway, Ed | ed.callaway@motorola.com |  |  | Motorola | F |  | 253 | 1 | E | Entire Annex needs to be updated to 15.4b. | Make updates. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 526 | Gifford, Ian | giffordi@ieee.org |  |  | Freescale | 06 | 6.1.1 | 27 | 53 | E | The term "Europe" is orphaned and should be moved to the next page. | I suggest moving "Europe" to page 28 with the associated and dashed text. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 527 | Gifford, Ian | giffordi@ieee.org |  |  | Freescale | 06 | 6.1.1 | 28 | 16 | E | Small nit; the US Code of Federal Regulations citation "FCC CFR47, Section 15.247" is non standard. | I suggest "FCC 47 CFR, Section 15.247". |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 561 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6 | 27 | 3 | E | The 2005 style guide indicates that there is not supposed to be any text between a Clause heading and first subclause, i.e., "6. PHY specification" should be followed directly by "6.1 General requirements and definitions" with no intervening text. The relevant quote from the IEEE 2005 Style Guide, page 16, is "Hanging paragraphs (i.e., paragraphs following a main clause head or subhead) should not be used since reference to the text would be ambiguous. It may be necessary to include a subhead with the title "General" to avoid instances of hanging paragraphs, as shown in Figure 2." (I know, we didn't do this right all the time in 802.15.3 either). | Move the text from 6 to 6.1 or create a new 6.1 (numbering the rest appropriately) that is "6.1 General" |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 562 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6 | 27 | 6 | E | LQI and ED need to be spelled out as this is the first reference to them in the text. | Change as indicated. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 563 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.1.2 | 29 | 19 | E | Table 2: 3 issues: 1) The format of the table, specifically the line widths, doesn't match other tables in the draft. 2) The continuation of the table on the second page requires a " (continued)" in the second title. 3) There is no need to list 29 rows with "reserved" when it can be done in 1 row. | 1) Change the table format to match other tables in the draft. 2) Add the variable to add "continued" to the table title (I show you how to do it). 3) Change the row with Channel page 3 to be: ¦ 3-31 ¦ 00011-11111 ¦ reserved ¦ reserved ¦ and delete the rest of the rows. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 567 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.2.1.1.1 | 32 | 26 | E | Table 5: "Unsigned Integer" should be "Unsigned integer" | Change capitalization as indicated. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 568 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.2.1.1 | 32 | 1 | E | This is a general comment for all SAP primitives. A .request and a .response need "Effect of receipt but not "When generated". Likewise, a .confirm and a .indication require only "When Generated" and not "Effect of receipt". The reason is that the SAP, the PD-SAP in this case, is only supposed to place requirments on the layer below it, the PHY in this case. This can be seen by the content free text that accompanies 6.2.1.1.2. This allows the removal of all of the 5 deep subclause numbering for the SAP primitves. Just have 6.2.1.1 with the introductory text, the text from 6.2.1.1.1 and the text in 6.1.1.1.3, and no fifth layer subclauses. Using "Semantics of the service primitve", "When generated" and "Effect of receipt" also creates many subclauses that have exactly the same title, which makes it impossible to differentiate them by the text alone. | Change as indicated here and for all SAP primitives. It will make the draft shorter and easier to read. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 571 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.2.2.4.1 | 36 | 52 | E | The ED measurement should be cross-referenced to where it is defined. | Add "as defined in 6.x.x.x" to the description. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 579 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.7.2.3 | 53 | 15 | E | The font for the figure captions in this subclause are all wrong, e.g., Figs. 23, 24, etc. Please reapply the style for a Figure title. Likewise, the font | Change as indicated, ask if you need help, it is should be quick to fix. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 580 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.7.2.3 | 53 | 23 | E | Table 27 et al.: The font in this table doesn't match the fonts for other tables in the draft. The numbers in the column would look better if they were centered instead of right justified. Also, the fonts for the table captions appear to be wrong for all of the tables in this subclause. | Change as indicated, ask if you need help, it is should be quick to fix. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 584 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.8.2.4 | 58 | 31 | E | Comma missing, change "and 915 MHz bands respectively" to be "and 915 MHz bands, respectively" | Change as indicated. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 585 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.8.3.2 | 59 | 47 | E | The subscript isn't subscripted for fc. | Make the "c" a subscript to match the Table |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 586 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.9.1 | 60 | 47 | E | The font for "aTurnaroundTime (see" is too small | Fix the font size for the text. This is also broken in 6.9.2, likely due to that old glue stick again. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 587 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.7.2.1 | 52 | 26 | E | The text uses "start of frame delimiter" insead of its acronym, SFD, which is more descriptive. | Change to SFD. Also 6.7.4, p. 56, line 25 |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 590 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | 06 | 6.9.6 | 62 | 21 | E | It is not necessary to specify "in decibels relative to 1 mW" as this is indicated by the units of "dBm" used later in the paragraph. | Delete ", in decibels relative to 1 mW," |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 704 | Gilb, James | gilb@ieee.org |  |  | Appairent Technologies | E | E.3.1.1 | 244 | 51 | E | The font and size for the third level headings are wrong. | Re-apply the correct formatting and remove overrides. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 707 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | Table 20 | 45 |  | E | Review the use of "shall" in the description column for phyChannelsSupported and phyTransmitPower. | Consider removing "shall" from these descriptions. For example, in the phyTransmitPower description, use " ... The lowest value of phyTransmitPower is interpreted as less than or equal to -32 dBm." |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 712 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | 6.7.2 | 51 | 53 | E | Replace (31+1)-chip with 32-chip to be consistent with the previous line. | See comment. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 713 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | 6.7.2.3 | 54 | 1220 | E | Consider the following re-wording of lines 12-20: | "The vector of bits comprising the data symbol is multiplied with the PSSS code table. That is, bit b0 of the data symbol is multiplied with sequence number "0", bit b1 is multiplied with sequence number "1", etc. Prior to multiplication, the data bits are converted to bipolar levels: data bit "1" becomes +1 and data bit "0" becomes -1. The result of multiplication is a modulated code table, which is similar to Table 27 or 28, but with each row either inverted or not according to the data bits. Subsequently, all rows of the modulated code table are linearly summed to create a multi-level 32-chip sequence. For example, chip 0 of the multi-level sequence is produced by linearly summing chip 0 from each of the modulated sequences." |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 714 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | 6.7.2.3 | 54 | 2141 | E | Consider the following re-wording of lines 21-41. | "Next, a precoding operation is applied to the multi-level 32-chip sequence. The precoding is independent from one symbol to the next, and is performed in two steps. In the first step a constant value is added to each of the 32 chips. The constant is selected such that the minimum and maximum values of the resulting seqeunce are symmetric about zero. Representing the orignal multi-level 32-chip symbol sequence by p(m), then the modified sequence p'(m) after step one of precoding is p'(m) = p(m) + [ Max{p(m)} + Min{p(m)} ]/2 In the second step, a scaling constant is multiplied by each chip in p'(m). The scaling constant is selected such that the resulting sequence has a maximum amplitude of 1. Letting p"(m) be the output of the second precoding step, then p"(m) = p'(m)/[ Max{p'(m)} ] The precoded sequence of 32 multi-level chips is modulated onto the carrier as described in 6.7.2.4." |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 717 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | 6.7.4 | 56 | 20 | E | First sentence of 6.7.4 refers to "the first data octet of the PDU", which is somewhat ambiguous. | Consider saying, "The SHR uses different coding than the PHR and PSDU. The SHR chips shall be transmitted with BPSK modulation using the same chip rates (6.7.2.4) and pulse shaping (6.7.2.4.1) that are used for the PHR and PSDU. However, the symbol-to-chip mapping for the sychronization header is different, as described below." |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 718 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | 6.7.2.4.1 | 54 | 49 | E | Add "root-raised-cosine", just as a familiar term that people know. | "The root-raised-cosine pulse shape used to represent each baseband chip is described by Equation (7):" |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 719 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | 6.8.2.1 | 57 | 10 | E | "Figure 21" should be changed to "Figure 24". | See comment. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 720 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | 6.8.2.3 | 57 | 40 | E | The sentence on line 40 refers to "Table 31", but it should refer to "Table 32". | See comment. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 723 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | 6.1.2 | 28 | 2537 | E | Subclauses 6.1.2 and 6.1.2.1 could be combined into a single subclause. It might read better and proivde more flexibility going forward if the channel number equations (lines 29-33) were defined explicitly for each channel page. As written, the definition of channel numbers k=0-26 appears global, independent of channel page. | Replace the "channel number description" column in Table 2 with a "channel frequency equation". For example: channel page 0 k=0: Fc = ... k=1-10: Fc = ... k=11-26: Fc = ... channel page 1 k=0: Fc = ... k=1-10: Fc = ... k=11-26: Reserved channel page 2 k=0: Fc = ... k=1-10: Fc = ... k=11-26: Reserved channel pages 3-31 Reserved Then remove equations from 6.1.2 and combine remaining text from 6.1.2 and 6.1.2.1 into a single subclause. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 724 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | 6.3 | 42 | 5151 | E | Spell out "synchronization header" and "PHY Header" on first use here on lines 51 and 52. | " - A synchronization header (SHR), which allows ..." " - A PHY header (PHR), which contains ..." |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 729 | Grohmann, Bernd | bernd.grohmann@danfoss.com |  |  | Danfoss A/S | 06 |  |  |  | E | Description of transmitter of PSSS should be extended to ease understanding. Earlier presentations on PSSS contained additional descriptions that should be provided to readers of the standard. | Add text, possible as non-normative annex. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 732 | Herold, Barry | epag03@email.mot.com |  |  | Motorola | 06 | 6.2.2.7.3 | 39 | 39 | E | return status not specified. | change PHY is in. to Phy is in, the PHY will issue the PLME-SET-TRX-STATE.confirm primative with a status SUCCESS. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 733 | Herold, Barry | epag03@email.mot.com |  |  | Motorola | 06 | 6.2.2.4.3 | 37 | 10 | E | What value of EnergyLevel is returned if the PLME-ED.request is not successful |  |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 783 | Heubaum, Karl | Karl.Heubaum@freescale.com |  |  | Freescale Semiconductor | 06 | 6.1.2.1 | 30 | 21 | E | The word "2" should be spelled out as "two" in "...channel numbering scheme 2 new PHY PIB...". | Reword the sentence to read, "...channel numbering scheme two new PHY PIB...". |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 784 | Heubaum, Karl | Karl.Heubaum@freescale.com |  |  | Freescale Semiconductor | 06 | 6.1.2.1 | 30 | 23 | E | The word "2" should be spelled out as "two" in "The description of the 2 new PHY PIB...". | Reword the sentence to read, "The description of the two new PHY PIB...". |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 803 | Janbu, Øyvind | o.janbu@chipcon.com |  |  | Chipcon | 06 | 6.1.2.1 | 30 | 15 | E | There is a mismatch bewteen the text "the bitmap for Channel 3 of Channel page 3 would be:" and the following line: "0 0 0 1 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 0 0" because this indicates channel 4 of channel page 3, not channel 3 of channel page 3 | Change the text so that it is correct. |  | X | O |  | 2005-03-11 | 2005-03-11 |  |  |  |  | O
|  |  | 804 | Janbu, Øyvind | o.janbu@chipcon.com |  |  | Chipcon | 06 | 6.1.2.1 | 30 | 21 | E | The text says that "To support the use of the channel page and channel numbering scheme 2 new PHY PIB attributes, phyPagesSupported and phyCurrentPage, will have to be added to Table 20 (PHY PIB attributes)." But the attributes are already added, so the text becomes unclear. And what does "2 new PHY PIB attributes" mean? New compared to what? | Change the text to "To support the use of the channel page and channel numbering scheme 2 PHY PIB attributes, phyPagesSupported and phyCurrentPage, are defined in Table 20 (PHY PIB attributes)." |  | X | O |  | 2005-03-11 | 2005-03-11 |  |  |  |  | O
P3 |  | 709 | 805 | Janbu, Øyvind | o.janbu@chipcon.com |  |  | Chipcon | 06 | 6.3.1.1 | 56 | 29 | E | There is a conflict between section 6.7.4.1 "Preamble for optional PSSS PHY" which states that the "preamble is generated by repeating a 26ø-chip sequence 8 times" and section 6.3.1.1 which states that "The preamble field shall be composed of 32 binary zeros" | Include an exception in section 6.3.1.1 which allows 6.7.4.1 to redefine the preamble for the optional PSSS PHY. |  | X | O |  | 2005-03-11 | 2005-03-11 |  |  |  |  | O
|  |  | 810 | Janbu, Øyvind | o.janbu@chipcon.com |  |  | Chipcon | 06 | 6.7.4 | 56 | 25 | E | The reference to "Figure 16" is wrong, should be Table 31. There are also other errors in the references, e.g. the reference to "Table 18" in secion 6.7.4.2 should have been Figure 17. | Verify and correct the references in section 6.7. |  | X | O |  | 2005-03-11 | 2005-03-11 |  |  |  |  | O
|  |  | 811 | Janbu, Øyvind | o.janbu@chipcon.com |  |  | Chipcon | 06 | Table 31 | 56 |  | E | The chips are numbered 1 through 26. However, the text refers to "The left-most chip number "0" in the diagram". | Change the chip numbering in Table 31 to 0 through 25 in stead of 1 through 26. |  | X | O |  | 2005-03-11 | 2005-03-11 |  |  |  |  | O
|  |  | 812 | Janbu, Øyvind | o.janbu@chipcon.com |  |  | Chipcon | 06 | 6.9.2 | 61 | 3 | E | The reference to section "7.5.6.4.2" is not a hyperlink. In addition, the referred section only describes acknowledgement timing, not timing in general as the text in section 6.9.2 indicates. | Make the reference a hyperlink. Possibly change the reference to section 7, which includes all text on transmission start times, and not only the acknowledgement timing in section 7.5.6.4.2? |  | X | O |  | 2005-03-11 | 2005-03-11 |  |  |  |  | O
|  |  | 871 | Lee, Simon | s-lee12@ti.com |  |  | Texas Instruments | 06 | 6.7.4.1 | 56 |  | E | A new preamble is defined for the optional PHY. How do legacy (mandatory PHYs in the 868/915 MHz band) interoperate or coexist with the optional PHY? | Please describe mechanisms, such as CTS/RTS reservations, such as the ones used in 802.11g. |  | X | O |  | 2005-03-11 | 2005-03-11 |  |  |  |  | O
|  |  | 879 | Liang, Li | liang.li@helicomm.com |  |  | wxzj Inc | F |  | 263 | 4 | E | Add "to" or "-" (eq, 868-868.6 MHz, etc.) |  |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 887 | Naeve, Marco | marconaeve@eaton.com |  |  | Eaton Corporation | 06 | 6.1.2.1 | 29 | 15 | E | What about channels 11 to 26 og page 1 and 2? | Add text to show that channels 11 - 26 of pages 1 and 2 are reserved. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 888 | Naeve, Marco | marconaeve@eaton.com |  |  | Eaton Corporation | 06 | 6.1.2.1 | 30 | 21 | E | This paragraph reads like instructions for the technical editor but not like something that should be part of the standard. | Remove last paragraph of 6.1.2.1 (line 21 to 24 on page 30). |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 889 | Naeve, Marco | marconaeve@eaton.com |  |  | Eaton Corporation | 06 | 6.4.2 | 45 | 42 | E | Description for the phyPagesSupported PIB attribute does not describe very well how this is supposed to be used. The type says bitmap but how large is the bitmap? (0 to 31, one for each bitmap?) Or is it supposed to be an array of 5 bit values (similar to phyChannelsSupported?) | Make description of phyPagesSupported similar to the one for phyChannelsSupported. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 890 | Naeve, Marco | marconaeve@eaton.com |  |  | Eaton Corporation | 06 | 6.9 | 60 | 43 | E | Clause 6.9 applies to the 2.4GHz PHY and the sub-GHz PHYs. Now there are more than one. | Change sentence from "...and the 868/915 MHz PHY." to "...and the 868/915 MHz PHYs." |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 891 | Naeve, Marco | marconaeve@eaton.com |  |  | Eaton Corporation | 06 | 6.9.3 | 61 | 39 | E | Says the EVM for IEEE Std 802.15.4-2003 is defined as. This document is 802.15.4-REVb/D1 | Updated text. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 934 | Naeve, Marco | marconaeve@eaton.com |  |  | Eaton Corporation | 06 | 6.7.1 | 51 | 44 | E | Correct spelling for this standrd is kb/s and not kbit/s. | Chasnge throughout the new subclause in clause 6. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 935 | Naeve, Marco | marconaeve@eaton.com |  |  | Eaton Corporation | 06 | 6.7.2.1 | 52 | 18 | E | For consitency update the figure to more closely resemble figure 18 | Update as suggested. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 936 | Naeve, Marco | marconaeve@eaton.com |  |  | Eaton Corporation | 06 | 6.7.2.3 | 53 | 15 | E | Figure 23 is unclear. | Either improve or remove figure. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 937 | Naeve, Marco | marconaeve@eaton.com |  |  | Eaton Corporation | 06 | 6.7.2.3 | 53 | 23 | E | For consitency throgh the standard change appearence of the table to better match the rest of the document (see table 21 for instance) | Change formating to tables 27 and 28. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 938 | Naeve, Marco | marconaeve@eaton.com |  |  | Eaton Corporation | 06 | 6.7 | 51 | 37 | E | (JAG) Change title to "Optional 868/915 MHz band PSSS PHY specifications" |  |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 939 | Naeve, Marco | marconaeve@eaton.com |  |  | Eaton Corporation | 06 | 6.8 | 56 | 45 | E | (JAG) Change title to "Optional 868/915 MHz band O-QPSK PHY specifications" |  |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 964 | Richard Roberts | rrober14@harris.com |  |  | Harris Corporation | 06 | 6.1.2.1 | 28 | 49 | E | Need to add the word "as" in the sentence. | The lower 27 bits of the channel bit map will be used as a bit mask ... |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 967 | Shimada, Shusaku | shusaku@ieee.org |  |  | Yokogawa Co. | F | 4 | 264 | 25 | E | "F.4 Known Japanese rules" and "The Japanese regulatory situation has proven difficult to understand ..." imply that there may be unknown rules other than ARIB T-66. But nothing other than that there. | "F.4 Applicable Japanese rules." could be better. And " Past Japanese regulatory situation might have been difficult to ..." would be even informative regarding the language barrier. Anyway 2.4GHz band PHY/MAC of 802.15.4 conforms Arib T-66 standard and Japanese regulatory rules, I believe. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 1063 | van Leeuwen, Hans | hvl@integration.com |  |  | Integration Associates | 06 | 00 | i | 1 | E | A detailed description or implementation example of the proposed PHY transmitter needs to be added as an informative Annex in order to make sure that initial implementations of the standard are t12:06 AM 3/10/2005he same. An actual FPGA implementation (non optimal and at baseband) would be helpful to get the standard accepted as well. |  |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 1071 | Virk, Bhupender | bvirk@ieee.org |  |  | CompXs Inc. | 06 | 6.1.2.1 | 28 | 4850 | E | The upper 5 MSBs, which are currently reserved, of 32 bit channel bitmap will be used as an integer value to specify 32 channel pages. | he upper 5 MSBs of 32 bit channel bitmap are used to specify 32 channel pages. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 1072 | Virk, Bhupender | bvirk@ieee.org |  |  | CompXs Inc. | 06 | Table 17 | 42 | 36 | E | border style inconsistent within table |  |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 1173 | Gorday, Paul | paul.gorday@motorola.com |  |  | Motorola | 06 | Table 1 | 27 |  | E | There seems to be enough support in literature to classify PSSS as OCDM (orthogonal code division multiplexing). | Consider using the more generic term, OCDM, instead of PSSS. An alternative would be to add a sentence or two, either in definitions, acronyms, or to 6.7.2, mentioning that OCDM is another name for PSSS. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 1180 | Lee, Kyung-Kuk | kyunglee@orthotron.com |  |  | Orthotron Co., Ltd. | 06 | 6.8.2.1 | 57 | 10 | E | wrong explanation of subclause. | The functional block diagram in Figure 24 is provided as a reference for specifying the 868/915 MHz band PHY modulation and spreading functions. The number in each block refers to the subclause that describes that function. The number in each block function. |  | X | O |  | 2005-03-11 | 2005-03-11
|  |  | 1187 | Roberts, Richard | rrober14@harris.com |  |  | Harris Corporation | 06 |  | 27 | 3 | E | Comment: Line 3 indicates that there are 4 PHY options for 15.4 and these are listed in Table 1. But upon looking at table 1 we see another use of the work "optional" in regards to 868/915 MHz. Thus, in effect we have said that there are 4 PHY options of which two are optional ... this is probably not what we intended. | Reword line 3 to say something like the following: This clause specifies the physical layer for IEEE802.15.4. |  | X | O |  | 2005-03-11 | 2005-03-11