## IEEEcover
2005-05-01 |  | IEEE P802.15-05/0263-00
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | LB29 Drafting status
Date Submitted | [May 13, 2005]
Source | [James P. K. Gilb] | Voice: [(858)-485-6401]
| [Appairent Technologies] | Fax: [(858)-485-6406]
| [16990 Via Tazon, #125] | E-mail: [last name at ieee dot org]
[San Diego, CA 92127]
Re: | []
Abstract | [This spreadsheet tracks the comment drafting status for both the assignments of issues to people as well as tracking when the resolutions are applied to the draft.]
Purpose | [To track the status of comments and the application of the resolutions to the draft.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after furt
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Commentswritten
|  | % done | 56.48%
|  | % assigned | 1.153%
|  | Left to go | 151
|  | Total finished | 196
|  | Left to claim | 4 | Enter 'done' when comment applied
CID | Status | Heberling | ADH comments | Gilb | JPKG comments | Hall | JH comments | Odman | KO comments | Tally | Claimed
1 | Done |  |  | Done | No change required, see CID 295 |  |  |  |  | 1 | 0 | 0
2 | Gilb |  |  | Gilb | Fix association figure |  |  |  |  | 0 | 0
3 | Gilb |  |  | Gilb | CID 3, 8, 159, 328: Re-write CSMA access |  |  |  |  | 0 | 0
4 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
5 | Gilb |  |  | Gilb | CID 5, 7, 164, 340, Text in database |  |  |  |  | 0 | 0
6 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
7 | Gilb |  |  | Gilb | CID 5, 7, 164, 340, Text in database |  |  |  |  | 0 | 0
8 | Gilb |  |  | Gilb | CID 3, 8, 159: Re-write CSMA access |  |  |  |  | 0 | 0
9 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
10 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
11 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
12 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
13 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
14 | Gilb |  |  | Gilb | Instructions in database |  |  |  |  | 0 | 0
15 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
16 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
17 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
18 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
19 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
20 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
21 | Gilb |  |  | Gilb | Explain why the field can be zero length |  |  |  |  | 0 | 0
22 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
23 |  |  |  |  | MLME description of changes and new figure |  |  |  |  | 0 | 1
24 | Gilb |  |  | Gilb | Revert to old priority model |  |  |  |  | 0 | 0
25 | Done |  |  | Done | Ran spell checker |  |  |  |  | 1 | 0
26 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
27 | Done |  |  | Done | No change required, see CID 295 |  |  |  |  | 1 | 0
28 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
29 | Gilb |  |  | Gilb | New MLME model figure |  |  |  |  | 0 | 0
30 | Gilb |  |  | Gilb | Need to write up the compatibility issues. |  |  |  |  | 0 | 0
31 | Done |  |  | Done | No change required, editorial |  |  |  |  | 1 | 0
32 | Gilb |  |  | Gilb | Check fonts on title page to see if they match |  |  |  |  | 0 | 0
33 | Done |  |  | Done | Correct in the framemaker copy, probably font foo when it was translated |  |  |  |  | 1 | 0
34 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
35 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
36 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
37 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
38 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
39 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
40 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
41 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
42 | Gilb |  |  | Gilb | Check with project editor |  |  |  |  | 0 | 0
43 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
44 | Done |  |  | Done | Paragraph removed, editorial |  |  |  |  | 1 | 0
45 | Done |  |  | Done | Paragraph removed, editorial |  |  |  |  | 1 | 0
46 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
47 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
48 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
49 | Gilb |  |  | Gilb | Check quote usage with project editor |  |  |  |  | 0 | 0
50 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
51 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
52 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
53 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
54 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
55 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
56 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
57 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
58 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
59 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
60 | Gilb |  |  | Gilb | Check with project editor |  |  |  |  | 0 | 0
61 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
62 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
63 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
64 | Done |  |  | Done | No change required, see CID 295 |  |  |  |  | 1 | 0
65 | Done |  |  | Done | No change required, see CID 294 |  |  |  |  | 1 | 0
66 | Gilb |  |  | Gilb | Add text to clause 6.3 |  |  |  |  | 0 | 0
67 | Done |  |  | Done | Change MSDU number in example |  |  |  |  | 1 | 0
68 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
69 | Odman | [6 empty] | Odman | Implied ACK text | 0 | 0
70 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
71 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
72 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
73 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
74 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
75 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
76 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
77 | Heberling | Heberling | Add MLME confirms | [6 empty] | 0 | 0
78 | Done |  |  | Done | Name changed |  |  |  |  | 1 | 0
79 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
80 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
81 | [8 empty] | Open issue | 0 | 1
82 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
83 | Done |  |  | Done | Name changed |  |  |  |  | 1 | 0
84 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
85 | Odman | [6 empty] | Odman | Implied ACK text | 0 | 0
86 | Done |  |  | Done | Withdrawn |  |  |  |  | 1 | 0
87 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
88 | Done |  |  | Done | No change required |  |  |  |  | 1 | 0
89 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
90 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
91 | Done |  |  | Done | Withdrawn |  |  |  |  | 1 | 0
92 | Gilb |  |  | Gilb | Text in database, see CID 210 |  |  |  |  | 0 | 0
93 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
94 | Gilb |  |  | Gilb | Figure out what needs to be moved from clause 6 to 8 |  |  |  |  | 0 | 0
95 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
96 | Gilb |  |  | Gilb | Text in database, see CID 210 |  |  |  |  | 0 | 0
97 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
98 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
99 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
100 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
101 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
102 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
103 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
104 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
105 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
106 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
107 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
108 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
109 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
110 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
111 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
112 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
113 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
114 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
115 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
116 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
117 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
118 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
119 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
120 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
121 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
122 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
123 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
124 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
125 | Done |  |  | Done | No change required, see CID 295 |  |  |  |  | 1 | 0
126 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
127 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
128 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
129 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
130 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
131 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
132 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
133 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
134 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
135 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
136 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
137 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
138 | Gilb |  |  | Gilb | Fix Fig 147b |  |  |  |  | 0 | 0
139 | Gilb |  |  | Gilb | Fix Fig 147b |  |  |  |  | 0 | 0
140 | Gilb |  |  | Gilb | Fix Fig 147c |  |  |  |  | 0 | 0
141 | Gilb |  |  | Gilb | Fix Fig. 141 |  |  |  |  | 0 | 0
142 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
143 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
144 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
145 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
146 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
147 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
148 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
149 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
150 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
151 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
152 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
153 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
154 | Gilb |  |  | Gilb | New MLME model figure |  |  |  |  | 0 | 0
155 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
156 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
157 | Done |  |  | Done | Changes made with CID 261 and 210 |  |  |  |  | 1 | 0
158 | Gilb |  |  | Gilb | Fix association figure |  |  |  |  | 0 | 0
159 | Gilb |  |  | Gilb | CID 3, 8, 159: Re-write CSMA access |  |  |  |  | 0 | 0
160 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
161 | Odman | [6 empty] | Odman | Implied ACK text | 0 | 0
162 | Done |  |  | Done | Paragraph removed, editorial |  |  |  |  | 1 | 0
163 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
164 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
165 | Gilb |  |  | Gilb | SEC update |  |  |  |  | 0 | 0
166 | Done |  |  | Done | No change required, see CID 295 |  |  |  |  | 1 | 0
167 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
168 |  |  |  |  | Open issue |  |  |  |  | 0 | 1
169 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
170 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
171 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
172 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
173 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
174 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
175 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
176 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
177 | Gilb |  |  | Gilb | See CID 177 |  |  |  |  | 0 | 0
178 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
179 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
180 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
181 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
182 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
183 | Done |  |  | Done | No change required |  |  |  |  | 1 | 0
184 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
185 | Gilb |  |  | Gilb | See CID 93 |  |  |  |  | 0 | 0
186 | Gilb |  |  | Gilb | Figure out what needs to be moved from clause 6 to 8 |  |  |  |  | 0 | 0
187 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
188 | Gilb |  |  | Gilb | See CID 95 |  |  |  |  | 0 | 0
189 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
190 | Done |  |  | Done | Withdrawn |  |  |  |  | 1 | 0
191 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
192 | Heberling | Heberling | See CID 77 | [6 empty] | 0 | 0
193 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
194 | Gilb |  |  | Gilb | Text in database, see CID 224 |  |  |  |  | 0 | 0
195 | Odman | [6 empty] | Odman | Identify the primitives that require timers | 0 | 0
196 | Gilb |  |  | Gilb | Text in database, see CID 79 |  |  |  |  | 0 | 0
197 | Gilb |  |  | Gilb | Text in database, see CID 80 |  |  |  |  | 0 | 0
198 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
199 | Odman | [6 empty] | Odman | Open issue | 0 | 0
200 | Gilb |  |  | Gilb | Define reason codes fro termination |  |  |  |  | 0 | 0
201 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
202 | Gilb |  |  | Gilb | Needs to be written |  |  |  |  | 0 | 0
203 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
204 | Done |  |  | Done | Name changed |  |  |  |  | 1 | 0
205 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
206 | Gilb |  |  | Gilb | Name changed |  |  |  |  | 0 | 0
207 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
208 | Odman | [6 empty] | Odman | Implied ACK text | 0 | 0
209 | Done |  |  | Done | Withdrawn |  |  |  |  | 1 | 0
210 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
211 | Odman | [6 empty] | Odman | New MSCs for handover | 0 | 0
212 | Gilb |  |  | Gilb | New figure 94a |  |  |  |  | 0 | 0
213 | Odman | [6 empty] | Odman | New MSCs for handover | 0 | 0
214 | Gilb |  |  | Gilb | See CID 261 |  |  |  |  | 0 | 0
215 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
216 | Gilb |  |  | Gilb | Fix association figure |  |  |  |  | 0 | 0
217 | Gilb |  |  | Gilb | Fix association figure |  |  |  |  | 0 | 0
218 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
219 | Odman | [6 empty] | Odman | Implied ACK text | 0 | 0
220 | Gilb |  |  | Gilb | Fix Fig. 122 |  |  |  |  | 0 | 0
221 | Done |  |  | Done | Withdrawn |  |  |  |  | 1 | 0
222 | Done |  |  | Done | Withdrawn |  |  |  |  | 1 | 0
223 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
224 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
225 | Odman | [6 empty] | Odman | Implied ACK text | 0 | 0
226 | Odman | [6 empty] | Odman | Implied ACK text | 0 | 0
227 | Odman | [6 empty] | Odman | Implied ACK text | 0 | 0
228 | Odman | [6 empty] | Odman | Implied ACK text | 0 | 0
229 | Odman | [6 empty] | Odman | Implied ACK text | 0 | 0
230 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
231 | Done |  |  | Done | No change required, see CID 295 |  |  |  |  | 1 | 0
232 | Done |  |  | Done | No change required, see CID 294 |  |  |  |  | 1 | 0
233 | Gilb |  |  | Gilb | New MLME description |  |  |  |  | 0 | 0
234 | Done |  |  | Done | No change required, see CID 295 |  |  |  |  | 1 | 0
235 | Done |  |  | Done | No change required, see CID 294 |  |  |  |  | 1 | 0
236 | Gilb |  |  | Gilb | New MLME description |  |  |  |  | 0 | 0
237 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
238 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
239 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
240 | Gilb |  |  | Gilb | Text in database, see CID 261 |  |  |  |  | 0 | 0
241 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
242 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
243 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
244 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
245 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
246 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
247 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
248 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
249 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
250 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
251 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
252 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
253 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
254 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
255 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
256 | Odman | [6 empty] | Odman | New MSCs for handover | 0 | 0
257 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
258 | Done |  |  | Done | Withdrawn |  |  |  |  | 1 | 0
259 | Gilb |  |  | Gilb | Fix Fig. 94 and add MLME |  |  |  |  | 0 | 0
260 | Gilb |  |  | Gilb | Fix Fig. 94A |  |  |  |  | 0 | 0
261 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
262 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
263 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
264 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
265 | Done |  |  | Done | No change required |  |  |  |  | 1 | 0
266 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
267 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
268 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
269 | Gilb |  |  | Gilb | Need to rewrite the paragraph |  |  |  |  | 0 | 0
270 | Gilb |  |  | Gilb | Fix Fig 113a, but this may be deleted with new CTA method |  |  |  |  | 0 | 0
271 | Odman | [6 empty] | Odman | Implied ACK text | 0 | 0
272 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
273 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
274 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
275 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
276 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
277 | Gilb |  |  | Gilb | Add explanations for reason codes to clause 8 |  |  |  |  | 0 | 0
278 | Done |  |  | Done | Withdrawn |  |  |  |  | 1 | 0
279 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
280 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
281 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
282 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
283 | Done |  |  | Done | Delete Relinquish CTA time command |  |  |  |  | 1 | 0
284 |  |  |  |  | Open issue |  |  |  |  | 0 | 1
285 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
286 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
287 | Done |  |  | Done | Withdrawn |  |  |  |  | 1 | 0
288 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
289 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
290 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
291 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
292 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
293 | Done |  |  | Done | Fixes to Implied ACK satisfy this |  |  |  |  | 1 | 0
294 | Done |  |  | Done | No change required |  |  |  |  | 1 | 0
295 | Done |  |  | Done | No change required |  |  |  |  | 1 | 0
296 | Done |  |  | Done | Withdrawn |  |  |  |  | 1 | 0
297 | Gilb |  |  | Gilb | Describe why the DME went away |  |  |  |  | 0 | 0
298 | Gilb |  |  | Gilb | New MLME description |  |  |  |  | 0 | 0
299 | Done |  |  | Done | Withdrawn |  |  |  |  | 1 | 0
300 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
301 | Done |  |  | Done | Withdrawn |  |  |  |  | 1 | 0
302 | Gilb |  |  | Gilb | See CID 175 |  |  |  |  | 0 | 0
303 | Done |  |  | Done | Withdrawn |  |  |  |  | 1 | 0
304 | Gilb |  |  | Gilb | Revert to old priority model |  |  |  |  | 0 | 0
305 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
306 | Gilb |  |  | Gilb | Need to add some new text |  |  |  |  | 0 | 0
307 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
308 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
309 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
310 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
311 | Done |  |  | Done | Name changed |  |  |  |  | 1 | 0
312 | Done |  |  | Done | Ran spell checker |  |  |  |  | 1 | 0
313 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
314 | Odman | [6 empty] | Odman | Implied ACK text | 0 | 0
315 | Done |  |  | Done | Withdrawn |  |  |  |  | 1 | 0
316 | Done |  |  | Done | Withdrawn |  |  |  |  | 1 | 0
317 | Done |  |  | Done | Withdrawn |  |  |  |  | 1 | 0
318 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
319 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
320 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
321 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
322 | Odman | [6 empty] | Odman | Implied ACK text | 0 | 0
323 | Odman | [6 empty] | Odman | Implied ACK text | 0 | 0
324 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
325 | Odman | [6 empty] | Odman | Implied ACK text | 0 | 0
326 | Gilb |  |  | Gilb | Need to modify figure 3 |  |  |  |  | 0 | 0
327 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
328 | Gilb |  |  | Gilb | New text for CSMA |  |  |  |  | 0 | 0
329 | Odman | [6 empty] | Odman | Implied ACK text | 0 | 0
330 | Gilb |  |  | Gilb | New MLME model figure |  |  |  |  | 0 | 0
331 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
332 | Done |  |  | Done | Rejected |  |  |  |  | 1 | 0
333 | Gilb |  |  | Gilb | New MLME description |  |  |  |  | 0 | 0
334 | Gilb |  |  | Gilb | Fix association figure |  |  |  |  | 0 | 0
335 | Gilb |  |  | Gilb | New text for CSMA |  |  |  |  | 0 | 0
336 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
337 | Odman | [6 empty] | Odman | Implied ACK text | 0 | 0
338 | Done |  |  | Done | Paragraph removed, editorial |  |  |  |  | 1 | 0
339 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
340 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
341 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
342 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
343 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
344 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
345 | Gilb |  |  | Gilb | Text in database |  |  |  |  | 0 | 0
346 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
347 | Done |  |  | Done | Editorial |  |  |  |  | 1 | 0
Total assigned |  | 2 |  | 196 |  | 0 |  | 22 |  | 220
Total resolved |  | 0 |  | 196 |  | 0 |  | 0 |  | 196
Total left to finish |  | 2 |  | 0 |  | 0 |  | 22 |  | 24