## IEEE cover
2005-11-14 |  | IEEE P802.15-05/0xxxr0
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | TG4a drafting status
Date Submitted | [November 14, 2005]
Source | [Jay Bain] | Voice: [256 539 4778]
| [Fearn Consulting] | Fax: [256 539 7335]
| [703 Owens Drive] | E-mail: [jbain at ieee dot org]
[Huntsville AL 35801]
Re: | []
Abstract | [This spreadsheet contains the status for the TG4a drafting process leading up to the letter ballot.]
Purpose | [To track the status of editing.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after furt
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## change notes
TG4a editing status
Editing history
History prior to IEEE document number assignment
revision 2 adds the breakdown of 6.5a CSS into sub clauses
revision 3 is a cleanup
revision 4 adds the breakdown of 6.8a UWB into sub clauses
revision 5 adds assignments to contributors or responsible editor
History post IEEE document number assignment
r0 added IEEE cover page and updated change notes

## Editing status
Clause number | Clause title | Contributor | Responsible editor | Due date | Status | Description of task
1 | Overview |  | Pat |  |  | 1 one page overview, scope, and purpose for 4a. Generate from 4b (consider structure of 3b (since it is also an amendment)).
2 | References |  |  |  |  | any to add?
3 | Definitions |  |  |  |  | what do we have?
4 | Abbreviations |  |  |  |  | what do we have?
5 | General description |  |  |  |  | Add text pointing to the new section 5.4a
5.4a | Characteristics of 802.15.4-Amendment a/predraft |  | Pat |  |  | {insert between existing 5.4 and 5.5 sections.}Add: characteristics of 4a LR-WPAN, listing for This amendment of the standard incorporated the following additions and enhancements to; overview of the amendment; description of each PHY; description of ranging; description of MAC additions. Added in rev4 - demodulation by non-coherent receivers and by coherent receivers
6.1 | General requirements and definitions |  | Jay |  |  | Change the first sentence to add 4a. Add ranging and any other PHY responsibilities to the bulleted list. Add a fifth paragraph to add the PHYs of the 4a amendment. Change the wording at the beginning of paragraph 4 to not confuse 4a with 4b PHY additions.
6.1.1 | Operating frequency range | Rainer/Phil | Jay |  |  | Add rows to Table 1 – Frequency bands and data rates to add the new bands and modulations as defined in 4a. For CSS, the 1st row is 1Mb/s and the second is 250kb/s. Tag the PHY(MHz) column as 2450 CSS.Amend regulatory text to call out 4a devices as well. Also add any new applicable regulatory documents.
6.1.2 | Channel assignments | Rainer/Phil | Jay |  |  | Consider amending - It may not be necessary to go into a history lesson. 4a has a dual use of the channel number bit map to include data rate so amend the text to reflect that.
6.1.2.1 | Channel numbering | Rainer/Phil | Jay |  |  | Retitle the sub clause to be for 4 and 4b
6.1.2.1a | Channel numbering for CSS | Rainer/Phil | Jay |  |  | Place table 1a to specify the channels for CSS - as taken from 802.11b
6.1.2.1b | Channel numbering for UWB | Rainer/Phil | Jay |  |  | Place table 1b to specify the channels for UWB
6.1.2.2 | Channel pages | Rainer/Phil | Jay |  |  | Add rows to Table 2 – Channel page and channel number to add CSS and UWB pages as well as multiple data rates for each. Add a new example for the bit map of a combined channel page, rate, and channel for CSS and channel page, rate, CDMA channel, and FDMA channel. Update the "reserved" row and the text of paragraph 2.
6.1.3 | Minimum LIFS and SIFS periods | Rainer/Phil | Jay |  |  | Add rows to Table 3 – Minimum LIFS and SIFS periods to add the two rates for CSS and the ? rates for UWB.
6.1.4 through 6.1.7 | RF power measurement, Transmit power, Out-of-band spurious emissions, Receiver sensitivity defiinitions |  |  |  |  | Verify that the text in these 4 sub clauses are correct for 4a devices.
6.2 | PHY service specifications | Lars | Jay |  |  | add sub clauses to cover new ranging stuff (data, management)
6.3.1 | General packet format | Rainer/Phil | Jay |  |  | Amend figure 16 if the use of frame length is 8 bits.
6.3.1.1 | Preamble field | Rainer/Phil | Jay |  |  | Add rows to table 19-- Preamble field length, to add CSS and UWB PHY requirements. Change the 2nd paragraph to point to appropriate preamble format sub clauses.
6.3.1.2 | SFD field | Rainer/Phil | Jay |  |  | add rows to table 20 -- SFD field length to add CSS and UWB PHY details. Amend the second paragraph update text and to point to the appropriate SFDs for CSS and UWB PHYs.
6.4.1 | PHY constants |  | Jay |  |  | amend table 22-- PHY constants. The PHY packet size has to be considered. It is 127 max for existing and might change for CSS and UWB. The aTurnaroundTime should be reviewed as well.
6.4.2 | PIB attributes |  | Jay |  |  | amend table 23- PHY PIB attributes as necessary to support 4a PHYs.
6.5 | 2450 MHz PHY specification | null | null |  |  | Just a note that we do not wish to amend this sub clause
6.5a | 2450 MHz PHY Chirp Spread Spectrum (CSS) | Rainer/Lee | John |  | 05/410r3 posted | small general introduction of perhaps 1 paragraph
6.5a.1 | Data rates | Rainer/Lee | John |  | 05/410r3 posted
6.5a.2 | Preamble | Rainer/Lee | John |  | 05/410r3 posted
6.5a.3 | Waveform | Rainer/Lee | John |  | 05/410r3 posted
6.5a.4 | Modulation | Rainer/Lee | John |  | 05/410r3 posted
6.5a.5 | Spreading | Rainer/Lee | John |  | 05/410r3 posted
6.5a.6 | Pulse Shape | Rainer/Lee | John |  | 05/410r3 posted
6.5a.7 | Channel Coding | Rainer/Lee | John |  | 05/410r3 posted
6.5a.8 | Symbol Rate | Rainer/Lee | John |  | 05/410r3 posted
6.5a.9 | Transmit Power Spectral Density Mask | Rainer/Lee | John |  | 05/410r3 posted
6.5a.10 | Transmit Power | Rainer/Lee | John |  | 05/410r3 posted
6.5a.11 | Receiver Sensitivity | Rainer/Lee | John |  | 05/410r3 posted
6.5a.12 | Receiver Jamming Resistance | Rainer/Lee | John |  | 05/410r3 posted
6.8a | 3100 to 10000 MHz PHY Ultra Wide Band (UWB) |  | Phil |  |  | General introduction to UWB PHY and phy components of ranging
6.8a.1 | Data rates |  | Phil
6.8a.2 | Preamble and delimiter |  | Phil
6.8a.2.1 | Timing of the delimiter at the antenna with respect to the timestamps |  | Phil/Vern |  |  | {shorten the title}
6.8a.3 | Waveform, pulse shape, and chipping rates |  | Phil |  |  | {shorten the title. Also, this is Verns "no-drool" rules}
6.8a.4 | Modulation |  | Phil
6.8a.5 | Spreading |  | Phil |  |  | {Ismail's cover sequence}
6.8a.6 | Channel coding within a band |  | Phil |  |  | {define the start points of the cover sequence}
6.8a.7 | Forward error correction |  | Phil
6.8a.8 | Symbol rate |  | Phil
6.8a.9 | Transmit power spectral density |  | Phil
6.8a.10 | Transmit power |  | Phil |  |  | {maybe folds into 6.9}
6.8a.11 | Receiver sensitivity |  | Phil
6.8a.12 | Receiver jamming resistance |  | Phil
6.9 | General radio specifications | Pat | John and Phil |  |  | amend the appropriate sub clauses within 6.9 to reflect new CSS and UWB radios
7 | MAC sublayer specification | Jay | Jay |  |  | add an introduction for 4a
7.1 | MAC sublayer service specification | Lars | Jay |  |  | add tbd for ranging, specifics of the two PHYs (structures (and associated text), tables, MSCs)
7.2 | MAC frame formats | Lars | Jay and Vern |  |  | add the new ranging structure
7.3 | MAC command frames | Vern, Zafer | Jay |  |  | add to Table 82 MAC command frames and then text for new over-the-air commands. We should not change any existing commands!!
7.4 | MAC constants and PIB attributes |  | Jay |  |  | Add rows to tables as required
7.5 | MAC functional description | Vern, Zafer | Vern and Jay |  |  | – leave what exists alone! – add the several ranging functional descriptions at the end of this subclause. Take from 5/603
7.5.8 | Frame security | null | null |  |  | leave this alone as this doesn’t seem to be the location for our ranging privacy capabilities.
7.6 | Security suite specifications | null | null |  |  | lets try to leave this one alone and place our privacy capabilities elsewhere.
7.7 | Message sequence charts illustrating MAC-PHY interaction | Zafer, Lars, others | Jay |  |  | this may be a place for some of our work !
Annex D1 (informative) | Ranging additional topics | Vern, Zafer? | Vern |  |  | {insert after Annex D} ranging topic items from 5/603 doc
Annex C | Protocol implementation conformance statement (PICS) proforma |  | Jay |  |  | amend to cover the optional and mandatory structure of 4a
Annex E (informative) | Coexistence with other IEEE standards and proposed standards |  | Phil, John, Vern |  |  | amend to add sections following the existing work (including what Rob Poor is doing for optional sub-GHz radios) for CSS and for UWB.
Annex F (informative) | IEEE 802.15.4 – REVb/D2 and Amendment A/D? regulatory requirements |  | Phil, John, Vern |  |  | amend to include appropriate UWB and CSS information.
Annex G (informative) | Bibliography |  |  |  |  | amend to add any appropriate references
notes:
Status field content -- U for unwritten; R for reviewed; I for incorporated