## Sheet1
TG4d activity
Task | start date | weeks | comments | 15 WG meetings
Japanese spec release for public comment | 2007-03-01 |  | Date not fixed - only a guess!
Translation of spec |  | 1 | OKI
translation of report |  | 1 | OKI
Presentation of specification to TG4d |  |  | OKI at March WG meeting | 2007-03-01
Call for Proposals |  | 8 | Proposals for PHY and MAC
Proposals at WG meeting |  | 1 |  | 2007-05-01
Start editing amendment |  | 0
Merge proposals during edit |  | 4
Create first draft |  | 4
discuss at WG meeting |  |  | at WG meeting | 2007-07-01
resolve any issues |  |  | at WG meeting | 2007-07-01
issue for letter ballot |  | 0 | at WG meeting | 2007-07-01
letter ballot |  | 4 | 30 days?
comment resolution |  | 4 | by editting committee
issue for recirc |  | 0 |  | 2007-09-01
recirculation ballot |  | 2 | 15 days
comment resolution |  | 2 | by editing committee
issue for sponsor ballot |  | 0 | at WG meeting | 2007-11-01
sponsor ballot |  | 4 | 30 days?
comment resolution |  | 2 | at WG meeting | 2008-01-01
issue for recirculation |  | 0 | at WG meeting | 2008-01-01
recirculation ballot |  | 2 | 15 days
comment resolution |  | 2 | by committee
move to accept amendment |  | 0 | at WG meeting | 2008-03-01