## Sheet1
|  | 2007 | [11 empty] | 2008
Activity | Meeting | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Task Group Formed | bar: 2007 1
Present draft spec for comment | March WG meeting | bar: 2007 3
Present outline for amendment | March WG meeting | bar: 2007 3
Call for proposal issued | bar: 2007 3
Prepare coexistence document | bar: 2007 3
Submit coexistence document | bar: 2007 4
Present coexistence document | May WG meeting | bar: 2007 5
Present Proposals | May WG meeting | bar: 2007 5
Start editting amendment | bar: 2007 5 to 2007 6
Merge Proposals | July WG meeting | bar: 2007 7
Instructions to editor | bar: 2007 7
Proposal draft completed | bar: 2007 8
1st letter ballot | bar: 2007 8
1st letter ballot completed | Sep WG meeting | bar: 2007 9
Resolution of comments completed | bar: 2007 9
1st recirculation | bar: 2007 9
Re-circulation completed | bar: 2007 10
Resolve re-circulation comments | bar: 2007 10
2nd re-circulation | bar: 2007 10
Resolve 2nd re-circulation comments. | Nov WG meeting | bar: 2007 11
Request Excom for Sponsor Ballot | Nov WG meeting | bar: 2007 11
Sponsor ballot period | bar: 2007 11 to 2007 12
Sponsor ballot comment resolution. | Jan WG meeting | bar: 2008 1
1st recirculation | bar: 2008 1
Re-circulation completed | bar: 2008 2
Resolve re-circulation comments | bar: 2008 2
Submit to Excom for Revcom | March WG meeting | bar: 2008 3
RevCom Approval | bar: 2008 4; 2008 7