## Sheet1
|  | 2007 | [11 empty] | 2008
Activity | Meeting | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Task Group Formed | Jan WG meeting | bar: 2007 1
Present draft spec for comment | July WG meeting | bar: 2007 7
Present outline for amendment | July WG meeting | bar: 2007 7
Call for proposal issued | bar: 2007 7
Prepare coexistence document | bar: 2007 4
Submit coexistence document | bar: 2007 4
Present coexistence document | May WG meeting | bar: 2007 5
Present Proposals | Sep WG meeting | bar: 2007 9
Start editting amendment | bar: 2007 9 to 2007 10
Merge Proposals | Nov WG meeting | bar: 2007 11
Instructions to editor | bar: 2007 11
Proposal draft completed | bar: 2007 12
1st letter ballot | bar: 2007 12
1st letter ballot completed | Jan WG meeting | bar: 2008 1
Resolution of comments completed | bar: 2008 1
1st recirculation | bar: 2008 1
Re-circulation completed | bar: 2008 2
Resolve re-circulation comments | bar: 2008 2
2nd re-circulation | bar: 2008 2
Resolve 2nd re-circulation comments. | March WG meeting | bar: 2008 3
Request Excom for Sponsor Ballot | March WG meeting | bar: 2008 3
Sponsor ballot period | bar: 2008 3 to 2008 4
Sponsor ballot comment resolution. | May WG meeting | bar: 2008 5
1st recirculation | bar: 2008 5
Re-circulation completed | bar: 2008 6
Resolve re-circulation comments | bar: 2008 6
Submit to Excom for Revcom | Sep WG meeting | bar: 2008 7
RevCom Approval | bar: 2008 4; 2008 7