## timeline
|  | 2007 | [11 empty] | 2008 | [11 empty] | 2008
Activity | Meeting | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Task Group Formed | Jan WG meeting | bar: 2007 1; 2007 9 to 2007 11; 2008 1 to 2008 5
Present draft spec for comment | Sep WG meeting | bar: 2007 9 to 2007 11; 2008 1 to 2008 5
Present outline for amendment | Sep WG meeting | bar: 2007 9 to 2007 11; 2008 1 to 2008 5
Call for proposal issued | bar: 2007 10 to 2007 11; 2008 1 to 2008 5
Prepare coexistence document | bar: 2007 10 to 2007 11; 2008 1 to 2008 4
Submit coexistence document | bar: 2007 10 to 2007 11; 2008 1 to 2008 4
Present coexistence document | May WG meeting | bar: 2007 10 to 2007 11; 2008 1 to 2008 5
Present Initial Proposals | Jan WG meeting | bar: 2007 10; 2008 1 to 2008 5
Present Final Proposals | March WG meeting | bar: 2008 1 to 2008 5
Baseline Proposal | March WG meeting | bar: 2007 9 to 2007 11; 2008 1 to 2008 5
Instructions to editor | bar: 2007 9 to 2007 10; 2008 2 to 2008 5
draft amendment completed | May WG meeting | bar: 2007 9 to 2007 11; 2008 1; 2008 3 to 2008 5
1st letter ballot | bar: 2007 9 to 2007 11; 2008 1 to 2008 5
1st letter ballot completed | July WG meeting | bar: 2008 5; 2008 7
Resolution of comments completed | bar: 2008 7
1st recirculation | bar: 2008 7
Re-circulation completed | bar: 2008 9
Resolve re-circulation comments | Sep WG meeting | bar: 2008 9
2nd re-circulation | bar: 2008 9
Resolve 2nd re-circulation comments. | Nov WG meeting | bar: 2008 11
Request Excom for Sponsor Ballot | Nov WG meeting | bar: 2008 1; 2008 5; 2008 11
Sponsor ballot period | bar: 2007 9 to 2007 11; 2008 2 to 2008 4; 2008 12 to 2008 1
Sponsor ballot comment resolution. | Jan WG meeting | bar: 2007 9 to 2007 11; 2008 1
1st recirculation | bar: 2007 9 to 2007 11; 2008 1
Re-circulation completed | bar: 2007 9 to 2007 11; 2008 2
Resolve re-circulation comments | March WG meeting | bar: 2007 9 to 2007 11; 2008 2
Submit to Excom for Revcom | March WG meeting | bar: 2007 9 to 2007 11; 2008 2
RevCom Approval | bar: 2007 9 to 2007 11; 2008 1 to 2008 5