## IEEE-Cover
2008-03-01 |  | IEEE P802.15.3-08/0020r7
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | DF0 comments
Date Submitted | March, 2008
Source | James P. K. Gilb | Voice: (858)-229-4822
| SiBEAM | Fax: [ ]
| 555 N. Mathilda, Suite 100 | E-mail: last name at ieee dot org
Sunnyvale, CA 94085
Re:
Abstract
Purpose | [This document provides a home for all comments, open issues and suggested resolutions concerning the TG3c draft DF0. In addition, this document will keep a running status of the disposition of the suggested resolutions.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## OI-List-Srtd
| Color Codes |  |  |  |  | W | Changes approved | This Sheet uses autoformat for cell colors except for closed. (Excel only handles 3 conditional formats)
|  | C | Closed |  |  | A | Assigned
|  | P | Proposal pending |  |  | O | Open, not assigned | Last Issue Number | 65
Issue Number | Commenter's Initials | Draft Version Number | Clause number e.g., 8.10.2 | Page number e.g., 1-1130, etc. | Line number e.g., 1-54 | Type of comments (E/e/T/t) | Class of Problem | Comment/Rationale (Issue and reasoning behind it.) | Recommended change (What change(s) it would take to make this clause acceptable.) | Disposition/Rebuttal (Do not write here during ballot phase; this is for comment resolution phase.) | Resolution Status O,A,W,P,C | Date Entered | Date Completed | Asignee | Issue Status | Resolution Status
1 | JPKG | DF0 | 12.2.1 | 9 | 26 | T | AV PHY | The equation for the FFT period in the OFDM PHY is wrong for LRP and HRP modes | Change to f_s(HR)/N_sc(HR) and f_s(LR)/N_sc(LR) | Change as indicated. | C |  |  | James Gilb |  |  | ZL = lan@nict.go.jp
2 | EK | DF0 | Various |  |  | T | MAC | Do we need a capability bit that indicates a DEV is MMC PNC capable? | Determine if that is necessary. | No, it can be determined from the PHY capabilities. | C |  |  | James Gilb |  |  | ST = solomon.trainin@intel.com
3 | IL | DF0 | 12.2 |  |  | T | AV PHY | Need to describe when the LRP is used. | Used for bcst, mcst, beacon, CAP and some MAC commands. Need to generate text. |  | C |  |  | James Gilb | PM1, 3/19/08 |  | JY = james.yee@mediatek.com
4 | JPKG | SC | 7.2a |  |  | E | MAC | Keep refences to 2.4 GHz, add reference to mmWave PHY. | Change as indicated here and throughout. Where only "PHY" is mentioned, add references to both Clause 121 and Clause 12, as appropriate. | Change as indicated. | C |  |  | James Gilb |  |  | Edwin Kwon = cy.kwon@samsung.com
5 | JPKG | SC | 7.2.5a |  |  | T | MAC | Do we need reserved stream indices for beamforming and channel probing. | Pending, depending on if we need the stream index. |  | A |  |  | James Gilb, ZL | AM1, 3/20/08 |  | Pyo = cwpyo@nict.go.jp
6 | JPKG | SC | 7.3.1.1a |  |  | T | MAC | Does the resolution of the superframe timing need to be less than 1 us? |  | May need it for CTAs but not superframe or CAP | C |  |  | Shu Kato | PM2, 3/18/08 |  | Sum = sum@nict.go.jp
7 | JPKG | SC | 7.3.2.2.3 |  |  | T | MAC | Will Dly-ACK do what is necessary for Blk-ACK or are there unique things that Blk-ACK needs to do. Also, can this concept be extended to include the AV PHY directional ACK. |  |  | A |  |  | Shu Kato, Edwin Kwon | AM1, 3/20/08 |  | James Gilb = last name at ieee dot org
8 | IL | SC | 7.4.11a |  |  | T | MAC | Do we add SIFS and MIFS capabilities here or in another information element. |  | Change 0011 to be 0.8 us and 0.8 us, change the reserved values to be all unused and resolve as indicated in 15-08-0102-03 | C |  |  | Ismail Lakkis |  |  | Ismail Lakkis = ilakkis@tensorcom.com
9 | IL | SC | 7.4.11a |  |  | T | MAC | How do we encode all of the supported data rates. | If we add another IE with the data rates, is it sent infrequently so that we don't need to worry about its size? |  | A |  |  | Ismail Lakkis | PM1, 3/19/08 |  | H. Harada = harada@nict.go.jp
10 | JPKG | All | 7.4.11a |  |  | T | PHY | We need to define the preferred fragment size mapping for each of the PHY modes or possibly one for all PHY modes. |  | Resolve as indicated in 15-08-0102-03 | C |  |  | H. Harada, J. Gilb, I. Lakkis |  |  | Shu Kato = shu.kato@nict.go.jp
11 | ST | SC | 7.4.22 |  |  | T | MAC | How do DEVs know when the superframe starts and when the last beacon ends if they receive one beacon in the middle of a set of beacons. |  | Information element in the beacon which contains the offset in time from the start of the superframe. | C |  |  | Ismail Lakkis, Pyo |  |  | Jisung Oh = jisung0714.oh@samsung.com
12 | IL | AV | 7.4.22 |  |  | T | AV PHY | How does a DEV know when the first symbol of the beacon is sent when there is repetition coding. |  | Information element in the beacon which contains the offset in time from the start of the superframe. | C |  |  | James Gilb, Ismail Lakkis |  |  | Tuncer Baykas = tbaykas@ieee.org
13 | JPKG | SC | 7.4.23 |  |  | T | Beamforming | Is this IE needed in light of the contributions on beamforming. If so, does it have the correct information. |  |  | A |  |  | Ismail Lakkis, Pyo, Jisung Oh | AM1, 3/20/08 |  | Su Khiong = sk.yong@samsung.com
14 | JPKG | SC | 7.4.24 |  |  | T | Beamforming | Can we update this IE to include all of the information useful for beam formed as well as sectorized antennas? What additional information is required? |  |  | A |  |  | Ismail Lakkis, Pyo, Jisung Oh | AM1, 3/20/08 |  | Makto Noda = MakatoB.Noda@jp.sony.com
15 | JPKG | SC | 7.5.11 |  |  | T | Beamforming | Are these the right set of commands? |  |  | A |  |  | Ismail Lakkis, Pyo, Jisung Oh | AM1, 3/20/08
16 | JPKG | SC | 7.5.12.1 |  |  | T | Channel probing | What is the definition of the value of the Channel Status Information field? |  | James to provide example ideas | A |  |  | JPKG | PM1, 3/19/08
17 | JPKG | SC | 7.5.13 |  |  | T | UEP | Can this be done with an information element? Also, there are some updates to the frame format that need to be reviewed. |  | Need information element, either capability or UEP IE TBD. | A |  |  | Edwin Kwon, Pyo | AM1, 3/20/08
18 | JPKG | SC | 8.2.3 |  |  | T | MAC | Why is handover optional? Should it be restricted to certain cases. | Perhaps we can define a reduced function PNC. | Handover optional for mmWave PHYs | C |  |  | Ismail Lakkis, James Gilb, Shu Kato
19 | CK | SC | 8.2.3 |  |  | T | MAC | Need rules to describe that the beacon PHY mode shall not change while in operation. Also, that on handover, the new PNC uses the same PHY mode for the beacon as the old PNC. If so, we may be able to leave PNC Des-Mode as the top criteria for handover. |  | Add three rules, only handover to DEV that supports current PHY mode. Beacon PHY mode never changes while piconet inoperation. After handover, beacon PHY remains the same. Table 55 can be unchanged. | C |  |  | James Gilb, JY, ZL
20 | IL | DF0 | 12.1 |  |  | E | PHY | Add requirement that MMC PNCs implement the common mode. |  | Resolve as indicated in 15-08-0102-03 | C |  |  | Sum, H. Harada, James Gilb
21 | JPKG | DF0 | 12.1 |  |  | T | PHY | What PHY mode is used in the CAP | Add a note that the PHY mode used in the CAP is the same as the PHY mode used for the beacon. | The CAP PHY mode and contention CTAs shall use the same PHY mode as the beacon. | C |  |  | James Gilb, Sum, H. Harada
22 | ST | SC | 5 |  |  | E | Introduction | Add a description of the MMC PNC to Clause 5 in relation to the beaconing and the CAP. | Add text that matches the normative descritpion when that is completed. | Editorial | C |  |  | James Gilb, Sum, H. Harada
23 | JPKG | All | 12.1 |  |  | T | PHY | Each PHY needs to explicitly define the base rate that will be used |  | For SC, it is 50 Mb/s, HSI TBD. JPKG to provide better understanding of base rate | A |  |  | JPKG | PM1, 3/19/08
24 | JPKG | All | 12.1 |  |  | E | All | The PHY mode names will be SC (single carrier), HSI (high speed interface), AV (audio/video), alternative: SC, MC1, MC2 |  | Editorial | C |  |  | James Gilb
25 | JPKG | SC | 8.2.5a |  |  | E | MAC | Move the new text in this subclause to the informative annex. | Move as indicated. | Editorial | C |  |  | James Gilb
26 | IL | All | 12.1 |  |  | T | PHY | Can all three PHY modes use the same SIFS and list this in the capabilities field to be used in an CTA. |  | Each PHY uses its default SIFS and MIFS in the CAP and after all beacons. | C |  |  | Ismail Lakkis, Tuncer Baykas, James Gilb
27 | IL | SC | 8.6.2a |  |  | T | MAC | Do we allow multiple beacons? If so, are they restricted to one PHY mode? Do we allow multiple beacons for sectored antenna applications. |  | Yes, allow repeated beacons, all same PHY mode which supports sectorized antennas. | C |  |  | Ismail Lakks, H. Harada, Tuncer Baykas, JY
28 | IL | All | 7.2 |  |  | T | Frame formats | Can we unify the use of FCS's and types of FCS? |  | No change required. | C |  |  | Ismail Lakks, James Gilb, H. Harada
29 | JPKG | SC | 8.7a |  |  | T | Frame formats | Can we unify the aggregation? |  | JPKG to provide suggested text for AV OFDM | A |  |  | Edwin Kwon, Pyo, James Gilb | PM1, 3/19/08
30 | JPKG | SC | 7.2 |  |  | T | Frame formats | Do we use one or two HCS for the headers, including the extended MAC header. |  | No change required. | C |  |  | Edwin Kwon, Pyo, James Gilb
31 | JPKG | SC | 8.8.3b |  |  | T | ACK | The rules for Blk-ACK need to be filled out. | Refer to Dly-ACK and Imm-ACK subclauses for the types of rule that need to be defined. | Similar to Imm-ACK except that you send Blk-ACK if the header is correct always. Blk-ACK can be used at any time, including the CAP. | C |  |  | Pyo, Shu Kato
32 | JPKG | SC | 8.12a |  |  | E | MAC | Table 58a does not need any changes. |  | Editorial, also PNC does not hand over to a different PHY modes as previously resolved. | C |  |  | James Gilb
33 | JPKG | SC | 8.16 |  |  | T | Beamforming | Work on a unified beamforming submission. |  |  | A |  |  | Ismail Lakkis, James Gilb, Shu Kato, Tuncer Baykas, Jisung Oh, Su Khiong | AM1, 3/20/08
34 | IL | SC/HSI | 12 |  |  | T | PHY | Can the SC and HSI PHY use a single preamble format? |  |  | A |  |  | Ismail Lakkis | PM1, 3/19/08
35 | ST | SC | 8.18 |  |  | T | UEP | There needs to be a way for the upper layer that is the source of data to say if the use of UEP is allowed for the data stream. |  |  | A |  |  | Edwin Kwon, James Gilb, ZL, Pyo | PM2, 3/19/08
36 | JPKG | SC | 8.18 |  |  | T | UEP | Rather than using commands, if the UEP capailities are exchanged as part of the normal capabilities exchange, then the commands are not needed. |  |  | A |  |  | Edwin Kwon, James Gilb, ZL, Pyo | AM1, 3/20/08
37 | JPKG | SC | 8.19 |  |  | E | Beamforming | The section repeats information from the channel time request for command. | Remove redundant information. |  | C |  |  | James Gilb
38 | JPKG | SC | 8.19 |  |  | T | Channel probing | Can we use the existing facilities in 802.15.3b to accomplish this in a manner that improves the performance. | JPKG will propose text | JPKG to create text | A |  |  | James Gilb | PM1, 3/19/08
39 | IL | SC | 8.19 |  |  | T | Beamforming | This is probably very efficient when both sides are sectorized. However, when one side is not, regular beamforming would need to be used. Keep this section inmind when reviewing beamforming. |  |  | A |  |  | Ismail Lakkis, James Gilb, Shu Kato, Tuncer Baykas, Jisung Oh, Su Khiong | AM1, 3/20/08
40 | MN | SC | 12.1.4.2.1 | 80, 81 |  | T | Frame formats | It is beter to use two different HCS for combined PHY and MAC header and MAC subheader | Shown in the document 08/042r1 | Reject, no change will be made | C |  |  | Makato Noda
41 | GB | DF1 | 12.10.2 |  |  | T | PHY | To enable low latency communication enable switching between RX and TX (SIFS) in a much shorter period than 1 usec |  | Resolve as indicated in comment 8. | C
42 | GB | DF1 | 12.3.1.5 |  |  | T | PHY | In order to have low phy overhead shorten the short preamble. An example can be composed of 8 Syncs 2 SFDs and 1 CES | Applies only to the SC PHY. | Resolved with the changes approved for comment 8. | C
43 | GB | DF1 | 8.7 |  |  | T | MAC | Enable MSDU aggregation |  |  | A |  |  |  | AM2, 3/20/08
44 | GB | DF1 | 7.3.2.3 |  |  | T | MAC | Enable Block Ack to be aggregated with data |  | Put Blk-ACK bits in MAC subheader. | A |  |  |  | AM2, 3/20/08
45 | GB | DF1 | 7.3.2.3 |  |  | T | MAC | Consider adding compressed BA for efficiency |  | Put Blk-ACK bits in MAC subheader. | A |  |  |  | AM2, 3/20/08
46 | GB | DF1 | 7.4 |  |  | T | MAC | Add new capability bit for bus_root and bus_endpoint, those devices will support low latency communication. |  | Withdraw | C
47 | GB | DF1 | 8 |  |  | T | MAC | Enable CTA to be bi-directional (meaning interchanging transmissions between 2 DEV at the same CTA) |  | Put Blk-ACK bits in MAC subheader. | A |  |  |  | AM2, 3/20/08
48 | YK | DF1 | 7.5.12 12.2.4.3 | 23 63 |  | T | MAC | Current UEP procedure doesn't seem to support various color depths of video data. | Presentation will be provided for this comment. | Add sentence to UEP section that says "UEP only supports 8 bits per color." | C |  |  |  | PM1, 3/19/08
49 | YK | DF1 | 7.5.12 12.2.4.3 | 23 63 |  | T | MAC | Need to have an indication for the position of the middle point which separates MSBs from LSBs. (According to DF1, it seems that the default color depth is 8 bits which consist of 4 bits of MSBs and 4 bits of LSBs.) | Presentation will be provided for this comment. |  | A |  |  |  | PM1, 3/19/08
50 | YK | DF1 | 7.5.12 12.2.4.3 | 23 63 |  | T | MAC | To make UEP be optimized for various types of video formats, UEP procedure needs to be applicable not only for MSBs and LSBs but also other classifications, for example, luminance and chrominance and so on. | Presentation will be provided for this comment. |  | A |  |  |  | PM1, 3/19/08
51 | ZL | DF2 | 12.2.4.3 | 63 |  | T | MAC | Current MAC subheader (80 bytes) is very big, the subheader size shall be reduced for the sake of efficiency. |  | Resolve as indicated in 15-08-0102-03 | C
52 | TB | DF2 | 12.2.5.5.3 | 68 |  | T | PHY | The cyclic prefix in 12.2.5.5.3 should be removed from the baseline document |  | Resolve as indicated in 15-08-0102-03 | C
53 | TB | DF2 | 12.2.4.1 | 59 |  | T | PHY | More compact header design will enable lower latencies (unified header with HSI OFDM). |  | Resolve as indicated in 15-08-0102-03 | C
54 | TB | DF2 | 12.2.4.1.11 | 62 |  | T | PHY | Is the optional BURST length of 512 for FDE necessary for SC PHY, if not it should be eliminated. | Eliminate burst length 512 from DF2 | Resolve as indicated in 15-08-0102-03 | C
55 | TB | DF2 |  |  |  | T | PHY | How simple decision feedback equalization can be supported for SC PHY at high speeds. |  |  | A |  |  | Tuncer Baykas | AM2, 3/20/08
56 | AB | DF2 | 8.16.1.1 8.16.1.2 | 31 & 33 | 16 & 1 | T | MAC | The max values for M and N is not specified. Is that a problem ? |  |  | A |  |  |  | AM1, 3/20/08
57 | AB | DF2 | 12.2.3 | 56 | 35 | T/E | PHY | The preamble is sent at 1728 Mchips/s not at 13.5 samples/s. The wording "code repetition" to designate a length of 128 chips is inappropriate and confusing as regards the CES where the a and b sequences are 256 chips long. Also in Figure 158. | Change 13.5 Samples/s to 1728 Mchips/s. Delete the sentence says "A preamble code repetition is ..." | Editorial | C
58 | ZL | DF2 | 7.3.1.1 |  |  | T | MAC | Do we need higher resolution for the CTA timing and/or the TUs in channel time request | 160 ns resolution for both timings | Change as indicated in 15-08-0178-01. | C |  |  | JPKG, ZL | PM1, 3/19/08
59 | IL | DF2 |  |  |  | T | MAC | Clarify that the CAP can be used for any data rate and that the ACK follows the rate of the sent packet |  |  | A |  |  | IL | AM1, 3/20/08
60 | IL | DF2 | Table 137 | 81 |  | E | PHY | Table 137 uses msb(7:4) and lsb(3:0 should be msb octet and lsb octet |  |  | A |  |  | IL
61 | IL | DF2 |  |  |  | T | PHY | Spreading step is missing from HSI-OFDM and its description |  |  | A |  |  | IL | AM1, 3/20/08
62 | IL | DF2 |  |  |  | T | PHY | SFD figure 146 is wrong (remove) and table 145 has wrong description. |  |  | A |  |  | IL | AM1, 3/20/08
63 | IL | DF2 |  |  |  |  | PHY | Change RS to (252,236), was (226(210) |  | Editorial, approved previously. | C |  |  | JPKG
64 | IL | DF2 |  |  |  | T | PHY | "data field change. |  |  | A |  |  |  | AM1, 3/20/08
65 | IL | DF2 |  |  |  | T | PHY | Constellation normalization factor is wrong in table 153. |  |  | A |  |  |  | AM1, 3/20/08
66 | IL | DF2 |  |  |  | T | PHY | figure FFT is missing from the modulator, but this falls under "data field" so if changing the entire section is accepted, then it is done. |  |  | A |  |  |  | AM1, 3/20/08
67 | TB | DF2 | 12.2.2.2 | 49 |  | T | PHY | Can SC PHY and HSI OFDM unify their LDPC codes |  | SC PHY change 576 to 672, rate codes matching the same ones including matrices in HSI. 1/2, 3/4 and 7/8. | C |  |  | TB
68 | EG, CSC, AB | DF2 | 12.3, 12.4 |  |  | T | PHY | Two different OFDM PHYs are not needed and are very costly for product development and implementation. | option 1 (preferred): merge the two OFDM PHYs into a single, harmonized one option 2 (worst case): remove 12.3 or 12.4 |  | O
69 | EG, CSC, AB | DF2 | 12.2, 12.3, 12.4 |  |  | T | PHY | The Common Rate is needed for the management of piconets. Therefore, it should be mandatory for all devices. | Make Common Rate mandatory for all devices. |  | C
70 | TB | DF2 | 12.2.2.1 | 46 |  | T | PHY | The QPSK constellation in SC PHY should be rotated 45 degrees to have pi/2 bpsk |  | Resolve as indicated in 15-08-0186-02 | C |  |  | TB
71 | ZL | DF2 | 12.3.1.6 | 85 |  | E | PHY | Table 142, Table 143 and Table 144 contain the same value. | Update the tables with the correct values. |  | A |  |  | IL | AM1, 3/20/08
72 | ZL | DF2 | 12.3.1.6 | 86 | 26 | E | PHY | The value of g-13:13 needs to be updated by HSI. |  | Page 85-86, line 34 Delete from "The time domain..." through and including equation 2. | C
73 | KK | DF2 | 7.2 7.3.2 8.8 12.2.5 |  |  | T | MAC | ACK policies can be simplified, e.g. Imp-ACK can be merged into Imm-ACK. Blk-ACK can be replaced by Dly-ACK. Some comments about UEP and aggregation are also provided. | Presentation will be provided for this comment. (15-08-0125-01-003c) | Postpone until next meeting | C |  |  | KK
74 | KK | DF2 | 8.7a 12.2.4.3 | 27 64 |  | T | MAC | The aggregation procedure is modified in order to make it transparent to MAC layer. | Presentation will be provided for this comment. (15-08-0126-01-003c) | Postpone until next meeting | C |  |  | KK
75 | KT | DF2 | 12.2.4 | 59 |  | T | PHY | This Header is defined for SC p/2-BPSK, not for SC-OOK (Class4). Header for SC-OOK should be described. |  |  | A |  |  | Takahashi | AM1, 3/2/08
76 | KT | DF2 | 12.2.3 | 56 |  | T | PHY | This Preamble is defined for SC p/2-BPSK, not for SC-OOK (Class4). Preamble for SC-OOK should be described. |  |  | A |  |  | Takahashi | AM1, 3/2/08
77 | KT | DF2 | 12.2.8.4 | 72 |  | T/E | PHY | How to deal with line spectra in the center frequency in case of SC-OOK mode? |  |  | A |  |  | Takahashi | AM1, 3/20/08
78 | AM | DF2 | 12.2.4 | 59 |  | T | PHY | Should the header for Class 4 modulation scheme be defined? |  |  | A |  |  | Takahashi | AM1, 3/20/08
79 | AM | DF2 | 12.2.3 | 56 |  | T | PHY | Shold the preamble for Class 4 modulation scheme be defined? |  |  | A |  |  | Takahashi | AM1, 3/20/08
80 | AM | DF2 | Table 96 | 43 | 30 | T | PHY | Review the PHY-SAP data rate for DRB1, Class 4 |  |  | A |  |  | Takahashi | AM1, 3/20/08
81 | AM | DF1 | 12.2.2.1.7 | 48 |  | E | PHY | Review the text as there is no reference to the pilots |  | Text will be reviewed | C
82 | AM | DF1 | 5.5.1 | 4 | 39 | E | PHY | Change from 'dual rail bipolar' to 'dual AMI' where AMI is alternate mark inversion. AMI is technically accurate. Can be abbreviated as DAMI. |  | Change as indicated | C
83 | AM | DF1 | 12.2 | 41 | 27 | E | PHY | -same as above - |  | Change as indicated | C
84 | AM | DF1 | 12.2 | 42 | 2 | E | PHY | -same as above - |  | Change as indicated | C
85 | AM | DF1 | Table 96 | 43 | 30 | E | PHY | -same as above - |  | Change as indicated | C
86 | AM | DF1 | Figure 149 | 46 | 52 | E | PHY | -same as above - |  | Change as indicated | C
87 | AM | DF1 | 12.2.2.1.7 | 48 | 37 | E | PHY | -same as above - |  | Change as indicated | C
88 | AM | DF1 | 12.2.2.1.7 | 39 | 39 | E | PHY | -same as above - |  | Change as indicated | C
89 | JPKG | DF2 | Various |  |  | T | MAC | There are a few "<missing definition>" items in the draft. | Define all the fields that have <missing definition> |  | A |  |  | JPKG | AM2, 3/20/08

## Closed issues
| Color Codes |  |  |  |  | W | Changes approved | This Sheet uses autoformat for cell colors except for closed. (Excel only handles 3 conditional formats)
|  | C | Closed |  |  | A | Assigned
|  | P | Proposal pending |  |  | O | Open, not assigned | Last Issue Number | 0
Issue Number | Commenter's Initials | Draft Version Number | Clause number e.g., 8.10.2 | Page number e.g., 1-1130, etc. | Line number e.g., 1-54 | Type of comments (E/e/T/t) | Class of Problem | Comment/Rationale (Issue and reasoning behind it.) | Recommended change (What change(s) it would take to make this clause acceptable.) | Disposition/Rebuttal (Do not write here during ballot phase; this is for comment resolution phase.) | Resolution Status O,A,W,P,C | Date Entered | Date Completed | Asignee | Issue Status | Resolution Status

## Score Sheet
|  |  | % | By assignee, all not closed.
Open | O | 1 | 1.124% | JPKG | 4
Assigned | A | 39 | 43.82% |  | 0
Written | W | 0 | 0% |  | 0
Closed | C | 49 | 55.06% |  | 0
Withdrawn | Z | 0 | 0% |  | 0
Unsatisfied | U | 0 | 0% |  | 0
Total # of Issues |  | 89 | 100% |  | 36
Problem Class |  | Class Total
PHY |  | 40
MAC |  | 27
Beam forming |  | 6
Frame formats |  | 4
Synch |  | 0
Table |  | 0
CTA |  | 0
Frame Format |  | 0
Frame Length |  | 0
Total |  | 77