## TG4c timeline
|  | 2007 | [11 empty] | 2008 | [11 empty] | 2009
Activity | Meeting | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Task Group Formed | Jan WG meeting | bar: 2007 3
Call for Intent issued | Sep WG meeting
Hear Responses to Call for Intent | Sep WG meeting
Call for proposal issued
Present Proposals | July WG meeting | bar: 2007 7
Present Proposals | Sep WG meeting | bar: 2007 9
Present Proposals | Nov WG meeting | bar: 2007 11
Start editting amendment | Jan WG meeting | bar: 2008 1 to 2008 2
Merge Proposals | bar: 2008 3
Instructions to editor | bar: 2008 3
Proposal draft completed | March WG meeting | bar: 2008 3
1st letter ballot | bar: 2008 3 to 2008 5
1st letter ballot completed | bar: 2008 5
Resolution of 1st letter ballot comments | May WG meeting | bar: 2008 5
1st recirculation | bar: 2008 5 to 2008 7
1st Re-circulation completed | bar: 2008 7
Resolve 1st re-circulation comments | July WG meeting | bar: 2008 7
2nd re-circulation | bar: 2008 7 to 2008 9
2nd Re-circulation completed | bar: 2008 9
Resolve 2nd re-circulation comments. | Sep WG meeting | bar: 2008 9
Request Excom for Sponsor Ballot | Sep WG meeting | bar: 2008 9
Sponsor ballot period | bar: 2008 9 to 2008 11
Sponsor ballot comment resolution | Nov WG meeting | bar: 2008 11
1st recirculation | bar: 2008 11 to 2009 1
Re-circulation completed | bar: 2009 1
Resolve re-circulation comments | bar: 2009 1
Submit to Excom for Revcom | Jan WG meeting | bar: 2009 1
RevCom Approval | March RevCom mtg | bar: 2009 1