## TG4c timeline
|  | 2007 | [11 empty] | 2008 | [11 empty] | 2009
Activity | Meeting | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Task Group Formed | Jan WG meeting | bar: 2007 3
Call for Intent issued | Sep WG meeting
Hear Responses to Call for Intent | Sep WG meeting
Call for proposal issued
Present Proposals | July WG meeting | bar: 2007 7
Present Proposals | Sep WG meeting | bar: 2007 9
Present Proposals | Nov WG meeting | bar: 2007 11
Start editting amendment | Jan WG meeting | bar: 2008 1 to 2008 2
Merge Proposals | bar: 2008 3
Instructions to editor | bar: 2008 3
Proposal draft completed | March WG meeting | bar: 2008 3
1st letter ballot | bar: 2008 3 to 2008 5
1st letter ballot completed | bar: 2008 5
Resolution of 1st letter ballot comments | May WG meeting | bar: 2008 5
1st recirculation | bar: 2008 6
1st Re-circulation completed | bar: 2008 6
Resolve 1st re-circulation comments | July WG meeting | bar: 2008 7
Request Excom for Sponsor Ballot | July WG meeting | bar: 2008 7
Sponsor ballot period | bar: 2008 7 to 2008 9
Sponsor ballot comment resolution | Sep WG meeting | bar: 2008 9
1st recirculation | bar: 2008 9 to 2008 11
Re-circulation completed | bar: 2008 11
Resolve re-circulation comments | bar: 2008 11
Submit to Excom for Revcom | Nov WG meeting | bar: 2008 11
RevCom Approval | Dec RC meeting | bar: 2008 12