## IEEE_Cover
2008-05-12 |  | IEEE P802.15.3-08/0255r4
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | DF3 issues tracking
Date Submitted | May, 2008
Source | James P. K. Gilb | Voice: (858)-229-4822
| SiBEAM | Fax: [ ]
| 555 N. Mathilda, Suite 100 | E-mail: last name at ieee dot org
Sunnyvale, CA 94085
Re:
Abstract
Purpose | [This document provides a home for all comments, open issues and suggested resolutions concerning the TG3c draft DF3. In addition, this document will keep a running status of the disposition of the suggested resolutions.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## OI_List_Srtd
| Color Codes |  |  |  |  | W | Changes approved | This Sheet uses autoformat for cell colors except for closed. (Excel only handles 3 conditional formats)
|  | C | Closed |  |  | A | Assigned
|  | P | Proposal pending |  |  | O | Open, not assigned | Last Issue Number | 65
Issue Number | Commenter's Initials | Draft Version Number | Clause number e.g., 8.10.2 | Page number e.g., 1-1130, etc. | Line number e.g., 1-54 | Type of comments (E/e/T/t) | Class of Problem | Comment/Rationale (Issue and reasoning behind it.) | Recommended change (What change(s) it would take to make this clause acceptable.) | Disposition/Rebuttal (Do not write here during ballot phase; this is for comment resolution phase.) | Resolution Status O,A,W,P,C | Date Entered | Date Completed | Asignee | Issue Status | Resolution Status
1 | JPKG | SC | 7.2.5a |  |  | T | MAC | Do we need reserved stream indices for beamforming and channel probing. | Pending, depending on if we need the stream index. | Resolve as indicated in 15-08-0355-00 | C |  |  |  | Tuesday |  | ZL = lan@nict.go.jp
2 | JPKG | SC | 7.4.23 |  |  | T | Beamforming | Do we need the IE? What is the correct information? What commands are necessary |  | Resolve as indicated in 15-08-0355-00 | C |  |  |  | Tuesday |  | ST = solomon.trainin@intel.com
3 | JPKG | SC | 7.5.12.1 |  |  | T | Channel probing | What is the definition of the value of the Channel Status Information field? Can we use existing facilities in 802.15.3b to accomplish this? |  | Resolve as indicated in 15-08-0225-01 with text in section 1.2 of 15-08-0253-00, change ROUS to RSSIr | C | [5 empty] | JY = james.yee@mediatek.com
4 | JPKG | SC | 7.5.13 |  |  | T | UEP | Can this be done with an information element? Also, there are some updates to the frame format that need to be reviewed. |  | Resolve as indicated in 15-08-0225-01, the appendix goes into the informative annex and change the SC and HSI-OFDM to match the current coding. | C | [5 empty] | EK = Edwin Kwon = cy.kwon@samsung.com
5 | JPKG | SC | 8.16 |  |  | T | Beamforming | Work on a unified beamforming submission. |  | Resolve as indicated in 15-08-0355-00 | C |  |  |  | Tuesday |  | Pyo = cwpyo@nict.go.jp
6 | IL | SC/HSI | 12 |  |  | T | PHY | Can the SC and HSI PHY use a single preamble format? |  | Withdrawn | C |  |  |  | Wednesday |  | Sum = sum@nict.go.jp
7 | ST | SC | 8.18 |  |  | T | UEP | There needs to be a way for the upper layer that is the source of data to say if the use of UEP is allowed for the data stream. |  | Resolve as indicated in 15-08-0253-02. | C |  |  |  | Wednesday |  | James Gilb = last name at ieee dot org
8 | IL | SC | 8.19 |  |  | T | Beamforming | This is probably very efficient when both sides are sectorized. However, when one side is not, regular beamforming would need to be used. Keep this section inmind when reviewing beamforming. |  | Resolve as indicated in 15-08-0355-00 | C |  |  |  | Tuesday |  | IL = Ismail Lakkis = ilakkis@tensorcom.com
9 | YK | DF1 | 7.5.12 12.2.4.3 | 23 63 |  | T | MAC | Need to have an indication for the position of the middle point which separates MSBs from LSBs. (According to DF1, it seems that the default color depth is 8 bits which consist of 4 bits of MSBs and 4 bits of LSBs.) | Presentation will be provided for this comment. | Resolve as indicated in 15-08-0333-0 but applies only to UEP type 2. | C |  |  |  | Tuesday |  | H. Harada = harada@nict.go.jp
10 | YK | DF1 | 7.5.12 12.2.4.3 | 23 63 |  | T | MAC | To make UEP be optimized for various types of video formats, UEP procedure needs to be applicable not only for MSBs and LSBs but also other classifications, for example, luminance and chrominance and so on. | Presentation will be provided for this comment. | Resolve as indicated in 15-08-0333-0 but applies only to UEP type 2. | C |  |  |  | Tuesday |  | Shu Kato = shu.kato@nict.go.jp
11 | TB | DF2 |  |  |  | T | PHY | How simple decision feedback equalization can be supported for SC PHY at high speeds. |  | Withdrawn | C | [5 empty] | Jisung Oh = jisung0714.oh@samsung.com
12 | EG, CSC, AB | DF2 | 12.3, 12.4 |  |  | T | PHY | Two different OFDM PHYs are not needed and are very costly for product development and implementation. | option 1 (preferred): merge the two OFDM PHYs into a single, harmonized one option 2 (worst case): remove 12.3 or 12.4 | Reject. | C |  |  |  | Wednesday |  | Tuncer Baykas = tbaykas@ieee.org
13 | KK | DF2 | 7.2 7.3.2 8.8 12.2.5 |  |  | T | MAC | ACK policies can be simplified, e.g. Imp-ACK can be merged into Imm-ACK. Blk-ACK can be replaced by Dly-ACK. Some comments about UEP and aggregation are also provided. | Presentation will be provided for this comment. (15-08-0125-01-003c) | Withdrawn | C | [5 empty] | SKY = Su Khiong = sk.yong@samsung.com
14 | KK | DF2 | 8.7a 12.2.4.3 | 27 64 |  | T | MAC | The aggregation procedure is modified in order to make it transparent to MAC layer. | Presentation will be provided for this comment. (15-08-0126-01-003c) | Withdrawn | C | [5 empty] | Makto Noda = MakatoB.Noda@jp.sony.com
15 | KT | DF2 | 12.2.8.4 | 72 |  | T/E | PHY | How to deal with line spectra in the center frequency in case of SC-OOK mode? |  | Resolve as indicated in 15-08-0342-00. | C |  |  |  | Wednesday |  | JAT = Jason Trachewsky = jat@broadcom.com
16 | EG, CSC, AB | DF2 | 12.2, 12.3, 12.4 |  |  | T | PHY | The Common Rate is needed for interference control and the management of piconets. Therefore, it should be mandatory for all PNC capable devices. | Make Common Rate mandatory for all PNC capable devices or find another solution wich allows interference control and efficient management of piconets. | Resolve as indicated in 15-08-0335-00 | C | [5 empty] | MS, RY = Michael Sim Raymond Yu
17 | IL | DF3 | 12.3.1.10 | 90 | 1:8 | T | PHY | HSI-OFDM: There are too many reserved bits in the PHY header |  | Withdrawn | C |  |  |  | Wednesday |  | HRS = Huai Rong Shao
18 | IL | DF3 | 12.3.1.2 | 81 |  | T | PHY/MAC | HSI-OFDM: Is it possible to combine the base and optional headers to fit in one OFDM symbol at the highest rate? |  | Withdrawn | C |  |  |  | Wednesday |  | JSOH = Jisung Oh
19 | IL | DF3 | 12.3.1.9 | 89 |  | T | PHY/MAC | HSI-OFDM: The new optional header is shorter now. So all references to the optional header should change accordingly |  | Define the length of the subheader in one location only, delete from all other locations. | C |  |  |  | Wednesday |  | GB = Gal Basson
20 | IL | DF3 | 12.3.2.3.3 | 97 | 41:45 | T | PHY | HSI-OFDM: The LDPC partiy check matrices are missing |  | Add a cross reference Figure 191 in the SC section as it is the same matrix. | C | [5 empty] | YK = Yasunao Katayama
21 | IL | DF3 | 12.3.2.3.2 | 96 | 50 | T | PHY | HSI-OFDM: The outer interleaver depth of 4 RS codes is incorrect and is not an integer multiple of LDPC blocks. |  | Change the outer interleaver depth to be 7 in the HSI-OFDM PHY section. | C | [5 empty] | AYK = Assaf Kasher
22 | IL | DF3 | 12.3.2.5.2&3 | 100 |  | T | PHY | HSI-OFDM: The spreader buy 4 and 28 are messed up by the tone interleaver. |  | Withdrawn | C |  |  |  | Wednesday
23 | IL | DF3 | 12.2.2.3 | 55 | 24:26 | T | PHY | SC: Subclause 12.2.2.3 talks about two different spreading method for length 2 and 4, whereas description is provided for only one of them. |  | Resolve as indicated in 15-08-0322-00. | C |  |  |  | Tuesday
24 | IL | DF3 | 12.2.2.3 | 55 |  | T | PHY | SC: Should there be spreading at block level or at bit level |  | In the draft it is explained that it is as the bit level, 12.2.2.3, no change required. | C
25 | IL | DF3 | 12.2.1.1 | 44 | 47:448 | T | PHY | SC: Define a Fall back mode based on LDPC |  | Add an optional MCS of Pi/2 BPSK mod. LDPC 1/2 rate with spreading of 2. This will be class 1, use the corresponding MCS number and renumber the rest. No change required to supported MCS field, is already handled. | C
26 | JAT | DF2 | 6.3.21 |  | 5-6 | T |  | What is the TxDiversityThreshold and what do the units and valid range of 0-255 mean? | Define specifically what is meant and what the range of values mean? E.g., is the value intended to be logarithmically-encoded (e.g., in dB, etc.)? | Resolve as indicated in 15-08-0325-00 with the change that the step size for FER and BER is 0.25 in the exponent and the negative exponent is passed. | C |  |  |  | Mon PM1
27 | JAT | DF2 | 7.5.11.4 |  | 39-40 | T |  | “The Transmit Antenna field contains the information of the antenna index which has the largest received SNR among antennas used until now in the current packet transmission.” I can’t state how many ways this phrasing disturbs me. | First of all, packets aren’t transmitted by a MAC/PHY. Frames are. (This is a nit.) At the PHY layer, it is a burst. Second, why state exactly how antenna selection is to be performed? What if I want to use a min-BER, max-capacity or ??? Algorithm? It should be allowed to do so. | Rephrase to become “The Transmit Antenna field contains the information of the antenna index with the best received metric value.”The selection algorithm of the antenna is implementation-dependant | C
28 | JAT | DF2 | 7.5.11.6 |  |  | T |  | The Channel Status Information field must be defined. | This is a serious issue. What am I agreeing to by leaving this field undefined? | Resolve as indicated in 15-08-0225-01 with text in section 1.2 of 15-08-0253-00, change ROUS to RSSIr | C
29 | JAT | DF2 | 8.2.5 |  | 51-53 | T |  | I’m a bit uncomfortable that relegating OOK and OFDM devices to child piconets solves all the interop issues. First of all, if an OOK PNC (for example) finds an unused channel (how does it determine a channel is unused??), it may set up an OOK PNC. How do other non-OOK devices then detect it, since they cannot detect the OOK beacons except by noting the presence of foreign interference (which is a bit unreliable)? | Clearly state rules for how OOK and OFDM PNCs can create their own piconets on “clean” channels (what is a clean channel?)? Or, better yet, disallow use of OOK or force OOK PNCs to be SC PNCs, capable of transmitting pi/2-BPSK beacons. (DEVs would have no such requirement). OFDM PNCs should always be required to be dual-mode, at least at the lowest SC rates. They should also transmit SC beacons for compatibility. | Add clarification, In an unused channel, the OOK/HSI-OFDM PNC broadcasts Common Rate beacons in the beacon period. Since the channel is vacant there will be no reply for the beacon. Then the OOK/HSI-OFDM PNC will proceed to broadcast respective OOK/HSI-OFDM beacons in the private CTA to allow any present OOK/HSI-OFDM DEVs to detect the corresponding PNCs. The piconet setup of these OOK/HSI-OFDM PNCs are conducted in CTAP so there is no issue on foreign interference. | C
30 | JAT | DF2 |  |  | 46-52 | T |  | “A compliant mm-wave PHY shall implement at least one of the following PHY modes a) SC mmWave PHY Mode, as a) SC mmWave PHY Mode, as defined in 12.2, b) HSI mmWave PHY mode, as defined in 12.3, or c) AV mm-Wave PHY defined in 12.4." It seems strange that if one or more of the three Modes is implemented then that makes mm-Wave compliant PHY. What about interoperability? One of the modes should be mandatory with possibly one additional mode optional. Having too many implementation choices will create interoperability problems and make technology less attractive, maybe even unusable in some applications. | Out of the three modes make one mode mandatory and possibly only one PHY mode optional. Another possibility is to reduce the current 3 modes into the following: 1) SC mode for LOS conditions with little equalization and no support for low-complexity FDE defined as a zero-GI subset of SCBT (SC with support for low-complexity FDE). Keep it simple with only low-spectral-efficiency, bandwidth-efficient modes (e.g., pi/2-BPSK). 2) OFDM mode for high throughput and NLOS conditions. SCBT generally shows an advantage at lower input SNRs/spectral efficiencies, while OFDM is generally better at higher spectral efficiencies on frequency-selective channels. Lower datarates in 1) and/or 2) can be made mandatory and higher rates optional. Our preference is for mode 1 (SC/SCBT) to be the mandatory mode with only lower data rates supported in this way. There would then be no interoperability problems and it would be very easy to accommodate both 1) and/or 2) in a chip. OFDM modulation requires about 5.5-6 dB PA backoff to meet ACPR requirements and may not be a good candidate for a short-range system such as .15.3c integrated in a hand-held device. | Resolve as indicated in 15-08-0335-00 | C
31 | JAT | DF2 |  |  | 50-52 | T |  | There are 2 OFDM modes, HSI and AV. These two modes should be consolidated into a single OFDM mode or one should be eliminated. It is very uncommon practice to have two such similar modes defined in a standard, and it creates unnecessary interoperability problems. | Eliminate one OFDM mode or consolidate the two OFDM modes into a single OFDM mode. Options may be defined within the common OFDM PHY for particular applications. | Reject | C
32 | JAT | DF2 | 12.2.1.1 |  | Table 96 | T |  | Different MCSs have different coding. Choose one coding, make it mandatory, and have other coding possibly as an optional feature. | As in comment. We prefer use of a simple short block length LDPC. As an alternative, we could accept RS(255, 239) encoding or LDPC. We prefer not to concatenate these codes but to define suitable LDPC codes that enable lower-complexity decoding without an error floor for low-BER applications. | Reject: Currently RS coding is chosen to be the mandatory FEC due to its low complexity. LDPC is chosen as the high grain alternative when high coding is required for specific application. | C
33 | JAT | DF2 | 12.2.1.1 |  | Table 96 | T |  | Why was Class 4 included in the Draft? It does not increase PHY-SAP throughput over other MCSs. These are subset of Class 1 and Class 2. Does it significantly outperform Class 1 and Class 2 from the sensitivity point of view? | Remove Class 4 devices from the draft. | Redirect: Class 4 was included to provide an alternative for low power consumption and low complexity applications. Add this explanation to Clause 5. | C
34 | JAT | DF2 | 12.2.1.1 |  | Table 96 | T |  | Class 2 MR5 is very similar to MR4. | Remove Class 2 MR5 MCS. | Redirect: Add the following explanation to Clause 5: MR5 is an MCS with QPSK and RS(255,239), and Common Rate is the MCS with BPSK+RS(255,239). Since BPSK and QPSK uses similar circuits, it is easy for SC systems to employ QPSK+RS(255,239) besides Common Rate, without any additional complexity. Therefore, we recommend to keep MR5 for the design simplicity and flexibility. | C
35 | JAT | DF2 | 12.2.1.4 |  | Table 100 | T |  | There is no need to have 3 different preamble types. This increases implementation/testing complexity. | Define only two preamble types derived from short/medium and medium/long preambles. | Reject: We recommend to keep the preamble design as flexible as possible to cater different system and application demands. The methods to choose the preamble can be implementation-dependant. | C
36 | JAT | DF2 | 12.2.8.1 |  |  | T |  | What are max EIRP limits? | Please define max EIRP for different countries/bands. | Add references to the EIRP subclauses where possible for the current regulatory documents, as of 2008. | C
37 | JAT | DF2 | 12.2.8.3 |  |  | T |  | It is more common to define EVM in dB values. | Please define EVM in dB for different MCSs. | Resolve as indicated in 15-08-0325-00 with the change to -10 dB for Class 1, -7 dB for OOK, -14 dB for DAMI. | C |  |  |  | Tuesday
38 | MS, RY | DF2 | 8.2.5 | 25 | 53 | T | MAC | Need to descirbe how to construct an OOK piconet by OOK PNC when no SC Piconet is detected |  | Add this paragraph to subclause 12.1.?? “When a PNC capable OOK DEV detects an SC piconet, the PNC capable OOK DEV may join the SC piconet and request a CTA to create a child piconet in which other non-PNC capable OOK devices may use OOK. On the other hand, when a PNC capable OOK DEV detects no SC piconet and tends to start as PNC, the PNC capable OOK shall construct a piconet of SC mode and create a child piconet of OOK inside the CTA of the superframe for which other OOK devices will use OOK.” | C
39 | MS, RY | DF2 | 8.2.5 | 26 | 1 | T | MAC | Need to describe where and how to send the SC beacon in the superframe of an OOK piconet formed by an OOK PNC |  | Resolve as indicated in comment 38. | C
40 | HRS | DF3 | 7.3.2 | 16 | 1 | T | MAC | Blk-ACK frame format is missing | Should add Blk-ACK figure and diagram in 7.3.2 | Format of Blk-ACK is defined in section 12.2.4.3 MAC subheader and aggregated data frame format. No change required. | C
41 | HRS | DF3 | 7.4.7 | 17 | 10-31 | T | MAC | In Fig. 42, should have one bit to indicate Blk-ACK, and two bits to indicate different aggregation schemes | Uee one reserved bit to indicate Blk-ACK, and two reserved bits to indicate aggregation schemes: 00: no aggregation, 01: standard aggregation, 10: low-lantency aggregation, 11: reserved | Uee one reserved bit to indicate Blk-ACK, and two reserved bits to indicate aggregation schemes: 00: no aggregation, 01: standard aggregation, 10: low-lantency aggregation, 11: reserved | C
42 | HRS | DF3 | 7.4.7 | 18 | 7-23 | T | PHY/MAC | Table 49a, Do MIFS and SIFS use the same value? Is it possible SIFS can be shorter than 1.0us? | Further discussion on this | Resolve as indicated in 15-08-0345-00 | C
43 | HRS | DF3 | 7.4.24 | 19 | 8-20 | T | PHY/MAC | Only Tx antenna number , does Rx antenna number information needed? | Add Rx antenna number | This function is just for TX diversity, so Rx antenna number is not needed. No change required | C
44 | HRS | DF3 | 8.16.3 | 37 | 40-54 | T | MAC/PHY | What's the Rx antenna configuration? Does RX also switch Rx antenna according to Tx antenna switch? | Further discussion on this | This function is just for TX diversity, so Rx antenna number is not needed. No change required | C
45 | HRS | DF3 | 8.16.3 | 37 | 51 | T | MAC/PHY | What's the value of the threshold to trigger TX anteena switch? | Further discussion on this | The threshold is implementation dependent. No change required. | C
46 | SK | DF3 | 12.1.7.1 |  |  | T | PHY | the bit allocated for HSI OFDM is missing | Provide the bit(s) needed to suport HIS OFDM | Add 3 to the header to indicate the number of bits. | C
47 | SK | DF3 | 12.2..2 | 48-51 | ALL | T | PHY | Normalization factor for pi/2 16-QAM is given. The other normalization factors for therest of the modulation schemes are missing | Provide the normalization factors for the missing modulations | Resolve as indicated in 15-08-0322-00. | C |  |  |  | Tuesday
48 | SK | DF3 | 12,.2.3 | 58 | 51-52 | T | PHY | How SC and non PNC capable OOK DEVs co-exist? | Further discussion on this | Resolve as indicated in comment 38. | C
49 | SK | DF3 | 12.2.4 | 61 | Figure 199 | T | PHY | Spreading factors are 1, 2, 4 and 32. | Remove the SF 32 in the spreader module | Editorial change, remove SF 32. | C
50 | SK | DF3 | 12.2.4.1.3. | 62 | Table 113 | T | PHY | SI to S4 are not mapped to the corresponding spreading factors. | add description about the mapping | Change as described in 15-08-0310-00 | C
51 | SK | DF3 | 12.2.2.4 | 66 | Fig. 203 | T | MAC | UEP MCS shows in EEP frame format | UEP MCS shall be changed to EEP MCS | Put in a cross reference to where the UEP modes are defined. 0 is the 2040 Mb/s SC mode, 1 is the 2652 SC mode, all other values are reserved. Change UEP mode field to be specific for the frame that is being defined, i.e., the EEP frame has it set to zero. | C
52 | JSOH | DF3 | 12.3.2.3 | 95 | 19 | T | PHY | Description on MUX in Fig. 219 is missing | detailed information on MUX should be incorporated especially for UEP coding rates. | Resolve as indicated in 15-08-0307-00. | C
53 | JPKG | DF3 | 6.3 |  |  | T | MLME | With more than one PHY mode possible, the upper layers need the ability to determine the PHY mode of piconets found and to specify the PHY mode of a piconet that is started. | Change as described in 15-08-0253-00 | Change as described in 15-08-0253-00 | C
54 | JPKG | DF3 | 12.1.7.3 | 43 | 1 | T | Channel probing | The Receive Status field is undefined | Change as described in 15-08-0253-00 | Resolve as indicated in 15-08-0225-01 with text in section 1.2 of 15-08-0253-00, change ROUS to RSSIr | C
55 | JPKG | DF3 | 8.8.4 |  |  | T | Retransmission | Need to add a rule that allows video packets with errors to be passed to the higher layers and define an FCSL to enable this | Change as described in 15-08-0253-00 | Change as described in 15-08-0253-02, section 1.16. | C |  |  |  | Tuesday AM1
56 | JPKG | DF3 | 12.4.3 | 124 | 52 | T | AV PHY | The use of the long and short omni preamble is not well defined | Change as described in 15-08-0253-00 | Change as described in 15-08-0253-00 | C
57 | JPKG | DF3 | 8.12 |  |  | T | AV PHY | Add clarification that the ACKs for HRP are sent with directional ACK and describe HR0, HRRX, HRTX and HRTR | Change as described in 15-08-0253-00 | Change as described in 15-08-0253-02, section 1.8 | C |  |  |  | Tuesday
58 | JPKG | DF3 | 8.8.3b | 27 | 45 | T | Retransmission | These rules seem overly restrictive Retransmission doesn't need a lot of rules | Delete all but the required rules. | Withdrawn | C |  |  |  | Tuesday
59 | GB | DF3 | 12.3.2.7.1 | 103 |  | T | PHY | Seed suppose to be 15 bits not 16 as written today |  | Remove the extra zero to the right. | C |  |  |  | In DF4
60 | GB | DF3 | 12.3.2.7.1 | 102 |  | T | PHY | Pilot number 5 is not defined well |  | Put pilot 5 only in the upper group. | C
61 | GB | DF3 | 8.7a.2 | 26-27 |  | T | MAC | replace description of Low latency aggregation with attached text in doc "DF3 - comments for low latency aggregation.doc" section 8.7a.2 |  | Resolve as indicated in 15-08-0321-01 | C
62 | GB | DF3 | 8.8.3b | 27-28 |  | T | MAC | replace description of Block ACK for Low latency aggregation with attached text in doc "DF3 - comments for low latency aggregation.doc" section 8.8.3b |  | Resolve as indicated in 15-08-0321-01 | C
63 | GB | DF3 | 12.2.4.3.2 | 65-66 |  | T | PHY | add a "Block-ACK base sequence field" (to optional MAC header adjuscent to BA field) - in order resolve ACK/NAK correlation ambiguity of corrupted MSDU number and BA-bit-offset |  | Resolve as indicated in 15-08-0319-03. | C
64 | YK | DF2 | 12.2.2.1 | 46 |  | T | PHY | The relative amplitide and phase offset of different SC modulations w.r.t. pi/2-BPSK/(G)MKS need to be clarified to assure interoperability |  | Resolve as indicated in 15-08-0322-00. | C
65 | CC | DF3 | 7.4.7 | 17 |  | T |  | Block ACK and Aggregation support are not indicated in the capabilities. Support is mandatory? All types of aggregation? | Include Block ACK and aggregation in capabilities | Resolve as indicated in comment 41. | C
66 | CC | DF3 | 7.4.22 | 18 | 35 | T |  | Figure 48e: what is the unit? Bits or octets? | Define unit | Add octet to the figure | C
67 | CC | DF3 | 8.6.2 | 25 |  | T | Beamforming | If the PNC sends extended beacons through directional transmissions, a recipient DEV has no way of knowing when the following CAP or CTA starts. The way the Beacon Offset is defined right now, this cannot be done. | Define how a device can determine the beginning of the CAP/CTA | Resolve as indicated in 15-08-0355-00 | C
68 | CC | DF3 | 12.2.4.3.1 | 65 | 34 | T |  | Subframe Information undefined | Define Subframe Information field | Define as: 00: MSB subframe, 01: LSB subframe, 10: MSB and LSB subframe, 11 reserved. | C
69 | CC | DF3 | 7.5.11.6 | 22 | 16 | T |  | Channel Status Information undefined | Define Channel Status Information field | Resolve as indicated in comment 3. | C
70 | CC | DF3 | 12.4 | 107 | 42 | T |  | From this sentence, it appears to be possible for a DEV (including the PNC) not to support HRP. That would imply that the max data rate is around 10Mbps as provided through the LRP. However, the minimum required data rate a DEV shall support in 15.3c is 1Gbps. | Define a mandatory HRP mode | Reject, see document 15-08-0253-02 for explanation. | C
71 | CC | DF3 | 7.5.11.1 | 20 | 15 | T | Beamforming | Number of beam fields undefined | Define Number of beam fields | Resolve as indicated in 15-08-0355-00 | C
72 | CC | DF3 | 7.5.11.2 | 20 | 35 | T | Beamforming | Transmit beam number field undefined | Define Transmit beam number field | Resolve as indicated in 15-08-0355-00 | C
73 | CC | DF3 | 7.5.11.2 | 20 | 37 | T | Beamforming | Received beam number field undefined | Define Received beam number field | Resolve as indicated in 15-08-0355-00 | C
74 | CC | DF3 | 7.5.11.2 | 20 | 39 | T | Beamforming | Beam status information field undefined | Define Beam status information fields | Resolve as indicated in 15-08-0355-00 | C
75 | CC | DF3 | 8.2 | 23 |  | T |  | The process for starting piconets for the AV PHY needs to be specified since it is not clear how the LPR and HRP impact this process. | Describe how to start piconets for the AV PHY | Reject. The normal 802.15.3 process is used. LRP is used for beacons as stated in the draft. | C
76 | CC | DF3 | 8.7a | 25 |  | T |  | The two aggregation methods should be merged. Having two aggregation schemes increases complexity in implementation and makes the spec unecessarily complicated | Merge aggregation schemes | Reject: No. the two aggregation methods have different purposes, which are high throughput video transmission/ file downloading and low latency application. | C
77 | CC | DF3 | 8.8.3b | 28 | 23 | T |  | numberOfSubramesLimit undefined in the draft | Define numberOfSubramesLimit | Change name to MaximumNumberOfSubframes and put in the PIB. It is implementation dependent. | C
78 | CC | DF3 | 12.4.1.1 | 108 |  | T |  | In the AV PHY, there can be a major interference problem when two nearby piconets operate in the same HRP channel but different LRP channels. | Define interference mitigation mechanisms amongst piconets operating in the same HRP channel but different LRP channels. Simple procedures like switch HRP channel will not solve the problem in many scenarios. | Reject. There are mechanisms in 802.15.3 to handle overlapping piconets. In addition, the beamformed transmitter reduces the energy incident on victim receivers. | C
79 | CC | DF3 | 12 | 40 |  | T |  | Having two OFDM PHY only introduces confusion. | Merge the two OFDM PHYs or remove one of them | Reject | C
80 | CC | DF3 | 12.1.5 and D2 | 145 |  | T |  | The MMC PNC should not be the way to interoperate DEVs with different PHYs. There should be a mandatory mode for DEV interoperation. | Remove the concept of MMC PNC and introduce a mandatory mode that all DEVs are able to communicate. | Resolve as indicated in 15-08-0335-00 | C
81 | CC | DF3 | 8.4 | 24 |  | T |  | The access scheme of the CAP is very inefficient: i) considerations for beamformed operation in the CAP are not taken into account; ii) only one CAP is allowed per superframe; | Define more efficient access scheme for the CAP | Reject: No solution is provided. Also 802.15.3 does allow more than one CAP per superframe. | C
82 | CC | DF3 | 8.4 | 24 |  | T |  | DEVs are not allowed to access the medium during unallocated time over the superframe. | Include access schemes for unallocated channel time, which is very important for bursty traffic, low latency applications. | Reject: Open CTA and open MCTA in 802.15.3 support the same purpose. | C
83 | CC | DF3 | General |  |  | T |  | There are several TBDs in the draft | Replace TBDs by proper definition | Resolve as indicated in 15-08-0346-00 | C
84 | CC | DF3 | 7.4.7 | 18 | 26 | T |  | UEP field undefined | Define UEP field | Resolve as indicated in comment 4. | C
85 | PG | DF3 | 8.4.2 | 24 |  | T |  | DEVs using directional antennas during CSMA/CA can create significant 'hidden node' collisions and affect network performance | Add mechanisms to minimize and recover from 'hidden node' collisons caused by directional antennas | Reject: No solution is provided. | C
86 | PG | DF3 | 8.4.2 | 24 |  | T |  | Two piconets operating in close proximity on same channel, but different medium access mechaims during a given time (e.g., one CSMA/CA another TDMA), can cause significant interference to one another. This is beacause TDMA mostly operates using beamformed mode while CSMA/CA uses "OMNI" mode. This can lead to severe performance degradation. | Include special mechanisms to address simulatneous operation of TDMA and CSMA/CA. | Reject: No solution is provided. | C
87 | KK | DF3 | 12.4.3.8 |  |  | T | MAC | Should we unify blk-ack and directional-ack for providing unified aggregation? |  | Reject, the directional ACK provides low overhead because the LRP is used for ACK'ing HRP packets. The LRP is used because the application of streaming uncompressed video is highly asymmetric. | C
88 | KK | DF3 | 8.7a 12.2.4.3 | 27 64 |  | T | MAC | The aggregation procedure is modified in order to make it transparent to MAC layer. That is to say, the aggregated frames can be acknowledged by either Blk-ACK, or Dly-ACK. This concept will help unify different aggregation methods. | Presentation will be provided. | Withdrawn | C
89 | KK | DF3 | 7.1 7.2.7.6 12.2.2.4 |  |  | T | MAC | If UEP is applied, current FCS field of maximum 4 octets can't include both of MSB/LSB fields. Hence, the length of FCS should be extended to maximum 8 octets. |  | Withdrawn | C |  |  |  | Wednesday, PM1
90 | KK | DF2 | 7.3.2.1 7.3.2.2 7.2.3.3 | 16 |  | T | MAC | This MSB/LSB retransmission bits are only defined for Blk-ACK, not for all other ACKs (Imm-ACK, Dly-Ack, and Imp-ACK). Is it possible or necessary for ACKs other than Blk-ACK to support MSB/LSB retransmission? |  | Withdrawn | C
91 | RJS | DF3 | 7.2.1.4 & 12.4.3.8 | 14 & 129 |  | T | MAC/PHY | Two incompatible aggregate ack mechanisms are being defined, one in the MAC section and one in the AV PHY section. | Provide a single aggregate ack mechanism | Reject, the directional ACK provides low overhead because the LRP is used for ACK'ing HRP packets. The LRP is used because the application of streaming uncompressed video is highly asymmetric. | C
92 | RJS | DF3 | 8.7a & 12.4.4 | 25 & 130 |  | T | MAC/PHY | Three incompatible aggregation techniques are defined, two in the MAC section (8.7a) and one in the AV PHY section (12.4.4) | Provide a single aggregation mechanism or at a minimum clarify the applicabilty of the MAC section to the PHYs. Perhaps standard aggregation is a special case of low latency aggregation. | No technical change. The aggregation methods have different purposes. Add an editorial descritpion of why the two methods are used to clause 5. | C
93 | RJS | DF3 | 8.8.3b | 28 | 6 | T | MAC | It is not clear whether the requirement is that retransmitted frames be sent in the next frame AND at the head of the frame or whether the requirement is that IF the retransmitted frames are sent in the next frame that they be placed at the head of the frame. | Clarify the requirement. I suspect the intent was to require immediate retransmission. | Resolve as indicated in 15-08-0326-01 | C
94 | RJS | DF3 | 8.8.3b | 28 | 3 | T | MAC | There are no in-order delivery requirements in the described block ack mechanism other than "The destination transfers consecutive valid subframes to the FCSL." which from the context applies to a single aggregate frame only. | Clarify in-order delivery requirements. Address buffering requirements in receiver, retention of later (higher sequence number) frames until retransmission of earlier (lower sequence number) frames completes successfully, timeouts or other mechanisms to handle cases where retransmission frails. | Resolve as indicated in 15-08-0319-03. | C
95 | RJS | DF3 | 8.7a.2 | 27 | 9 | T | MAC | The in-order delivery requirements for low latency aggregation do not address retransmission failure. | Define behavior for the case where retransmission fails (maximum retransmits exceeded) for a particular MSDU. | Resolve as indicated in 15-08-0326-01, no change required. | C
96 | AYK |  | General | 0 | 0 | T |  | Three PHY modes are redundant, especially having two similar OFDM modes. This will create market confusion. Devices from different vendors will not interoperate. | Remove at least one of the OFDM modes, or preferably leave only one OFDM PHY mode in the draft. | Reject | C
97 | AYK |  | General | 0 | 0 | T |  | There is no common mode that is mandatory for all devices - how is interoperability going to work | Define a mandatory common mode that all devices must support. Broadcast beacons in this mode. | Resolve as indicated in 15-08-0335-00 | C
98 | AYK |  | 12.4.5.1 | 136 | 44 | T |  | This is the 3rd transmit mask defined in the draft, and it is different from the other masks significantly. The transmit mask defines interference limits from one network to another one. There may be interference from SC network to the AV-PHY network and vice versa. The mask must be the same. | Define a single transmit mask for all PHY modes that every transmissio must comply with. | Reject: Three PHY modes have been provided to address different use cases in a way that allows low power, low cost devices. Because of this, the spectral mask that can be readily achieved is different for each of the three PHYs. In addition, due to the use of directional antennas, the interference from nearby networks is significantly less than systems with near omni transmit patterns. Thus the requirements for the transmit masks are more relaxed. | C
99 | AYK |  | 12.4.5.1 | 136 | 41 | T |  | Video bandwidth is not defined for transmit mask measurement. | Define a video bandwidth of 1/10 of resolution bandwidth. | Add to the text that the video bandwidth is 300 kHz. | C
100 | AYK |  | 12.2.8.4 | 73 | 41 | T |  | Transmit mask measurement parameters are not defined - define resolution bandwidth to 3MHz and video bandwidth to 1/10 of the resolution bandwidht | as in commnet | Resolve as indicated in 15-08-0364-01. | C
101 | AYK |  | 12.3.4.1 | 104 | 28 | T |  | Transmit mask meausrment parameters definition are refered to FCC part 15. Part 15 has many measurements defined, can it be specific to which one we are refering? | Define resolution bandwidth and video band width in the text. | Resolve as indicated in 15-08-0364-01. | C
102 | AYK |  | 12.2.8.3 | 73 | 27 | T |  | EVM measurement is extermely fuzzy, It is not clear what is an "ideal receiver", it is not clear how averaging is being done. | Define the receiver and the measurement in an explicit way - take 802.11 clause 17.3.9.7 as an example. | Resolve as indicated in 15-08-0364-01. | C
103 | AYK |  | 12.4.1.1 | 108 | 42 | T |  | The channelization scheme here is a repeat (albeit in a different format) of the table in 12.2.7.2. No channelization is defined for HIS PHY | Move channelizaiton to clause 12.1 | Accept | C
104 | AYK |  | 12.4.2 | 111 | 45 | T |  | Sampling rate of the AV-PHY is different from that of the HIS PHY and is unrelated to the chip rate of the SC-PHY | change the sample rate of the AV-PHY to 2592MHz. | Reject: The sampling rate for the AV PHY was selected to make it easy to synthesize with the crystal oscillators that are typically available in consumer electronic AV devices. | C
105 | AYK |  | 12.2 | 41 | 0 | T |  | PCLP transmit and receive procedure are not defined for SC PHY | Define transmit and receive procedures for this PHY | Reject: 802.15.3 does not have a PLCP. | C
106 | AYK |  | 12.3 | 77 | 0 | T |  | PLCP transmit and receive procedure are not defined for HIS PHY | Define transmit and receive procedures for HSI PHY | Reject: 802.15.3 does not have a PLCP. | C
107 | AYK |  | 12.4 | 107 | 37 | T |  | PLCP transmit and receive procedure are not defined for AV-PHY | Define transmit and receive procedures for AV-PHY | Reject: 802.15.3 does not have a PLCP. | C
108 | AYK |  | 12.2.3 | 58 | 46 | T |  | Use of Golay sequences in preamble is not better than using m-sequences. The m-sequences provides better timing estimation due to larger zero autocorrelation zone. They can also easily provide channel estimation without the need for two types of sequences. There are algorithms to perform cross correlation with m-sequences with the same complexity to that required by Golay sequences. | Replace Golay sequences with m-sequences. | Reject: Golay sequences provide sufficient performance with lower complexity than the m-sequences. M-sequence does not have a zero correlation zone. Golay code has a zero correlation zone. Matched filter implementation is the same complexity. A cross correlation filter for Golay would have lower complexity. | C
109 | AYK |  | 12.3.1.10 | 89 | 6 | T |  | Number of modes is too large. | Number of PCES modes should be reduced to 1, number of CP modes should be reduced to 1 | A) Reduce CP mode to 1 bit (0 - CP = 64, 1 - CP = 128). Further study is needed to see the possibility of removing CP = 128; B) Reduce PCES to 1 bit (0 - Infinity, 1 – 128) | C
110 | AYK |  | 12.3.1.10.4 | 90 | 8 | T |  | Header controls CP of the symbol following the header decoding. This may cause problems when implementing because of the need to buffer the data untill the length of the CP is know. | Define that CP affects the cylic prefix of the second symbol in the Data field | Withdrawn | C
111 | AYK |  | 12.3.1.1 | 79 | 33 | T |  | Freame format is different than one from SC - there is no need for that, unify format and header fields - introducing some mininla redundancy | as in commnet | HSI frame format is the same as for the SC except for the PHY header. | C |  |  |  | Wednesday
112 | AYK |  | 12.3.1.10.79 | 92 | 3 | T |  | Aggregation shceme is different from than of SC (12.2.4.3.2( | Unify into a single scheme | HSI-OFDM uses the same aggregation as the SC PHY. Add text that indicates this. | C
113 | AYK |  | 12.2..1.1 | 45 | 15 | T |  | OOK provides no benfit when mask compliancs is requried at the transmit and operation with devices at neighboring channels is needed | remove OOK modulation | Resolve as indicated in 15-08-0342-00. | C |  |  |  | Wednesday
114 | AYK |  | 12.2.1.1. | 45 | 19 | T |  | DRB provides no benefit | remove DRB from the standard. | Reject: DRB (now DAMI) provides throughput improvement with very low power use. | C
115 | AYK |  | 12.1.5 |  |  | T |  | Having 3 PHY modes generates an unnecessary burden of multiple beacons when a MMC supports other than SC mode | Define a single common mode, or remove all PHYs but one | Resolve as indicated in 15-08-0335-00 | C
116 | AYK |  |  |  |  | T | Beamforming | OFDM AV PHY does not define beamforming to match Section 8.16.1 | Define beamforming inside 12.4 that matches section 8.16.1 or remove OFDM AV PHY | Resolve as indicated in 15-08-0355-00. Add text that AV PHY uses same beam forming method, but not extended beacons or modified CAP. | C
117 | AYK |  |  |  |  | T | Beamforming | Omni transmission is undefined for SC PHY and OFDM HIS PHY | Define method for omni transmission for these PHYs | Resolve as indicated in 15-08-0355-00 | C
118 | AYK |  |  |  |  | T | Beamforming | Beamforming flow is not described in details. Some elements may be missing, for example - mapping of beamforming feedback to actual transmission | Map all elements of beamforming flow (according to 8.16.1) to PHY operations (in section 12) | Resolve as indicated in 15-08-0355-00 | C
119 | AYK |  | 7.5.11.2 |  |  | T | Beamforming | Beamforming response is not completely defined | Define all fields | Resolve as indicated in 15-08-0355-00 | C
120 | AYK | 3 | 8.6.11.1 |  |  | T | Beamforming | Beamforming measurements are not well defined and their mapping to beamforming response is not defined | Define | Resolve as indicated in 15-08-0355-00 | C
121 | AYK | 3 |  |  |  | T | Beamforming | Beam training sequences are not defined for either PHY | Define | Resolve as indicated in 15-08-0355-00 | C
122 | AYK |  |  |  |  | T | SC-PHY | Common rate is special in its very low rate relatively for any other rate. The CR is unefficient but its use is allowed for data transmission | Limit use of CR only for control and omni transmissions | Add text to 12.2 that says “CR should be used only for command frames and omni-directional transmissions.” | C
123 | AYK |  | 12.2.9.5 |  |  | T |  | Reference to minimum sensitivity as in 12.2.9.2 is ambigious since that section provides numbers only for the reference sensitivity | Remove reference to 12.2.9.2 as the true sensitivity is sought (but how can this be tested?) | Eliminate the word "reference"with respect to sensitivity in the subclause. | C
124 | ST | DF3 | 8.16.1.1 | 31 | 28 | T | Beamforming | As stated beamforming between DEV and PNC needs M superframes. It may be too long for application's latency limitation or too slow in relation to channel variances. It is not clear while one superframe may contain only N sequences and the entire process needs M superframes. | The algorithm should be scalable to allow full completion in one superframe if the PNC and DEV have a capability to allocate enough time for that. | Resolve as indicated in 15-08-0355-00 | C
125 | ST | DF3 | 8.16.1.2 | 34 | 6 | T | Beamforming | As stated beamforming between DEVs needs M superframes. It may be too long for application's latency limitation or too slow in relation to channel variances. It is not clear while one superframe may contain only N sequences and the entire process needs M superframes. | The algorithm should be scalable to allow full completion in one superframe if the PNC and DEV have a capability to allocate enough time for that. | Resolve as indicated in 15-08-0355-00 | C
126 | ST | DF3 | 8.16.1.2 | 33 | 7 | T | Beamforming | "… beam forming training sequences, as described in <xref 12.4.6>" There is no such a sequence defined | Define beamforming training sequence | Resolve as indicated in 15-08-0355-00 | C
127 | ST | DF3 | 7.5.11.2 | 20 | 35 | T | Beamforming | The Transmit Beam Number field <missing definition> | Please define | Resolve as indicated in 15-08-0355-00 | C
128 | ST | DF3 | 7.5.11.2 | 20 | 38 | T | Beamforming | The Received Beam Number field <missing definition> | Please define | Resolve as indicated in 15-08-0355-00 | C
129 | ST | DF3 | 7.5.11.2 | 20 | 40 | T | Beamforming | The Beam Status Information field <missing definition> | Please define | Resolve as indicated in 15-08-0355-00 | C
130 | ST | DF3 | 12.4.4.2 | 134 | 40 | T |  | "The Integrity Code field is defined in 7.2.7.5." The subframe format does not contain the related nonce fields needed to calculate the Integrity code | Define the related fields and clarify the subframe integrity code calculation | Change as described in 15-08-0253-03 | C
131 | ST | DF3 | 8.4.1 | 24 | 19 | T |  | For the HSI mmWave PHY mode they are listed in <TBD> | Define TBD | Resolve as indicated in comment 83. | C |  |  |  | Wednesday
132 | ST | DF3 | 8.4.2 | 24 | 21 | T |  | There are different factors that implies the CSMA/CA mechanism in the 60GHz band. The current definition does not address such important things like directed antennas, beamforming etc. It may happen that the CSMA/CA need changes to make it work in 60GHz band | Provide verified definition for CSMA/CA like mechnism for 60GHz band | Reject: No solution is provided. | C
133 | ST | DF3 |  |  |  | T |  | General comment. There are 8 TBDs found in the draft | Release the TBDs | Resolve as indicated in comment 83. | C
134 | ST | DF3 | 8.7a.1 | 25 | 21 | T |  | Standard aggregation (MAC feature) is defined for the SC Phy only. There is no feasibility issue seen to limit supporting of this feature to this PHY only. The MAC features should be PHY independent | If this feature is useful extend it to all PHYs else remove it | Reject: No, AV aggregation and SC use different frame format. No change | C
135 | ST | DF3 | 8.7a.2 | 26 | 47 | T |  | Low latency aggregation (MAC feature) is defined for the SC Phy only. There is no feasibility issue seen to limit supporting of this feature to this PHY only. The MAC features should be PHY independent | If this feature is useful extend it to all PHYs else remove it | Reject, No, AV aggregation and SC use different frame format. No change | C
136 | ST | DF3 | 12.3.1.11 | 93 | 28 | T |  | No defintion of the MAC header of the HSI PHY | Define the MAC header | Add a cross reference to the MAC header subclause. | C
137 | ST | DF3 | 12.3.1.12 | 94 | 4 | T |  | No defintion of the MAC subheader of the HSI PHY | Define the MAC subheader | Add a cross reference to the MAC header subclause. | C
138 | ST | DF3 | 12.4.4 | 130 | 33 | T |  | There is a lot of fields defined in the MAC header of the AV PHY. At least part of the fields is not mentioned in the MAC functional description thus leaving those fileld useless | Define related functionality in the caluse 8. MAC functional description or remove the fields | Change as described in 15-08-0253-03 | C
139 | ST | DF3 | General |  |  | T |  | The spec draft defines the MAC header as part of PHY definition. Such an approach complicates the spec and more important significantly increases complexity of implementation, verification, and certification. There is no limitation seen to unify the MAC header making it PHY independent thus extending the useful MAC features to any PHY | Unify the MAC header definition and move it to the clause 7. | Accept | C
140 | ST | DF3 | General |  |  | T |  | The spec draft defines the MAC features dependent on the PHY. It makes each MAC PHY dependent, and supporting separate set of features. As a result there is no MAC compatibility and the spec effectively becomes set of few separate specs. Such an approach complicates the spec and more important significantly increases complexity of implementation, verification, and certification. There is no limitation seen to unify the MAC features. | Unify definition of the MAC functionality and make it independent on the supporting PHY. Unify the MPDU formats. | Reject, No, AV aggregation and SC use different frame format. No change | C
141 | AS | DF3 | 12 | 40 |  | T |  | The two OFDM PHYs are very muchthe same, it is not compatible and cleates confusion in the market | Merge or eliminate one of the two OFDM PHYs | Reject. | C
142 | AS | DF3 | 12 | 40 |  | T |  | UEP is a function of video transmission and specific to the application, We are not tasked to develop applications, rather a general purpuse PHY for all applications. Otherwise, we need to introduce video and audio compression to the spec. | Remove UEB from the PHY. Alternatively, push UEP to MAC or applications layer, remove from the PHY section. | Reject: UEP needs to be in the PHY to get its advantage. No change. | C
143 | AS | DF3 | 12 | 40 |  | T | Beamforming | Why there are multiple beamforming algorithms proposed. What are the similarities, differences and how to determine whichone to implement | Remove or add one beamforming scheme for all modes | Resolve as indicated in 15-08-0355-00 | C
144 | AS | DF3 | 12 | 40 |  | T |  | Too Many MCSs optional in OFDM and SC. | What is the mandatory MCS that all device can connect | Reject: No specific solution. | C
145 | ZL | DF3 | 12.2.1.7 | 51 | 1-18 | T | PHY | DAMI employs a single-sideband signal along with two low-power pilots. It is not clear from the description here. | Modified text submission to clearly indicate the SSB and the pilot. | Change as described in 15-08-0311-02. | C
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218

## Editorial issues
| Color Codes |  |  |  |  | W | Changes approved | This Sheet uses autoformat for cell colors except for closed. (Excel only handles 3 conditional formats)
|  | C | Closed |  |  | A | Assigned
|  | P | Proposal pending |  |  | O | Open, not assigned | Last Issue Number | 65
Issue Number | Commenter's Initials | Draft Version Number | Clause number e.g., 8.10.2 | Page number e.g., 1-1130, etc. | Line number e.g., 1-54 | Type of comments (E/e/T/t) | Class of Problem | Comment/Rationale (Issue and reasoning behind it.) | Recommended change (What change(s) it would take to make this clause acceptable.) | Disposition/Rebuttal (Do not write here during ballot phase; this is for comment resolution phase.) | Resolution Status O,A,W,P,C | Date Entered | Date Completed | Asignee | Issue Status | Resolution Status
1 | IL | DF3 | 12.3.1 | 77 | 51 | E | PHY | HSI-OFDM: Remove title 12.3.1 and renumber the HSI-OFDM accordingly (agreed upon during last meeting) |  | Work with Ismail to make the format the clause in a more logical fashion. | C |  |  | JPKG
2 | IL | DF3 | 12.3.1.7 | 88 | 1:30 | E | PHY | HSI-OFDM: Table 138 should be removed (agreed upon during last meeting) |  | Remove Table 138. | C |  |  | JPKG | In DF4
3 | IL | DF3 | 12.3.2.7.1 | 102 | 52 | E | PHY | HSI-OFDM: the pilots subcarriers for m = 3 is specified twice. |  | Delete extra pilot | C |  |  | JPKG
4 | IL | DF3 | 12.3.2.2 | 95 | 2 | E | PHY | HSI-OFDM: 16 bits scrambler seed is defined instead of 15 |  | Change as indicated | C |  |  | JPKG | In DF4
5 | IL | DF3 | 12.2.2.1.1 | 48 | 9:13 | E | PHY | SC: p/2-BPSK explanation is not clear |  | Add editorial clarification | C |  |  | JPKG
6 | IL | DF3 | 12.2.2.1.3 | 48 |  | E | PHY | SC: Combine pi/2-BPSK, Pre-coded (G)MSK in one sublcause |  | Change as indicated | C |  |  | JPKG
7 | JAT | DF2 | 6.3.21 |  | 50-51 | E |  | SupportedAntennaNumber should probably be SupportedNumAntennas and defined as “number of supported antennas” | Modify the text to clarify what is meant (e.g., as in comment). | Change to SupportedNumAntennas and definition | C |  |  | JPKG | In DF4
8 | MS, RY | DF2 | 8.2.5 | 25 | 53 | E | MAC | Need to clarify the difference(s) between OOK PNC and SC PNC in the draft. |  | Updates that clarify the usage of OOK PNC should handle this. | C |  |  | JPKG
9 | SK | DF3 | 12.2.3.4.1 | 65 | 6 | E | MAC | ACK/NACK or msb ACK field is used for msbs of the subframe | Replace if a subframe was" in line 6 with "if the msbs of the subframe were" and move the text from line 4-8 to line 11 | Rewrite for two cases, first is EEP, second is for UEP. | C |  |  | JPKG
10 | SK | DF3 | 12.2.3.3 | 60 | 30-31 | E |  | The sentence in line 30-31 is incomplete | Delete "Show" | Change as indicated. | C |  |  | JPKG
11 | JSOH | DF3 | 12.2.2.4 | 58 | 22 | E | PHY | The sentence ends incompletely | correct the last part : "as illustrated in Fig. 196" | Change as indicated. Also, similar error in line 1, same page. Search draft for similar occurances. | C |  |  | JPKG
12 | JPKG | DF3 | 12.4.3 | 124 |  | E | AV PHY | Clarify the usage of AV PHY HCS | Change as described in 15-08-0253-00 | Change as indicated | C |  |  | JPKG
13 | JPKG | DF3 | 12.4.2 | 112 | 50 | E | AV PHY | The figure doesn't match the description, should be RS encoder and outer interleaver instead of outer encoder | Change as described in 15-08-0253-00 | Change as indicated | C |  |  | JPKG
14 | JPKG | DF3 | 12.2.4.7 | 115 | 7 | E | AV PHY | The description of the outer encoder is confusing. | Change as described in 15-08-0253-00 | Change as indicated | C |  |  | JPKG
15 | JPKG | DF3 | 12.2.4.10.2 | 117 | 46 | E | AV PHY | Change “Station” to “DEV” in two places | Change as described in 15-08-0253-00 | Change as indicated | C |  |  | JPKG
16 | JPKG | DF3 | 12.4.2.12 | 122 | 53 | E | AV PHY | In Table 166, it should just be “16-QAM” | Change as described in 15-08-0253-00 | Change as indicated | C |  |  | JPKG
17 | JPKG | DF3 | 12.4.3.4 | 127 | 36 | E | AV PHY | The order of the paragraphs is backwards, change to match the order used elsewhere. | Change as indicated. | Change as indicated | C |  |  | JPKG
18 | KK | DF3 | 8.7a 8.8 | 25-28 |  | E | MAC | The referred section numbers beginning with "0.1." in the context should be "12.2". | Fix the cross references. | Change as indicated | C |  |  | JPKG
19 | RJS | DF3 | 12.4.4.1 | 44 |  | E | MAC | The extended MAC header is defined in the PHY section | Define the extended MAC header in the MAC frame format section | Change as indicated | C |  |  | JPKG
20 | AYK |  | 12 | General |  | E | PHY | The format of each of the 3 PHY sections is different from the other ones | Define a single format with the same subclauses in each PHY accept where a difference is necessary. | The editors will re-format the subclauses to share format as much as possible. | C |  |  | JPKG
21 | AYK |  | 12.3.1.5 | 85 | 9 | E | PHY | Order of segments in frame confusing | Reorder with earlier times on the left. | Reject: The order of segements in all frame figures in the draft and 802.15.3 is earliest time on the right, not the left. Changing it here would not be consistent with the rest of the standard. | C |  |  | JPKG
22 | AYK |  | 5.5.1 |  |  | E | SC PHY | Description of SC PHY is out of date and is not in correspondence to 12.2.2.2. Reminiscent of convolutional coding is mentioned, for example. | Revise 5.5.1 | Rewrite 5 to match more closely the current PHY descriptions. | C |  |  | JPKG
23 | ZL | DF3 | 12.2 | 43 | 30 | E | SC PHY | change DRB to DAMI (in the table) | Change as indicated. | Change as indicated | C |  |  | JPKG
24 | ZL | DF3 | 12.2.1.1 | 45 | 19 | E | SC PHY | change DRB1 to DAMI1 (in the table) | Change as indicated. | Change as indicated | C |  |  | JPKG
25 | JPKG | DF3 | 12.4.3 | 124 |  | E | AV PHY | Move the modulation description of the directional header and payload to one location, probably at the beginning of 12.4.3.8 | Change as indicated. | Change as indicated | C |  |  | JPKG
26 | JPKG | DF3 | 12 | various |  | E | PHY | The frame format pictures are messed up in the draft. Simplify them and remove redundancies. | Change as indicated. | Change as indicated | C |  |  | JPKG
27 | IL | DF2 |  | 12 |  | E | MAC | In Figure 2, the fields are backwards. | Change the order of the fields to match the convention | Change as indicated | C |  |  | JPKG
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123

## Arrived late
| Color Codes |  |  |  |  | W | Changes approved | This Sheet uses autoformat for cell colors except for closed. (Excel only handles 3 conditional formats)
|  | C | Closed |  |  | A | Assigned
|  | P | Proposal pending |  |  | O | Open, not assigned | Last Issue Number | 65
Issue Number | Commenter's Initials | Draft Version Number | Clause number e.g., 8.10.2 | Page number e.g., 1-1130, etc. | Line number e.g., 1-54 | Type of comments (E/e/T/t) | Class of Problem | Comment/Rationale (Issue and reasoning behind it.) | Recommended change (What change(s) it would take to make this clause acceptable.) | Disposition/Rebuttal (Do not write here during ballot phase; this is for comment resolution phase.) | Resolution Status O,A,W,P,C | Date Entered | Date Completed | Asignee | Issue Status | Resolution Status
1 | AB | DF3 | 7.5.11.2 8.16.1 | 20 30-34 | 17 | T | Beamforming | Provide an alternate means to feedback the beamforming response. In the current text, an index to a beanforming vector is communicated. The alternate method should allow to feedback explicitely the transmit beamforming vector. This provides significant improvement in multipath scenarios | Add some text in 7.5.11.2 and 8.16.1 so that the Beam forming response can have an alternate format. The computed TX beamforming vector can be transmitted explicitely (or, if the codebook approach is adopted, as a linear combination of codebook words) | Resolve as indicated in 15-08-0355-00 | C |  |  | Ismail Lakkis |  |  | ZL = lan@nict.go.jp
2 | HZ | DF3 | 12.2.4.1 | 62 | 5-8 | T | PHY | there are 4 possible PW lengths, how to signal this info in PHY header? | Use 2 bits to specify PW lengths. | Resolve as indicated in 15-08-0362-02. | C | [5 empty] | ST = solomon.trainin@intel.com
3 | HZ | DF3 | 12.2 | 43 | 37 | T | PHY | Here the spec mentions "with an option to substitude PW with CP", but CP is SC mode is not specified in DF3 at all, it was removed in DF3 . | remove this sentence, | Accept | C | [5 empty] | JY = james.yee@mediatek.com
4 | HZ | DF3 | 12.2.2.1.1 | 48 | 9-13 | T | PHY | The description on pi/2 BPSK and pi/2 QPSK is unclear,better to give math expressions. Also, is the rotation initiated from 1 or j? Current text can have multiple interpretations. | Clarify | Resolve as described in comment 64. | C | [5 empty] | EK = Edwin Kwon = cy.kwon@samsung.com
5 | HZ | DF3 | 12.2.2.1.3 | 48 |  | T | PHY | Figure 189, more description in terms of equations is required to equate pi/2 BPSK modulator and GMSK modulator. For example initial phase of the chip level rotator. Also, the differential operation (xor) as currently specified is incorrect. If g_n is the input to the GMSK modulator then in the real field g_n = d_n x d_(n-1) which is inverse of xor. In general, complete specification through equations would help rule out ambiguity |  | Resolve as indicated in 15-08-0362-02. | C | [5 empty] | Pyo = cwpyo@nict.go.jp
6 | HZ | DF3 | 12.2.2.1 | 48 | 5 | T | PHY | Would be useful in general to describe all the modulations precisely through equations. Current text has multiple interpretations |  | Resolve as indicated in 15-08-0362-02. | C | [5 empty] | Sum = sum@nict.go.jp
7 | HZ | DF3 | 12.2.2.3.1 | 55 | 30-50 | T | PHY | What are the settings on D and W on generating the Golay codes specified in DF3? | Give D and W for all the Golays codes provided in the draft spec. | Reject. The Golay code sequences are already specified in the DF3, pages 85, 86, 134, 135 and 136. | C | [5 empty] | James Gilb = last name at ieee dot org
8 | HZ | DF3 | 12.2.4 | 61 | 23 | T | PHY | In step b) of line 23, "format the frame header into bursts", is PW inserted in each burst in header? If yes, how to specify the PW length of the header. If No, clearly state that PW length=0 for header. | as in comment | Resolve as indicated in 15-08-0362-02. | C | [5 empty] | IL = Ismail Lakkis = ilakkis@tensorcom.com
9 | HZ | DF3 | 12.2.4 | 61 | 26-54 | T | PHY | In Fig 199, Burst builder is before mapper, while in Fig207 (Payload), Burst builder is after mapper. | unitfy, move burst build after mapper | Resolve as indicated in 15-08-0362-02. | C | [5 empty] | H. Harada = harada@nict.go.jp
10 | HZ | DF3 | 12.2.4 | 61 | 24 | T | PHY | What does step c) mean? Preamble and PCES are not related to header | remove step c) | Accept | C | [5 empty] | Shu Kato = shu.kato@nict.go.jp
11 | HZ | DF3 | 12.2.5 | 68 | 10-22 | T | PHY | For payload construction procedure, should PW and PCES also modulated using pi/2 BPSK before their insertions? | add the text saying that PCES and PW are modulated using pi/2 BPSK | Accept. Refer to 15-08-0362-02 for the wordking. | C | [5 empty] | Jisung Oh = jisung0714.oh@samsung.com
12 | HZ | DF3 | 12.2.5.5.1 | 70 | 7-10 | T | PHY | There is no definition on the length of subblock. | define the length of subblock | Remove subblock | C | [5 empty] | Tuncer Baykas = tbaykas@ieee.org
13 | HZ | DF3 | 12.3.1.5 | 85 | 1-10 | T | PHY | Figures 187 and 212 should be drawn with the same convention. | Moving from left to right, first SYNC, then SFD, CES. | Resolve as indicated in 15-08-0362-02. | C | [5 empty] | SKY = Su Khiong = sk.yong@samsung.com
14 | HZ | DF3 | 12.2.2.2.1 | 51 | 27 | T | PHY | Sec. 12.2.2.2.1 -- Generator polynomials are not narrow-sense. Does not make a difference to performance, but was this specifically intended? |  | Change the equation for g(x) to be from k=1 to 16 and x- alpha^k | C | [5 empty] | Makto Noda = MakatoB.Noda@jp.sony.com
15 | HZ | DF3 | 12.3.2.3.1 | 95 | 35 | T | PHY | Sec. 12.3.2.3.1 -- Generator polynomials are not narrow-sense. Does not make a difference to performance, but was this specifically intended? |  | Change the equation for g(x) to be from k=1 to 16 and x- alpha^k | C | [5 empty] | JAT = Jason Trachewsky = jat@broadcom.com
16 | HZ | DF3 | 12.3.2.5.3 | 101 | 5 | T | PHY | The given q sequence is of length 11, rather than 12 | redefine q with 12 elements. | Add -1 to the right of the sequence | C | [5 empty] | MS, RY = Michael Sim Raymond Yu
17 | HZ | DF3 | 12.3.2.3.2 | 96 | 50 | T | PHY | The HSI outer interleaver is not specified | give detailed description of the out interleaver | Resolve as indicated in 15-08-0377-00, change read to Reed, add “mod” between and and is and change operator to function. | C | [5 empty] | HRS = Huai Rong Shao
18 | HZ | DF3 | 12.3.2.3.4 | 97 | 50 | T | PHY | Bit interleaver is OPTIONAL, but how to signal it in header? Also, is bit interleaver mandatory or optional or forbidden in header? If bit interleaver is optional in header, how to signal it in preamble? | Clarify | Add text that indicates that interleaving the header is forbidden, use a reserved bit in the PHY header to indicate that the body does or does no use the interleaver. | C | [5 empty] | JSOH = Jisung Oh
19 | HZ | DF3 | 12.3.2.7 | 102 | 24 | T | PHY | In table 146, 2nd row and 3rd column, the upper limit tone index for null subcarriers is 255 rather than 256 | change to 255 | Accept | C | [5 empty] | GB = Gal Basson
20 | HZ | DF3 | 12.3.1.4 | 84 | 8 | T | PHY | In table 132, 3rd row and 3rd column, Should be 216 rather than 236, for RS(232,216)? In page 80 line 22, the spec says RS(232,216). Which RS coding rate is defined here? | unify the definition | Accept in principle, change RS(232,216) to be RS(252, 236) where it appears in the draft. | C | [5 empty] | YK = Yasunao Katayama
21 | HZ | DF3 | 12.3.2.3 | 95 | 20 | T | PHY | RS(232,216) rahter than "RS(253,236)"? In page 80 line 22, the spec says RS(232,216). Which RS coding rate is defined here? | unify the definition | Accept in principle, change RS(232,216) to be RS(252, 236) where it appears in the draft. | C | [5 empty] | AYK = Assaf Kasher
22 | HZ | DF3 | 12.3.1.2 | 82 | 11 | T | PHY | In table 130, last row and last column, number of padding bits for the case SF=1 in header is not correct. |  | Remove the column “pad bits” from the table. | C
23 | HZ | DF3 | 12.3.1.8 | 88 | 1-30 | T | PHY | Table 138 is not consistent with table 137, the conditions should be defined by combining CES length and Header rate . |  | Remove table 138. | C
24 | HZ | DF3 | 12.3.1.6 | 86 | 50 | T | PHY | Where is the filter g defined in DF3? If it is the same as that in DF1, then the index of g filter should be -12:12, rather than "-13:13" as in DF1. But in general, g filter is NOT necessary in the preamble. It is just a matter of power scaling issue, which can be done using simple baseband scaling factor, and should be completely an implementation issue. The mandatory g filter in the standard will only increase the receiver channel estimation complexity, and gives no performance improvement. | remove the g filter from the spec. | Accept | C
25 | HZ | DF3 | 12.2.4.3.1 | 64 | 41-54 | T | PHY | Currently we allow different subframes in the aggregated frame being modulated using different MCSs. That will unnecessarily increase the receiver implementation complexity, and in some cases may lead to catastrophic performance drop regarding error rate, due to the MCS switches over subframes. | We may need to reconsider the impact of MCS switching over aggregated subframes, on the receiver designs, and probably use the same MCS all through the aggreagated packet (like AMPDU in 802.11n), and only signal the unified MCS by PHY header. | Reject. Since our aggregation is integrated msb and lsb subframes, switching the MCs over subrames is unavoidable. | C
26 | HZ | DF3 | 12.2.3.2 | 60 | 6-9 | T | PHY | This paragraph needs elaboration. How is SFD2 defined to indicate CES length. Is it reliable enough to only use SFD1 as delimiter, regarding frame timing reference detection? | Clarify | Resolve as indicated in 15-08-0362-02. | C
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146 | AB
147 | HZ
148 | HZ
149 | HZ
150 | HZ
151 | HZ
152 | HZ
153 | HZ
154 | HZ
155 | HZ
156 | HZ
157 | HZ
158 | HZ
159 | HZ
160 | HZ
161 | HZ
162 | HZ
163 | HZ
164 | HZ
165 | HZ
166 | HZ
167 | HZ
168 | HZ
169 | HZ
170 | HZ
171 | HZ
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218

## Score Sheet
Technical issues
|  |  | % | By assignee, all not closed.
Open | O | 0 | 0% | JPKG | 0
Assigned | A | 0 | 0% | Tuncer Baykas | 0
Written | W | 0 | 0% | Ismail Lakkis | 0
Closed | C | 145 | 100% | Takahashi | 0
Withdrawn | Z | 0 | 0% | KK | 0
Unsatisfied | U | 0 | 0% | Gal Basson | 0
Total # of Issues |  | 145 | 100% |  | 0
Problem Class |  | Class Total
PHY |  | 23
MAC |  | 19
Beam forming |  | 21
Frame formats |  | 0
Synch |  | 0
Table |  | 0
CTA |  | 0
Frame Format |  | 0
Frame Length |  | 0
Total |  | 63
Technical and Editorial Issues
|  |  | % | By assignee, all not closed.
Open | O | 0 | 0% | JPKG | 0
Assigned | A | 0 | 0% |  | 0
Written | W | 0 | 0% |  | 0
Closed | C | 172 | 100% |  | 0
Withdrawn | Z | 0 | 0% |  | 0
Unsatisfied | U | 0 | 0% |  | 0
Total # of Issues |  | 172 | 100% |  | 0
Arrived late issues
%
Open | O | 0 | 0%
Assigned | A | 0 | 0%
Written | W | 0 | 0%
Closed | C | 26 | 100%
Withdrawn | Z | 0 | 0%
Unsatisfied | U | 0 | 0%
Total # of Issues |  | 26 | 100%