## Cover
2008-05-12 |  | IEEE P802.15.3c-08/291r0
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | Resolution of old comments from Orlando meeting
Date Submitted | May, 2008
Source | Chang-woo Pyo | Voice: +81-46-847-5074
| NICT | Fax: +81-46-847-5110
| 3-4 Hikari-no-oka, Yokosuka | E-mail: cwpyo@nict.go.jp
, Kanagawa 239-0847, Japan
Re:
Abstract
Purpose | [This document provides a home for all comments, open issues and suggested resolutions concerning the TG3c draft DF3. In addition, this document will keep a running status of the disposition of the suggested resolutions.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Summary
Summary of remaining comments from Orlando
There are 17 comments left from Orlando meeting
4 comments have tentative answers
Number 3: channel probing comment to be resolved as indicated in 08-225-1
Number 4, 7: UEP comments to be resolved as indicated in 08-225-1
Number 12: TDE comment to be resolved as that no change of the frame format is needed
4 beamforming related comments will be resolved as indicated in the updated beamforming text
2 UEP comments from ETRI are still open
2 MAC comments from KK are still open
1 OOK related PHY comment is still open
1 Unify SC/HSI preamble PHY comment is still open
1 common rate related comment is still open
1 merging two OFDM comment is still open
1 redundant from speed sheet

## OI_List_Srtd
| Color Codes |  |  |  |  | W | Changes approved | This Sheet uses autoformat for cell colors except for closed. (Excel only handles 3 conditional formats)
|  | C | Closed |  |  | A | Assigned
|  | P | Proposal pending |  |  | O | Open, not assigned | Last Issue Number | #REF!
Issue Number | Commenter's Initials | Draft Version Number | Clause number e.g., 8.10.2 | Page number e.g., 1-1130, etc. | Line number e.g., 1-54 | Type of comments (E/e/T/t) | Class of Problem | Comment/Rationale (Issue and reasoning behind it.) | Recommended change (What change(s) it would take to make this clause acceptable.) | Disposition/Rebuttal (Do not write here during ballot phase; this is for comment resolution phase.) | Resolution Status O,A,W,P,C | Date Entered | Date Completed | Asignee | Issue Status | Resolution Status
1 | JPKG | SC | 7.2.5a |  |  | T | MAC | Do we need reserved stream indices for beamforming and channel probing. | Pending, depending on if we need the stream index. |  | A |  |  | James Gilb, ZL |  |  | ZL = lan@nict.go.jp
2 | JPKG | SC | 7.4.23 |  |  | T | Beamforming | Do we need the IE? What is the correct information? What commands are necessary |  |  | A |  |  | Ismail Lakkis, Pyo, Jisung Oh |  |  | ST = solomon.trainin@intel.com
3 | JPKG | SC | 7.5.12.1 |  |  | T | Channel probing | What is the definition of the value of the Channel Status Information field? Can we use existing facilities in 802.15.3b to accomplish this? | NICT has suggested a solution as described in 08/225r1 | JPKG to create text | A |  |  | JPKG |  |  | JY = james.yee@mediatek.com
4 | JPKG | SC | 7.5.13 |  |  | T | UEP | Can this be done with an information element? Also, there are some updates to the frame format that need to be reviewed. | NICT has suggested a solution as described in 08/225r1 | Need information element, either capability or UEP IE TBD. | A |  |  | Edwin Kwon, Pyo |  |  | EK = Edwin Kwon = cy.kwon@samsung.com
5 | JPKG | SC | 8.16 |  |  | T | Beamforming | Work on a unified beamforming submission. |  |  | A |  |  | Ismail Lakkis, James Gilb, Shu Kato, Tuncer Baykas, Jisung Oh, Su Khiong |  |  | Pyo = cwpyo@nict.go.jp
6 | IL | SC/HSI | 12 |  |  | T | PHY | Can the SC and HSI PHY use a single preamble format? | Awaiting HSI-OFDM answer |  | A |  |  | Ismail Lakkis |  |  | Sum = sum@nict.go.jp
7 | ST | SC | 8.18 |  |  | T | UEP | There needs to be a way for the upper layer that is the source of data to say if the use of UEP is allowed for the data stream. | NICT has suggested a solution as described in 08/225r1 |  | A |  |  | Edwin Kwon, James Gilb, ZL, Pyo |  |  | James Gilb = last name at ieee dot org
8 | IL | SC | 8.19 |  |  | T | Beamforming | This is probably very efficient when both sides are sectorized. However, when one side is not, regular beamforming would need to be used. Keep this section inmind when reviewing beamforming. |  |  | A |  |  | Ismail Lakkis, James Gilb, Shu Kato, Tuncer Baykas, Jisung Oh, Su Khiong |  |  | IL = Ismail Lakkis = ilakkis@tensorcom.com
9 | IL | SC | 8.19 |  |  | T | Beamforming | This is probably very efficient when both sides are sectorized. However, when one side is not, regular beamforming would need to be used. Keep this section inmind when reviewing beamforming. |  |  | A |  |  | Ismail Lakkis, James Gilb, Shu Kato, Tuncer Baykas, Jisung Oh, Su Khiong |  |  | H. Harada = harada@nict.go.jp
10 | YK | DF1 | 7.5.12 12.2.4.3 | 23 63 |  | T | MAC | Need to have an indication for the position of the middle point which separates MSBs from LSBs. (According to DF1, it seems that the default color depth is 8 bits which consist of 4 bits of MSBs and 4 bits of LSBs.) | Presentation will be provided for this comment. | Discuss in Jacksonville | A | [5 empty] | Shu Kato = shu.kato@nict.go.jp
11 | YK | DF1 | 7.5.12 12.2.4.3 | 23 63 |  | T | MAC | To make UEP be optimized for various types of video formats, UEP procedure needs to be applicable not only for MSBs and LSBs but also other classifications, for example, luminance and chrominance and so on. | Presentation will be provided for this comment. | Discuss in Jacksonville | A | [5 empty] | Jisung Oh = jisung0714.oh@samsung.com
12 | TB | DF2 |  |  |  | T | PHY | How simple decision feedback equalization can be supported for SC PHY at high speeds. | SC can support TDE without change in the frame format |  | A |  |  | Tuncer Baykas |  |  | Tuncer Baykas = tbaykas@ieee.org
13 | EG, CSC, AB | DF2 | 12.3, 12.4 |  |  | T | PHY | Two different OFDM PHYs are not needed and are very costly for product development and implementation. | option 1 (preferred): merge the two OFDM PHYs into a single, harmonized one option 2 (worst case): remove 12.3 or 12.4 |  | O | [5 empty] | SKY = Su Khiong = sk.yong@samsung.com
14 | KK | DF2 | 7.2 7.3.2 8.8 12.2.5 |  |  | T | MAC | ACK policies can be simplified, e.g. Imp-ACK can be merged into Imm-ACK. Blk-ACK can be replaced by Dly-ACK. Some comments about UEP and aggregation are also provided. | Presentation will be provided for this comment. (15-08-0125-01-003c) | Postpone until next meeting | A |  |  | KK |  |  | Makto Noda = MakatoB.Noda@jp.sony.com
15 | KK | DF2 | 8.7a 12.2.4.3 | 27 64 |  | T | MAC | The aggregation procedure is modified in order to make it transparent to MAC layer. | Presentation will be provided for this comment. (15-08-0126-01-003c) | Postpone until next meeting | A |  |  | KK |  |  | JAT = Jason Trachewsky = jat@broadcom.com
16 | KT | DF2 | 12.2.8.4 | 72 |  | T/E | PHY | How to deal with line spectra in the center frequency in case of SC-OOK mode? |  | Waiting on a number for the carrier leakage. | A |  |  | Takahashi |  |  | MS, RY = Michael Sim Raymond Yu
17 | EG, CSC, AB | DF2 | 12.2, 12.3, 12.4 |  |  | T | PHY | The Common Rate is needed for interference control and the management of piconets. Therefore, it should be mandatory for all PNC capable devices. | Make Common Rate mandatory for all PNC capable devices or find another solution wich allows interference control and efficient management of piconets. | [7 empty] | HRS = Huai Rong Shao