## IEEE_Cover
2008-05-11 |  | IEEE P802.15.3-08/0300
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | DF0 comments
Date Submitted | March, 2008
Source | Ismail Lakkis | Voice: (858)-231-9753
| SiBEAM | Fax: [ ]
| 10875 Rancho Bernardo Rd, #108 | E-mail: ilakkis@tensorcom.com
San Diego, CA 92127
Re:
Abstract
Purpose | [This document provides a home for all comments, open issues and suggested resolutions concerning the TG3c draft DF0. In addition, this document will keep a running status of the disposition of the suggested resolutions.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Summary
HIS OFDM Comment Resolution
18 Comments in total | 32 to 49

## Resolution Spreadsheet
| Color Codes |  |  |  |  | W | Changes approved | This Sheet uses autoformat for cell colors except for closed. (Excel only handles 3 conditional formats)
|  | C | Closed |  |  | AV | Assigned
|  | P | Proposal pending |  |  | O | Open, not assigned | Last Issue Number | #REF!
Issue Number | Commenter's Initials | Draft Version Number | Clause number e.g., 8.10.2 | Page number e.g., 1-1130, etc. | Line number e.g., 1-54 | Type of comments (E/e/T/t) | Class of Problem | Comment/Rationale (Issue and reasoning behind it.) | Recommended change (What change(s) it would take to make this clause acceptable.) | Disposition/Rebuttal (Do not write here during ballot phase; this is for comment resolution phase.) | Resolution Status O,A,W,P,C | Date Entered | Date Completed | Asignee | Issue Status | Resolution Status
85 | CC | DF3 | General |  |  | T | GEN | There are several TBDs in the draft | Replace TBDs by proper definition | [7 empty] | EK = Edwin Kwon = cy.kwon@samsung.com
81 | CC | DF3 | 12 | 40 |  | T | GEN | Having two OFDM PHY only introduces confusion. | Merge the two OFDM PHYs or remove one of them | [7 empty] | ZL = lan@nict.go.jp
143 | AS | DF3 | 12 | 40 |  | T | GEN | The two OFDM PHYs are very muchthe same, it is not compatible and cleates confusion in the market | Merge or eliminate one of the two OFDM PHYs | [7 empty] | JAT = Jason Trachewsky = jat@broadcom.com
98 | AYK |  | General | 0 | 0 | T | GEN | Three PHY modes are redundant, especially having two similar OFDM modes. This will create market confusion. Devices from different vendors will not interoperate. | Remove at least one of the OFDM modes, or preferably leave only one OFDM PHY mode in the draft. | [7 empty] | James Gilb = last name at ieee dot org
117 | AYK |  | 12.1.5 |  |  | T | GEN | Having 3 PHY modes generates an unnecessary burden of multiple beacons when a MMC supports other than SC mode | Define a single common mode, or remove all PHYs but one | [7 empty] | Jisung Oh = jisung0714.oh@samsung.com
82 | CC | DF3 | 12.1.5 and D2 | 145 |  | T | GEN | The MMC PNC should not be the way to interoperate DEVs with different PHYs. There should be a mandatory mode for DEV interoperation. | Remove the concept of MMC PNC and introduce a mandatory mode that all DEVs are able to communicate. | [7 empty] | ST = solomon.trainin@intel.com
99 | AYK |  | General | 0 | 0 | T | GEN | There is no common mode that is mandatory for all devices - how is interoperability going to work | Define a mandatory common mode that all devices must support. Broadcast beacons in this mode. | [7 empty] | IL = Ismail Lakkis = ilakkis@tensorcom.com
83 | CC | DF3 | 8.4 | 24 |  | T | GEN | The access scheme of the CAP is very inefficient: i) considerations for beamformed operation in the CAP are not taken into account; ii) only one CAP is allowed per superframe; | Define more efficient access scheme for the CAP | [7 empty] | JY = james.yee@mediatek.com
87 | PG | DF3 | 8.4.2 | 24 |  | T | GEN | DEVs using directional antennas during CSMA/CA can create significant 'hidden node' collisions and affect network performance | Add mechanisms to minimize and recover from 'hidden node' collisons caused by directional antennas | [7 empty] | Pyo = cwpyo@nict.go.jp
88 | PG | DF3 | 8.4.2 | 24 |  | T | GEN | Two piconets operating in close proximity on same channel, but different medium access mechaims during a given time (e.g., one CSMA/CA another TDMA), can cause significant interference to one another. This is beacause TDMA mostly operates using beamformed mode while CSMA/CA uses "OMNI" mode. This can lead to severe performance degradation. | Include special mechanisms to address simulatneous operation of TDMA and CSMA/CA. | [7 empty] | Sum = sum@nict.go.jp
115 | AYK |  | 12.2..1.1 | 45 | 15 | T | GEN | OOK provides no benfit when mask compliancs is requried at the transmit and operation with devices at neighboring channels is needed | remove OOK modulation | [7 empty] | H. Harada = harada@nict.go.jp
116 | AYK |  | 12.2.1.1. | 45 | 19 | T | GEN | DRB provides no benefit | remove DRB from the standard. | [7 empty] | Shu Kato = shu.kato@nict.go.jp
124 | AYK |  |  |  |  | T | GEN | Common rate is special in its very low rate relatively for any other rate. The CR is unefficient but its use is allowed for data transmission | Limit use of CR only for control and omni transmissions | [7 empty] | Tuncer Baykas = tbaykas@ieee.org
134 | ST | DF3 | 8.4.2 | 24 | 21 | T | GEN | There are different factors that implies the CSMA/CA mechanism in the 60GHz band. The current definition does not address such important things like directed antennas, beamforming etc. It may happen that the CSMA/CA need changes to make it work in 60GHz band | Provide verified definition for CSMA/CA like mechnism for 60GHz band | [7 empty] | SKY = Su Khiong = sk.yong@samsung.com
135 | ST | DF3 |  |  |  | T | GEN | General comment. There are 8 TBDs found in the draft | Release the TBDs | [7 empty] | Makto Noda = MakatoB.Noda@jp.sony.com
146 | AS | DF3 | 12 | 40 |  | T | GEN | Too Many MCSs optional in OFDM and SC. | What is the mandatory MCS that all device can connect | [7 empty] | MS, RY = Michael Sim Raymond Yu
24 | IL | DF3 | 12.2.2.3 | 55 | 24:26 | T | SC | SC: Subclause 12.2.2.3 talks about two different spreading method for length 2 and 4, whereas description is provided for only one of them. | Spreading by repetition wasn’t explained. Add a section (12.2.3.3) for spreading by repetition | [7 empty] | HRS = Huai Rong Shao
25 | IL | DF3 | 12.2.2.3 | 55 |  | T | SC | SC: Should there be spreading at block level or at bit level | It is bit level | [7 empty] | JSOH = Jisung Oh
26 | IL | DF3 | 12.2.1.1 | 44 | 47:448 | T | SC | SC: Define a Fall back mode based on LDPC | Add an MCS of Pi/2 BPSK mod. LDPC 1/2 rate with spreading of 2 | [7 empty] | GB = Gal Basson
48 | SK | DF3 | 12.2..2 | 48-51 | ALL | T | SC | Normalization factor for pi/2 16-QAM is given. The other normalization factors for therest of the modulation schemes are missing | Provide the normalization factors for the missing modulations, it will be provided by the editors | [7 empty] | YK = Yasunao Katayama
51 | SK | DF3 | 12.2.4 | 61 | Figure 199 | T | SC | Spreading factors are 1, 2, 4 and 32. | Remove the SF 32 in the spreader module, Editorial change SF32 in the figure will be deleted | [7 empty] | AYK = Assaf Kasher
52 | SK | DF3 | 12.2.4.1.3. | 62 | Table 113 | T | SC | SI to S4 are not mapped to the corresponding spreading factors. | add description about the mapping , A new table with spreading factor values will be created
65 | GB | DF3 | 12.2.4.3.2 | 65-66 |  | T | SC | add a "Block-ACK base sequence field" (to optional MAC header adjuscent to BA field) - in order resolve ACK/NAK correlation ambiguity of corrupted MSDU number and BA-bit-offset | We agree
66 | YK | DF2 | 12.2.2.1 | 46 |  | T | SC | The relative amplitide and phase offset of different SC modulations w.r.t. pi/2-BPSK/(G)MKS need to be clarified to assure interoperability | Figure 188 is modified to describe relative amplitude and phase offset clearly, and Section 12.2.2.1 is modified to describe the procedure of phase offset including anti-clockwise
107 | AYK |  | 12.2 | 41 | 0 | T | AV | PCLP transmit and receive procedure are not defined for SC PHY | Define transmit and receive procedures for this PHY, Out of scope PLCP is a term used in 802.11 not but not .15
110 | AYK |  | 12.2.3 | 58 | 46 | T | SC | Use of Golay sequences in preamble is not better than using m-sequences. The m-sequences provides better timing estimation due to larger zero autocorrelation zone. They can also easily provide channel estimation without the need for two types of sequences. There are algorithms to perform cross correlation with m-sequences with the same complexity to that required by Golay sequences. | Replace Golay sequences with m-sequences, Issue should be rejected Golay sequences provide sufficient performance with 1/8 complexity
125 | AYK |  | 12.2.9.5 |  |  | T | SC | Reference to minimum sensitivity as in 12.2.9.2 is ambigious since that section provides numbers only for the reference sensitivity | Remove reference to 12.2.9.2 as the true sensitivity is sought (but how can this be tested?) We suggest to have editorial change eliminating word "reference" in the section
18 | IL | DF3 | 12.3.1.10 | 90 | 1:8 | T | HSI | HSI-OFDM: There are too many reserved bits in the PHY header | Look into sending PHY HDR, MAC and Optional HDRs in smaller number of symbols
19 | IL | DF3 | 12.3.1.2 | 81 |  | T | HSI | HSI-OFDM: Is it possible to combine the base and optional headers to fit in one OFDM symbol at the highest rate? | Look into sending PHY HDR, MAC and Optional HDRs in smaller number of symbols
20 | IL | DF3 | 12.3.1.9 | 89 |  | T | HSI | HSI-OFDM: The new optional header is shorter now. So all references to the optional header should change accordingly | Accepeted: Change Figure 214 and references to optional header
21 | IL | DF3 | 12.3.2.3.3 | 97 | 41:45 | T | HSI | HSI-OFDM: The LDPC partiy check matrices are missing | LDPC matrices are the same with SC and will be provided again
22 | IL | DF3 | 12.3.2.3.2 | 96 | 50 | T | HSI | HSI-OFDM: The outer interleaver depth of 4 RS codes is incorrect and is not an integer multiple of LDPC blocks. | The outer interleaver depth is 7 RS codes (change all references to that)
23 | IL | DF3 | 12.3.2.5.2&3 | 100 |  | T | HSI | HSI-OFDM: The spreader by 4 and 28 are messed up by the tone interleaver. | Accepted. Group will provide spreading matrices for 2 and 24 (invert interleaver)
47 | SK | DF3 | 12.1.7.1 |  |  | T | HSI | the bit allocated for HSI OFDM is missing | Provide the bit(s) needed to suport HIS OFDM
54 | JSOH | DF3 | 12.3.2.3 | 95 | 19 | T | HSI | Description on MUX in Fig. 219 is missing | Text was already provided to James (will work with James)
61 | GB | DF3 | 12.3.2.7.1 | 103 |  | T | HSI | Seed suppose to be 15 bits not 16 as written today | In page 103 remove the 0 to the right.
62 | GB | DF3 | 12.3.2.7.1 | 102 |  | T | HSI | Pilot number 5 is not defined well | In page 102, pilot 5 is part of the upper group (not lower group)
108 | AYK |  | 12.3 | 77 | 0 | T | HSI | PLCP transmit and receive procedure are not defined for HIS PHY | Define transmit and receive procedures for HSI PHY
111 | AYK |  | 12.3.1.10 | 89 | 6 | T | HSI | Number of modes is too large. | •A) Reduce CP mode to 1 bit (0 ó CP = 64, 1 ó CP = 128). Further study is needed to see the possibility of removing CP = 128; •B) Reduce PCES to 1 bit (0 ó Infinity, 1ó 128)
112 | AYK |  | 12.3.1.10.4 | 90 | 8 | T | HSI | Header controls CP of the symbol following the header decoding. This may cause problems when implementing because of the need to buffer the data untill the length of the CP is know. | We are looking having one CP mode, i.e CP = 64 only if simulation shows that 128 is not needed.
113 | AYK |  | 12.3.1.1 | 79 | 33 | T | HSI | Freame format is different than one from SC - there is no need for that, unify format and header fields - introducing some mininla redundancy | Reorder PHY header in SC like header + bits specific to HSI OFDM
114 | AYK |  | 12.3.1.10.79 | 92 | 3 | T | HSI | Aggregation shceme is different from than of SC (12.2.4.3.2( | HIS uses the same aggregation scheme as SC
133 | ST | DF3 | 8.4.1 | 24 | 19 | T | HSI | For the HSI mmWave PHY mode they are listed in <TBD> | Define TBD
138 | ST | DF3 | 12.3.1.11 | 93 | 28 | T | HSI | No defintion of the MAC header of the HSI PHY | Define the MAC header NICT: MAC header is already defined in 802.15.3 spec. (give ref)
139 | ST | DF3 | 12.3.1.12 | 94 | 4 | T | HSI | No defintion of the MAC subheader of the HSI PHY | Define the MAC subheader NICT: HSI use same MAC subheader with SC (give ref)
58 | JPKG | DF3 | 12.4.3 | 124 | 52 | T | AV | The use of the long and short omni preamble is not well defined | Change as described in 15-08-0253-00
59 | JPKG | DF3 | 8.12 |  |  | T | AV | Add clarification that the ACKs for HRP are sent with directional ACK and describe HR0, HRRX, HRTX and HRTR | Change as described in 15-08-0253-00
72 | CC | DF3 | 12.4 | 107 | 42 | T | AV | From this sentence, it appears to be possible for a DEV (including the PNC) not to support HRP. That would imply that the max data rate is around 10Mbps as provided through the LRP. However, the minimum required data rate a DEV shall support in 15.3c is 1Gbps. | Define a mandatory HRP mode
77 | CC | DF3 | 8.2 | 23 |  | T | AV | The process for starting piconets for the AV PHY needs to be specified since it is not clear how the LPR and HRP impact this process. | Describe how to start piconets for the AV PHY
80 | CC | DF3 | 12.4.1.1 | 108 |  | T | AV | In the AV PHY, there can be a major interference problem when two nearby piconets operate in the same HRP channel but different LRP channels. | Define interference mitigation mechanisms amongst piconets operating in the same HRP channel but different LRP channels. Simple procedures like switch HRP channel will not solve the problem in many scenarios.
100 | AYK |  | 12.4.5.1 | 136 | 44 | T | AV | This is the 3rd transmit mask defined in the draft, and it is different from the other masks significantly. The transmit mask defines interference limits from one network to another one. There may be interference from SC network to the AV-PHY network and vice versa. The mask must be the same. | Define a single transmit mask for all PHY modes that every transmissio must comply with.
101 | AYK |  | 12.4.5.1 | 136 | 41 | T | AV | Video bandwidth is not defined for transmit mask measurement. | Define a video bandwidth of 1/10 of resolution bandwidth.
102 | AYK |  | 12.2.8.4 | 73 | 41 | T | AV | Transmit mask measurement parameters are not defined - define resolution bandwidth to 3MHz and video bandwidth to 1/10 of the resolution bandwidht | as in commnet
103 | AYK |  | 12.3.4.1 | 104 | 28 | T | AV | Transmit mask meausrment parameters definition are refered to FCC part 15. Part 15 has many measurements defined, can it be specific to which one we are refering? | Define resolution bandwidth and video band width in the text.
104 | AYK |  | 12.2.8.3 | 73 | 27 | T | AV | EVM measurement is extermely fuzzy, It is not clear what is an "ideal receiver", it is not clear how averaging is being done. | Define the receiver and the measurement in an explicit way - take 802.11 clause 17.3.9.7 as an example.
105 | AYK |  | 12.4.1.1 | 108 | 42 | T | AV | The channelization scheme here is a repeat (albeit in a different format) of the table in 12.2.7.2. No channelization is defined for HIS PHY | Move channelizaiton to clause 12.1
106 | AYK |  | 12.4.2 | 111 | 45 | T | AV | Sampling rate of the AV-PHY is different from that of the HIS PHY and is unrelated to the chip rate of the SC-PHY | change the sample rate of the AV-PHY to 2592MHz.
109 | AYK |  | 12.4 | 107 | 37 | T | AV | PLCP transmit and receive procedure are not defined for AV-PHY | Define transmit and receive procedures for AV-PHY
118 | AYK |  |  |  |  | T | AV | OFDM AV PHY does not define beamforming to match Section 8.16.1 | Define beamforming inside 12.4 that matches section 8.16.1 or remove OFDM AV PHY
132 | ST | DF3 | 12.4.4.2 | 134 | 40 | T | AV | "The Integrity Code field is defined in 7.2.7.5." The subframe format does not contain the related nonce fields needed to calculate the Integrity code | Define the related fields and clarify the subframe integrity code calculation
140 | ST | DF3 | 12.4.4 | 130 | 33 | T | AV | There is a lot of fields defined in the MAC header of the AV PHY. At least part of the fields is not mentioned in the MAC functional description thus leaving those fileld useless | Define related functionality in the caluse 8. MAC functional description or remove the fields
141 | ST | DF3 | General |  |  | T | AV | The spec draft defines the MAC header as part of PHY definition. Such an approach complicates the spec and more important significantly increases complexity of implementation, verification, and certification. There is no limitation seen to unify the MAC header making it PHY independent thus extending the useful MAC features to any PHY | Unify the MAC header definition and move it to the clause 7.
44 | HRS | DF3 | 7.4.24 | 19 | 8-20 | T | BF/ANT | Only Tx antenna number , does Rx antenna number information needed? | Add Rx antenna number NICT: this function is just for TX diversity, so Rx antenna number is not needed
45 | HRS | DF3 | 8.16.3 | 37 | 40-54 | T | BF/ANT | What's the Rx antenna configuration? Does RX also switch Rx antenna according to Tx antenna switch? | Further discussion on this NICT:refer to the answer of the previous comment
46 | HRS | DF3 | 8.16.3 | 37 | 51 | T | BF/ANT | What's the value of the threshold to trigger TX anteena switch? | Further discussion on this NICT: it should be implementation issue
73 | CC | DF3 | 7.5.11.1 | 20 | 15 | T | BF/ANT | Number of beam fields undefined | Define Number of beam fields NICT: all the information will be updated after new beamforming procedure is finalized
74 | CC | DF3 | 7.5.11.2 | 20 | 35 | T | BF/ANT | Transmit beam number field undefined | Define Transmit beam number field NICT: all the information will be updated after new beamforming procedure is finalized
75 | CC | DF3 | 7.5.11.2 | 20 | 37 | T | BF/ANT | Received beam number field undefined | Define Received beam number field NICT: all the information will be updated after new beamforming procedure is finalized
76 | CC | DF3 | 7.5.11.2 | 20 | 39 | T | BF/ANT | Beam status information field undefined | Define Beam status information fields NICT: all the information will be updated after new beamforming procedure is finalized
119 | AYK |  |  |  |  | T | BF/ANT | Omni transmission is undefined for SC PHY and OFDM HIS PHY | Define method for omni transmission for these PHYs NICT: SC doesn't define special frame format for omni transmission. All the frame format defined can apply to either omni or directional transmission. So what we need to do is just cleary saying that in each period of superframe, omni or directional transmission is performed
120 | AYK |  |  |  |  | T | BF/ANT | Beamforming flow is not described in details. Some elements may be missing, for example - mapping of beamforming feedback to actual transmission | Map all elements of beamforming flow (according to 8.16.1) to PHY operations (in section 12)
121 | AYK |  | 7.5.11.2 |  |  | T | BF/ANT | Beamforming response is not completely defined | Define all fields
122 | AYK | 3 | 8.6.11.1 |  |  | T | BF/ANT | Beamforming measurements are not well defined and their mapping to beamforming response is not defined | Define
123 | AYK | 3 |  |  |  | T | BF/ANT | Beam training sequences are not defined for either PHY | Define
126 | ST | DF3 | 8.16.1.1 | 31 | 28 | T | BF/ANT | As stated beamforming between DEV and PNC needs M superframes. It may be too long for application's latency limitation or too slow in relation to channel variances. It is not clear while one superframe may contain only N sequences and the entire process needs M superframes. | The algorithm should be scalable to allow full completion in one superframe if the PNC and DEV have a capability to allocate enough time for that.
127 | ST | DF3 | 8.16.1.2 | 34 | 6 | T | BF/ANT | As stated beamforming between DEVs needs M superframes. It may be too long for application's latency limitation or too slow in relation to channel variances. It is not clear while one superframe may contain only N sequences and the entire process needs M superframes. | The algorithm should be scalable to allow full completion in one superframe if the PNC and DEV have a capability to allocate enough time for that.
128 | ST | DF3 | 8.16.1.2 | 33 | 7 | T | BF/ANT | "… beam forming training sequences, as described in <xref 12.4.6>" There is no such a sequence defined | Define beamforming training sequence
129 | ST | DF3 | 7.5.11.2 | 20 | 35 | T | BF/ANT | The Transmit Beam Number field <missing definition> | Please define
130 | ST | DF3 | 7.5.11.2 | 20 | 38 | T | BF/ANT | The Received Beam Number field <missing definition> | Please define
131 | ST | DF3 | 7.5.11.2 | 20 | 40 | T | BF/ANT | The Beam Status Information field <missing definition> | Please define
145 | AS | DF3 | 12 | 40 |  | T | BF/ANT | Why there are multiple beamforming algorithms proposed. What are the similarities, differences and how to determine whichone to implement | Remove or add one beamforming scheme for all modes
39 | MS, RY | DF2 | 8.2.5 | 25 | 53 | T | MAC | Need to descirbe how to construct an OOK piconet by OOK PNC when no SC Piconet is detected | Presentation will be provided by PYO
40 | MS, RY | DF2 | 8.2.5 | 26 | 1 | T | MAC | Need to describe where and how to send the SC beacon in the superframe of an OOK piconet formed by an OOK PNC | Presentation will be provided by PYO
41 | HRS | DF3 | 7.3.2 | 16 | 1 | T | MAC | Blk-ACK frame format is missing | Should add Blk-ACK figure and diagram in 7.3.2 NICT: the format of Blk-ACK is defined in section 12.2.4.3
42 | HRS | DF3 | 7.4.7 | 17 | 10-31 | T | MAC | In Fig. 42, should have one bit to indicate Blk-ACK, and two bits to indicate different aggregation schemes | Uee one reserved bit to indicate Blk-ACK, and two reserved bits to indicate aggregation schemes: 00: no aggregation, 01: standard aggregation, 10: low-lantency aggregation, 11: reserved NICT: agree
43 | HRS | DF3 | 7.4.7 | 18 | 7-23 | T | MAC | Table 49a, Do MIFS and SIFS use the same value? Is it possible SIFS can be shorter than 1.0us? | Further discussion on this NICT: it doesn't mean MIFS and SIFS have to use the same value, please elabreate why SIFS can not be less than 1.0us
49 | SK | DF3 | 12,.2.3 | 58 | 51-52 | T | MAC | How SC and non PNC capable OOK DEVs co-exist? | Further discussion on this Presentation will be provided by PYO
53 | SK | DF3 | 12.2.2.4 | 66 | Fig. 203 | T | MAC | UEP MCS shows in EEP frame format | UEP MCS shall be changed to EEP MCS
55 | JPKG | DF3 | 6.3 |  |  | T | MAC | With more than one PHY mode possible, the upper layers need the ability to determine the PHY mode of piconets found and to specify the PHY mode of a piconet that is started. | Change as described in 15-08-0253-00 NICT: information provided in 0253 is not complete and solid enough to solve the problem
56 | JPKG | DF3 | 12.1.7.3 | 43 | 1 | T | MAC | The Receive Status field is undefined | Change as described in 15-08-0253-00 NICT: information provided in 0253 is not complete and solid enough to solve the problem
57 | JPKG | DF3 | 8.8.4 |  |  | T | MAC | Need to add a rule that allows video packets with errors to be passed to the higher layers and define an FCSL to enable this | Change as described in 15-08-0253-00
60 | JPKG | DF3 | 8.8.3b | 27 | 45 | T | MAC | These rules seem overly restrictive Retransmission doesn't need a lot of rules | Delete all but the required rules.NICT: need to go through the text and identify which part of rule is not needed
63 | GB | DF3 | 8.7a.2 | 26-27 |  | T | MAC | replace description of Low latency aggregation with attached text in doc "DF3 - comments for low latency aggregation.doc" section 8.7a.2 | NICT: resolution as indicated in wilocity document
64 | GB | DF3 | 8.8.3b | 27-28 |  | T | MAC | replace description of Block ACK for Low latency aggregation with attached text in doc "DF3 - comments for low latency aggregation.doc" section 8.8.3b | NICT: resolution as indicated in wilocity document
67 | CC | DF3 | 7.4.7 | 17 |  | T | MAC | Block ACK and Aggregation support are not indicated in the capabilities. Support is mandatory? All types of aggregation? | Include Block ACK and aggregation in capabilities
68 | CC | DF3 | 7.4.22 | 18 | 35 | T | MAC | Figure 48e: what is the unit? Bits or octets? | Define unit
69 | CC | DF3 | 8.6.2 | 25 |  | T | MAC | If the PNC sends extended beacons through directional transmissions, a recipient DEV has no way of knowing when the following CAP or CTA starts. The way the Beacon Offset is defined right now, this cannot be done. | Define how a device can determine the beginning of the CAP/CTA
70 | CC | DF3 | 12.2.4.3.1 | 65 | 34 | T | MAC | Subframe Information undefined | Define Subframe Information field Presentation will be provided by Samsung
71 | CC | DF3 | 7.5.11.6 | 22 | 16 | T | MAC | Channel Status Information undefined | Define Channel Status Information field
78 | CC | DF3 | 8.7a | 25 |  | T | MAC | The two aggregation methods should be merged. Having two aggregation schemes increases complexity in implementation and makes the spec unecessarily complicated | Merge aggregation schemes NICT: the two aggregation methods are proposed for different application. High throughput video transmission/ file downloading and low latency application. It is very difficult to create a unified aggregation which can support both of the application requirment
79 | CC | DF3 | 8.8.3b | 28 | 23 | T | MAC | numberOfSubramesLimit undefined in the draft | Define numberOfSubramesLimit NICT: yes the paramter definition is missing, the value is implementation dependent
84 | CC | DF3 | 8.4 | 24 |  | T | MAC | DEVs are not allowed to access the medium during unallocated time over the superframe. | Include access schemes for unallocated channel time, which is very important for bursty traffic, low latency applications. Presentation will be provided by PYO
86 | CC | DF3 | 7.4.7 | 18 | 26 | T | MAC | UEP field undefined | Define UEP field
89 | KK | DF3 | 12.4.3.8 |  |  | T | MAC | Should we unify blk-ack and directional-ack for providing unified aggregation? | NICT: No, the blk-ACK and directional-ACK are defined for different aggregation procedure used for SC/HSI and AV-OFDM, respectively. The usage of these two ACKs is totally different. We have tried to merge them, but realized that it is very hard
90 | KK | DF3 | 8.7a 12.2.4.3 | 27 64 |  | T | MAC | The aggregation procedure is modified in order to make it transparent to MAC layer. That is to say, the aggregated frames can be acknowledged by either Blk-ACK, or Dly-ACK. This concept will help unify different aggregation methods. | Presentation will be provided.
91 | KK | DF3 | 7.1 7.2.7.6 12.2.2.4 |  |  | T | MAC | If UEP is applied, current FCS field of maximum 4 octets can't include both of MSB/LSB fields. Hence, the length of FCS should be extended to maximum 8 octets. | NICT: when UEP is applied, two separate FCS will be used for MSB ans LSB parts. Please refer to 8.7a line 51
92 | KK | DF2 | 7.3.2.1 7.3.2.2 7.2.3.3 | 16 |  | T | MAC | This MSB/LSB retransmission bits are only defined for Blk-ACK, not for all other ACKs (Imm-ACK, Dly-Ack, and Imp-ACK). Is it possible or necessary for ACKs other than Blk-ACK to support MSB/LSB retransmission? | NICT: No, other ACKs don't have to support UEP. UEP is just an optional function used with aggregation, while other ACK(Imm-ACK, Dly-ACK, Imp-ACK) are for general purpose
93 | RJS | DF3 | 7.2.1.4 & 12.4.3.8 | 14 & 129 |  | T | MAC | Two incompatible aggregate ack mechanisms are being defined, one in the MAC section and one in the AV PHY section. | Provide a single aggregate ack mechanism NICT: rather than spending a lot of effort to unify already proposed aggregation, more effort should be put to how to corrporate different aggregation operating on different PHYs
94 | RJS | DF3 | 8.7a & 12.4.4 | 25 & 130 |  | T | MAC | Three incompatible aggregation techniques are defined, two in the MAC section (8.7a) and one in the AV PHY section (12.4.4) | Provide a single aggregation mechanism or at a minimum clarify the applicabilty of the MAC section to the PHYs. Perhaps standard aggregation is a special case of low latency aggregation. NICT: refer to comment 78
95 | RJS | DF3 | 8.8.3b | 28 | 6 | T | MAC | It is not clear whether the requirement is that retransmitted frames be sent in the next frame AND at the head of the frame or whether the requirement is that IF the retransmitted frames are sent in the next frame that they be placed at the head of the frame. | Clarify the requirement. I suspect the intent was to require immediate retransmission. NICT: yes, the requirement is try to complete retransmission as fast as possible
96 | RJS | DF3 | 8.8.3b | 28 | 3 | T | MAC | There are no in-order delivery requirements in the described block ack mechanism other than "The destination transfers consecutive valid subframes to the FCSL." which from the context applies to a single aggregate frame only. | Clarify in-order delivery requirements. Address buffering requirements in receiver, retention of later (higher sequence number) frames until retransmission of earlier (lower sequence number) frames completes successfully, timeouts or other mechanisms to handle cases where retransmission frails.NICT: please clarify why in-order deliver requirement is important
97 | RJS | DF3 | 8.7a.2 | 27 | 9 | T | MAC | The in-order delivery requirements for low latency aggregation do not address retransmission failure. | Define behavior for the case where retransmission fails (maximum retransmits exceeded) for a particular MSDU.NICT: the behavior of retranimssion is defined already, the proposed retransmission doesn't rely on the In-order deliver requirement
136 | ST | DF3 | 8.7a.1 | 25 | 21 | T | MAC | Standard aggregation (MAC feature) is defined for the SC Phy only. There is no feasibility issue seen to limit supporting of this feature to this PHY only. The MAC features should be PHY independent | If this feature is useful extend it to all PHYs else remove it NICT: no, AV aggregation and SC use different frame format. It is hard to extend to other AV
137 | ST | DF3 | 8.7a.2 | 26 | 47 | T | MAC | Low latency aggregation (MAC feature) is defined for the SC Phy only. There is no feasibility issue seen to limit supporting of this feature to this PHY only. The MAC features should be PHY independent | If this feature is useful extend it to all PHYs else remove it NICT: same to the previous comment
142 | ST | DF3 | General |  |  | T | MAC | The spec draft defines the MAC features dependent on the PHY. It makes each MAC PHY dependent, and supporting separate set of features. As a result there is no MAC compatibility and the spec effectively becomes set of few separate specs. Such an approach complicates the spec and more important significantly increases complexity of implementation, verification, and certification. There is no limitation seen to unify the MAC features. | Unify definition of the MAC functionality and make it independent on the supporting PHY. Unify the MPDU formats.
144 | AS | DF3 | 12 | 40 |  | T | MAC | UEP is a function of video transmission and specific to the application, We are not tasked to develop applications, rather a general purpuse PHY for all applications. Otherwise, we need to introduce video and audio compression to the spec. | Remove UEB from the PHY. Alternatively, push UEP to MAC or applications layer, remove from the PHY section. Presentation will be provided by PYO
50
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218