## IEEE_Cover
January, 2009 |  | IEEE P802.15.3-09/0008r02
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | LB48 comments
Date Submitted | January, 2009
Source | James P. K. Gilb | Voice: (858)-229-4822
| SiBEAM | Fax: [ ]
| 555 N. Mathilda, Suite 100 | E-mail: last name at ieee dot org
Sunnyvale, CA 94085
Re:
Abstract
Purpose | [This document provides contains the comments and resolutions for LB48.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Comment entry
CID | Name | Vote | Clause | Subclause | Page | Line | Type | PartOfNoVote | Comment | SuggestedRemedy | Response | Status | Category | AssignedTo | E status | T status
1 | Chin-Sean Sum | Y | 12 | 12.2 | 75 | 9 | E | N | The name "Mandatory Low Rate (MLR)" is confusing. | Change name to "Mandatory Transmission Rate" or other more suitable names | Accept in principle: Change to MPR, mandatory PHY rate. | C | Editorial | JPKG | C
2 | Raymond Yu Zhan | Y | 12 | 12.2.8 | 101 | 24-26 | T | N | At Table 121, why does OOK and DAMI adopt pilot word length of 64? This pilot word with legnth of 64 in 12.2.3.4.1 is modulated using Pi/2-BPSK. OOK pilot word design is descibed as in D2.5. | Change back the data rate calculation. For OOK, the OOK pilot word design as in D2.5 can be used for data rate calculation. | Accept in principle: Resolve as indicated in 15-09-0036-00. | C | OOK | Raymond |  | C
3 | Raymond Yu Zhan | Y | 12 | 12.2.8.4 | 101 | 40-42 | E | N | The "code repetition" of OOK spreading scheme is conflicted with the "code repetition" of Golay sequence at the preamble of CMS | Change the "code repetition" to "spreading scheme" at the title. Change the "code repetition" to "bit repetition" at the Line 42. | Accept in principle: Make the changes requested but chant the title to be “OOK/DAMI spreading” | C | Editorial | JPKG | C
4 | Raymond Yu Zhan | Y | D2 | D2.4 | 195 | 12-18 | E | N | At Table D2.2, "00", "01", "10" and "11" of "SFD3 SFD4" do not match the "+" and "-" at the Figure D2.1 | Change "00" to "++", "01" to "+-", "10" to "-+" and "00" to "--". | Accept | C | Editorial | JPKG | C
5 | Raymond Yu Zhan | Y | D2 | D2.4 | 195 | 27 | E | N | Subclause 12.2.3.1.3 is no longer valid as a reference. | Need to clearly define how to define the cyclic prefix and cyclic postfix. |  | A | Editorial | JPKG | A
6 | Raymond Yu Zhan | Y | D2 | D2.4 | 195 | 28 | E | N | Subclause 12.2.3.1.3 is no longer valid as a reference. | Change "12.2.3.1.3" to "Table 100". | Accept | C | Editorial | JPKG | C
7 | Raymond Yu Zhan | Y | D2 | D2.5 | 195 | 36 | E | N | The "code repetition" of OOK spreading scheme is conflicted with the "code repetition" of Golay sequence at the preamble of CMS | Change the "code repetition" to "bit repetition". | Accept | C | Editorial | JPKG | C
8 | Raymond Yu Zhan | Y | D2 | D2.5 | 195 | 43 | E | N | The "code repetition" of OOK spreading scheme is conflicted with the "code repetition" of Golay sequence at the preamble of CMS | Change the "code repetition" to "bit repetition". | Accept | C | Editorial | JPKG | C
9 | Raymond Yu Zhan | Y | D2 | D2.5 | 195 | 46-48 | E | N | At the Figure D2.2, the "code repetition" of OOK spreading scheme is conflicted with the "code repetition" of Golay sequence at the preamble of CMS | Change the "code repetition" to "bit repetition". | Accept | C | Editorial | JPKG | C
10 | Michael Sim | Y | 12 | 12.2.8 | 101 | 24-26 | T | N | At Table 121, why does OOK and DAMI adopt pilot word length of 64? This pilot word with legnth of 64 in 12.2.3.4.1 is modulated using Pi/2-BPSK. OOK pilot word design is descibed as in D2.5. | Change back the data rate calculation. For OOK, the OOK pilot word design as in D2.5 can be used for data rate calculation. | Accept in principle: Resolve as indicated in 15-09-0036-00. | C | OOK | Raymond |  | C
11 | Michael Sim | Y | D2 | D2.5 | 196 | 5-7 | E | N | For consistence, at the Figure D2.3, the block sequence should be transmitted from right to left. So the Np pilot symbols should be on the left of N transmit symbols. | Change the order of "N transmit symbols" and "Np pilot symbols". | Accept | C | Editorial | JPKG | C
12 | Junyi Wang | Y | 13 | 13 | 157 |  | T | N | It is better to add a figure in the introduction of BF to show the relation between BF operation and directional association. The figure shall contain two cases, (1) omni-antenna: assocaiation follows 802.15.3, (2) directional antenna: directional associatoin, the part shall be further divided into 2 subpart: proactive and on-demand BF. | Add a figure at the end of introduction part of 13 | Accept in principle: Resolve as indicated in 15-09-0027-00. Add not applicable to AV PHY for IE support | C | Beamforming | Wang |  | C
13 | Junyi Wang | Y | 13 | 13.3 | 160 | 23 | T | N | We think the cluster encoding is only used in PET, if it is true please clarify it L23, "The following cluster encoding scheme is only used in PET." | Change as recommended | Accept in principle: Resolve as indicated in 15-09-0027-00. | C | Beamforming | Wang |  | C
14 | Junyi Wang | Y | 13 | 13.3.1 | 162 | 53 | T | N | There is no clear reason why the cases that K<M and K/=M/2 are not of interest. | Delete the sentence if there is no clear reason. | Accept. Remove the sentences. | C | Beamforming | Wang |  | C
15 | Junyi Wang | Y | 13 | 13.3.1 | 163 | 1-2 | E | N | It seems that the codebook ID is only useful in PET, if it is true, clarify the fact on the related places | Change as recommended | Accept in principle: Add to p. 163, line 2, “The Codebook ID field is used only if both DEVs support PET.” | C | Editorial | JPKG | C
16 | Junyi Wang | Y | 13 | 13.5.1.1.2 | 169 |  | T | N | It is better to remove SAS sector level and beam level training, since they are the spectial cases of AAS, and for a DEV, it is hard to decide wether the system is AAS or SAS, because AAS or SAS is not only depends on Antenna configuration but also depends on channel. Since the channel may not reciprocal for uplink and dowlink in NLOS channel, it may result different optimal patterns for transmission and receiption even for the same antenna configuration. | Change as recommended | Withdraw, 19 January, 2009. No change required. | C | Beamforming | Wang |  | C
17 | Junyi Wang | Y | 13 | 13.5.1.2.1 | 174 | 1/5 | T | N | There is no definition of "phase vector" and "amplitude vector" | Define them or delete "vector" | Accept in principle: Resolve as indicated in 15-09-0027-00. | C | Beamforming | Wang |  | C
18 | Junyi Wang | Y | 13 | 13.5.1.2.1 | 174 | 2/7 | T | N | It is said there that "phase resolution" and "amplitude resolution" are greater than one, which are conflict with what defined in L38 and L42 of page 40. Furhtermore there is no mapping talbe for these two fields. | Clarify them. And aliagn two explainations. | Accept in principle: Resolve as indicated in 15-09-0027-00. | C | Beamforming | Wang |  | C
19 | Junyi Wang | Y | 13 | 13.5.2 | 178 | 45-46 | T | N | It is said here that "When beam switching criterion is used, pattern tracking reduces to beam tracking", Is it true? And what is beam switching criterion, what is pattern tracking, what is the difference from beam tracking? | To be discussed | Accept in principle: Remove the sentence “When beam switching ... beam tracking.” | C | Beamforming | Wang |  | C
20 | Junyi Wang | Y | 13 | 13.5.2 | 178 | 48 | T | N | There is no definiation of "beam grouping method" | Define it | Accept in principle: Resolve as indicated in 15-09-0027-00. | C | Beamforming | Wang |  | C
21 | Junyi Wang | Y | 8 | 8.6.6.1 | 47 | Figure 125 b | E | N | In the last block of "beacon frame Tx direction #0", I^{(1,t)-1} shall be I^(1,t) -1, -1 shall not be in the superscript. | revise it | Accept. | C | Editorial | JPKG | C
22 | Junyi Wang | Y | 8 | 8.6.6.1 | 47 | 47 | E | N | Add a reference to clause 13 for Sector Training Field and clarify that it is used in pro-active BF, | Change as recommended | Accept in principle: Add a cross reference to 13.7. | C | Editorial | JPKG | C
23 | Junyi Wang | Y | 13 | 13.3 |  |  | E | N | The codebook is called beam forming codebook in 13.3 but called beam codebook in 13.3.1. | Unify them | Accept in principle: Change “beam codebook” to “beam forming codebook” | C | Editorial | JPKG | C
24 | Junyi Wang | Y | 13 | 13.3 | 161 | Figure 216 | E | N | for the fourth figure of the first line, the code "000000111" has 9 bits, one bit 0 is redundant | Delete the redundant bit | Accept | C | Editorial | JPKG | C
25 | Junyi Wang | Y | 13 | 13.3.1 | 162 | 31 | E | N | "beams" shall be "beam patterns" | Change as recommended | Accept | C | Editorial | JPKG | C
26 | Junyi Wang | Y | 13 | 13.3.1 | 162 |  | E | N | There is no definition of "mod" | Define it | Accept in principle: Add a definition for mod from Matlab to the first occurance and cross reference the rest. | C | Editorial | JPKG | C
27 | Junyi Wang | Y | 13 | 13.4 | 164 | 12 | E | N | There is no "burst size" used in the standard anymore, use "subblock length" instead. | Change as recommended | Accept | C | Editorial | JPKG | C
28 | Junyi Wang | Y | 13 | 13.4 | 162 | 13 | E | N | Repalce "SC" with "SC PHY", "HSI-OFDM" with "HSI-OFDM PHY" | Change as recommended |  | A | Editorial | JPKG | A
29 | Junyi Wang | Y | 13 | 13.5.1 | 165 | 19 | E | N | "BCV" is never used in the following context. | Delete it. |  | A | Editorial | JPKG | A
30 | Junyi Wang | Y | 13 | 13.5.1.1.1/13.5.1.2.1 | 165/172 | Figure 219 / 242 | E | N | Delete Figure 219, 242, but explain the four steps in text since the figure is inconsistent with the standard, we never use such a kind of figure to express the time sequential events | Change as recommended |  | A | Editorial | JPKG | A
31 | Junyi Wang | Y | 13 | 13.5.1.1.1 | 166 | 1-2/35-36 | E | N | Since the definition for long preamble is changed in Dallas, the long preamble, long SYNC and long CES shall be changed into CMS preamble, CMS SYNC and CMS CES respectively. | Change as recommended |  | A | Editorial | JPKG | A
32 | Junyi Wang | Y | 13 | 13.5.1.1.1 | 166 | 27 | E | N | It is better to move sentence in L27 of page 164 to the end of L21 of page 162 and combine Figure 224 and Figure 225, since it is hard to understand the relationship of these two figures. | Change as recommended |  | A | Editorial | JPKG | A
33 | Junyi Wang | Y | 13 | 13.5.1.1.1 | 166 | 39 | E | N | "transmit sector" shall be "receive sector" | Change as recommended |  | A | Editorial | JPKG | A
34 | Junyi Wang | Y | 13 | 13.5.1.1.1 | 166 | 47 | E | N | Delete "process" | Change as recommended |  | A | Editorial | JPKG | A
35 | Junyi Wang | Y | 13 | 13.5.1.1.1 | 166 | 47-48 | E | N | Delete "For the AV-PHY … repetitions block" since the same sentence apears later in L1-2 of page 165. | Change as recommended |  | A | Editorial | JPKG | A
36 | Junyi Wang | Y | 13 | 13.5.1.1.1 | 167 | 8-9 | E | N | Delete "The LQI is a measure that … dependent" since LQI has already explained in 7.4.27. | Change as recommended |  | A | Editorial | JPKG | A
37 | Junyi Wang | Y | 13 | 13.5.1.1.1 | 167 | Figure 227 | E | N | Figure 227 is just the second part of Figure 225, It is no meaning to show here again, delete Figure 227 and give reference in L12 of page 165. And then add "annouce command with Imp-ACK" in Figure 225 | Change as recommended |  | A | Editorial | JPKG | A
38 | Junyi Wang | Y | 13 | 13.5.1.1.1 | 167 | Figure 228 | E | N | The title of Figure 228 shall be "AAS Setor to Beam mapping" to keep consisitent with context. | Change as recommended |  | A | Editorial | JPKG | A
39 | Junyi Wang | Y | 13 | 13.5.1.1.1 | 167/168/173/174 | Figure 229/230/250/ 251/ 253/ 254 | E | N | Delete the first row of Figure 229 and figure 230 and change the title into "The payload of Announce comamnd for feedback" . The number of bits of each field has already defined in clause 7 and do need to emphasize the length here again. | Change as recommended |  | A | Editorial | JPKG | A
40 | Junyi Wang | Y | 13 | 13.5.1.2 | 172 | 7 | E | N | "clusters" shall be "cluster mapping" | Change as recommended |  | A | Editorial | JPKG | A
41 | Junyi Wang | Y | 13 | 13.5.1.2.1 | 172 | 15 | E | N | "beam level " shall be "beam level training" | Change as recommended |  | A | Editorial | JPKG | A
42 | Junyi Wang | Y | 13 | 13.5.1.2.1 | 173/174 | Figure 248/252 | E | N | "Annouce command" shall be added in each block of DEV1->DEV2 and DEV2->DEV1 feedback in these figures and then delete the meanless Figure 249 | Change as recommended |  | A | Editorial | JPKG | A
43 | Junyi Wang | Y | 13 | 13.5.1.2.1 | 173 | 36 | E | N | Do not use term "frame" | Delete "frame" |  | A | Editorial | JPKG | A
44 | Junyi Wang | Y | 13 | 13.5.1.2.1 | 174 | 31 | E | N | The word "stage" is not necessary | Delete it. |  | A | Editorial | JPKG | A
45 | Junyi Wang | Y | 13 | 13.5.1.2.1 | 174 | 31/32 and title of figure 252 | E | N | Replace ''HR" with "HRS" | Change as recommended |  | A | Editorial | JPKG | A
46 | Junyi Wang | Y | 13 | 13.5.1.2.1 | 174 | 39 | E | N | "beams mapping" shall be "beam mapping" | Change as recommended |  | A | Editorial | JPKG | A
47 | Junyi Wang | Y | 13 | 13.5.1.2.1 | 175 | 5 | E | N | "z-axis" and "x-axis" shall be "pollar angle" and "Azimuth angle" respectively. | Change as recommended |  | A | Editorial | JPKG | A
48 | Junyi Wang | Y | 13 | 13.5.1.2.1 | 175 | 18 | E | N | Delete "as illustrated in Figure 242" since it is not illustrated there. | Change as recommended |  | A | Editorial | JPKG | A
49 | Junyi Wang | Y | 13 | 13.5.2 | 179 | Figure 266 | E | N | It is not clear what Figure 266 explains for, from the figure, I can not find that the tracking frequency of the best cluster is higher than the second best cluster. | Revise or delete the figure |  | A | Editorial | JPKG | A
50 | Junyi Wang | Y | 13 | 13.5.2 | 179 | 10 | E | N | "Drection Tracking field " shall be "Beam Tracking Field" | Change as recommended |  | A | Editorial | JPKG | A
51 | Junyi Wang | Y | 13 | 13.5.2 | 179 | 12 | E | N | "Beam level phase" shall be "Beam level training" | Change as recommended |  | A | Editorial | JPKG | A
52 | Junyi Wang | Y | 13 | 13.5.2 | 179 | Figure 267 | E | N | "tracking feild" shall be "Beam Tracking field "; "HR beams" shall be "HRS beams" | Change as recommended |  | A | Editorial | JPKG | A
53 | Junyi Wang | Y | 13 | 13.5.2 | 179 | 21-26 | E | N | We do not know why to explain the simple procedure in such a hard way. Why don't we just say "The odd tracking frame is used to estimate the best cluster and the even tracking frame is used to estimate the second best cluster " | Suggest to state as recommended and Revise the related figures. |  | A | Editorial | JPKG | A
54 | Junyi Wang | Y | 13 | 13.5.2 | 181 | 1-2 | E | N | Delete the sentence "The PNC number of sectors…Figure 42a", it is no reason to mention J^(1,t) again. | Change as recommended |  | A | Editorial | JPKG | A
55 | Junyi Wang | Y | 13 | 13.5.2 | 181 | 9 | E | N | beam level phase' shall be 'beam level training' | Change as recommended |  | A | Editorial | JPKG | A
56 | Ismail Lakkis | Y | 12 | 12.1.11 | 66 | 50 | E | N | Add a line stating that "CMS is the base rate for the SC PHY mode." The objective is not to mention CMS anymore in the SC PHY mode clause so we should make the CMS subclause complete. |  |  | A | Editorial | JPKG | A
57 | Ismail Lakkis | Y | 12 | 12.1.11 | 67 |  | E | N | replace "dependant" with "dependent". |  |  | A | Editorial | JPKG | A
58 | Ismail Lakkis | Y | 12 | 12.1.11 | 67 | 1-25 | E | N | Replace lines 1-25 by: "The CMS is designed for NLOS operation and is based on a chip rate of 1728 Mchips/s, spreading codes of length 64, and Reed Solomon coding. The CMS frame shall be formatted as illustrated in Figure 129. (than put figure) The CMS frame header shall be formatted as illustrated in Figure 130. The goal of the frame header is to convey necessary information about both the PHY and the MAC to aid decoding of the data field at the receiver. When transmitting a CMS frame, the PHY preamble is sent first, followed by the frame header, and finally by the data field. The PHY preamble is defined in 12.1.11.5. The MAC header is defined in 7.2. The frame header construction is detailed in 12.1.11.6. The data field is constrcuted as specified in 12.1.11.7." |  |  | A | Editorial | JPKG | A
59 | Ismail Lakkis | Y | 12 | 12.1.11 | 67 | 23-25 | E | N | Delete "The chips in the frame ... of length 512 chips." This is not necessary since CMS has its own subclause and there is not need to create blocks. |  |  | A | Editorial | JPKG | A
60 | Ismail Lakkis | Y | 12 | 12.1.11.1 | 67 | 51-54 | E | N | 12.1.11.1 is too long since it is not detailing the p/2-BPSK. It is enought to say "The CMS shall be modulated using p/2-BPSK/pre-coded (G)MSK as outlined in 12.2.2.1.1." |  |  | A | Editorial | JPKG | A
61 | Ismail Lakkis | Y | 12 | 12.1.11.3 | 68 | 16 | T | N | Add the following after line 16: "As shown in Figure 131, a PRBS generated using an LFSR is used to vary the spreading code from one bit to another, i.e. each bit is spread with Golay code a64 or golay code b64 depending on the LFSR output. The LFSR shall be run at a rate equals to 1/64 the bit rate and shall be initialized with the following 15bit seed value: [x-1, x-2, ..., x-15] =[0101 0000 0011 111]. Each input bit shall be held for 64 chips as it is XORed with Golay code a64 or Golay code b64 operating at the chip rate." |  | Accept | C |  |  |  | C
62 | Ismail Lakkis | Y | 12 | 12.1.11.4 | 68 | 45-46 | E | N | Replace "To avoid spikes in the spectrum, scrambling shall be ..." with "Scrambling shall be employed to whiten the CMS frames. Scrambling shall be used for the MAC header, HCS, and the entire data field as detailed in 12.2.5.1." |  |  | A | Editorial | JPKG | A
63 | Ismail Lakkis | Y | 12 | 12.1.11.5 | 68-69 | 51,11-21 | E | N | Replace lines 51 and 11-22, that is "The CMS premable is shown ... repetitions of u512" by "The CMS preamble can be subdivided into three distinct portions as shown in Figure 132: a SYNC field used primarly for frame detection, an SFD field used to establish frame timing, and a CES field used for channel estimation. A pair of Golay complementary sequences of length 128, a128 and b128 listed in Table 100, are used to construct the different portions of the preamble. The SYNC field shall consist of 128 repetitions of a128. The SFD field shall consist of [u512 u512 ubar512 u512]. The CES field shall consist of 6 repetitions of u512 followed by bbar128. The golay code u512 is constructed as follows: u512 = [a128 bbar128 abar128 bbar128]" |  |  | A | Editorial | JPKG | A
64 | Ismail Lakkis | Y | 12 | 12.1.11.6 | 69 | 35-39 | T | N | Remove the sentence "The CMS frame header consists ... frame header." add the following to the end of line 38: "1) Constrcut .... by the MAC as specified in 12.1.11.6.1," This is necessary since we dont know what is the PHY header. |  | Accept | C |  |  |  | C
65 | Ismail Lakkis | Y | 12 | 12.2.3.2.1 | 92 | Fig 149 | T | N | Test does not explain the order of transmission since the header is broken into 2 subfigures. Why don’t we use Figure 134 which is clearer and remove Figure 134 from 12.1.11.6.1 |  | Accept in principle: Cross reference to Figure 134 rather than Figure 149. Delete Figure 149 as it is the same as Figure 134 and replace with a cross reference. | C |  |  |  | C
66 | Ismail Lakkis | Y | 12 | 12.1.11.8 | 71 | 33-37 | T | N | Remove "A compliant ... signal bandwidth." CCA is not necessarly done using energy detection, there are other ways to fo it. So let us use similar text as 802.11. |  | Accept in principle: Remove “by using energy detection” | C |  |  |  | C
67 | Ismail Lakkis | Y | 12 | 12.2.2.6.3 | 83-84 | Table 110 | E | N | Table 110 and Figure 139 are mingled together, please separate them. |  |  | A | Editorial | JPKG | A
68 | Ismail Lakkis | Y | 12 | 12.2.2.6.2 | Fig 139 |  | T | N | LDPC matrices are optimized for AWGN, if possible provide better matrices for Multipath |  | Withdraw, 19 January, 2009. No change required. | C |  |  |  | C
69 | Ismail Lakkis | Y | 12 | 12.2.3.1 | Fig 147 |  | E | N | Figure is pregnant in the horizental direction |  |  | A | Editorial | JPKG | A
70 | Ismail Lakkis | Y | 12 | 12.3.3.1 |  |  | T | N | Unify Golay sequences with SC if possible |  | Withdraw, 19 January, 2009. No change required. | C | HSI | Lakkis |  | C
71 | Rick Roberts | N | 12 | 12.1 | 61 |  | T | Y | Merger of OFDM PHY types. | I still feel that we don't need both an AV OFDM PHY and an HSI OFDM PHY. Merge these two OFDM PHYs together and have only one OFDM PHY option. It would be acceptable to incorporate the low rate AV PHY concept in doing this merger. | Reject: Different PHYs are a result of demands of different market segments, which are stated in the usage models. For example usage model 5 is for Kiosk applications. It demands 1.5 Gbps in 1 m range. SC-PHY can provide such a data rate in such a short range with less complexity thus lower cost than an OFDM PHY. Whereas usage model 1 requires uncompressed video streaming. Due to the nature of uncompressed video signals a special PHY (AV PHY) is selected to provide high throughput. Usage model 4 requires a Conference ad hoc system in which all devices inside the WPAN will have bidirectiona, NLOS high speed, low latency communication which is answered by HSI PHY. Mandatory data rates of all those PHYs are selected according to specific usage models. As with any other standard we want to give implementers more options than the mandatory ones, therefore for SC PHY higher data rates are introduced which require equalization. However it is not appropriate to compare optional features of SC PHY with mandatory features of any OFDM PHY. Although AV and HSI OFDM PHYs share the same modulation technique, their frame design and approach to communication is very different. | C | Multiple PHYs | Baykas |  | C |  | Different PHYs are a result of demands of different market segments, which are stated in the usage models. For example usage model 5 is for Kiosk applications. It demands 1.5 Gbps in 1 m range. SC-PHY can provide such a data rate in such a short range with less complexity thus lower cost than an OFDM PHY. Whereas usage model 1 requires uncompressed video streaming. Due to the nature of video signals, a special PHY (AV PHY) is selected. Usage model 4 requires a Conference ad hoc system in which all devices inside the WPAN will have bidirectional NLOS high speed communication which is answered by HSI PHY. Mandatory data rates of all those PHYs are selected according to specific usage models. As with any other standard we want to give implementers more options than the mandatory ones, therefore for SC PHY higher data rates are introduced which require equalization. However it is not appropriate to compare optional features of SC PHY with mandatory features of any OFDM PHY. Although AV and HSI OFDM phys share the same modulation technique, their frame design and approach to communication is very different.
72 | Rick Roberts | N | 12 | 12.1.11 | 66 |  | T | Y | Lack of common mode for all 802.15.3c devices | Only AV and HSI PNC devices are required to support the common mode. How does a consumer know if they are buying a PNC or not? This leaves the problem of 15.3c compliant devices not being able to interop, which is unacceptable. Make the CM mandatory for all 15.3c compliant devices, not just the PNC. And note: the previous rejection of this comment missed the point; and that is, we need complete interoperability of all and every PHY, not just coexistence! | Reject: The SC and HSI PHYs are interoperable since they are both sending CMS beacons for coexistence and interoperability. For other cases, the CMS sync frame shall be use for interference mitigation. Therefore no change is required. | C | Common mode | Sum |  | C
73 | Christopher Hansen | N | 12 | 12.2.8 | 100 | 17 | T | Y | DAMI and OOK are inefficient. | Remove section 12.2.8 | Reject: The OOK/DAMI modes are designed for low complexity and low power consumption. The OOK mode can adopt the simplest envelope detection for low complexity, power consumption and cost implementation DAMI is for high data rate applications, and offers low power consumption and complexity | C | OOK | Bosco |  | C
74 | Christopher Hansen | N | 12 | 12.3 | 103 | 1 | T | Y | It doesn't make sense to have 2 complete OFDM PHY modes that are so similar. | Unify the two OFDM PHYs in 12.3 and 12.4. | Reject: Different PHYs are a result of demands of different market segments, which are stated in the usage models. For example usage model 5 is for Kiosk applications. It demands 1.5 Gbps in 1 m range. SC-PHY can provide such a data rate in such a short range with less complexity thus lower cost than an OFDM PHY. Whereas usage model 1 requires uncompressed video streaming. Due to the nature of uncompressed video signals a special PHY (AV PHY) is selected to provide high throughput. Usage model 4 requires a Conference ad hoc system in which all devices inside the WPAN will have bidirectiona, NLOS high speed, low latency communication which is answered by HSI PHY. Mandatory data rates of all those PHYs are selected according to specific usage models. As with any other standard we want to give implementers more options than the mandatory ones, therefore for SC PHY higher data rates are introduced which require equalization. However it is not appropriate to compare optional features of SC PHY with mandatory features of any OFDM PHY. Although AV and HSI OFDM PHYs share the same modulation technique, their frame design and approach to communication is very different. | C | Multiple PHYs | Baykas |  | C
75 | Christopher Hansen | N | 12 | 12.3.2.6 | 109 | 32 | T | Y | Skewed constellations increase implementation complexity without providing any benefit over coding schemes for unequal error protection. Since we already have an effective UEP mode using coding why should we include this mode? | Remove the skewed constellation mode. | Reject: The skewed constellation as an option provides different advantages as compared with coding schemes. | C | UEP | Huai Rong |  | C
76 | Henk de Ruijter | Y |  | 12.1.11.3 | 68 | 29 | E | N | The second adder (or exor) at the bottom of Figure 131 has only one input. | Connect the missing input signal to the adder (or exor) at the bottom of Figure 131. |  | A | Editorial | JPKG | A
77 | Yongsun Kim | Y | 7 | 7.2.1.4 | 13 | 50 | E | Y | "... are defined Table 40." | "... are defined in Table 40." |  | A | Editorial | JPKG | A
78 | Yongsun Kim | Y | 7 | 7.2.8.1 | 16 | 12 | E | Y | "subframe were correctly or incorrectly received." | "subframe were correctly received." |  | A | Editorial | JPKG | A
79 | Yongsun Kim | Y | 7 | 7.2.8.1 | 16 | 12 | E | Y | "The bit position zero corresponds to …" | "The bit position zero of the ACK or lsb ACK field corresponds to …" |  | A | Editorial | JPKG | A
80 | Yongsun Kim | Y | 7 | 7.2.8.2 | 18 | 5 | E | Y | "MPDU response number" | "MSDU response number" |  | A | Editorial | JPKG | A
81 | Yongsun Kim | Y | 7 | 7.2.8.2 | 18 | 40-41 | E | Y | "MPDU Response Number" | "MSDU Response Number" |  | A | Editorial | JPKG | A
82 | Yongsun Kim | Y | 7 | 7.2.8.2 | 18 | 43-44 | E | Y | "MPSDU Request Number" | "MSDU Request Number" |  | A | Editorial | JPKG | A
83 | Yongsun Kim | Y | 8 | 8.7a.1 | 53 | 2 | E | Y | "as defined in Figure 10aa." The Figure 10aa does not show how two FCSs are attached. | give correct figure number |  | A | Editorial | JPKG | A
84 | Yongsun Kim | Y | 8 | 8.8.3b.1 | 54 | 53 | E | Y | "subframes contained will be the same to those of the previous transmitted frame." | "subframes contained will be the same as those of the previous transmitted frame." |  | A | Editorial | JPKG | A
85 | Yongsun Kim | Y | 8 | 8.8.3b.2 | 55 | 24, 25, 26 | E | Y | "MPDU" | "MSDU" |  | A | Editorial | JPKG | A
86 | Yongsun Kim | Y | 8 | 8.8.3b.2 | 55 | 32, 37 | E | Y | "MAC sub header" | "MAC subheader" |  | A | Editorial | JPKG | A
87 | Yongsun Kim | Y | 7 | 7.2.1 | 13 | 20 | E | Y | In Fig. 9 Frame control field format, 'b8-7"for Ack Policy field and "b5-3"for Frame type field need "b" for consistency. | "b8-b7", "b5-b3" |  | A | Editorial | JPKG | A
88 | Yongsun Kim | Y | 7 | 7.2.9.1.1 | 20 | 49 | E | Y | Spelling error | "~will be ignored~" |  | A | Editorial | JPKG | A
89 | Yongsun Kim | Y | 7 | 7.2.8.2 | 18 | 1 | E | Y | Need to add "field" for clarify the term. | "The MAC subheader field for low latency aggregation shall be formatted as ~" | Accept in principle: Add “field” and change the from 10 bits to 9 bits for MSDU subheader number, add reserved bit. Also 9 bits in figure 10j. | C | Editorial | JPKG | C
90 | Benjamin Rolfe | Y | 6 | 6.6 | 10 | 13 | T |  | What is the purpose of the InterlacedFieldIndication, VideoFrameNumber, HPosition, VPosition parameters and how are they used? Why does the MAC need these paremeters? These appear to be uppre layer responsibility. I do not see these used in MAC procedures or other text. | Clarify the purpose of the parameters or remove them. If they are provided for upper layer use, why are they part of the MAC and not payload? If they are used BY the MAC, this needs to be explained. | Accept in principle: Add the following paragraph to 6.6, “The parameters InterlacedFieldIndication, VideoFrameNumber, HPosition and VPosition are used by the AV PHY in the Video Subheader field, as described in 7.2.9.1.4. These fields are sent in the MAC header because it has lower error rate than the subpackets carrying video data. For uncompressed video applications, video data that is in error can still be displayed, but only if the position of the pixel data is known.” | A | Video | JPKG |  | A | Wed PM2
91 | Benjamin Rolfe | Y | 6 | 6.5.1 | 9 | 40 | T |  | How is the parameter MACPIB_QuasiOmniBeaconEndTime and how is the value determined? | Clarify the purpose of the group parameter and how it is used and/or set by the MAC. | Accept in princple: MACPIB_QuasiOmniBeaconEndTime is used to indicate the start point of the CAP in the case of Quasi-omni beacon is present. The value is determined by the number of Quasi-omni beacons. For naming consistency, change “MACPIB_QuasiOmniBeaconEndTime” to be “MACPIB_CAPStartTime”. | C | MAC | Pyo |  | C
92 | Benjamin Rolfe | Y | 6 | 6.6 | 10 | 13 | T |  | DataType: why specify the type of applciation data being carried. I see that this is used by the MAC to determine if errored frames are discarded or passed up. I think what this is saying is that the FCS ignored for video data. Allowing upper layers to specify how errors are handled is appropriate, without the MAC making application layer decisions or knowing this much about the payload. The application can decide if errored frames are needed by setting 'ignore'. And where is this special handling of video data described? | Remove "DataType" and replace with an appropriate MAC layer parameter such as "ignoreErrors". | Accept in principle: Replace “DataType” with “UncompressedVideo” which is a boolean, values TRUE, FALSE, description “Set to TRUE if the Data field contains uncompressed video data.” For InterlacedFieldIndication, VideoFrameNumber, HPosition and VPosition fields, add “if the UncompressedVideo field is set to TRUE.” | A | Video | JPKG |  | A | Wed PM2
93 | Benjamin Rolfe | Y |  |  |  |  | E |  | General Comment: in the text, direct references should be made to PID and parameter names as lised in the tables. For example: on page 21, line 44 in clause 6.6.4 "Data identified as video" should be something like "if the DataType field of the received MAC frame is VIDEO or UNCOMPRESSED_VIDEO...". | Clarify as required | Accept | C | Editorial | JPKG | C
94 | Benjamin Rolfe | Y | 6 | 6.6.5 | 11 | 44 | T |  | Use of "DataType" should be eliminated and replaced with an indication that the errored frames should be passed up anyway. |  | Accept in principle: Resolve as indicated in CID 92. | A | Video | JPKG |  | A | Wed PM2
95 | Benjamin Rolfe | Y | 7 | 7.2.9.1.4 | 22 | 21 | T |  | Why is the MAC decoding video data? | Clarify why application functions are defined in the MAC. | Accept in principle: See CID 92. Also add the note to 7.2.9.1.4, “The Video Subheader is included as part of the MAC header because the error rate for the MAC header is lower than that of the subframes.” | A | Video | JPKG |  | A | Wed PM2
96 | Benjamin Rolfe | Y | 7 | 7.4.24 | 34 | 18 | T |  | UEP may be used on other kinds of data other than video. The type of data passed to the MAC is application specific. Use of UEP should not be determined by data type. The msb/lsb separation is used for just that, regardless of the type of data. | None of the text regarding video is necessary. Remove it, or at least indicate is is a "for example" illustrative elaboration. | Accept in principle: Resolve as indicated in 15-09-0032-00. | C | UEP | Pyo |  | C
97 | Benjamin Rolfe | Y | 8 | 8.71.2 | 43 | 45 | T |  | States that "MSDUs that are incorrectly received are discarded' but elsewhere it is implied some MSDUs that have errors can be passed up if the type is video (see prior comments). This is confusing - are agregated frames never video? | Clarify how this relates to different data types. | Accept in principle: Resolve as indicated in 15-09-0032-00. | C | MAC | Pyo |  | C
98 | Benjamin Rolfe | Y | 12 | 12.1 |  |  | E |  | There seem to be a lot of MAC requirements in this subclause of the PHY specification. | Put MAC requirements in the right MAC sections? |  | A | Editorial | JPKG | A
99 | Chang woo Pyo | Y | 8 | 8.6.6.2 |  |  | T |  | Better to improve the hidden node in CAP for DEV-DEV communication | Need to discuss | Withdraw, 19 January, 2009. No change required. | C |  |  |  | C
100 | Tuncer Baykas | Y | 12 | 12.1.11 | 66 |  | T | N | Current CMS has a fixed range. Different applications may need different ranges. | Make CMS range variable. | Withdraw, 19 January, 2009. No change required. | C |  |  |  | C
101 | Tuncer Baykas | Y | 12 | 12.2.3.1 | 89 |  | T | N | Change the design of current SCPHY preambles to offer higher frame efficiency, without reducing overall frame error rate. | If possible shorten preambles. | Accept in principle: Resolve as indicated in 15-09-0021-00. | C |  |  |  | C
102 | Eduardo Casas | N | 12 | 1 to 4 | 61-156 | all | T | Y | Three PHYs are two too many. No evidence was presented that the performance of any of these PHYs is significantly better than any other so the two additional PHYs simply makes coexistence and interoperability more difficult for no good reason. ---> Clarification for LB47: The assertion that the SC PHY is optimized for low power is not self-evident since a higher rate PHY enables the device to stay in sleep mode more often thus reducing power consumption. It's also not self-evident that a fully-integrated AV or HSI PHY implementation would have significantly lower cost since it would not consume significantly smaller die area than a SC implementation (the die area being dominated by passive RF components). There seems to be no justification for including a SC PHY. The response to this comment claims that both HSI and AV PHY are optimized for low latency. This supports the original comment that one of them is redundant and should be removed. --> Comment for LB48: the stock justification for rejecting my comment did not address the substance of my previous comments (that SC implementations will not have lower power consumption for typical use cases or significantly lower costs than OFDM implementations and that both OFDM modes offer low latency). | Remove any two of sections 12.2, 12.3 and 12.4 and make editorial changes as required. | Reject: Different PHYs are a result of demands of different market segments, which are stated in the usage models. For example usage model 5 is for Kiosk applications. It demands 1.5 Gbps in 1 m range. SC-PHY can provide such a data rate in such a short range with less complexity thus lower cost than an OFDM PHY. Whereas usage model 1 requires uncompressed video streaming. Due to the nature of uncompressed video signals a special PHY (AV PHY) is selected to provide high throughput. Usage model 4 requires a Conference ad hoc system in which all devices inside the WPAN will have bidirectiona, NLOS high speed, low latency communication which is answered by HSI PHY. Mandatory data rates of all those PHYs are selected according to specific usage models. As with any other standard we want to give implementers more options than the mandatory ones, therefore for SC PHY higher data rates are introduced which require equalization. However it is not appropriate to compare optional features of SC PHY with mandatory features of any OFDM PHY. Although AV and HSI OFDM PHYs share the same modulation technique, their frame design and approach to communication is very different. | C | Multiple PHYs | Baykas |  | C
103 | Eduardo Casas |  | 12 | 12.4.1.2 | 127 | 23 | T | Y | A SIFS time of 2us corresponds to over 5000 samples at the nominal sampling rate. Such a large SIFS adds a very high per-frame overhead and results in very low throughput for applications that require transmission of short frames (such as wireless equivalents of wired peripheral buses). Note that the SIFS duration for the 802.11 OFDM PHY is only 200-320 samples. Achieving such low turn-around times is technically challenging but will be necessary if the specification is to support applications other than simple streaming and file transfer. ---> Clarification for LB47: The intent of the original comment was to point out that the proposed SIFS is very long relative to typical packet lengths used in data networks. The protocols used by these data networks cannot be easily changed and a PHY with a 5000-sample SIFS will be an inefficient transport for these protocols. --> Comment for LB48: It was acknolwedged in the LB47 comment that achieving low SIFS times is technically challenging. However, for many applications it will be latency, not the raw data rate that limits throughput. Aggregation is not a solution for protocols that involve command-response exchanges or small windows sizes. Without short SIFS the AV PHY will only be suitable for streaming and file transfer applications and would thus not be a suitable PHY for 802.15.3c. | Reduce pPHYSIFSTime to no more than 500 samples (approximately 200ns). | Reject: Keep 2 us as SIFS time for AV PHY, since the time required to switch from transmit to receive is not solely a function of the sample rate. Many other system design considerations have an impact on this time. As one example, turning the power on and off for RX and TX blocks has a time that is determined by the bypass networks on the supply lines. These current spikes often push the VCO frequency around as well, requiring time to settle. The draft provides a method for improving the efficiency of short packets by aggregation including one specifically targeted at bi-directional low-latency applications. Additional information for LB 48: For video streaming, the subframes are longer, approximately 50 us with aggregated frames having a duration > 200 us of which the 2 us SIFS is a small percentage. For data networking, the low latency aggregation is used with the HSI PHY. This PHY allows the negotiation of lower SIFS time, if supported by the devices. In addition, up to 256 subframes can be aggregated with the low latency aggregation, making longer packets. Finally, the latency of the system has a lower bound based on the duration of the beacon and CAP, which will be on the order of 100s of us. | C | AV PHY | JPKG |  | C
104 | Eduardo Casas | N | 8 | 8.16.2.2 | 56 | 50-51 | T | Y | In order to promote coexistence it is not sufficient that a multi-mode PNC transmit beacons in the CR in addition to it's preferred mode. In order to allow efficient sharing of the spectrum, a multi-mode PNC must also be capable of allocating channel time to DEVs of different modes so that piconets of different modes can operate simultaneously on the same channel. Same-channel multi-mode operation is important because in many regulatory domains there will be only three channels available and some DEVs will only be able to operate on one of these channels (since that is all that some PHYs require). ---> Additional Comment for LB47: The text now in 12.1.8 does exactly what the original recommended change said should *not* be done! --> Comment for LB48: This comment is not related to interference mitigation but to efficient sharing of spectrum. The response to my LB47 comment does not address the issue that was raised which is that the specification does not require multi-mode PNCs to receive CR -- it only requires that they transmit it. | Add text in this subclause to the effect that all PNC-capable devices shall allow SC DEVs to associate and shall respond to channel time allocation requests from SC DEVs. It is *not* sufficient to simply say that multi-mode PNCs must act as SC PNCs since this would allow such PNCs to simply transmit CR beacons and not respond to CR transmissions from DEVs. | Reject: The SC and HSI PHYs are interoperable since they are both sending CMS beacons for coexistence and interoperability. For other cases, the CMS sync frame shall be use for interference mitigation. Therefore no change is required. | C | Common mode | Sum |  | C
105 | Eduardo Casas | N | 12 | 12.1.10 | 66 | 28-42 | E | Y | examples are not normative | move all except the first sentence of this section back to an informative annex, label as informative or remove it |  | A | Editorial | JPKG | A
106 | Bruce Bosco | Y | 12 | 12.2.8.4 | 101 | 40 | E |  | Subclause title may cause confusion | change to "Bit repetition" |  | A | Editorial | JPKG | A
107 | Bruce Bosco | Y | D2 | D2.4 | 194 | 30 | E |  | "Code repetition" may cause confusion | Change "code repetition" to "bit repetition" |  | A | Editorial | JPKG | A
108 | Bruce Bosco | Y | D2 | Fig. D2.1 | 194 |  | E |  | "Code repetition" may cause confusion | Change "code repetition" to "bit repetition" in figure |  | A | Editorial | JPKG | A
109 | Bruce Bosco | Y | D2 | D2.5 | 195 | 36 | E |  | "Code repetition" may cause confusion | change to "Bit repetition" |  | A | Editorial | JPKG | A
110 | Bruce Bosco | Y | D2 | D2.5 | 195 | 43 | E |  | "Code repetition" may cause confusion | change to "Bit repetition" |  | A | Editorial | JPKG | A
111 | Bruce Bosco | Y | D2 | Fig. D2.2 | 195 | 45 | E |  | "Code repetition" may cause confusion | Change "code repetition" to "bit repetition" in figure |  | A | Editorial | JPKG | A
112 | Bruce Bosco | Y | 12 | 12.2.8 | 100 | 17 | E |  | 12.2.8 is description of optional PHY modes. Seems like following other PHY modes, many of which are optional, directly. We accept the description of OOK/DAMI in 12.2.8 with details in Annex D2. | Consider moving 12.2.8 immediately following 12.2.2.1. Moving MCS table (Table 121) would be sufficient. Remainder can stay in 12.2.8. |  | A | Editorial | JPKG | A
113 | Hiroshi Harada | Y | 12 | 12.1.11.6.1 | 70 | 40 | E |  | "Seed" must be "seed" by talking Figure 134 expression into account | Change it. |  | A | Editorial | JPKG | A
114 | Hiroshi Harada | Y | 12 | 12.2.2.1 | 76 | 42-42 | T |  | A modulation scheme pi/2 QPSK+RS(255,239)+SF=1 must be included. This scheme can easily increase data rate by using 2 streams of LR1-SF1 (mandatory mode). The circuti size of the modululation and demodulation size is much lower than that used LDPC. This is very useful for short range and broadband communication for KIOSK and video transmission with the rate of around 3Gbps. The data rate may be similar with MR4. To include both or either of them, is discussion point. | Please include (or recover) pi/2 QPSK+RS(255,239)+SF=1 to realize simple short range communciation system. | Accept. Use numbers from D00 | C | SC PHY | Sum |  | C
115 | Hiroshi Harada | Y | 12 | 121.2.2.9 | 87 | 2 | E |  | Please cleary state "UEP is an optional function "in this section. This is because the readers who only read PHY part misunderstand that UEP is mandatory mode. | Please cleary state "UEP is an optional function". |  | A | Editorial | JPKG | A
116 | Hiroshi Harada | Y | 12 | 12.3.2.1 | 103 | 25-48 | E |  | Please use same notation between Table 122 and Tables 137 and 138. Nevertheless both use OFDM, this feels quite strange if differenct expression is used. | Please use same same index in colum and row for both figure. |  | A | Editorial | JPKG | A
117 | Hiroshi Harada | Y | 12 | 12.3.2.3 | 105 | 1 | E |  | Please unify the expression, variables between Table 125 and Tables 143 and 144. Nevertheless both use OFDM, this feels quite strange if differenct expression is used. | HIS-OFDM and AV-OFDM use OFDM, so please use same notation to express general parameters in order to make the standardized document easy to read. |  | A | Editorial | JPKG | A
118 | Hiroshi Harada | Y | 12 | 12.3.2.4 | 106 | 18 | E |  | What means of doted line to express the block of bit inter leaver. | Please explain why doted line is needed ortherwize remove it. |  | A | Editorial | JPKG | A
119 | Hiroshi Harada | Y | 12 | 12.4 | 125 | 8 | E |  | Please use same notation between Table 122 and Tables 137 and 138. Nevertheless both use OFDM, this feels quite strange if differenct expression is used. | Please use same same index in colum and row for both figure. |  | A | Editorial | JPKG | A
120 | Hiroshi Harada | Y | 12 | 12.4.2 | 129 | 10 -48 | E |  | Please unify the expression, variables between Table 125 and Tables 143 and 144. Nevertheless both use OFDM, this feels quite strange if differenct expression is used. | HIS-OFDM and AV-OFDM use OFDM, so please use same notation to express general parameters in order to make the standardized document easy to read. |  | A | Editorial | JPKG | A
121 | Hiroshi Harada | Y | 12 | 12.4.2 | 130 | 2-24 | E |  | Is the block "upconversion" needed in Figures 187 and 188? This is because somebody may be use D/A converter after symbol shaping. This is not unpconversion. | Remove it. |  | A | Editorial | JPKG | A
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309 | [14 empty] | 0
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
Note on A1: An integer, starting with 1, incrementing by one.
Note on C1: Affiliation of the voter
Note on H1: Enter T for technical, E for editorial
Note on L1: Do not make entries, to be filled out in comment resolution
Note on M1: Do not make entries, to be filled out in comment resolution
Note on N1: Do not make entries, to be filled out in comment resolution

## Status
Technical comments |  |  | Percent complete
Open | O | 0 | 0%
Assigned | A | 4 | 11.43%
Closed | C | 31 | 88.57%
Written | W | 0 | 0%
Total |  | 35
Editorial comments |  |  | Percent complete
Open | O | 0 | 0%
Assigned | A | 68 | 79.07%
Closed | C | 18 | 20.93%
Written | W | 0 | 0%
Total |  | 86
Total # comments |  |  | Percent complete
Open | O | 0 | 0%
Assigned | A | 72 | 59.5%
Closed | C | 49 | 40.5%
Written | W | 0 | 0%
Total |  | 121
Initial tally
Technical | T | 35
Editorial | E | 86
Total |  | 121

## Commenter summary
Commenter name | Vote | Email address | Affiliation | # comments | File name | 1st CID | Last CID
Chin-Sean Sum | Y | sum@nict.go.jp | NICT | 1 | TG3c-comment-sheet-Chin-Sean-Sum.xls | 1 | 1
Raymond Yu Zhan | Y | Raymond.Yuz@sg.panasonic.com | Panasonic | 8 | TG3c-comment-form (Raymond Yu Zhan).xls | 2 | 9
Michael Sim | Y | Michael.Simhc@sg.panasonic.com | Panasonic | 2 | TG3c-comment-form (Michael Sim).xls | 10 | 11
Junyi Wang | Y | junyi.wang@nict.go.jp | NICT | 44 | LB48-WANG-JUNYI-YES.xls | 12 | 55
Ismail Lakkis | Y | ilakkis@yahoo.com | Tensorcom | 15 | TG3c-comment-form.xls | 56 | 70
Rick Roberts | N | richard.d.roberts@intel.com | Intel | 2 | Rick-Roberts-TG3c-comment-entry-form.xls | 71 | 72
Christopher Hansen | N | chansen@broadcom.com | Broadcom | 3 | TG3c-comment-entry-form-lb-48-Hansen.xls | 73 | 75
Henk de Ruijter | Y | Hendricus.DeRuijter@silabs.com | Silicon Lab | 1 | TG3c-comment-entry-form.xls | 76 | 76
Yongsun Kim | Y | doori@etri.re.kr | ETRI | 13 | LB48comments_yongsunkim.xls | 77 | 89
Benjamin Rolfe | Y | ben@blindcreek.com | Self | 9 | TG3c-comment-entry-form-LB48-BRolfe.xls | 90 | 98
Chang woo Pyo | Y | cwpyo@nict.go.jp | NICT | 1 | TG3c-comment-entry-form-changwoopyo.xls | 99 | 99
Tuncer Baykas | Y | tbaykas@gmail.com | NICT | 2 | TG3c-comment-sheet-D04-Baykas.xls | 100 | 101
Eduardo Casas | N | eduardo.casas@intel.com | Intel | 4 | TG3c-comment-sheet.xls | 102 | 105
Bruce Bosco | Y | Bruce.A.Bosco@motorola.com | Motorola | 7 | lb48-comments-Bruce_Bosco.xls | 106 | 112
Hiroshi Harada | Y | harada@nict.go.jp | NICT | 9 | TG3c-comment-entry-form_Harada.xls | 113 | 121
Total # comments |  |  |  | 121
Total # commenters |  |  |  | 15
Total # approve |  |  |  | 12
Total # disapprove |  |  |  | 3