## IEEE Cover
July, 2009 |  | IEEE P802.15.3-09/0493r00
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15.3c Sponsor Ballot (SB1) Comments
Date Submitted | July, 2009
Source | James P. K. Gilb | Voice: (858)-240-2950
| SiBEAM | Fax: [ ]
| 555 N. Mathilda, Suite 100 | E-mail: last name at ieee dot org
Sunnyvale, CA 94085
Re: | 802.15.3c SB3 comments
Abstract | This document contains comments submitted by voters for the second recirculation sponsor ballot (SB3) of the 802.15.3c draft spec. D10.
Purpose | [This document provides contains the comments for SB3.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Comment Entry
Comment ID | Date | Comment # | Name | Email | Phone | Style | Index # | Classification | Vote | Affiliation | Category | Page | Subclause | Line | Comment | File | Must Be Satisfied | Proposed Change | Resolution Status | Resolution Detail | Other1 | Other2 | Other3 | Type | Assigned | Time | Editorial | Technical
6757800023 | 7-Jul-2009 5: 2:55 EDT | 9 | Noda, Makoto | makotob.noda@jp.sony.com | +81 3 5448 4619 | Individual | 9 | Producer | Approve | Sony Corporation | Editorial | 101 | 12.3.2.4.2 | 26 | The symbols for mutiplexer outputs b0, b1, ... has been defined as an unscrambled data bit bn in the line 25 in p. 85. |  | No | Unify the definition of bn. | [8 empty] | 0
6757700023 | 7-Jul-2009 8: 2:55 EDT | 8 | Noda, Makoto | makotob.noda@jp.sony.com | +81 3 5448 4619 | Individual | 8 | Producer | Approve | Sony Corporation | Technical | 92 | 12.2.4.3 | 42 | Although a good example to generate RF center frequency and symbol clock frequency from the same reference oscillator has been shown in the Slide 8 of the document 07/760/r0 for the symbol clock frequency of 1728 MHz, no example has been shown for the symbol clock frequency of 1760 MHz. Thus the feasibility of "The transmit center frequency ... from the same reference oscillator" is not clear. |  | No | Please post a document to IEEE server showing an example to generate RF center frequency and symbol clock frequency from the same reference oscillator for the symbol clock frequency of 1760 MHz. No change is required if the example is reasonable. | [9 empty] | 0
6757600023 | 7-Jul-2009 8: 2:55 EDT | 7 | Noda, Makoto | makotob.noda@jp.sony.com | +81 3 5448 4619 | Individual | 7 | Producer | Approve | Sony Corporation | Editorial | 81 | 12.2.2.7 | 46 | Rate-14/15 LDPC code is regular. |  | No | "rate 14/15 irregular LDPC" should be simply "rate-14/15 LDPC". | [8 empty] | 0
6757500023 | 7-Jul-2009 8: 2:55 EDT | 6 | Noda, Makoto | makotob.noda@jp.sony.com | +81 3 5448 4619 | Individual | 6 | Producer | Approve | Sony Corporation | Technical | 75 | 12.2.2.5.1 | 48 | Definition of dn is inconsistent with Fig. 164. For BPSK/(G)MSK modulation, a datum chip dn of -1 or 1 is not associated with an input bit of 0 or 1. For other modulations, the symbol dn indicates an input bit. |  | No | Define an input bit as dn and a datum chip gn as (1-2*dn). Associate each constellation point with input bit dn in Fig. 164 (a) and (b). | [9 empty] | 0
6757400023 | 7-Jul-2009 8: 2:55 EDT | 5 | Noda, Makoto | makotob.noda@jp.sony.com | +81 3 5448 4619 | Individual | 5 | Producer | Approve | Sony Corporation | Editorial | 72 | 12.2.2.1 |  | Some data rates listed in Table 103 are not correct. |  | No | Correct the data rates as 825 for MCS2 with PW=0, 2700 for MCS9 with PW=64, 2870 for MCS10 with PW=64, and 2890 for MCS11 with PW=64. | [8 empty] | 0
6757300023 | 7-Jul-2009 8: 2:55 EDT | 4 | Noda, Makoto | makotob.noda@jp.sony.com | +81 3 5448 4619 | Individual | 4 | Producer | Approve | Sony Corporation | Technical | 64 | 12.1.8.3 | 2 | Pilot word length 64 is mandatory as shown in Table 115. The default of Received Status field, however, suggests SC pilot word length 0. |  | No | The default value for the SC pilot word may be 00. | [9 empty] | 0
6757200023 | 7-Jul-2009 8: 2:55 EDT | 3 | Noda, Makoto | makotob.noda@jp.sony.com | +81 3 5448 4619 | Individual | 3 | Producer | Approve | Sony Corporation | Editorial | 64 | 12.1.8.3 | 2 | Definition of "default" is not clear. The "default" is provided in Pilot Word Type field but that is not provided in Preamble Type field. |  | No | Describe the definition of "default". If the words of "default" in this draft are not necessary, remove them. | [8 empty] | 0
6757100023 | 7-Jul-2009 8: 2:55 EDT | 2 | Noda, Makoto | makotob.noda@jp.sony.com | +81 3 5448 4619 | Individual | 2 | Producer | Approve | Sony Corporation | Technical | 30 | 40728 | 46 | Pilot word length 64 is mandatory as shown in Table 115. The capability field, however, permits a pilot word length 0 or 8 only. |  | No | Define the Pilot Word Capability field as; 0: Support pilot word length 64 only, 1: Support pilot word lengths 8 and 64, 2: Support pilot word lengths 0 and 64, 3: Support pilot word lengths 0, 8 and 64. | [9 empty] | 0
6757000023 | 7-Jul-2009 8: 2:55 EDT | 1 | Noda, Makoto | makotob.noda@jp.sony.com | +81 3 5448 4619 | Individual | 1 | Producer | Approve | Sony Corporation | Technical | 27 | 40728 |  | Because PCES is an optional feature defined in 12.2.3.4.2 and 12.3.2.10, capability IE would have a field for its capability. |  | No | Add a field to indicate PCES capability, if necessary. | [9 empty] | 0
Note on T1: Agree Principle Disagree Out of scope Unresolvable

## Summary
Check:
Regular expressions are disabled
Whole cell matching is enabled
Technical | 5 | Overall | 9
Open | 5 | Open | 9
Suggested | 0 | Suggested | 0
Agree | 0 | Agree | 0
Disagree | 0 | Disagree | 0
Principle | 0 | Principle | 0
Out of scope | 0 | Out of scope | 0
Unresolvable | 0 | Unresolvable | 0
Total resolved | 0 | Total resolved | 0
Percent | 0% | Percent | 0%
Editorial | 4
Open | 4
Suggested | 0
Agree | 0
Disagree | 0
Principle | 0
Out of scope | 0
Unresolvable | 0
Total resolved | 0
Percent | 0%
Written | 0
Percent | 0%
Assigned
JPKG | 0
Sum | 0
Lan | 0
Tuncer | 0
Total assigned | 0
Percent | 0%