IEEE P802.15

Wireless Personal Area Networks

| Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs) |  |
| --- | --- | --- |
| Title | Schedule |  |
| Date Submitted | 5 August, 2010 |  |
| Source | Clint Chaplin Samsung Electronics 75 W. Plumeria Drive, San Jose, CA 95134 | Voice: +1-408-768-0827 Fax: E-mail: clint.chaplin@gmail.com |
| Re: |  |  |
| Abstract | 802.15.7 Schedule |  |
| Purpose | Informational |  |
| Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein. |  |
| Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15. |  |

| ~ 802.15.7 Calendar August 2010 ~ |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
| 1 | 2 Ad-Hoc | 3 Ad-Hoc | 4 Ad-Hoc | 5 Ad-Hoc Generate “rip” for attendees to review | 6 Review and fix document | 7 Review and fix document |
| 8 Review and fix document | 9 Review and fix document | 10 Review and fix document. Sponsor Ballot Formation closes | 11 Review and fix document | 12 Review and fix document | 13 Review and fix document | 14 Review and fix document |
| 15 Editors finalize document | 16 Editors finalize document | 17 Editors finalize document | 18 Editors finalize document | 19 Send finalized document to Rick Alfin. Send document out for MEC | 20 Start first WG recirculation ballot. | 21 |
| 22 | 23 | 24 | 25 | 26 | 27 | 28 |
| 29 | 30 | 31 | Notes: |  |  |  |

| ~ 802.15.7 Calendar September 2010 ~ |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  |  |  | 1 | 2 | 3 | 4 First WG recirculation ballot closes |
| 5 | 6 | 7 | 8 Ad-Hoc | 9 Ad-Hoc | 10 Ad-Hoc | 11 Ad-Hoc |
| 12 IEEE 802.15 meeting | 13 IEEE 802.15 meeting | 14 IEEE 802.15 meeting | 15 IEEE 802.15 meeting | 16 IEEE 802.15 meeting | 17 IEEE 802.15 meeting. Start EC ballot for approval to forward to Sponsor ballot | 18 |
| 19 Start second WG recirculation ballot | 20 | 21 | 22 | 23 | 24 | 25 |
| 26 | 27 | 28 | 29 | 30 | Notes: |  |

| ~ 802.15.7 Calendar October 2010 ~ |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  |  |  |  |  | 1 | 2 EC ballot for approval to forward to Sponsor ballot closes |
| 3 | 4 Second WG recirculation ballot closes | 5 | 6 Start initial Sponsor Ballot | 7 | 8 | 9 |
| 10 | 11 | 12 | 13 | 14 | 15 | 16 |
| 17 | 18 | 19 | 20 | 21 | 22 | 23 |
| 24 | 25 | 26 | 27 | 28 | 29 | 30 |
| 31 | Notes: |  |  |  |  |  |

| ~ 802.15.7 Calendar November 2010 ~ |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  | 1 | 2 | 3 | 4 | 5 Initial Sponsor ballot closes | 6 |
| 7 | 8 IEEE 802 Plenary | 9 IEEE 802 Plenary | 10 IEEE 802 Plenary | 11 IEEE 802 Plenary | 12 IEEE 802 Plenary | 13 IEEE 802 Plenary |
| 14 | 15 | 16 | 17 | 18 | 19 | 20 |
| 21 | 22 | 23 | 24 | 25 | 26 | 27 |
| 28 | 29 | 30 | Notes: |  |  |  |

| ~ 802.15.7 Calendar December 2010 ~ |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  |  |  | 1 | 2 | 3 | 4 |
| 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| 19 | 20 | 21 | 22 | 23 | 24 | 25 |
| 26 | 27 | 28 | 29 | 30 | 31 | Notes: |