## IEEE Cover
December, 2010 |  | IEEE P802.15.3-10/0946r03
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15.4i Letter Ballot Comments, initial ballot
Date Submitted | December, 2010
Source | James P. K. Gilb | Voice: (858)-240-2950
| Self | Fax: [ ]
E-mail: last name at ieee dot org
Re: | 802.15.4i-D02.pdf
Abstract | This document contains comments submitted by voters for the initial letter ballot of the 802.15.4i draft spec. D02.
Purpose | [This document provides contains the comments for WG LB64.
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Comment Entry
CID | Name | Affiliation | Category | Page | Subclause | Line | Comment | Proposed Change | Must Be Satisfied | Resolution Status | Resolution Detail | Other1 | Other2 | Other3 | Type | Assigned | Time | Editorial | Technical
1 | Ed Callaway | Sunrise Micro Devices | Editorial | 1 | 1.3 | 45 | "is accurate to one meter" seems a little strong of a statement, considering some of the implementers with which I'm familiar. | "may be accurate to one meter" | No | Disagree | This section is an exact copy of the PAR that has been submitted for revision. The WG cannot change this subclause. No change required. |  |  |  | Written |  |  | Disagree
2 | Ed Callaway | Sunrise Micro Devices | Editorial | 7 | 4.1 | 14 | "Unique 64-bit extended addresses or allocated 16-bit short address" seems like a plural-singular symmetry violation, especially since each device has a unique 64-bit extended address. (Yes, I know it wasn't edited.) | "Unique 64-bit extended address or allocated 16-bit short address" | No | Agree |  |  |  |  | Written |  |  | Agree
3 | Ed Callaway | Sunrise Micro Devices | Editorial | 17 | 5.1 | 30 | "Table 69.." should be "Table 69." | Make it so. | No | Agree |  |  |  |  | Written |  |  | Agree
4 | Ed Callaway | Sunrise Micro Devices | Editorial | 17 | 5.1 | 33 | "… “phy” and are listed …": For symmetry purposes I'd like to see an example similar to that of the MAC PIB description. | "… “phy”, e.g., phyCurrentChannel, and are listed ..." | No | Agree |  |  |  |  | Written |  |  | Agree
5 | Ed Callaway | Sunrise Micro Devices | Editorial | 18 | 5.1.1.1 | 24 | "PANs that wish to use the superframe structure (referred to as a beacon-enabled PAN) shall ..." has a plural-singular symmetry violation. (Yes, I know it wasn't edited.) | "PANs that wish to use the superframe structure (referred to as beacon-enabled PANs) shall ..." | No | Agree |  |  |  |  | Written |  |  | Agree
6 | Ed Callaway | Sunrise Micro Devices | Editorial | 18 | 5.1.1.1 | 28 | "PANs that do not wish to use the superframe structure (referred to as a nonbeacon-enabled PAN) shall ..." has a plural-singular symmetry violation. (Yes, I know it wasn't edited.) | "PANs that do not wish to use the superframe structure (referred to as nonbeacon-enabled PANs) shall ..." | No | Agree |  |  |  |  | Written |  |  | Agree
7 | Ed Callaway | Sunrise Micro Devices | Editorial | 24 | 5.1.2.1.2 | 35 | "A device shall be able to store between one and an implementation-specified maximum number of PAN descriptors." | Is this equivalent to, "A device shall be able to store at least one PAN descriptor"? | No | Agree |  |  |  |  | Written |  |  | Agree
8 | Ed Callaway | Sunrise Micro Devices | Editorial | 28 | 5.1.2.3.1 | 13 | "… MLME-RESET.request, as descrbied in 6.2.7.1, primitive with ..." is disconbobulated in at least two dimensions (syntax and spelling). | "...MLME-RESET.request primitive, as described in 6.2.7.1, with..." | No | Agree |  |  |  |  | Written |  |  | Agree
9 | Ed Callaway | Sunrise Micro Devices | Editorial | 28 | 5.1.2.3.1 | 22 | "… MLME-START.confirm, as described in 6.2.11.2, primitive with ..." is disconbobulated (syntax). | "… MLME-START.confirm primitive, as described in 6.2.11.2, with ..." | No | Agree |  |  |  |  | Written |  |  | Agree
10 | Ed Callaway | Sunrise Micro Devices | Editorial | 32 | 5.1.3.1 | 44 | "… MLME-ASSOCIATE.confirm primitive, as descrived in 6.2.1.4, with ..." | "… MLME-ASSOCIATE.confirm primitive, as described in 6.2.1.4, with ..." | No | Agree |  |  |  |  | Written |  |  | Agree
11 | Ed Callaway | Sunrise Micro Devices | Editorial | 95 | 6.2.5.4 | 36 | Figure 59 has the ACK spelled "Acknowledgement"; this represents one of the four instantiations of this spelling in the document. (Yes, I know it wasn't edited.) | Everywhere else it's "Acknowledgment" (much to my distaste, as I'm an "Acknowledgement" guy, but there it is). | No | Agree |  |  |  |  | Written |  |  | Agree
12 | Ed Callaway | Sunrise Micro Devices | Editorial | 84 | 6.2.3 | 10 | Figures 56 and 57 (twice) have the ACK spelled "Acknowledgement"; this represents one of the four instantiations of this spelling in the document. (Yes, I know it wasn't edited.) | Everywhere else it's "Acknowledgment" (much to my distaste, as I'm an "Acknowledgement" guy, but there it is). | No | Agree |  |  |  |  | Written |  |  | Agree
13 | Ed Callaway | Sunrise Micro Devices | Editorial | 33 | 5.1.3.1 | 17 | "if the association response command frame was not received" should not have been changed -- it was correct as written. | change it back to "if [noun] … were not received …" The verb is in a subjunctive mood, since it deals with a hypothetical situation. | No | Agree |  |  |  |  | Written |  |  | Agree
14 | Ed Callaway | Sunrise Micro Devices | Editorial | 38 | 5.1.6.1 | 12 | "If the status from the outgoing frame security procedure is SUCCESS, in order transmit the frame, the MAC sublayer shall transmit the frame." Eh? | Maybe, "If the status from the outgoing frame security procedure is SUCCESS, the MAC sublayer shall transmit the frame."? | No | Agree |  |  |  |  | Written |  |  | Agree
15 | Ed Callaway | Sunrise Micro Devices | Editorial | 39 | 5.1.6.2 | 54 | "it shall match macExtendedAddress or a broadcast or multicast extended address." To the best of my knowledge and belief, there are no broadcast or multicast extended addresses supported in 15.4. They're all short addresses. | "it shall match macExtendedAddress." | No | Principle | Change "or a broadcast or multicast extended address" to be "or an extended addres with the group it set, as defined in IEEE Std 802-2001." |  |  |  | Written |  |  | Principle
16 | Ed Callaway | Sunrise Micro Devices | Editorial | 50 | 5.1.8.3 | 52 | "… sendingthe frame" should be, at least, "… sending the frame." But, of course, the receiving device didn't send the frame, so this doesn't make much sense, either. | How about, "… sending the frame (for the originator) and receiving the frame (for the recipient)."? | No | Agree |  |  |  |  | Written |  |  | Agree
17 | Ed Callaway | Sunrise Micro Devices | Editorial | 58 | 5.2.2.1.1 | 11 | Tsk! A subfield! I thought they were all extinct by now. | Change "subfield" to "field". | No | Agree |  |  |  |  | Written |  |  | Agree
18 | Ed Callaway | Sunrise Micro Devices | Editorial | 87 | 6.2.3.1 | 20 | Question: If "for other PHY types, this is an empty list", as mentioned in the CodeList description in Table 17, isn't it necessary to include this possibility in the Valid Range column? I mean, most other parameters must have a value, and a non-entry would be a problem for them. This situation occurs in many other Tables, so I may live to regret this comment. | Append "Otherwise, an empty list." to the CodeList Valid Range entry. | No | Principle | Change the vaild range entry to be "-" because the allowed values are more fully described in th description. |  |  |  | Written |  |  | Principle
19 | Ed Callaway | Sunrise Micro Devices | Editorial | 88 | 6.2.3.2 | 43 | "processing:," in the SecurityLevel description in Table 18, should be "processing,". | Make it so. | No | Agree |  |  |  |  | Written |  |  | Agree
20 | Ed Callaway | Sunrise Micro Devices | Editorial | 89 | 6.2.4.1 | 51 | The PIBAttributeIndex parameter was put in so that, for example, individual channel pages in phyChannelsSupported could be requested, without handling The Whole Thing™. While I admit that phyChannelsSupported is one of the worst data structures ever conceived by the mind of man, we're stuck with it. Was the PIBAttributeIndex parameter taken out for a reason? (Although as I write this I see that it's only valid for the MAC PIB, not the PHY, which only goes to show that I don't know what I'm talking about. Oh, well.) | Consider replacing the PIBAttributeIndex parameter in 6.2.4 and 6.2.10. Just consider it. | No | Principle | Add "as defined in Table 70" to the valid range for the primitives in 6.2.4 and 6.2.10. Any individual PHY PIB attribute can be requested individually through this interface by specifying the PHY PIB item. |  |  |  | Written |  |  | Principle
21 | Ed Callaway | Sunrise Micro Devices | Editorial | 99 | 6.2.7.1 | 25 | "… in an implementation dependent manner" needs a hyphen. | "… in an implementation-dependent manner." | No | Agree |  |  |  |  | Written |  |  | Agree
22 | Ed Callaway | Sunrise Micro Devices | Editorial | 103 | 6.2.9.1 | 7 | Table 30: If ScanChannels is a "list of integers," its valid range can't be "any valid channel number," unless you're only considering very short lists. It can be "any list of valid channel numbers," for example… | Change the ScanChannels Valid Range entry to, "Any list of valid channel numbers." | No | Agree |  |  |  |  | Written |  |  | Agree
23 | Ed Callaway | Sunrise Micro Devices | Editorial | 105 | 6.2.9.2 | 17 | Table 31: If UnscannedChannels is a "list of integers," its valid range can't be "any valid channel number," unless you're only considering very short lists. It can be "any list of valid channel numbers," for example… | Change the UnscannedChannels Valid Range entry to, "Any list of valid channel numbers." | No | Agree |  |  |  |  | Written |  |  | Agree
24 | Ed Callaway | Sunrise Micro Devices | Editorial | 108 | 6.2.11.1 | 37 | "The channel page on to use." | "The channel page to use." | No | Agree |  |  |  |  | Written |  |  | Agree
25 | Ed Callaway | Sunrise Micro Devices | Editorial | 115 | 6.2.12.2 | 27 | The end of this section needs a period (full stop). | Make it so. | No | Agree |  |  |  |  | Written |  |  | Agree
26 | Ed Callaway | Sunrise Micro Devices | Editorial | 123 | 6.3.1 | 54 | "transfer of a data" | "transfer of data" | No | Agree |  |  |  |  | Written |  |  | Agree
27 | Ed Callaway | Sunrise Micro Devices | Editorial | 126 | 6.3.2 | 38 | "transfer of a data" | "transfer of data" | No | Agree |  |  |  |  | Written |  |  | Agree
28 | Ed Callaway | Sunrise Micro Devices | Editorial | 129 | 6.3.3 | 3 | "reception of data another device." | "reception of data from another device." | No | Agree |  |  |  |  | Written |  |  | Agree
29 | Ed Callaway | Sunrise Micro Devices | Editorial | 130 | 6.3.3 | 38 | "Non-UWB PHYs use a value of OFF." Eh? UWBPRF is an integer. | I have no idea. "Non-UWB PHYs ignore this parameter."? | No | Principle | Change to "This parameter shall be ignored by non-UWB PHYs." |  |  |  | Written |  |  | Principle
30 | Ed Callaway | Sunrise Micro Devices | Editorial | 134 | 6.4.4 | 14 | Are the unusual brackets around 6 × phySymbolsPerOctet in Equation (1) meant to indicate the ceiling function, or are they just strange brackets? | If they do represent the ceiling function, then (a) I would replace them with ceil(•), as in Equation (3), and (b) in both places, indicate the level of ceiling significance (is it rounded up to the octet? Backoff period? What?) If they do not represent the ceiling function, then I would replace them with parentheses. | No | Principle | Change the equation to use "ceil()" and indicate that it is the next highest integer number of symbols in the text. |  |  |  | Written |  |  | Principle
31 | Ed Callaway | Sunrise Micro Devices | Editorial | 134 | 6.4.4 | 30 | I find the separate listing of variable (and constant!) definitions difficult to read in this section -- especially since there are so few of them, and much of the explanation is describing where a particular number came from. | Describe the numbers and variables in a text format, as was done following Equation (1). It's much easier to read than a list that starts with "7", and has only two entries. | No | Agree |  |  |  |  | Written |  |  | Agree
32 | Ed Callaway | Sunrise Micro Devices | Editorial | 162 | 8.1.2 | 27 | "channels pages" should be "channel pages". Also, a period (full stop) is needed at the end of this paragraph. | Make it so. | No | Agree |  |  |  |  | Written |  |  | Agree
33 | Ed Callaway | Sunrise Micro Devices | Editorial | 163 | 8.1.2.2 | 11 | "channels numbers" | "channel numbers" | No | Agree |  |  |  |  | Written |  |  | Agree
34 | Ed Callaway | Sunrise Micro Devices | Editorial | 170 | 9.1 | 29 | "The PHY SAP and PLME SAP are not defined in this standard as they are rarely, if ever, exposed in a typical implementation." | How about, "The PD-SAP and PLME-SAP are not defined in this standard as they are not expected to be exposed in a typical implementation."? | No | Agree |  |  |  |  | Written |  |  | Agree
35 | Ed Callaway | Sunrise Micro Devices | Editorial | 174 | 9.4 | 27 | Again, the ceiling function needs a significance statement, throughout this subclause. aMaxPHYPacketSize + 1 is rounded up to the next … what? It's already defined in octets. Backoff periods? | Add a significance statement to the ceiling function in the text. | No | Principle | Indicate in the text that it is the next highest integer number of symbols. |  |  |  | Written |  |  | Principle
36 | Ed Callaway | Sunrise Micro Devices | Editorial | 174 | 9.4 | 54 | What's "phyMaxFrameDurationηs"? | Is it supposed to be "phyMaxFrameDuration"? "phyMaxFrameDuration ns" [!]? | No | Principle | This was broken in 802.15.4a-2007 (aside from the general brokenness of adding UWB PHYs). Change to "phyMaxFrameDuration" and search for otther occurances (they use the plural sometimes in 802.15.4a-2007.) |  |  |  | Written |  |  | Principle
37 | Ed Callaway | Sunrise Micro Devices | Editorial | 235 | 14.4.5 | 52 | "he UWB PHY supports the CCA modes defined 8.2.9" probably should be, "The UWB PHY supports the CCA modes defined in 8.2.9." | Make it so. | No | Agree |  |  |  |  | Written |  |  | Agree
38 | Ed Callaway | Sunrise Micro Devices | Editorial | 244 | 15.2.4 | 23 | Good try -- I mean, it is an improvement over "Guassina" -- but how about "Gaussian filter"? :-) | Make it so. | No | Agree |  |  |  |  | Written |  |  | Agree
39 | Ed Callaway | Sunrise Micro Devices | Editorial | 244 | 15.2.4 | 27 | Second sentence should start with a capital letter: "The deviation shall ..." | Make it so. | No | Agree |  |  |  |  | Written |  |  | Agree
40 | Ed Callaway | Sunrise Micro Devices | Editorial | 272 | D.7.1 | 20 | "The requirements for the functional device types is ..." | "The requirements for the functional device types are ..." | No | Agree |  |  |  |  | Written |  |  | Agree
41 | Ed Callaway | Sunrise Micro Devices | Editorial | 311 | G.1 | 17 | "… but that operation these bands is not described in this Annex." | "… but operation in those bands is not described in this Annex." | No | Agree |  |  |  |  | Written |  |  | Agree
42 | Ed Callaway | Sunrise Micro Devices | Editorial | 314 | G.4 | 17 | "The transmit power (EIRP) is limited to 10 mW" really belongs in its own subclause, a new G.4.1 entitiled "Transmit Power". The first (and only) sentence of G.4 itself should say something moronic like, "The following specifies CWPAN MPSK PHY radio performance", or words similar. | Make it so. | No | Agree |  |  |  |  | Written |  |  | Agree
43 | Ed Callaway | Sunrise Micro Devices | Editorial | 315 | G.4.5 | 16 | "and channel 0 is the alternate channels." | "and channel 0 is an alternate channel." (The channel numbering scheme makes it difficult for me to tell if channel 4 is a viable alternate channel, so I wimped out.) | No | Agree |  |  |  |  | Written |  |  | Agree
44 | Ed Callaway | Sunrise Micro Devices | Editorial | 164 | 8.1.2.4 | 33 | "across 780 MHz band" should be, "across the 780 MHz band". | Make it so. | No | Agree |  |  |  |  | Written |  |  | Agree
45 | Ed Callaway | Sunrise Micro Devices | General | 316 | H.2 | 33 | "PIB parameter": Shouldn't this be "PIB attribute"? I found a few other instances of "PIB parameter" outside of Annex H, too. (Yes, I know they weren't edited.) | Globally replace "PIB parameter" with "PIB attribute". | No | Agree |  |  |  |  | Written |  |  |  | Agree
46 | Yang Yang | SIMIT,CAS / WSNIRI | Editorial | 23 | 5.1.2.1.2 | 29 | “Pasive chanel" | change to "Passive channel" | Yes | Agree |  |  |  |  | Written |  |  | Agree
47 | Yang Yang | SIMIT,CAS / WSNIRI | Editorial | 23 | 5.1.2.1.2 | 30 | "communicatons" | change to "communications" | Yes | Agree |  |  |  |  | Written |  |  | Agree
48 | Yang Yang | SIMIT,CAS / WSNIRI | Editorial | 23 | 5.1.2.1.2 | 45 | “set to indicate an active scan" | change to "set to indicate an active or passive scan" | Yes | Agree |  |  |  |  | Written |  |  | Agree
49 | Yang Yang | SIMIT,CAS / WSNIRI | Editorial | 23 | 5.1.2.1.2 | Figure 19 | name of scan in this figure is wrong. | change the two "Passive scan" to "Active scan" | Yes | Agree |  |  |  |  | Written |  |  | Agree
50 | Yang Yang | SIMIT,CAS / WSNIRI | Editorial | 27 | 5.1.2.2.2 | 44 | "AR field" is not a correct description. | change it to "Acknowledgement Request field", and find other places to change it. | Yes | Disagree | The draft consistently uses "AR field" to refer to this field. In Figure 31, the field is "AR" and in 5.2.1.1.4, where the field is defined, it is referred to as the AR field. |  |  |  | Written |  |  | Disagree
51 | Charles Farlow | Medtronic | Technical | 211-242 | 14 |  | The comment I submitted with Letter Ballot #58: [Sub-clause 15.1 introduces a "sub-GHz UWB" mode as "The sub-gigahertz band, which consists of a single channel and occupies the spectrum from 249.6 MHz to 749.6 MHz" and Table F.19 (Table F.19-UWB average emission limits, EIRP in dBm/MHz) references FCC 15.209. Two fundamental comments: 1) If the draft means to convey that such a "sub-GHz UWB" mode currently falls within the regulatory framework of FCC Rule 15.209, then the operation of said mode must also comply with the restricted band provisions defined in FCC Rule 15.205, which would prevent use of a 500 MHz swath of spectrum. There are no provisions in the "sub-GHz UWB" PHY to explicitly control emissions into the restricted bands set forth in FCC Rule 15.205. 2) If the proposal is analyzed under the UWB provisions of Subpart F of Part 15 of the FCC rules, which deals explicitly with UWB, then FCC Rule 15.205 does not apply. However, Subpart F restricts operation below 960 MHz to applications such as through-the-wall imaging (only for certain emergency personnel), wall imaging systems, and ground penetrating radar. "Sub-GHz UWB" operation for personal area network communication is not permissible under FCC rules as they exist today.] was not resolved to my satisfaction. | Remove the "sub-GHz UWB" mode of operation from the standard. This change is identical to the one proposed in my response to Letter Ballot #58. On Nov. 11, 2010, I e-mailed James Gilb in response to the proposed Letter Ballot #58 resolution: [The reply does not address my comments or concerns. The FCC Rules do not support the sort of devices the standard contemplates operating on an ultra-wideband basis over the band 249.6 MHz to 749.6 MHz. Further, the IEEE Code of Ethics states "1. to accept responsibility in making decisions consistent with the safety, health and welfare of the public, and to disclose promptly factors that might endanger the public or the environment;" Accordingly, an IEEE standard must not specify systems contrary to published regulations in those geographies where there is an explicit or implied intent to market products compliant to said standard.] | Yes | Disagree | The group has reconsidered this comment and has decided not to make the change because the FCC has approved sub GHz UWB devices in this band. For all PHYs, the implementer is responsible for verifying that all regulatory and safety requirements have been met. |  |  |  | Written |  |  |  | Disagree
52 | Clint Chaplin | Samsung Electronics | Editorial | 17 | 5.1 | 31 | "Table 69.." | "Table 69." |  | Agree |  |  |  |  | Written |  |  | Agree
53 | Clint Chaplin | Samsung Electronics | Editorial | 17 | 5.1 | 35 | "throught" | "through" |  | Agree |  |  |  |  | Written |  |  | Agree
54 | Clint Chaplin | Samsung Electronics | Editorial | 22 | 5.1.2.1 | 52 | "detetion" | "detection" |  | Agree |  |  |  |  | Written |  |  | Agree
55 | Clint Chaplin | Samsung Electronics | Editorial | 23 | 5.1.2.1.2 | 29 | "pasive chanel scan" | "passive channel scan" |  | Agree |  |  |  |  | Written |  |  | Agree
56 | Clint Chaplin | Samsung Electronics | Technical | 39 | 5.1.6.1 | 12 | "If the status from the outgoing frame security procedure is SUCCESS, in order transmit the frame, the MAC sublayer shall transmit the frame." Um, what? | "If the status from the outgoing frame security procedure is SUCCESS, the MAC sublayer shall transmit the frame." | Yes | Agree |  |  |  |  | Written |  |  |  | Agree
57 | Clint Chaplin | Samsung Electronics | Editorial | 50 | 5.1.8.3 | 51 | "the MAC sublayers on both sides of the link shall initiate timers after the sendingthe frame." Um, what? | "the MAC sublayers on both sides of the link shall initiate timers after sending the frame." | Yes | Agree |  |  |  |  | Written |  |  | Agree
58 | Clint Chaplin | Samsung Electronics | Editorial | 117 | 6.2.13.1 | 41 | "higher layer using the MCPS-DATA.indication primitive, 6.3.3)." | "higher layer using the MCPS-DATA.indication primitive, 6.3.3." |  | Principle | Change to "higher layer using the MCPS-DATA.indication primitive, as defined in 6.3.3." |  |  |  | Written |  |  | Principle
59 | Clint Chaplin | Samsung Electronics | Editorial | 129 | 6.3.3 | 3 | "The MCPS-DATA.indication primitive indicates the reception of data another device" | "The MCPS-DATA.indication primitive indicates the reception of data from another device" |  | Agree |  |  |  |  | Written |  |  | Agree
60 | Clint Chaplin | Samsung Electronics | Technical | 130 | 6.3.3 | 38 | "The pulse repetition value of the received PPDU. Non-UWB PHYs use a value of OFF." How do you indicate "OFF" using an integer? Or was this supposed to be 0xff? | I can't tell what the correct text should be. | Yes | Principle | Change to "This parameter is invalid for non UWB PHYs." |  |  |  | Written |  |  |  | Principle
61 | Clint Chaplin | Samsung Electronics | Editorial | 162 | 8.1.2 | 28 | "This combination allows the channel page and channel number combination to be represented as a 32 bit number" missing period | Add period |  | Principle | Delete the sentence. The representation of the channel page and number is internal to the implementation and so the format should not be defined in the standard. |  |  |  | Written |  |  | Principle
62 | Clint Chaplin | Samsung Electronics | Technical | 250 | B.2.2 | 36 | "Throughout this standard, the" This was a previously submitted comment, and the suggested remidy last time was accepted. However, it seems that it was never implemented. | "Throughout this clause, the" | Yes | Principle | Change to "Throughout this Annex". Sorry about missing this one. Search and replace failed because, inexplicably, some editor decided to make this a variable instead of text. One of the many bizarre editorial things in the document. |  |  |  | Written |  |  |  | Principle
63 | Clint Chaplin | Samsung Electronics | Editorial | 280 | E.1.1 | 22 | "the application will then stop the counter with a using MLME primitives." | "the application will then stop the counter using MLME primitives." | Yes | Agree |  |  |  |  | Written |  |  | Agree
64 | Clint Chaplin | Samsung Electronics | Editorial | 311 | G.1 | 17 | "but that operation these bands is not described in this Annex." | "but that operation in these bands is not described in this Annex." |  | Agree |  |  |  |  | Written |  |  | Agree
65 | Rene Struik | independent | Technical | 140 | 7.2 | 24-25 | (TR) 7.2, p. 140, l., 24-25: The outgoing and incoming frame security procedure shall always be executed, since otherwise security vulnerabilities may arise. Suggested remedy: please correct. | Please correct | Yes | Principle | Delete the phrase “and if security is implemented,” | [7 empty] | Principle
66 | Rene Struik | independent | Technical | 141 | 7.2.1 | 17 | (TR) 7.2.1, p. 141, l. 17: The identifier used should be the globally unique EUI-64 aExtendedAddress. Suggested remedy: please correct. | Please correct | Yes | Principle | There is no "aExtendedAddress" in the standard. The MAC address is a PIB entry because it is different, but unique for each MAC implementation. Hence the correct name is "macExtendedAddress". Add dagger to the MAC PIB attribute for maxExtendedAddress. On page 52, change “as defined by IEEE Std 802-2001” to be “as assigned by the IEEE RAC. With a footnote for the RAC web page.” | [7 empty] | Principle
67 | Rene Struik | independent | Technical | 142 | 7.2.3 |  | (TR) 7.2.3, p. 142, Step b), l. 1: (and elsewhere) The I/O parms should provide more detail so as to allow subsequent processed sufficient information to act upon, as previously in draft. Suggested remedy: please correct. | Please correct. | Yes | Disagree | The parameters that are returned are listed in 7.2.3, line 46. This applies to all steps. The only thing that needs to be specified is the value of the relevant parameters. The current text in this subclause specifies this correctly and in a more concise manner than previously. No change required. |  |  |  | Written |  |  |  | Disagree
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171 | [19 empty] | W
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
Note on M1: Agree Principle Disagree Out of scope Unresolvable

## Summary
Check:
Regular expressions are disabled
Whole cell matching is enabled
Technical | 8 | Overall | 67
Open | 0 | Open | 0
Suggested | 0 | Suggested | 0
Agree | 2 | Agree | 50
Disagree | 2 | Disagree | 4
Principle | 4 | Principle | 13
Out of scope | 0 | Out of scope | 0
Unresolvable | 0 | Unresolvable | 0
Total resolved | 8 | Total resolved | 67
Percent | 100% | Percent | 100%
Editorial | 59
Open | 0
Suggested | 0
Agree | 48
Disagree | 2
Principle | 9
Out of scope | 0
Unresolvable | 0
Total resolved | 59
Percent | 100%
Written | 65
Percent | 97.01%
Assigned
JPKG | 0
Sum | 0
Lan | 0
Tuncer | 0
Total assigned | 0
Percent | 0%

## Commenter summary
Commenter name | Vote | Affiliation | # comments | File name | 1st CID | Last CID
Ed Callaway | Y | Sunrise Micro Devices | 45 | P802-15-4i_Comment_Entry_Form-1-20101119-Callaway.xls | 1 | 45
Yang Yang | Y | SIMIT/WSNIRI | 5 | P802-15-4i_Comment_Entry_Form-Yang.xls | 46 | 50
Charles S. Farlow | N | Medtronic, Inc. | 1 | P802-15-4i_Comment_Entry_Form Farlow LB64.xls | 51 | 51
Clint Chaplin | N | Samsung Electronics | 13 | P802-15-4i_Comment_Entry_Form_Chaplin_Clint.xls | 52 | 64
Rene Struik | N | Independent | 3 | P802-15-4i_Comment_Entry_Form (Rene Struik, November 30, 2010).xls | 65 | 67
Total # comments |  |  | 67
Total # commenters |  |  | 5
Total # approve |  |  | 2
Total # disapprove |  |  | 3