## Slide 1: TG4k Project Time line (draft)
January 20, 2011
Shu Kato (NICT)

## Slide 2: Important Time Frames for TG Timeline - Depending on how many technical comments received at the first Letter Ballot -
1. Examples taken
i. Completed: TG3c (from March 2005 to September 2009: 5.5 years)
ii. In progress: TG4f (12, 2008~ ), TG4g (12, 2008~ ),
2. Important time frames
Time from TG formed to CFA
Time from TG formed to Tech Guidelines
Time from TG formed to CFP issued
Time from CFP to final Proposal
Time form final proposal to Baseline document completion
Time from Letter Ballot resolution
Time from Sponsor Ballot resolution
Time from Sponsor Ballot completion to EC approval / NESCOM submission

## Slide 3: Lessons Learned From Past /Current Task Group Performance 3c (3, 2005 – 9,2009) / 4f (12, 2008~) / 4g (12, 2008~)
Important time frames to be considered: TG3c / TG4f / TG4g
TG formed to CFA: - / 2 / -
TG formed to Tech Guidelines: - / 6 / 4
Task Group formed to CFP issued: 22 / 6 / 2
CFP to final Proposal: 4 / 4 / 6
Final proposal to Baseline doc. completion: 10 / 14 / 6
Letter Ballot resolution:
14 (about 500 tech. comments, 3 recirculation) /
Nov., 2010 ~ (first LB comment (134 Tech. comments) resolution be completed in Jan., 2011) /
Mar., 2010~ (first LB failed(about 1400 tech. comments), 2nd LB comment (713 tech. comments)resolution be completed in Mar., 2011)
vii. Sponsor Ballot resolution: 4 ( 1 recirculation) / - / -
viii. Sponsor Ballot completion to Revcom approval: 2 / - / -

## Slide 4: Draft 802.15.4k Timeline Assumptions: two LB recirculation and two SB recirculation