## Slide 1
NOTE: Update all red fields replacing with your information; they are required. This is a manual update in appropriate
fields. All Blue fields are informational and are to be deleted. Black stays. After updating delete this box/paragraph.
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: [Task Group 802.15.4k Timeline (draft)]
Date Submitted: [ “20 January, 2011”]
Source: [Shu Kato] Company [NICT]
Address [3-4, Hikarino-oka, Yokosuka, Japan. 239-0847]
Voice:[+81-46-847-5083], E-Mail:[shu.kato@nict.go.jp]
[If this is a response to a Call for Contributions, cite the name and date of the Call for Contributions to which this document responds, as well as the relevant item number in the Call for Contributions.]
[Note: Contributions that are not responsive to this section of the template, and contributions which do
not address the topic under which they are submitted, may be refused or consigned to the “General Contributions” area.]
Abstract: [Draft Task Group 802.15.4k Time line]
Purpose: [For P802.15 .4k to create a reasonable timeline to complete the standardization]
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: Task Group 802.15.4k Timeline (draft)
January 20, 2011
Shu Kato (NICT)

## Slide 3: Purpose
Draft TG4k Timeline assuming following
  Working in parallel for CFA and CFP
  Less than 300 technical comments as the outcome of the Letter Ballot
  Two recirculation for Letter Ballot comment resolution over 6 months
  One Sponsor Ballot recirculation over 4 months

## Slide 4: Important Time Frames for TG Timeline - Depending on how many technical comments received at the first Letter Ballot -
1. Examples taken
i. Completed: TG3c (from March 2005 to September 2009: 4.5 years)
ii. In progress: TG4f (12, 2008~ ), TG4g (12, 2008~ ),
2. Important time frames
Time TG formed
Time for CFA
Time for Tech Guidelines
Time for CFP
Time for Final Proposal
Time for Baseline Document completion
Time for Letter Ballot resolution
Time for Sponsor Ballot resolution
Time for Revcom approval

## Slide 5: Past /Current Task Group Performance Examples TG3c (2005/3 – 2009/9) / TG4f (2008/12~) / TG4g (2008/12~)
Important time frames to be considered: TG3c / TG4f / TG4g
Time for CFA: - / 2 / -
Time for Tech Guidelines: - / 6 / 4
Time for CFP issued: 22 / 6 / 2
Time for Final Proposal: 4 / 4 / 6
Time for Baseline Doc. completion: 10 / 14 / 6
Time for Letter Ballot resolution:
14 (about 500 tech. comments, 3 recirculation) /
Nov., 2010 ~ (first LB comment (134 Tech. comments) resolution be completed in Jan., 2011) /
Mar., 2010~ (first LB failed(about 1400 tech. comments), 2nd LB comment (713 tech. comments) resolution be completed in Mar., 2011)
vii. Time for Sponsor Ballot resolution: 4 ( 1 recirculation) / - / -
viii. Time for Revcom approval: 2 / - / -

## Slide 6: 802.15.4k Timeline (draft) Assumptions: two LB recirculation and one SB recirculation