## Timeline
DCN: |  | 15-11-0130-07-004j
|  |  |  | 2011 | [11 empty] | 2012 | [11 empty] | 2013
| # | Task | Comments | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
| 1 | Draft call for Applications | Complete | bar: 2011 Jan
| 2 | Issue Call for Applications | Complete | bar: 2011 Jan
| 3 | Application Submission Period | Complete | bar: 2011 Jan to 2011 Mar
| 4 | Draft call for Proposals | Complete | bar: 2011 Mar
| 5 | Issue Call for Proposals | Complete | bar: 2011 Mar
| 6 | Proposals Submission Period | Complete | bar: 2011 Mar to 2011 Jul
| 7 | Evaluate Proposals | Complete | bar: 2011 May; 2011 Jul to 2011 Nov
| 8 | Begin Amendment Editing | Complete | bar: 2011 Nov to 2011 Dec
| 9 | Create First Draft Specification | Complete | bar: 2012 Jan
| 10 | Discuss First Draft Specification | Complete | bar: 2012 Jan to 2012 Mar
| 11 | Issue Letter ballot | In Progress | bar: 2012 Mar
| 12 | Letter Ballot Period | bar: 2012 Mar to 2012 Apr
| 13 | Comment Resolution | bar: 2012 May to 2012 Jul
| 14 | Coexistence Document | bar: 2012 Apr to 2012 Jul
| 15 | Issue Recirculation Ballot | bar: 2012 Jul
| 16 | Recirculation Ballot | bar: 2012 Jul to 2012 Aug
| 17 | Comment Resolution | bar: 2012 Aug to 2012 Sep
| 18 | Issue Sponsor Ballot | bar: 2012 Sep
| 19 | Sponsor Ballot | bar: 2012 Sep to 2012 Oct
| 20 | Comment Resolution | bar: 2012 Oct to 2012 Nov
| 21 | Issue Recirculation Ballot | bar: 2012 Nov
| 22 | Recirculation Ballot | bar: 2012 Nov to 2012 Dec
| 23 | Comment Resolution | bar: 2012 Dec to 2013 Jan
| 24 | Accepted Amendment | bar: 2013 Jan
Plenary and Interim Meeting Months

## Legend
Plenary and Interim Meeting Months
Completed Tasks
In Progress tasks