## IEEE_Cover
October 2010 |  | P802-15-Comment_Entry_Form.xls
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15 Letter Ballot Comment Submission
Date Submitted | 2011-04-22
Source | Pat Kinney | Voice: +1.847.960.3715
Kinney Consulting
| 251 Clair View Ct, Lake Zurich, IL, USA | E-mail: pat.kinney@ieee.org
Re:
Abstract | 802.15 Comments for Letter Ballot
Purpose | [This document is used to submit comments on IEEE 802.15 Working Group Letter Ballots.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Comments
INSTRUCTIONS: You MUST use this form to enter your comments. When complete, submit with your vote as described in the Letter Ballot Notification Name / Affiliation - These fields are required. Email / Phone # - please enter a valid email address and contact telephone number. The editors may use these to contact you if there are questions relating to your comment. This information will NOT be made public. Clause/Sub-clause/Page/Line Number - Any data entered must be integers only; no alpha characters or symbols. If you wish to reference multiple pages, provide the details in the comment field. Please specify Table / Figure References in the comment field in addition to the Page and Line Number. Comment/Proposed Change - These fields are required. Enter your comment and proposed change in these fields, respectively. Use plain text characters only. If you use any characters entered with "Ctrl" or "Alt" keys; or if you use symbols of any kind, it may result in an error which invalidates the comment. Must be Satisfied? - Keep in mind that all comments submitted will be addressed. If you feel a comment "Must be Satisfied" enter "Yes" and spell out completely. Comments may be marked "Yes" in the "Must be Satisfied" box when submitting a "YES" (Approve) vote. If your vote is a "DO NOT APPROVE" at least one comment must be marked "Yes" in the "Must be Satisfied" box. In the case of a "DO NOT APPROVE" vote those comments that have a "Yes" in the "Must be Satisfied" box will be considered as the reason for the "DO NOT APPROVE" vote.
CID | Name | Affiliation | Email | Phone # | Clause | Sub-clause | Page | Line # | Comment | Proposed Change | Must Be Satisfied? (if so enter Yes) | Status | Resolution
4 | Marco Hernandez | NICT, Japan | Marco@nict.go.jp | 81-046-847-5430 | 17 | 17.2.2 | 25 | 10 | A SFD for frame synchronization is needed when there are repetitions of the SHR preamble. As there are not repetitions of the SHR preamble, once timing synchronization is achieved, the start of the frame is also known. | Remove SFD for all modes. | Yes | Rejected | This comment is Out-of-Scope since it is not based upon text in draft 5 that was changed, text that is affected by changes, or text that is the subject of unresolved comments associated with do not approve votes. Additionally, the SFD is required for frame synchronization.
11 | Ryuji Kohno | NICT/YNU | kohno@ynu.ac.jp | 81-453394115 | 17 | 17.2.2 | 25 | 10 | A SFD for frame synchronization is needed when there are repetitions of the SHR preamble. As there are not repetitions of the SHR preamble, once timing synchronization is achieved, the start of the frame is also known. | Remove SFD for all modes. |  | Rejected | This comment is Out-of-Scope since it is not based upon text in draft 5 that was changed, text that is affected by changes, or text that is the subject of unresolved comments associated with do not approve votes. Additionally, the SFD is required for frame synchronization.
6 | Ryuji Kohno | NICT/YNU | kohno@ynu.ac.jp | 81-453394115 | 17 | 17.6.3 | 29 | 7 | In Table 17.10, none of the three PSD masks satisfy Japanese and Korean regulations. The low end frequency of the PSD mask of Band 2 starts from 7121.92 MHz which is out of the regulated PSD mask of 7.25 GHz in Japan and is also out of the range of regulated PSD mask of 7.2 GHz in Korea. Also, the minimum bandwidth of 400 MHz does not satisfy the Japanese and Korean regulation rules. As an international standard, it should be satisfy the regulations of Asian countries such as Japan and Korea. | Make the low end frequency of the PSD mask of Band 2 be higher than 7.25 GHz and the minimum bandwith being larger 450 MHz. | Yes | Rejected | This comment is Out-of-Scope since it is not based upon text in draft 5 that was changed, text that is affected by changes, or text that is the subject of unresolved comments associated with do not approve votes. Futhermore, it is noted that this comment is the same technical issue as in CID #26 of LB74. The previously stated resolution is as follows. The PSD masks provide a minimum and a maximum for each of the bands. The bands allow, but do not guarantee, compliance with all national regulatory rules. They provide the ability to design a compliant device that meets all known regulations with regard to frequency. This includes compliance with Korean and Japanese regulations. The mask upper limits correspond to 15.4a bands, while the lower limits guarantee a minimum level of interoperability (see CID 23 response). The upper limits allow for flexibility in choice of bandwidth, while not precluding compliance with Korean or Japanese regulations. The lower bound of band 2 can be utilized for indoor operation in the US, but a device does not have to reach down to that frequency to be fully compliant with the 4f standard. For example, a device may have a PSD lower bound of 7.2 GHz, or 7.25 GHz and still be fully compliant with the draft standard, and Korean or Japanese regulatory requirements.
13 | Huan-Bang Li | NICT | lee@nict.go.jp | 81-468475104 | 17 | 17.6.3 | 29 | 7 | In Table 17.10, none of the three PSD masks satisfy Japanese and Korean regulations. The low end frequency of the PSD mask of Band 2 starts from 7121.92 MHz which is out of the regulated PSD mask of 7.25 GHz in Japan and is also out of the range of regulated PSD mask of 7.2 GHz in Korea. Also, the minimum bandwidth of 400 MHz does not satisfy the Japanese and Korean regulation rules. As an international standard, it should be satisfy the regulations of Asian countries such as Japan and Korea. | Make the low end frequency of the PSD mask of Band 2 be higher than 7.25 GHz and the minimum bandwith being larger 450 MHz. | Yes | Rejected | This comment is Out-of-Scope since it is not based upon text in draft 5 that was changed, text that is affected by changes, or text that is the subject of unresolved comments associated with do not approve votes. Futhermore, it is noted that this comment is the same technical issue as in CID #26 of LB74. The previously stated resolution is as follows. The PSD masks provide a minimum and a maximum for each of the bands. The bands allow, but do not guarantee, compliance with all national regulatory rules. They provide the ability to design a compliant device that meets all known regulations with regard to frequency. This includes compliance with Korean and Japanese regulations. The mask upper limits correspond to 15.4a bands, while the lower limits guarantee a minimum level of interoperability (see CID 23 response). The upper limits allow for flexibility in choice of bandwidth, while not precluding compliance with Korean or Japanese regulations. The lower bound of band 2 can be utilized for indoor operation in the US, but a device does not have to reach down to that frequency to be fully compliant with the 4f standard. For example, a device may have a PSD lower bound of 7.2 GHz, or 7.25 GHz and still be fully compliant with the draft standard, and Korean or Japanese regulatory requirements.
7 | Ryuji Kohno | NICT/YNU | kohno@ynu.ac.jp | 81-453394115 | 17 | 17.6.3 | 29 | 6 | It says 'the upper -10 dBr point of the transmitter PSD shall be at least 200 MHz above a nominal frequency, fn, 6 and the lower -10 dBr point shall be at most 200 MHz below the same nominal frequency'. According to this definition, an UWB spectrum could be equal to 400 MHz. That is not allowed in most regulations including FCC's. | Make modification to satisfy local ragulatory requirement. | yes. | Rejected | This comment is Out-of-Scope since it is not based upon text in draft 5 that was changed, text that is affected by changes, or text that is the subject of unresolved comments associated with do not approve votes. Futhermore, it is noted that this comment is the same technical issue as in CID #23 of LB74. The previously stated resolution is as follows. The minimum occupancy mask was chosen in order to force there to be some level of compatibility between different implementations, while allowing freedom to optimize signals for different purposes. It is only a minimum occupancy limit, is relative to peak PSD, and does not specify spectral symmetry. Wider bandwidths can comply with both this standard and regional regulatory requirements. In this manner, implementations with different bandwidths and different roll-offs can interact. It is designed to accommodate relevant regulatory requirements while allowing flexibility. (Also see resolution detail to CID 26 below for additional information regarding this topic)
14 | Huan-Bang Li | NICT | lee@nict.go.jp | 81-468475104 | 17 | 17.6.3 | 29 | 6 | It says 'the upper -10 dBr point of the transmitter PSD shall be at least 200 MHz above a nominal frequency, fn, 6 and the lower -10 dBr point shall be at most 200 MHz below the same nominal frequency'. According to this definition, an UWB spectrum could be equal to 400 MHz. That is not allowed in most regulations including FCC's. | Make modification to satisfy local ragulatory requirement. | yes. | Rejected | This comment is Out-of-Scope since it is not based upon text in draft 5 that was changed, text that is affected by changes, or text that is the subject of unresolved comments associated with do not approve votes. Futhermore, it is noted that this comment is the same technical issue as in CID #23 of LB74. The previously stated resolution is as follows. The minimum occupancy mask was chosen in order to force there to be some level of compatibility between different implementations, while allowing freedom to optimize signals for different purposes. It is only a minimum occupancy limit, is relative to peak PSD, and does not specify spectral symmetry. Wider bandwidths can comply with both this standard and regional regulatory requirements. In this manner, implementations with different bandwidths and different roll-offs can interact. It is designed to accommodate relevant regulatory requirements while allowing flexibility. (Also see resolution detail to CID 26 below for additional information regarding this topic)
2 | Marco Hernandez | NICT, Japan | Marco@nict.go.jp | 81-046-847-5430 | 17 | 17 | 21 | 6 | Mandatory modes are guidelines for implementers about what to implement regardless of simplex or complex systems. Line 5 is enough. | For the sake of clarity, please remove sentence. | Yes | Rejected | This comment is Out-of-Scope since it is not based upon text in draft 5 that was changed, text that is affected by changes, or text that is the subject of unresolved comments associated with do not approve votes. Additionally, the sentence adds clarity.
9 | Ryuji Kohno | NICT/YNU | kohno@ynu.ac.jp | 81-453394115 | 17 | 17 | 21 | 6 | Mandatory modes are guidelines for implementers about what to implement regardless of simplex or complex systems. Line 5 is enough. | For the sake of clarity, please remove sentence. |  | Rejected | This comment is Out-of-Scope since it is not based upon text in draft 5 that was changed, text that is affected by changes, or text that is the subject of unresolved comments associated with do not approve votes. Additionally, the sentence adds clarity
1 | Marco Hernandez | NICT, Japan | Marco@nict.go.jp | 81-046-847-5430 | 17 | 17 | 21 | 5 | operational | operate | Yes | Rejected | This comment is Out-of-Scope since it is not based upon text in draft 5 that was changed, text that is affected by changes, or text that is the subject of unresolved comments associated with do not approve votes. Additionally, the word operational clearly states the intention.
8 | Ryuji Kohno | NICT/YNU | kohno@ynu.ac.jp | 81-453394115 | 17 | 17 | 21 | 5 | operational | operate |  | Rejected | This comment is Out-of-Scope since it is not based upon text in draft 5 that was changed, text that is affected by changes, or text that is the subject of unresolved comments associated with do not approve votes. Additionally, the word operational clearly states the intention.
5 | Marco Hernandez | NICT, Japan | Marco@nict.go.jp | 81-046-847-5430 | 17 | 17.3 | 25 | 21 | Six parity bits are added to the PHR for protection without mentioning from which channel code those come from. | Define the employed channel code or remove sentence. | Yes | Rejected | This comment is Out-of-Scope since it is not based upon text in draft 5 that was changed, text that is affected by changes, or text that is the subject of unresolved comments associated with do not approve votes. Additionally, channel refers to the RF channel. PHR SECDED Check Bits are defined in paragraph 17.3.3 on page 26 line 14.
12 | Ryuji Kohno | NICT/YNU | kohno@ynu.ac.jp | 81-453394115 | 17 | 17.3 | 25 | 21 | Six parity bits are added to the PHR for protection without mentioning from which channel code those come from. | Define the employed channel code or remove sentence. |  | Rejected | This comment is Out-of-Scope since it is not based upon text in draft 5 that was changed, text that is affected by changes, or text that is the subject of unresolved comments associated with do not approve votes. Additionally, channel refers to the RF channel. PHR SECDED Check Bits are defined in paragraph 17.3.3 on page 26 line 14.
15 | Igor Dotlic | NICT | dotlic@nict.go.jp | 818954056033 | 17 | 17.1.1 | 21 | 23 | T_PULSE is not defined. For receivers with energy-detection architecture this is an important parameter for a receiver design, i.e. integration window (T_I) calculation. T_I DOES exist in energy-detection architectures. See e.g. http://dx.doi.org/10.1109/MSP.2009.932617 | Define T_PULSE | Yes | Rejected | This comment is Out-of-Scope since it is not based upon text in draft 5 that was changed, text that is affected by changes, or text that is the subject of unresolved comments associated with do not approve votes. This comment was previously resolved in CID #62 of LB63, and CIDs 5 and 6 of LB72. In summary, the limits of T_PULSE are defined by the limits of the PSD mask.
3 | Marco Hernandez | NICT, Japan | Marco@nict.go.jp | 81-046-847-5430 | 17 | 17.2.1.3 | 25 | 7 | The draft already defined that 1 represents a pulse/burst is transmitted and 0 represents no pulse/burst is transmitted. | In order to follow the same notation, change - by 0 and P by 1. | Yes | Rejected | This comment is Out-of-Scope since it is not based upon text in draft 5 that was changed, text that is affected by changes, or text that is the subject of unresolved comments associated with do not approve votes. Additionally, these are not bits they are pulses as defined in the paragraph.
10 | Ryuji Kohno | NICT/YNU | kohno@ynu.ac.jp | 81-453394115 | 17 | 17.2.1.3 | 25 | 7 | The draft already defined that 1 represents a pulse/burst is transmitted and 0 represents no pulse/burst is transmitted. | In order to follow the same notation, change - by 0 and P by 1. |  | Rejected | This comment is Out-of-Scope since it is not based upon text in draft 5 that was changed, text that is affected by changes, or text that is the subject of unresolved comments associated with do not approve votes. Additionally, these are not bits they are pulses as defined in the paragraph.