## IEEE_Cover
October 2010 |  | P802-15-Comment_Entry_Form.xls
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15 Letter Ballot Comment Submission
Date Submitted | 2011-04-22
Source | Pat Kinney | Voice: +1.847.960.3715
Kinney Consulting
| 251 Clair View Ct, Lake Zurich, IL, USA | E-mail: pat.kinney@ieee.org
Re:
Abstract | 802.15 Comments for Letter Ballot
Purpose | [This document is used to submit comments on IEEE 802.15 Working Group Letter Ballots.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Comments
CID | Name | Affiliation | Clause | Sub-clause | Page | Line # | Comment | Proposed Change | Must Be Satisfied? (if so enter Yes)
1 | Charles Farlow | Medtronic | 2 | N/A | 2 | 17 | Comment C45 submitted for LB76 was: [[Technical] The current ETSI MICS standard (EN 301 839-1) is not a draft. The standard should not be proceeded by the term "Draft".] The categorization of this comment's "Must Be Satisfied?" field is changed from "Yes" to "No"; as requested in LB76 comment resolution, this comment will be resubmitted for the Sponsor Ballot. | Eliminate the term "Draft" | No
2 | Charles Farlow | Medtronic | 2 | N/A | 2 | 20 | Comment C46 submitted for LB76 was: [[Technical] The referenced ETSI standard was published in October 2009.] The categorization of this comment's "Must Be Satisfied?" field is changed from "Yes" to "No"; as requested in LB76 comment resolution, this comment will be resubmitted for the Sponsor Ballot. | Replace "January 2009" with "October 2009"; this is also consistent with the "Document history" contained within EN 301 839-1. | No
3 | Charles Farlow | Medtronic | 7 | 7.9 | 123 | 4-7 | Comment C47 submitted for LB76 was: [[Technical] The revised standard does not match the comment resolution spreadsheet. The implant must also select the appropriate channel in compliance with clause 10. The term "clause" rather than "subclause" is used in ETSI standards. The proposed change matches the comment resolution spreadsheet with the addition of clause 8.6 for low power low duty cycle operation as discussed in the last session (May 2011).] The categorization of this comment "Must Be Satisfied?" field is changed from "Yes" to "No"; as requested in LB76 comment's resolution, this comment will be resubmitted for the Sponsor Ballot. | Change "The hub may choose a new channel only when required by, and in compliance with, applicable considerations and regulations including clause 10 or subclause 8.6 of ETSI EN 301 839-1. An implant shall communicate as a node with a hub, taking into account applicable considerations and regulations including subclause 8.6 of ETSI EN 301 839-1." to "The hub may choose a new channel only when required by, and in compliance with, applicable regulations including clause 8.6 or clause 10 of ETSI EN 301 839-1. An implant shall communicate as a node with a hub, in compliance with applicable regulations including clause 8.6 or clause 10 of ETSI EN 301 839-1." | No
4 | Charles Farlow | Medtronic | 7 | 7.9.4 | 128 | 19 | Comment C48 submitted for LB76 was: [[Editorial] The phrase "low power low duty cycle" is used throughout the document (and associated abbreviations).] As requested in LB76 comment resolution, this comment will be resubmitted for the Sponsor Ballot. | Include a definition of "low power low duty cycle" in sub-clause 3.2. | No
5 | Charles Farlow | Medtronic | 7 | 7.9.4 | 128 | 21,23 | Comment C49 submitted for LB76 was: [[Editorial] The term "clause" rather than "subclause" is used in ETSI standards.] As requested in LB76 comment resolution, this comment will be resubmitted for the Sponsor Ballot. | Change both instances of "subclause" to "clause" | No
6 | Charles Farlow | Medtronic | 7 | 7.9.4 | 128 | 22-23 | Comment C50 submitted for LB76 was: [[Technical] Duty cycle isn't the only limitation defined in the ETSI standard for Low Power Low Duty Cycle communication. There is also a limit on the number of transmissions and operating frequency.] The categorization of this comment's "Must Be Satisfied?" field is changed from "Yes" to "No"; this comment will be resubmitted for the Sponsor Ballot. | Change "A node may initiate a frame transaction with a hub at any time in a channel, and with a duty cycle, as specified in applicable regulations including subclause 8.6 of ETSI EN 301 839-1." to "A node may initiate a frame transaction with a hub at any time in a channel specified from 403.5 MHz to 403.8 MHz, in compliance with the limits for duty cycle and maximum number of transmissions specified in clause 8.6 of ETSI EN 301 839-1." | No
7 | Charles Farlow | Medtronic | 9 | 9.8.2 | 201 | 4 | Comment C51 submitted for LB76 was: [[Technical] The listed ETSI clause is not correct.] The categorization of this comment's "Must Be Satisfied?" field is changed from "Yes" to "No"; as requested in LB76 comment resolution, this comment will be resubmitted for the Sponsor Ballot. | Change "clause 8.6" to "clause 8.3"; Clause 8.3 is "Effective radiated power of the fundamental emission" | No
8 | Charles Farlow | Medtronic | 11 | 262-263 | 11.8.1 | 3-13, 1-4 | The technical portion of comment C52 submitted for LB76 was: [The low-frequency spectral mask may not be sufficient to prevent suspension of therapy in the large population of patients with implanted medical devices. Additionally, the spectral mask may not be sufficient to prevent interference with signals from MICS implants emitted at relatively low levels of EIRP (generally less than 200 nW).] The group's rebuttal is not sufficient since the masks may not be sufficient (this is pending understanding of the transmit power limit) to prevent potential degradation of medical device operation. The addition of the qualitative phrase "to protect the safety for the human body" in sub-clause 11.8.2 is not sufficient to ensure patient safety. The IEEE legal guidance states "... If this is a matter of concern, its should be discussed further with members of the implantable medical device industry to determine an appropriate spectral mask." HBC proponents have not worked in good faith to resolve concerns voiced by members of the implantable medical device industry. | While low frequency masks (below the HBC frequency of operation) are defined in D04, the discussion with AdvaMed to establish maximum output power levels and an appropriate spectral mask is not yet complete (three conference calls held to date). The minutes from the last conference call are documented in IEEE P802.15-11-0441-00-0006. The proposed resolution is to remove clause 11 and any text referencing this clause from the draft standard, with the HBC mode potentially being further considered in a new Study Group or Task Group. This action would provide AdvaMed members and HBC proponents additional time to analyze potential degradation of medical device operation (due to EMI produced by HBC), without delaying approval of IEEE 802.15.6 and its other modes. | Yes
9 | Charles Farlow | Medtronic | 11 | 263 | 11.8.2 | 6-8 | The technical portion of comment C53 submitted for LB76 was: [The group's rebuttal is not sufficient since the phrase "The radiation power to the human body .." is ambiguous. This phrase (including measurement methodology) must be fully explained and understood so members of the medical device industry can make the appropriate conversions as required to evaluate compliance to ANSI/AAMI PC69 Annex M (Correlation between levels of test voltages used in the standard and radiated field strengths).] The addition of the qualitative phrase "to protect the safety for the human body" in sub-clause 11.8.2 is not sufficient to ensure patient safety. The IEEE legal guidance states "... Further, if the proper transmit power is a matter of concern, it should be discussed further with members of the implantable medical device industry to determine an appropriate transmit power level." HBC proponents have not worked in good faith to resolve concerns voiced by members of the implantable medical device industry. | The related discussion with AdvaMed to establish maximum output power levels and an appropriate spectral mask is not yet complete (three conference calls held to date). The minutes from the last conference call are documented in IEEE P802.15-11-0441-00-0006. The proposed resolution is to remove clause 11 and any text referencing this clause from the draft standard, with the HBC mode potentially being further considered in a new Study Group or Task Group. This action would provide AdvaMed members and HBC proponents additional time to analyze potential degradation of medical device operation (due to EMI produced by HBC), without delaying approval of IEEE 802.15.6 and its other modes. | Yes